## Sheet1
Applied filters: AR Amt Gross is not blank Business Unit Type is C, CJ, LJ, MJ, LP, or FJ Year Period is 2020-03 Group Desc is WATER & MINERAL SERVICES GROUP Region and Desc is 413 - WATER RESOURCES Group Desc is not CORPORATE or OPERATIONS SERVICES Filter - Last 2 Years is Yes Business Unit Type is C, CJ, DO, LJ, LP, MJ, ST, or FJ Company and Desc does not contain '99*' and does not contain '099*' Company and Desc does not contain '00099*' Filter - Current Period and Prior is Yes
Contract Type | Business Unit Type | Active | Job | Job Parent | Job Desc | Project Manager Desc | Percent Complete ** | Orig Budget - Revenue | Job Budget Amt Revisions - JTD - Revenue | Revised Budget - Revenue | Actual Amt - JTD - Hypothetical Revenue | Actual Amt - JTD - Billings | AR Amt Gross | AR Amt Trade Open | AR Amt Retainage Open | Forecast - Revenue * | Orig Budget - Costs | Job Budget Amt Revisions - JTD - Costs | Revised Budget - Costs | Actual Amt - MTD - Costs | Actual Amt - MTD - Labor | Actual Amt - MTD - Equipment | Actual Amt - MTD - Hauling | Actual Amt - MTD - Material | Actual Amt - MTD - Subcontract | Actual Amt - MTD - Cost Offsets | Actual Amt - JTD - Costs | Actual Amt - JTD - Labor | Actual Amt - JTD - Equipment | Actual Amt - JTD - Hauling | Actual Amt - JTD - Material | Actual Amt - JTD - Subcontract | Actual Amt - JTD - Cost Offsets | Actual Amt - JTD - Billings > Cost | Actual Amt - JTD - Cost > Billings | Job % Spent Amt - JTD - Costs | Commit Amt Open - JTD | Remaining Amt - JTD - Costs | Forecast - Costs * | Orig Budget - Profit | Orig Budget - Profit % | Budget Revisions - JTD - Profit | Revised Budget - Profit | Revised Budget - Profit % | Budget Revisions - YTD - Profit | Budget Revisions - MTD - Profit | Actual Amt - JTD - Margin | Actual Amt - JTD - Margin % | Forecast - Profit * | Forecast - Profit % | Budget Variance - JTD - Revenue | Group and Desc | Region and Desc | Area and Desc | Office and Desc | Responsible BU Desc | Customer and Name | Market Segment Desc | Sub Market Desc | Planned Start Date | Planned Complete Date | Actual Start Date | Actual Complete Date | Contract Status Desc | Owner Type Summary Desc | Procurement Types Desc | .
CR | MJ | Yes | 700753 |  | MARK HOWARD SERVICE WORK | MAI, JONATHAN | 100% |  |  |  | 13933.83 | 13933.83 | 14133.41 | 1345.33 | 0 | 13933.83 |  |  |  | 414.23 | 385.28 |  |  | 28.95 |  |  | 9660.2 | 2589.97 | 87.45 |  | 6982.78 |  |  | 4273.63 | 0 |  |  | 0 | 9660.2 | [7 empty] | 4273.63 | 30.67% | 4273.63 | 30.67% | -13933.83 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700753¦¦2020-03-31
CR | C | Yes | 700754 |  | STEVE ZARCONE SERVICE WORK | MAI, JONATHAN | 100% |  |  |  | 7514.34 | 7514.34 | 7624.98 | 0 | 0 | 7514.34 | [10 empty] | 13334.57 | 7573.18 | 2545.48 |  | 3215.91 |  |  | 0 | 5820.23 |  |  | 0 | 13334.57 | [7 empty] | -5820.23 | -77.45% | -5820.23 | -77.45% | -7514.34 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700754¦¦2020-03-31
CR | MJ | Yes | 700755 |  | RICKY TRUJILLO SERVICE WORK | MAI, JONATHAN | 100% |  |  |  | 39598.31 | 39598.31 | 41875.99 | 0 | 0 | 39598.31 |  |  |  | 3843.98 | 3257.36 | 539.1 |  | 47.52 |  |  | 46740.09 | 14592.32 | 6835.32 |  | 25312.45 |  |  | 0 | 7141.78 |  |  | 0 | 46740.09 | [7 empty] | -7141.78 | -18.04% | -7141.78 | -18.04% | -39598.31 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700755¦¦2020-03-31
CR | MJ | Yes | 700756 |  | TOM HETZEL SERVICE WORK | MAI, JONATHAN | 100% |  |  |  | 33102.42 | 33102.42 | 33484.9 | 0 | 0 | 33102.42 |  |  |  | 648.36 | 529.85 | 109.27 |  | 9.24 |  |  | 28960.88 | 11949.4 | 5881.11 |  | 11130.37 |  |  | 4141.54 | 0 |  |  | 0 | 28960.88 | [7 empty] | 4141.54 | 12.51% | 4141.54 | 12.51% | -33102.42 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700756¦¦2020-03-31
CR | MJ | Yes | 700757 |  | REDLANDS SERVICE WORK | MAI, JONATHAN | 100% |  |  |  | 6949.8 | 6949.8 | 7166.8 | 0 | 0 | 6949.8 |  |  |  | 0 |  |  |  | 0 |  |  | 9221.22 | 3880.53 |  |  | 5340.69 |  |  | 0 | 2271.42 |  |  | 0 | 9221.22 | [7 empty] | -2271.42 | -32.68% | -2271.42 | -32.68% | -6949.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700757¦¦2020-03-31
CR | MJ | Yes | 700758 |  | HOLBROOK - SERVICE WORK | GRECKI, ROBERT | 100% |  |  |  | 39376.41 | 39376.41 | 39376.41 | 0 | 0 | 39376.41 |  |  |  | 1463.02 | 1249.84 | 198.22 |  | 14.96 |  |  | 23674.21 | 13051.11 | 4022.14 |  | 5725.96 | 875 |  | 15702.2 | 0 |  |  | 0 | 23674.21 | [7 empty] | 15702.2 | 39.88% | 15702.2 | 39.88% | -39376.41 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700758¦¦2020-03-31
CR | MJ | Yes | 700759 |  | DENVER SERVICE WORK | DELLETT, BRIAN W. | 100% |  |  |  | 45226.67 | 45226.67 | 45679 | 0 | 0 | 45226.67 |  |  |  | 2860.05 | 2449.86 | 362.67 |  | 47.52 |  |  | 46181.4 | 29351.62 | 2982.38 |  | 13847.4 |  |  | 0 | 954.73 |  |  | 0 | 46181.4 | [7 empty] | -954.73 | -2.111% | -954.73 | -2.111% | -45226.67 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700759¦¦2020-03-31
CR | MJ | Yes | 700760 |  | HOUSTON SERVICE WORK | OMAN, TIMOTHY S. | 100% |  |  |  | 195882 | 195882 | 185612 | 1400 | 0 | 195882 |  |  |  | 5032.5 | 3012.42 | 6518.13 |  | -4498.05 |  |  | 126317.35 | 62130.4 | 44153.9 |  | 9221.05 | 10812 |  | 69564.65 | 0 |  |  | 0 | 126317.35 | [7 empty] | 69564.65 | 35.51% | 69564.65 | 35.51% | -195882 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700760¦¦2020-03-31
CR | MJ | Yes | 700761 |  | KANSAS CITY SERVICE WORK | WARTICK, LOGAN M | 100% |  |  |  | 17904 | 17904 | 17904 | 7250 | 0 | 17904 |  |  |  | 2289.73 | 1669.69 | 343.18 |  | 276.86 |  |  | 16236.74 | 7733.53 | 1800.69 |  | 6702.52 |  |  | 1667.26 | 0 |  |  | 0 | 16236.74 | [7 empty] | 1667.26 | 9.312% | 1667.26 | 9.312% | -17904 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700761¦¦2020-03-31
CR | MJ | Yes | 700762 |  | WATER TECH SERVICE WORK | MUSSO, JENY A. | 100% |  |  |  | 413729.98 | 413729.98 | 413863.28 | 0 | 0 | 413729.98 |  |  |  | 18829.2 | 121.88 |  |  | 18707.32 |  |  | 303286.49 | 9607.06 | 6064.38 |  | 282216.05 | 5399 |  | 110443.49 | 0 |  |  | 0 | 303286.49 | [7 empty] | 110443.49 | 26.69% | 110443.49 | 26.69% | -413729.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700762¦¦2020-03-31
CR | MJ | Yes | 700763 |  | MEMPHIS SERVICE WORK | ANDERSON, STEPHEN P. | 100% |  |  |  | 682.5 | 682.5 | 682.5 | 0 | 0 | 682.5 |  |  |  | 249.31 | 244.03 |  |  | 5.28 |  |  | 898.7 | 804.61 | 70.2 |  | 23.89 |  |  | 0 | 216.2 |  |  | 0 | 898.7 | [7 empty] | -216.2 | -31.68% | -216.2 | -31.68% | -682.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700763¦¦2020-03-31
CR | MJ | Yes | 700764 |  | RAYNE SERVICE WORK | STUCKEY, WILLIAM C. | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 1912.51 | 1304.59 | 583.28 |  | 24.64 |  |  | 19021.4 | 14357.36 | 4025.38 |  | 638.66 |  |  | 0 | 19021.4 |  |  | 0 | 19021.4 | [7 empty] | -19021.4 |  | -19021.4 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700764¦¦2020-03-31
CR | MJ | Yes | 700765 |  | SALES TECH - LUKE PETERSEN | PETERSEN, LUKE A | 100% |  |  |  | 117847.58 | 117847.58 | 125739.99 | 2829.81 | 0 | 117847.58 |  |  |  | 5062.12 | 3444.43 | 1020.28 |  | 597.41 |  |  | 89543.67 | 53632.44 | 13930.09 |  | 20579.48 | 1401.66 |  | 28303.91 | 0 |  |  | 0 | 89543.67 | [7 empty] | 28303.91 | 24.02% | 28303.91 | 24.02% | -117847.58 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700765¦¦2020-03-31
CR | MJ | Yes | 700766 |  | SALES TECH - JASON GANSEBOM | GANSEBOM, JASON W. | 100% |  |  |  | 2502.59 | 2502.59 | 2504.49 | 0 | 0 | 2502.59 | [10 empty] | 3294.32 | 2496.45 | 648.73 |  | 149.14 |  |  | 0 | 791.73 |  |  | 0 | 3294.32 | [7 empty] | -791.73 | -31.64% | -791.73 | -31.64% | -2502.59 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700766¦¦2020-03-31
CR | MJ | Yes | 700767 |  | SCHOHARIE - SERVICE WORK | CROOK, CHARLES M | 100% |  |  |  | 3415 | 3415 | 3415 | 0 | 0 | 3415 | [10 empty] | 1437.99 | 1070.01 | 256.55 |  | 111.43 |  |  | 1977.01 | 0 |  |  | 0 | 1437.99 | [7 empty] | 1977.01 | 57.89% | 1977.01 | 57.89% | -3415 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700767¦¦2020-03-31
CR | MJ | Yes | 700768 |  | PENSACOLA SERVICE WORK | STUCKEY, WILLIAM C. | 100% |  |  |  | 2287.5 | 2287.5 | 2287.5 | 0 | 0 | 2287.5 |  |  |  | 497.48 | 486.92 |  |  | 10.56 |  |  | 991.22 | 912.14 | 58.84 |  | 20.24 |  |  | 1296.28 | 0 |  |  | 0 | 991.22 | [7 empty] | 1296.28 | 56.67% | 1296.28 | 56.67% | -2287.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700768¦¦2020-03-31
CR | MJ | Yes | 700769 |  | CHANDLER SERVICE WORK | COSTELLO, STEVEN | 100% |  |  |  | 8647.76 | 8647.76 | 8783.49 | 0 | 0 | 8647.76 |  |  |  | 1601.05 | 1086.31 | 300.53 |  | 214.21 |  |  | 3402.7 | 2372.44 | 608.39 |  | 371.87 | 50 |  | 5245.06 | 0 |  |  | 0 | 3402.7 | [7 empty] | 5245.06 | 60.65% | 5245.06 | 60.65% | -8647.76 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700769¦¦2020-03-31
CR | MJ | Yes | 700770 |  | ST LOUIS SERVICE WORK | MEYER, DAVID C. | [6 empty] | 0 | 0 | 0 | [36 empty] | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700770¦¦2020-03-31
CR | MJ | Yes | 700771 |  | SALES TECH - GAIL BALL | BALL, GAIL W. | 100% |  |  |  | 43370.73 | 43370.73 | 43370.73 | 0 | 0 | 43370.73 |  |  |  | 6098.17 | 4446.61 | 1002.66 |  | 349.7 | 299.2 |  | 25168.53 | 13020.11 | 2748.13 |  | 9058.59 | 341.7 |  | 18202.2 | 0 |  |  | 0 | 25168.53 | [7 empty] | 18202.2 | 41.97% | 18202.2 | 41.97% | -43370.73 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700771¦¦2020-03-31
CR | MJ | Yes | 700772 |  | BATON ROUGE SERVICE WORK | STUCKEY, WILLIAM C. | 100% |  |  |  | 87715.1 | 87715.1 | 87757.52 | 2430 | 0 | 87715.1 |  |  |  | 302.9 | 205.75 | 92.75 |  | 4.4 |  |  | 40520.13 | 20596.94 | 8246.83 |  | 7756.36 | 3920 |  | 47194.97 | 0 |  |  | 0 | 40520.13 | [7 empty] | 47194.97 | 53.8% | 47194.97 | 53.8% | -87715.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700772¦¦2020-03-31
CR | MJ | Yes | 700773 |  | OHIO SERVICE WORK | MCKENNA, JERRI L. | [6 empty] | 0 | 0 | 0 | [36 empty] | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700773¦¦2020-03-31
CR | MJ | Yes | 700774 |  | KENTUCKY SERVICE WORK | MCKENNA, JERRI L. | 100% |  |  |  | 22702.17 | 22702.17 | 22702.17 | 0 | 0 | 22702.17 |  |  |  | 0 |  |  |  | 0 |  |  | 12033 | 7004.73 | 562.82 |  | 3602.24 | 863.21 |  | 10669.17 | 0 |  |  | 0 | 12033 | [7 empty] | 10669.17 | 47% | 10669.17 | 47% | -22702.17 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700774¦¦2020-03-31
CR | MJ | Yes | 700775 |  | AURORA SERVICE WORK | HEALY, THOMAS P. | 100% |  |  |  | 91636.2 | 91636.2 | 92016.12 | 0 | 0 | 91636.2 |  |  |  | 5398.19 | 4507.27 | 847.8 |  | 43.12 |  |  | 125099.77 | 92351.31 | 21679.89 |  | 10608.57 | 460 |  | 0 | 33463.57 |  |  | 0 | 125099.77 | [7 empty] | -33463.57 | -36.52% | -33463.57 | -36.52% | -91636.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700775¦¦2020-03-31
CR | MJ | Yes | 700776 |  | SAVANNAH SERVICE WORK | PARSLEY, TRISTAN S | 100% |  |  |  | 9567.26 | 9567.26 | 9567.26 | 0 | 0 | 9567.26 |  |  |  | 1603.88 | 1188.65 | 389.27 |  | 25.96 |  |  | 7951.77 | 4322.62 | 1060.71 |  | 2568.44 |  |  | 1615.49 | 0 |  |  | 0 | 7951.77 | [7 empty] | 1615.49 | 16.89% | 1615.49 | 16.89% | -9567.26 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700776¦¦2020-03-31
UP | C | Yes | 700916 |  | 52618 REPUBLIC SVCS BLF WELLS | MEYER, DAVID C. | 100% | 4259 | 22150 | 26409 | 40797.5 | 40797.5 | 36538.5 | 0 | 0 | 40797.5 | 2800 | 15866 | 18666 | [7 empty] | 26863.72 | 11805.62 | 1520.12 |  | 13537.98 |  |  | 13933.78 | 0 | 143.9% |  | 0 | 26863.72 | 1459 | 34.26% | 6284 | 7743 | 29.32% | 0 |  | 13933.78 | 34.15% | 13933.78 | 34.15% | -14388.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896943 - REPUBLIC SERVICES PROCUREMENT, INC | WATER | WATER REPAIR & INSTALLATION | 2019-03-13 | 2019-03-31 | 2019-03-13 | 2019-03-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 700916¦¦2020-03-31
CR | MJ | Yes | 700921 |  | HANFORD SERVICE WORK | PALMER, MAX R. | 100% |  |  |  | 5910.69 | 5910.69 | 6041.32 | 0 | 0 | 5910.69 | [10 empty] | 3121.96 | 338.99 |  |  | 2782.97 |  |  | 2788.73 | 0 |  |  | 0 | 3121.96 | [7 empty] | 2788.73 | 47.18% | 2788.73 | 47.18% | -5910.69 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 861 - WRD HANFORD | HANFORD - WA |  | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-12-31 | 2019-05-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 700921¦¦2020-03-31
FP | LJ | Yes | 877405 |  | 24893 BROWARD COUNTY INJECTION | BRUGGER, CRAIG J. | 100% | 6648843 | 0 | 6648843 | 6648842.6683 | 6482979.91 | 324149 | 0 | 324149 | 6648843 | 4701003 | 2188997 | 6890000 | 0 | [5 empty] | 0 | 7618093.62 | 1903951.49 | 1456669.11 |  | 3627015.27 | 630457.7 | 0.05 | 0 | 1135113.71 | 110.6% |  | 0.38 | 7618094 | 1947840 | 29.3% | -2188997 | -241157 | -3.627% | 0 |  | -969251 | -14.58% | -969251 | -14.58% | 0.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878439 - BROWARD COUNTY WATER & WASTEWATER | WATER | WATER SUPPLY | 2014-04-08 | 2019-07-30 | 2014-04-08 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877405¦¦2020-03-31
UP | MJ | Yes | 877406 |  | 28646 ASANTE LENNAR EQUIPMENT | MUSSO, JENY A. | 100% |  |  |  | 650200 | 650200 | 95181.68 | 0 | 0 | 650200 |  |  |  | 100.7 | 54.55 |  |  | 46.15 |  |  | 2889.78 | 238.49 |  |  | 2651.29 |  |  | 647310.22 | 0 |  |  | 0 | 2889.78 | [7 empty] | 647310.22 | 99.56% | 647310.22 | 99.56% | -650200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 877406 - LENNAR COMMUNITIES DEVELOPMENT INC | WATER | WATER TREATMENT | 2014-01-01 | 2019-12-31 | 2014-01-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877406¦¦2020-03-31
TM | CJ | Yes | 877407 |  | 28647 ASANTE LENNAR SERVICE AG | MUSSO, JENY A. | 100% |  |  |  | 107109.8 | 107109.8 | 3200.55 | 0 | 0 | 107109.8 |  |  |  | 178.96 | 40 |  |  | 138.96 |  |  | 85903.41 | 35508.11 |  |  | 46395.3 | 4000 |  | 21206.39 | 0 |  |  | 0 | 85903.41 | [7 empty] | 21206.39 | 19.8% | 21206.39 | 19.8% | -107109.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 877406 - LENNAR COMMUNITIES DEVELOPMENT INC | WATER | WATER TREATMENT | 2014-02-08 | 2019-12-31 | 2014-02-08 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877407¦¦2020-03-31
CPF | CJ | Yes | 877409 |  | 35496 KCMO DT AIRPORT RELIEF W | HEILIGER, TERENCE L. | 100% | 75546 | 98920.1 | 174466.1 | 174466 | 174466 | 8723.3 | 0 | 8723.3 | 174466 | 47216 | 98439 | 145655 | [7 empty] | 145654.65 | 39511.23 | 28338.19 |  | 71035.23 | 6770 |  | 28811.35 | 0 | 100% |  | 0 | 145654.65 | 28330 | 37.5% | 481.1 | 28811.1 | 16.51% | 0 |  | 28811.35 | 16.51% | 28811.35 | 16.51% | 0.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 878441 - KCI AIRPORT | WATER | WATER REPAIR & INSTALLATION | 2015-04-06 | 2019-12-25 | 2015-04-28 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877409¦¦2020-03-31
FP | LJ | Yes | 877411 |  | 37411 BRAZOS RIVER AUTHORITY | BRANHAM, DAVID W. | 99.87% | 2870170 | -156562.86 | 2713607.14 | 2570717.0649 | 2572513.62 | 766282.19 | 0 | 257401.36 | 2574013.62 | 2210030.9 | 4766322.1 | 6976353 | 10439.43 | 3088.7 | 1080.67 |  | 9356.67 | 17055.78 | -20142.39 | 7531002.83 | 2306358.55 | 1235966.21 |  | 2615103.75 | 1354940.09 | 18634.23 | 0 | 4958489.21 | 108% |  | 9657.37 | 7540660.2 | 660139.1 | 23% | -4922884.96 | -4262745.86 | -157.1% | 0 |  | -4966646.58 | -193.7% | -4966646.58 | -193% | 149250.89 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 878443 - BRAZOS RIVER AUTHORITY | WATER | WATER SUPPLY | 2015-09-04 | 2019-05-31 | 2015-09-01 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 877411¦¦2020-03-31
FP | LJ | Yes | 877412 |  | 37923 GEFA CRETACEOUS TEST WEL | MARTINEZ, MIGUEL E | 100% | 4892570 | -349891 | 4542679 | 4542678.7922 | 4542679 | 451267.9 | 0 | 451267.9 | 4542679 | 3914075 | 1284424 | 5198499 | 0 | [5 empty] | 0 | 5245779.94 | 627960.87 | 1267420.81 |  | 2898147.63 | 452250.59 | 0.04 | 0 | 703100.94 | 100.9% |  | 0.24 | 5245780.18 | 978495 | 20% | -1634315 | -655820 | -14.44% | 0 |  | -703101.18 | -15.48% | -703101.18 | -15.48% | 0.24 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878444 - GEORGIA ENVIRONMENTAL FINANCE AUTHORITY | WATER | WATER SUPPLY | 2015-11-11 | 2019-03-31 | 2015-11-11 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877412¦¦2020-03-31
CR | LJ | Yes | 877413 |  | 38434 NYAW PLANT 23 TEMP SYSTE | RANFT, DONALD R | 100% | 449500 | 686009 | 1135509 | 1135509 | 1094516.31 | 0 | 0 | 0 | 1135509 | 323640 | 782946 | 1106586 | [7 empty] | 1106586.23 | 177097.61 | 114351.83 |  | 450851.83 | 364284.96 |  | 0 | 12069.92 | 100% |  | 0 | 1106586.23 | 125860 | 28% | -96937 | 28923 | 2.547% | 0 |  | 28922.77 | 2.547% | 28922.77 | 2.547% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 849 - WRD BEVERLY | BEVERLY - WA | 878446 - LONG ISLAND AMERICAN WATER | WATER | WATER TREATMENT | 2015-12-08 | 2019-12-31 | 2015-12-08 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 877413¦¦2020-03-31
FP | C | Yes | 877414 | 877415 | 38723 GILLETTE WY MADISON TEST | SCHANAMAN, MIKE L. | 100% | 3400854 | -1813704 | 1587150 | 1587150 | 1587150 | 0 | 0 | 0 | 1587150 | 2235147 | -1128217.33 | 1106929.67 | [7 empty] | 1106929.96 | 208168.1 | 380544.2 |  | 310927.07 | 207290.59 |  | 480220.04 | 0 | 100% |  | 0 | 1106929.96 | 1165707 | 34.28% | -685486.67 | 480220.33 | 30.26% | 0 |  | 480220.04 | 30.26% | 480220.04 | 30.26% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878447 - GILLETTE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2016-01-26 | 2019-03-31 | 2016-01-26 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877414¦¦2020-03-31
FP | LJ | Yes | 877415 | 877415 | 38724 GILLETTE WY MADISON DRIL | DECKER, JASEN | 98.67% | 6859467 | 5146078 | 12005545 | 11845977.1129 | 11780604.98 | 180849.6 | 0 | 168455.66 | 12005545 | 4557394 | 5618349.01 | 10175743.01 | 6.5 |  |  |  | 6.5 |  |  | 10040669.42 | 1988813.84 | 1932769 |  | 4793409.16 | 1325677.42 |  | 1739935.56 | 0 | 98.67% |  | 135250 | 10175919.42 | 2302073 | 33.56% | -472271.01 | 1829801.99 | 15.24% | 0 |  | 1805307.69 | 15.24% | 1829625.58 | 15.24% | 159567.89 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878447 - GILLETTE, CITY OF | WATER | WATER SUPPLY | 2015-11-19 | 2019-03-31 | 2015-11-19 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877415¦¦2020-03-31
TM | CJ | Yes | 877418 |  | 40016 MEMORIAL HERMANN BACK UP | ALBARADO, JORDAN A | 100% | 10000 | 111691 | 121691 | 122442.39 | 122442.39 | 39932.35 | 0 | 0 | 122442.39 | 8500 | 95003.91 | 103503.91 | 10250.4 |  |  |  |  | 10250.4 |  | 119942.91 | 1560.32 | 480 |  | 1404.72 | 116497.87 |  | 2499.48 | 0 | 115.9% |  | 0 | 119942.91 | 1500 | 15% | 16687.09 | 18187.09 | 14.95% | 50.09 |  | 2499.48 | 2.041% | 2499.48 | 2.041% | -751.39 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878451 - MEMORIAL HERMANN HEALTH SYSTEM | WATER | WATER REPAIR & INSTALLATION | 2016-06-23 | 2019-07-31 | 2016-06-23 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877418¦¦2020-03-31
FP | CJ | Yes | 877422 |  | 40875 HONEYWELL BRIGHTON BEEBE | SCHANAMAN, MIKE L. | 100% | 332040 | -28134 | 303906 | 303906 | 303906 | 30390.6 | 0 | 0 | 303906 | 201354 | -81671 | 119683 | [7 empty] | 119683.33 | 23091.04 | 7215.77 |  | 76276.52 | 13100 |  | 184222.67 | 0 | 100% |  | 0 | 119683.33 | 130686 | 39.36% | 53537 | 184223 | 60.62% | 0 |  | 184222.67 | 60.62% | 184222.67 | 60.62% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878456 - HONEYWELL ACS | WATER | WATER REPAIR & INSTALLATION | 2016-03-31 | 2019-04-01 | 2016-03-31 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877422¦¦2020-03-31
CR | LJ | Yes | 877429 |  | 42315 NYAW PLANT 23 CAUSTIC CO | RANFT, DONALD R | 100% | 390000 | 112437 | 502437 | 502437 | 422467.06 | 0 | 0 | 0 | 502437 | 310000 | 179695 | 489695 | [7 empty] | 489695.01 | 202426.53 | 45064.69 |  | 242203.79 |  |  | 0 | 67227.95 | 100% |  | 0 | 489695.01 | 80000 | 20.51% | -67258 | 12742 | 2.536% | 0 |  | 12741.99 | 2.536% | 12741.99 | 2.536% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 849 - WRD BEVERLY | BEVERLY - WA | 878446 - LONG ISLAND AMERICAN WATER | WATER | WATER TREATMENT | 2016-08-14 | 2019-10-27 | 2016-08-14 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877429¦¦2020-03-31
FP | C | Yes | 877430 |  | 42606 LOCUST VALLEY REDRILL NO | GRECKI, ROBERT | 100% | 618713 | -5950 | 612763 | 691263 | 691263 | 208878.65 | 0 | 0 | 691263 | 385930 | 325360 | 711290 | 0 |  |  |  | 0 |  |  | 746630.11 | 389018.84 | 138180.71 |  | 199002.71 | 20427.85 |  | 0 | 55367.11 | 105% |  | 0 | 746630.11 | 232783 | 37.62% | -331310 | -98527 | -16.08% | 0 |  | -55367.11 | -8.01% | -55367.11 | -8.01% | -78500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878463 - LOCUST VALLEY, CITY OF | WATER | WATER SUPPLY | 2016-09-18 | 2019-03-17 | 2016-09-18 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877430¦¦2020-03-31
FP | CJ | Yes | 877431 |  | 42739 SUBURBAN WATER LINWOOD | BENJAMIN, JAMES F. | 100% | 12275 | 303155 | 315430 | 302205 | 302205 | 0 | 0 | 0 | 302205 | 10435 | 216487.59 | 226922.59 | 0 |  |  |  | 0 |  |  | 212590.3 | 16533.85 |  |  | 196056.45 |  |  | 89614.7 | 0 | 93.68% |  | 0 | 212590.3 | 1840 | 14.99% | 86667.41 | 88507.41 | 28.06% | 0 |  | 89614.7 | 29.65% | 89614.7 | 29.65% | 13225 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 878464 - DO NOT USE SUBURBAN WATER INC | WATER | WATER TREATMENT | 2016-09-13 | 2019-11-30 | 2016-09-13 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 877431¦¦2020-03-31
FP | LJ | Yes | 877432 |  | 42760 WYNN CONSTRUCTION CO I | EVANS, TRAVIS L | 100% | 669728 | 109871 | 779599 | 779599 | 779599 | 77959.9 | 0 | 77959.9 | 779599 | 400000 | 65520 | 465520 | [7 empty] | 466512.69 | 160267.55 | 57968.51 |  | 224151.85 | 24124.78 |  | 313086.31 | 0 | 100.2% |  | 0 | 466512.69 | 269728 | 40.27% | 44351 | 314079 | 40.29% | 0 |  | 313086.31 | 40.16% | 313086.31 | 40.16% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 878465 - WYNN CONSTRUCTION COMPANY INC | WATER | WATER SUPPLY | 2016-09-12 | 2019-12-09 | 2016-09-12 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877432¦¦2020-03-31
CPF | LJ | Yes | 877434 |  | 42891 KCMO NEW AIRPORT RELIEF | HEILIGER, TERENCE L. | 100% | 629682.1 | -37617.9 | 592064.2 | 592064.2 | 592064.1 | 30923.41 | 0 | 30923.41 | 592064.2 | 472261.58 | -93288 | 378973.58 | [7 empty] | 378973.76 | 84725.86 | 24065.93 |  | 67307.03 | 202874.94 |  | 213090.34 | 0 | 100% |  | 0 | 378973.76 | 157420.52 | 25% | 55670.1 | 213090.62 | 35.99% | 0 |  | 213090.44 | 35.99% | 213090.44 | 35.99% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 878441 - KCI AIRPORT | WATER | WATER SUPPLY | 2016-09-22 | 2019-12-31 | 2016-09-22 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877434¦¦2020-03-31
UP | CJ | Yes | 877437 |  | 43260 CSI INVEST WELLS 1&4 MS | TRAMMELL, DUANE R. | 100% | 50500 | 198000 | 248500 | 162561.36 | 162561.36 | 23800 | 0 | 0 | 162561.36 | 31250 | 128525 | 159775 | [7 empty] | 113714.07 | 19920.95 | 10354.81 |  | 45130.37 | 38307.94 |  | 48847.29 | 0 | 71.17% |  | 0 | 113714.07 | 19250 | 38.12% | 69475 | 88725 | 35.7% | 0 |  | 48847.29 | 30.05% | 48847.29 | 30.05% | 85938.64 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878468 - COYOTE SPRINGS INVESTMENT LLC | WATER | WATER REPAIR & INSTALLATION | 2016-10-22 | 2019-10-31 | 2016-10-22 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877437¦¦2020-03-31
FP | CJ | Yes | 877439 |  | 43296 WAWN VOC REMOVAL WELL RE | GRECKI, ROBERT | 100% | 502000 | -99700 | 402300 | 326576 | 326576 | 70288.8 | 0 | 16328.8 | 326576 | 370500 | -30100 | 340400 | 2362.17 | 1055.38 | 99.52 |  | 1207.27 |  |  | 316249.28 | 141417.01 | 30245.12 |  | 127065.15 | 17522 |  | 10326.72 | 0 | 92.91% |  | 0 | 316249.28 | 131500 | 26.2% | -69600 | 61900 | 15.39% | 0 |  | 10326.72 | 3.162% | 10326.72 | 3.162% | 75724 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878470 - WATER AUTHORITY OF WESTERN NASSAU | WATER | WATER REPAIR & INSTALLATION | 2016-10-30 | 2019-06-29 | 2016-10-30 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877439¦¦2020-03-31
FP | C | Yes | 877441 |  | 43714 BRIGHTVIEW MAINT PROG 3 | SEIDEN, ANDREW L. | 100% | 6300 | 0 | 6300 | 6300 | 6300 | 2100 | 0 | 0 | 6300 | 4361.94 | 0 | 4361.94 | [7 empty] | 6321.46 | 3800.78 | 564.97 |  | 1955.71 |  |  | 0 | 21.46 | 144.9% |  | 0 | 6321.46 | 1938.06 | 30.76% | 0 | 1938.06 | 30.76% | 0 |  | -21.46 | -0.3406% | -21.46 | -0.3406% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878472 - BRIGHTVIEW TREE COMPANY | WATER | WATER REPAIR & INSTALLATION | 2016-11-23 | 2019-11-19 | 2016-11-23 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877441¦¦2020-03-31
FP | C | Yes | 877444 |  | 43952 CALICO FARMS PWM 7 WELLS | SEIDEN, ANDREW L. |  | 14700 | 0 | 14700 |  |  | 0 | 0 | 0 |  | 10164 | 0 | 10164 | [20 empty] | 4536 | 30.86% | 0 | 4536 | 30.86% | 0 | [5 empty] | 14700 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878474 - DO NOT USE CALICO FARMS | WATER | WATER REPAIR & INSTALLATION | 2016-12-16 | 2019-12-15 | 2016-12-16 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877444¦¦2020-03-31
UP | C | Yes | 877445 |  | 43975 R BAKER DJ FARMS WELL VT | GRACE, GARY L. | 100% | 197403.54 | 6312.6 | 203716.14 | 200316.16 | 200316.16 | 30270.64 | 30270.64 | 0 | 200316.16 | 118050.91 | 11081.56 | 129132.47 | [7 empty] | 144768.08 | 21552.15 | 6209.94 |  | 116427.99 | 578 |  | 55548.08 | 0 | 112.1% |  | 0 | 144768.08 | 79352.63 | 40.2% | -4768.96 | 74583.67 | 36.61% | 0 |  | 55548.08 | 27.73% | 55548.08 | 27.73% | 3399.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878475 - R BAKER INC | WATER | WATER REPAIR & INSTALLATION | 2017-04-04 | 2019-03-01 | 2017-04-04 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877445¦¦2020-03-31
UP | C | Yes | 877453 |  | 44560 PRESTAGE FOODS TEST WELL | SNELTEN, BRIAN M | 100% | 1749334 | 129398 | 1878732 | 1874832 | 1874832 | 93741.6 | 93741.6 | 0 | 1874832 | 1207040 | -77252 | 1129788 | [7 empty] | 1129788.49 | 271117.2 | 194149.85 |  | 470627.84 | 193893.6 |  | 745043.51 | 0 | 100% |  | 0 | 1129788.49 | 542294 | 31% | 206650 | 748944 | 39.86% | 0 |  | 745043.51 | 39.74% | 745043.51 | 39.74% | 3900 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878481 - ISG | WATER | WATER SUPPLY | 2017-02-07 | 2019-06-23 | 2017-02-07 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877453¦¦2020-03-31
FP | C | Yes | 877464 |  | 45423 FLOWOOD NORTHEAST WELL | ANDERSON, STEPHEN P. | 100% | 1416077 | -663382 | 752695 | 752695 | 752695 | 101134.89 | 0 | 0 | 752695 | 1082856 | -283283 | 799573 | 181.76 |  |  |  | 181.76 |  |  | 842017.41 | 276562.1 | 167440.63 |  | 375103.95 | 22910.73 |  | 0 | 89322.41 | 105.3% |  | 0 | 842017.41 | 333221 | 23.53% | -380099 | -46878 | -6.228% | 0 |  | -89322.41 | -11.87% | -89322.41 | -11.87% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 878491 - FLOWOOD, CITY OF | WATER | WATER SUPPLY | 2017-04-07 | 2019-06-11 | 2017-04-07 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877464¦¦2020-03-31
UP | LJ | Yes | 877466 |  | 45588 ENID OK CITY OF | EVANS, TRAVIS L | 13.43% | 339350 | 267350 | 606700 | 81492.9226 | 89733.57 | 4397.2 | 0 | 4397.2 | 606700 | 267299 | 228782 | 496081 | [7 empty] | 66378.32 | 32488.47 | 5789.69 |  | 21201.14 | 6899.02 |  | 23355.25 | 0 | 13.38% |  | 427796.21 | 494174.53 | 72051 | 21.23% | 38568 | 110619 | 18.23% | 0 |  | 15114.6 | 18.55% | 112525.47 | 18.55% | 525207.08 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 878492 - ENID, CITY OF | WATER | WATER SUPPLY | 2017-04-18 | 2019-08-25 | 2017-04-18 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877466¦¦2020-03-31
FP | C | Yes | 877469 |  | 45928 LAWCO EUNICE NEW WELL | ALBARADO, JORDAN A | 100% | 333122 | 6371 | 339493 | 339493.1 | 339493.1 | 0 | 0 | 0 | 339493.1 | 238965 | 39449 | 278414 | [7 empty] | 278414.44 | 89678.72 | 37950.72 |  | 133764 | 17021 |  | 61078.66 | 0 | 100% |  | 0 | 278414.44 | 94157 | 28.27% | -33078 | 61079 | 17.99% | 0 |  | 61078.66 | 17.99% | 61078.66 | 17.99% | -0.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878495 - LOUISIANA WATER COMPANY | WATER | WATER SUPPLY | 2017-06-05 | 2019-08-01 | 2017-05-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 877469¦¦2020-03-31
TM | CJ | Yes | 877471 |  | 46007 MIDDLETOWN CT DEVELOPME | CROOK, CHARLES M | 100% | 297260 | 0 | 297260 | 307743.35 | 307743.35 | 198125.97 | 0 | 0 | 307743.35 | 207875 | 2900 | 210775 | 23479.01 | 12606.3 | 3028.38 |  | 7844.33 |  |  | 286400.38 | 124021.69 | 38913.91 |  | 100393.76 | 23071.02 |  | 21342.97 | 0 | 135.9% |  | 0 | 286400.38 | 89385 | 30.07% | -2900 | 86485 | 29.09% | 0 |  | 21342.97 | 6.935% | 21342.97 | 6.935% | -10483.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 878497 - MIDDLETOWN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2017-05-24 | 2019-04-25 | 2017-05-24 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 877471¦¦2020-03-31
CPF | CJ | Yes | 877472 |  | 46194 IDOT D8 CONTRACT 1610027 | MEYER, DAVID C. | 100% | 124645 | 124645.4 | 249290.4 | 175001.09 | 175001.09 | 95037.4 | 15961.52 | 0 | 175001.09 | 103455 | 125293.55 | 228748.55 | 9117.41 | 4483.66 | 315.35 |  | 4318.4 |  |  | 161916.1 | 45111.77 | 6680.6 |  | 87070.69 | 23053.04 |  | 13084.99 | 0 | 70.78% |  | 0 | 161916.1 | 21190 | 17% | -648.15 | 20541.85 | 8.24% | 0 |  | 13084.99 | 7.477% | 13084.99 | 7.477% | 74289.31 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878498 - ILLINOIS, STATE OF | WATER | WATER EQUIPMENT SALES | 2017-06-12 | 2019-06-28 | 2017-06-12 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877472¦¦2020-03-31
FP | C | Yes | 877476 | 877476 | 46435 LOS ALAMOS OTOWI WELL 2 | SEIDEN, ANDREW L. | 100% | 2149257 | 1543144 | 3692401 | 3852261.34 | 3852261.34 | 435180.93 | 0 | 0 | 3852261.34 | 1693604 | 2402260 | 4095864 | [7 empty] | 4235500.11 | 1075196.02 | 623014.37 |  | 1912635.62 | 624654.1 |  | 0 | 383238.77 | 103.4% |  | 0 | 4235500.11 | 455653 | 21.2% | -859116 | -403463 | -10.93% | 0 |  | -383238.77 | -9.948% | -383238.77 | -9.948% | -159860.34 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878501 - WILSON & COMPANY ALBUQUERQUE | WATER | WATER SUPPLY | 2017-06-26 | 2019-12-31 | 2017-06-26 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877476¦¦2020-03-31
FP | C | Yes | 877477 | 877476 | 46436 LOS ALAMOS OTOWI WELL 2 | SCHANAMAN, MIKE L. | 100% | 149385 | 10475 | 159860 | 0 | 0 | 0 | 0 | 0 | 0 | 111322 | 11568 | 122890 | [7 empty] | 177881.65 | 68496.16 | 19484.04 |  | 74901.45 | 15000 |  | 0 | 177881.65 | 144.7% |  | 0 | 177881.65 | 38063 | 25.48% | -1093 | 36970 | 23.13% | 0 |  | -177881.65 |  | -177881.65 |  | 159860 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878502 - DO NOT USE WILSON & COMPANY ALBUQUERQUE | WATER | WATER REPAIR & INSTALLATION | 2017-06-26 | 2018-12-31 | 2017-06-26 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877477¦¦2020-03-31
TM | CJ | Yes | 877478 |  | 46547 SAPUTO WELL 1 PUMP REPAI | CROOK, CHARLES M | 100% | 9240 | 29865 | 39105 | 23435 | 23435 | 5600 | 0 | 0 | 23435 | 5700 | 17919 | 23619 | [7 empty] | 11023.17 | 4048.5 | 808.53 |  | 6166.14 |  |  | 12411.83 | 0 | 46.67% |  | 0 | 11023.17 | 3540 | 38.31% | 11946 | 15486 | 39.6% | 0 |  | 12411.83 | 52.96% | 12411.83 | 52.96% | 15670 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 878503 - SAPUTO DAIRY FOODS USA LLC | WATER | WATER REPAIR & INSTALLATION | 2017-07-09 | 2019-08-03 | 2017-07-06 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877478¦¦2020-03-31
TM | CJ | Yes | 877479 |  | 46632 46632 DANIS UD ARENA | SIMPSON, CARL L. | 100% | 491006 | -30747 | 460259 | 460259 | 460259 | 49786.88 | 9930 | 39856.88 | 460259 | 332800 | 68402 | 401202 | 0.59 | 0.59 | [5 empty] | 408729.87 | 155037.66 | 80491.56 |  | 173200.65 |  |  | 51529.13 | 0 | 101.9% |  | 0 | 408729.87 | 158206 | 32.22% | -99149 | 59057 | 12.83% | 0 |  | 51529.13 | 11.2% | 51529.13 | 11.2% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878504 - DANIS CONSTRUCTION | WATER | WATER SUPPLY | 2017-07-11 | 2019-10-30 | 2017-07-11 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 877479¦¦2020-03-31
FP | C | Yes | 877482 |  | 46679 PROSPER METRO DISTRICT | SCHANAMAN, MIKE L. | 100% | 255880 | 60811 | 316691 | 316691 | 316691 | 15834.55 | 0 | 15834.55 | 316691 | 196319 | -219 | 196100 | [7 empty] | 198704.99 | 14401.72 | 4482.68 |  | 160080.09 | 19740.5 |  | 117986.01 | 0 | 101.3% |  | 0 | 198704.99 | 59561 | 23.28% | 61030 | 120591 | 38.08% | 0 |  | 117986.01 | 37.26% | 117986.01 | 37.26% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878506 - PROSPER COORDINATING METROPOLITAN DISTR | WATER | WATER REPAIR & INSTALLATION | 2017-07-18 | 2019-12-31 | 2017-07-18 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877482¦¦2020-03-31
FP | C | Yes | 877485 |  | 47046 HORSHAM WELL 20 | WILLIAMS, DONALD G. | 100% | 49650 | 4400 | 54050 | 54050 | 54050 | 2061 | 0 | 0 | 54050 | 37588 | 9074 | 46662 | [7 empty] | 46856 | 22128.99 | 2639.91 |  | 21578.01 | 509.09 |  | 7194 | 0 | 100.4% |  | 0 | 46856 | 12062 | 24.29% | -4674 | 7388 | 13.67% | 0 |  | 7194 | 13.31% | 7194 | 13.31% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 849 - WRD BEVERLY | BEVERLY - WA | 878509 - HORSHAM, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2017-08-27 | 2019-09-28 | 2017-08-27 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 877485¦¦2020-03-31
FP | LJ | Yes | 877488 |  | 47203 NYAW PLANT 2 CHEMICAL | RANFT, DONALD R | 99.14% | 600000 | 107242.55 | 707242.55 | 692713.8459 | 696242.55 | 0 | 0 | 0 | 698742.55 | 457364 | 204636 | 662000 | 2944.71 | 575.19 | 93.28 |  | 2249.85 |  | 26.39 | 695733.02 | 205288.74 | 67238.06 |  | 151169.25 | 272010.58 | 26.39 | 509.53 | 0 | 105.1% |  | 6054.98 | 701788 | 142636 | 23.77% | -97393.45 | 45242.55 | 6.397% | 0 |  | -3045.45 | -0.4397% | -3045.45 | -0.4358% | 14554.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878512 - NEW YORK AMERICAN WATER | WATER | WATER REPAIR & INSTALLATION | 2017-08-28 | 2019-12-30 | 2017-08-28 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877488¦¦2020-03-31
CR | C | Yes | 877490 |  | 47232 RCMHP PWM SERVICES | GRACE, GARY L. | 100% | 3705 | 0 | 3705 | 1235 | 1235 | 0 | 0 | 0 | 1235 | 1552 | 0 | 1552 | [7 empty] | 1219.39 | 632.19 | 169.96 |  | 417.24 |  |  | 15.61 | 0 | 78.57% |  | 0 | 1219.39 | 2153 | 58.11% | 0 | 2153 | 58.11% | 0 |  | 15.61 | 1.264% | 15.61 | 1.264% | 2470 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878514 - DO NOT USE RANCHO CALIMESA MHP | WATER | WATER REPAIR & INSTALLATION | 2017-09-24 | 2019-10-09 | 2017-09-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877490¦¦2020-03-31
UP | CJ | Yes | 877493 |  | 47322 CHESTERFIELD NY WELL DR | CROOK, CHARLES M | 100% | 133600 | 304560 | 438160 | 419748 | 419748 | 22225 | 0 | 0 | 419748 | 83617 | 249498.57 | 333115.57 | [7 empty] | 315564.93 | 153006.95 | 79000.13 |  | 83557.85 |  |  | 104183.07 | 0 | 94.73% |  | 0 | 315564.93 | 49983 | 37.41% | 55061.43 | 105044.43 | 23.97% | 0 |  | 104183.07 | 24.82% | 104183.07 | 24.82% | 18412 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 878517 - CHESTERFIELD, TOWN OF | WATER | WATER SUPPLY | 2017-09-07 | 2019-12-07 | 2017-09-07 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877493¦¦2020-03-31
CPF | CJ | Yes | 877494 |  | 47367 ARKANSAS CITY WELL 5 O | WARTICK, LOGAN M | 100% | 145074 | 0 | 145074 | 60338.49 | 60338.49 | 0 | 0 | 0 | 60338.49 | 87044 | 0 | 87044 | 8169.65 | 3539.02 | 684.92 |  | 1908.21 | 2037.5 |  | 48747.14 | 13978.35 | 6060.07 |  | 21120.22 | 7588.5 |  | 11591.35 | 0 | 56% |  | 0 | 48747.14 | 58030 | 40% | 0 | 58030 | 40% | 0 |  | 11591.35 | 19.21% | 11591.35 | 19.21% | 84735.51 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 878858 - ARKANSAS CITY, CITY OF | WATER | WATER SUPPLY | 2017-09-18 | 2019-01-31 | 2017-09-18 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877494¦¦2020-03-31
FP | C | Yes | 877502 |  | 47757 CITY OF LAKE CHARLES NE | ALBARADO, JORDAN A | 100% | 466336 | 7029 | 473365 | 473364 | 473364 | 0 | 0 | 0 | 473364 | 363478 | 11187 | 374665 | [7 empty] | 377186.54 | 123125.63 | 48850.39 |  | 91282.07 | 113928.45 |  | 96177.46 | 0 | 100.7% |  | 0 | 377186.54 | 102858 | 22.06% | -4158 | 98700 | 20.85% | 0 |  | 96177.46 | 20.32% | 96177.46 | 20.32% | 1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878526 - DO NOT USE LAKE CHARLES, CITY OF | WATER | WATER SUPPLY | 2017-10-12 | 2019-01-31 | 2017-10-12 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877502¦¦2020-03-31
FP | LJ | Yes | 877503 |  | 47810 JERICHO WELL 9 & 14 REHA | RANFT, DONALD R | 79.89% | 607600 | 0 | 607600 | 485386.2751 | 452600 | 130093.65 | 0 | 22630 | 607600 | 393358 | 2585 | 395943 | 4218.86 | 3540.56 | 175.92 |  | 502.38 |  |  | 339373.36 | 192594.88 | 41301.28 |  | 102804 | 2673.2 |  | 113226.64 | 0 | 85.71% |  | 85449.64 | 424823 | 214242 | 35.26% | -2585 | 211657 | 34.83% | 0 |  | 146012.92 | 30.08% | 182777 | 30.08% | 122213.72 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878527 - JERICHO WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2017-10-31 | 2019-08-30 | 2017-10-31 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877503¦¦2020-03-31
FP | C | Yes | 877504 |  | 47822 ALIQUIPPA WELL CLEANING | HARTMAN, MICHAEL | 100% | 321500 | 140437 | 461937 | 461937 | 461937 | 323213.93 | 0 | 0 | 461937 | 250000 | 167000 | 417000 | 8.91 | 0.1 |  |  | 8.81 |  |  | 554030.58 | 334820.35 | 21448.29 |  | 139656.81 | 58105.13 |  | 0 | 92093.58 | 132.9% |  | 0 | 554030.58 | 71500 | 22.24% | -26563 | 44937 | 9.728% | 0 |  | -92093.58 | -19.94% | -92093.58 | -19.94% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878528 - MUNICIPAL WATER AUTHORITY OF ALIQUIPPA | WATER | WATER SUPPLY | 2017-10-15 | 2019-05-30 | 2017-10-15 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877504¦¦2020-03-31
CPF | LJ | Yes | 877507 |  | 47930 KC DOWNTOWN AIRPORT PH | HEILIGER, TERENCE L. | 100% | 1879229 | -35465.25 | 1843763.75 | 1892539.75 | 1892539.75 | 142397.7 | 142397.7 | 0 | 1892539.75 | 1437312 | 50632 | 1487944 | [7 empty] | 1489109.31 | 414227.35 | 102058.52 |  | 370355.98 | 602467.46 |  | 403430.44 | 0 | 100.1% |  | 0 | 1489109.31 | 441917 | 23.52% | -86097.25 | 355819.75 | 19.3% | 0 |  | 403430.44 | 21.32% | 403430.44 | 21.32% | -48776 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 878441 - KCI AIRPORT | WATER | WATER SUPPLY | 2017-10-25 | 2019-07-31 | 2017-10-25 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877507¦¦2020-03-31
FP | CJ | Yes | 877510 |  | 48087 48087 MASON CO ASHTON PL | CURLEY, ROBERT E. | 100% | 109878 | 0 | 109878 | 25271.94 | 25271.94 | 1263.6 | 0 | 1263.6 | 25271.94 | 70522 | 0 | 70522 | [7 empty] | 17305.79 | 6683.53 | 1556.75 |  | 3049.89 | 6015.62 |  | 7966.15 | 0 | 24.54% |  | 0 | 17305.79 | 39356 | 35.82% | 0 | 39356 | 35.82% | 0 |  | 7966.15 | 31.52% | 7966.15 | 31.52% | 84606.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878533 - MASON, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2017-10-17 | 2019-01-30 | 2017-10-17 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877510¦¦2020-03-31
UP | C | Yes | 877512 |  | 48189 VEOLIA WATER W6B CITY WE | TRAMMELL, DUANE R. | 100% | 1088194 | 86760 | 1174954 | 1171255.32 | 1171255.32 | 325591.61 | 0 | 0 | 1171255.32 | 782388 | -12988 | 769400 | [7 empty] | 862058.96 | 256430.57 | 19962.25 |  | 215290.77 | 370375.37 |  | 309196.36 | 0 | 112% |  | 0 | 862058.96 | 305806 | 28.1% | 99748 | 405554 | 34.52% | 0 |  | 309196.36 | 26.4% | 309196.36 | 26.4% | 3698.68 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878535 - VEOLIA WATER RIALTO | WATER | WATER REPAIR & INSTALLATION | 2018-01-08 | 2019-08-31 | 2017-11-29 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877512¦¦2020-03-31
TM | CJ | Yes | 877513 |  | 48217 SHELBY IA WELL REHAB 6 | GANSEBOM, JASON W. | 100% | 8298 | 0 | 8298 | 1390.02 | 1390.02 | 0 | 0 | 0 | 1390.02 | 5396 | 0 | 5396 | [7 empty] | 1122.99 | 480.27 |  |  | 642.72 |  |  | 267.03 | 0 | 20.81% |  | 0 | 1122.99 | 2902 | 34.97% | 0 | 2902 | 34.97% | 0 |  | 267.03 | 19.21% | 267.03 | 19.21% | 6907.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878536 - SHELBY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2017-11-30 | 2019-01-31 | 2017-11-30 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877513¦¦2020-03-31
UP | CJ | Yes | 877515 |  | 48249 HARGIS FULLERTON WELL 9 | BRASHEAR, DAVID M | 100% | 48324 | 180493 | 228817 | 143787.14 | 143787.14 | 142544.5 | 0 | 0 | 143787.14 | 28532 | 128863 | 157395 | [7 empty] | 108274.08 | 2304.03 | 162.42 |  | 84910.13 | 20897.5 |  | 35513.06 | 0 | 68.79% |  | 0 | 108274.08 | 19792 | 40.96% | 51630 | 71422 | 31.21% | 0 |  | 35513.06 | 24.7% | 35513.06 | 24.7% | 85029.86 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878538 - HARGIS & ASSOCIATES INC | WATER | WATER REPAIR & INSTALLATION | 2017-12-01 | 2019-02-28 | 2017-12-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 877515¦¦2020-03-31
FP | CJ | Yes | 877516 |  | 48267 KANSAS CITY BPU CW MONIT | BELL, JAMES J. | 100% | 9600 | 9600 | 19200 | 19200 | 19200 | 9600 | 0 | 0 | 19200 | 6700 | 6600 | 13300 | 0 | 0 |  |  | 0 |  |  | 12838.95 | 11382.49 |  |  | 1456.46 |  |  | 6361.05 | 0 | 96.53% |  | 0 | 12838.95 | 2900 | 30.21% | 3000 | 5900 | 30.73% | 0 |  | 6361.05 | 33.13% | 6361.05 | 33.13% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878539 - KANSAS CITY BOARD OF PUBLIC UTILITIES | WATER | WATER SUPPLY | 2017-12-07 | 2019-12-30 | 2017-12-07 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877516¦¦2020-03-31
UP | CJ | Yes | 877517 |  | 48295 MSD DEER CREEK TUNNEL | MEYER, DAVID C. | 100% | 199050 | 50321 | 249371 | 240880 | 240880 | 51782.5 | 39738.5 | 12044 | 240880 | 127392 | -11386.75 | 116005.25 | 33091 | 15972.46 | 9545.13 |  | 7573.41 |  |  | 109079.39 | 50219.15 | 37995.93 |  | 20864.31 |  |  | 131800.61 | 0 | 94.03% |  | 0 | 109079.39 | 71658 | 36% | 61707.75 | 133365.75 | 53.48% | 10615.75 | 1817.25 | 131800.61 | 54.72% | 131800.61 | 54.72% | 8491 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878540 - SAK CONSTRUCTION | WATER | WATER SUPPLY | 2017-12-13 | 2019-02-09 | 2017-12-13 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877517¦¦2020-03-31
FP | CJ | Yes | 877518 |  | 48343 WESTBROOK FARMS | BENNETT, MARK C. | 100% | 24000 | 0 | 24000 | 19904.81 | 19904.81 | 4263.58 | 0 | 0 | 19904.81 | 16800 | 0 | 16800 | 2623.1 | 1084.23 | 358.64 |  | 1180.23 |  |  | 16080.99 | 1876.89 | 613.64 |  | 13590.46 |  |  | 3823.82 | 0 | 95.72% |  | 0 | 16080.99 | 7200 | 30% | 0 | 7200 | 30% | 0 |  | 3823.82 | 19.21% | 3823.82 | 19.21% | 4095.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878541 - WESTBROOK FARMS | WATER | WATER EQUIPMENT SALES | 2017-12-14 | 2019-12-14 | 2017-12-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877518¦¦2020-03-31
UP | CJ | Yes | 877519 |  | 48379 HARGIS FULLERTON PACKER | BRASHEAR, DAVID M | 100% | 378876 | 0 | 378876 | 254723.18 | 254723.18 | 0 | 0 | 0 | 254723.18 | 250091 | 3128 | 253219 | [7 empty] | 196613.19 | 1856.55 | 85 |  | 194633.64 | 38 |  | 58109.99 | 0 | 77.65% |  | 0 | 196613.19 | 128785 | 33.99% | -3128 | 125657 | 33.17% | 0 |  | 58109.99 | 22.81% | 58109.99 | 22.81% | 124152.82 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878538 - HARGIS & ASSOCIATES INC | WATER | WATER REPAIR & INSTALLATION | 2017-12-20 | 2019-07-01 | 2017-12-20 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877519¦¦2020-03-31
TM | C | Yes | 877521 |  | 48391 OXY CHEM 20 BOWL R&I | WARTICK, LOGAN M | 100% | 1000 | 20653 | 21653 | 23223 | 23223 | 23223 | 0 | 0 | 23223 | 600 | 14557.1 | 15157.1 | 149.67 | 86.91 | 11.66 |  | 51.1 |  |  | 20560.86 | 3089.32 | 23.32 |  | 17448.22 |  |  | 2662.14 | 0 | 135.7% |  | 0 | 20560.86 | 400 | 40% | 6095.9 | 6495.9 | 30% | 0 |  | 2662.14 | 11.46% | 2662.14 | 11.46% | -1570 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 895666 - OCCIDENTAL CHEMICAL CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2017-12-21 | 2019-02-28 | 2017-12-18 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877521¦¦2020-03-31
FP | C | Yes | 877523 |  | 48418 STUTTGART WATERWORKS EUR | BURGE, EVERETT E. | 100% | 3000 | 0 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 3000 | 1950 | 0 | 1950 | [7 empty] | 3425.33 | 2626.32 | 725 |  | 74.01 |  |  | 0 | 425.33 | 175.7% |  | 0 | 3425.33 | 1050 | 35% | 0 | 1050 | 35% | 0 |  | -425.33 | -14.18% | -425.33 | -14.18% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878545 - STUTTGART WATER WORKS | WATER | WATER EQUIPMENT SALES | 2018-01-02 | 2019-05-04 | 2018-01-02 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877523¦¦2020-03-31
FP | C | Yes | 877532 |  | 48612 LE AX CW MONITORING 2018 | BELL, JAMES J. | 100% | 12000 | 0 | 12000 | 12000 | 12000 | 6000 | 0 | 0 | 12000 | 7500 | 0 | 7500 | 0 |  |  |  | 0 |  |  | 6354.48 | 5915.5 |  |  | 438.98 |  |  | 5645.52 | 0 | 84.73% |  | 0 | 6354.48 | 4500 | 37.5% | 0 | 4500 | 37.5% | 0 |  | 5645.52 | 47.05% | 5645.52 | 47.05% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878554 - LE AX WATER DISTRICT | WATER | WATER SUPPLY | 2018-01-17 | 2019-02-28 | 2018-01-17 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877532¦¦2020-03-31
UP | C | Yes | 877540 |  | 48829 CSI WELL 2 RENTAL PUMP | MAI, JONATHAN | 100% | 192857 | 0 | 192857 | 192856.63 | 192856.63 | 0 | 0 | 0 | 192856.63 | 138783 | -68606 | 70177 | [7 empty] | 70288.33 | 30546.93 | 6191.71 |  | 33084.19 | 465.5 |  | 122568.3 | 0 | 100.2% |  | 0 | 70288.33 | 54074 | 28.04% | 68606 | 122680 | 63.61% | 0 |  | 122568.3 | 63.55% | 122568.3 | 63.55% | 0.37 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878468 - COYOTE SPRINGS INVESTMENT LLC | WATER | WATER SUPPLY | 2017-10-23 | 2019-07-31 | 2017-10-23 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877540¦¦2020-03-31
UP | C | Yes | 877542 |  | 48881 TOPA TOPA NEW PUMPING EQ | GRACE, GARY L. | 100% | 32830 | 18543 | 51373 | 51102.27 | 51102.27 | 1374.45 | 0 | 0 | 51102.27 | 23256 | 12922 | 36178 | [7 empty] | 46797.4 | 17802.15 | 6374.54 |  | 22620.71 |  |  | 4304.87 | 0 | 129.4% |  | 0 | 46797.4 | 9574 | 29.16% | 5621 | 15195 | 29.58% | 0 |  | 4304.87 | 8.424% | 4304.87 | 8.424% | 270.73 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878563 - TOPA TOPA RANCH & NURSERY LLC | WATER | WATER REPAIR & INSTALLATION | 2018-02-14 | 2019-04-30 | 2018-02-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877542¦¦2020-03-31
FP | CJ | Yes | 877543 |  | 48904 WINCHESTER PUMPS JUDY | MIESNER, EMILY E. | 100% | 484155 | 30710 | 514865 | 510023.45 | 510023.45 | 510023.45 | 0 | 51002.35 | 510023.45 | 370400 | 24568 | 394968 | [7 empty] | 405734.39 | 427.87 | 58.08 |  | 405248.44 |  |  | 104289.06 | 0 | 102.7% |  | 0 | 405734.39 | 113755 | 23.5% | 6142 | 119897 | 23.29% | 0 |  | 104289.06 | 20.45% | 104289.06 | 20.45% | 4841.55 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878564 - JUDY CONSTRUCTION COMPANY | WATER | WATER EQUIPMENT SALES | 2018-02-18 | 2019-10-30 | 2018-02-18 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877543¦¦2020-03-31
UP | C | Yes | 877546 |  | 48947 PRESTAGE FOODS IA WEL | SNELTEN, BRIAN M | 100% | 1699072 | 246688 | 1945760 | 1945759.99 | 1945759.99 | 97288 | 97288 | 0 | 1945759.99 | 1255988 | 254012 | 1510000 | [7 empty] | 1508191.4 | 586761.59 | 313267.2 |  | 477721.02 | 130441.59 |  | 437568.59 | 0 | 99.88% |  | 0 | 1508191.4 | 443084 | 26.08% | -7324 | 435760 | 22.4% | 0 |  | 437568.59 | 22.49% | 437568.59 | 22.49% | 0.01 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878481 - ISG | WATER | WATER SUPPLY | 2018-02-23 | 2019-04-30 | 2018-02-23 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877546¦¦2020-03-31
FP | C | Yes | 877551 |  | 49044 LAKE CHARLES AQUIFER S | ALBARADO, JORDAN A | 100% | 394900 | 0 | 394900 | 377400 | 377400 | 47860 | 0 | 0 | 377400 | 277281 | 12459 | 289740 | [7 empty] | 301424.41 | 105128.41 | 68036.01 |  | 119345.35 | 8914.64 |  | 75975.59 | 0 | 104% |  | 0 | 301424.41 | 117619 | 29.78% | -12459 | 105160 | 26.63% | 0 |  | 75975.59 | 20.13% | 75975.59 | 20.13% | 17500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878570 - MANCHAC CONSULTING GROUP INC | WATER | WATER SUPPLY | 2018-03-05 | 2019-04-30 | 2018-03-05 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877551¦¦2020-03-31
UP | C | Yes | 877552 | 877552 | 49107 CID NEW WELL 106 | TRAMMELL, DUANE R. | 100% | 634468 | 0 | 634468 | 597083 | 597083 | 0 | 0 | 0 | 597083 | 482793 | 10899 | 493692 | [7 empty] | 485707.57 | 146106.01 | 77124.48 |  | 251828.07 | 10649.01 |  | 111375.43 | 0 | 98.38% |  | 0 | 485707.57 | 151675 | 23.91% | -10899 | 140776 | 22.19% | 0 |  | 111375.43 | 18.65% | 111375.43 | 18.65% | 37385 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878571 - CORCORAN IRRIGATION DISTRICT | WATER | WATER SUPPLY | 2018-04-09 | 2019-05-07 | 2018-04-09 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877552¦¦2020-03-31
UP | C | Yes | 877553 | 877552 | 49108 CID NEW WELL TEST PUMPIN | TRAMMELL, DUANE R. | 100% | 39063 | 0 | 39063 | 34200 | 34200 | 0 | 0 | 0 | 34200 | 26535 | 1694 | 28229 | [7 empty] | 20961.78 | 8635.51 | 2668.5 |  | 9657.77 |  |  | 13238.22 | 0 | 74.26% |  | 0 | 20961.78 | 12528 | 32.07% | -1694 | 10834 | 27.73% | 0 |  | 13238.22 | 38.71% | 13238.22 | 38.71% | 4863 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878571 - CORCORAN IRRIGATION DISTRICT | WATER | WATER SUPPLY | 2018-05-28 | 2019-06-29 | 2018-05-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877553¦¦2020-03-31
UP | CJ | Yes | 877559 | 877559 | 49247 JOEL ALLEN 16 X 810 WEL | TRAMMELL, DUANE R. | 100% | 287191 | 0 | 287191 | 2321.8 | 2321.8 | 0 | 0 | 0 | 2321.8 | 216546 | 6292 | 222838 | [7 empty] | 1875.77 | 387.07 | 272 |  | 1216.7 |  |  | 446.03 | 0 | 0.8418% |  | 0 | 1875.77 | 70645 | 24.6% | -6292 | 64353 | 22.41% | 0 |  | 446.03 | 19.21% | 446.03 | 19.21% | 284869.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878576 - DO NOT USE ALLEN, JOEL | WATER | WATER SUPPLY | 2018-05-31 | 2019-07-12 | 2018-05-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877559¦¦2020-03-31
UP | CJ | Yes | 877560 | 877559 | 49248 JOEL ALLEN TP WELL 1 | TRAMMELL, DUANE R. | 100% | 31942 | 0 | 31942 | 835.02 | 835.02 | 0 | 0 | 0 | 835.02 | 24171 | 1406 | 25577 | [7 empty] | 674.61 |  | 674.61 |  |  |  |  | 160.41 | 0 | 2.638% |  | 0 | 674.61 | 7771 | 24.33% | -1406 | 6365 | 19.93% | 0 |  | 160.41 | 19.21% | 160.41 | 19.21% | 31106.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878577 - DO NOT USE ALLEN, JOEL | WATER | WATER REPAIR & INSTALLATION | 2018-07-02 | 2019-07-31 | 2018-07-02 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877560¦¦2020-03-31
UP | CJ | Yes | 877562 | 877562 | 49256 JOEL ALLEN 16 X 810 WEL | TRAMMELL, DUANE R. | 100% | 287191 | 0 | 287191 | 2166.68 | 2166.68 | 0 | 0 | 0 | 2166.68 | 216546 | 6283 | 222829 | [7 empty] | 1750.45 | 486.34 | 272 |  | 992.11 |  |  | 416.23 | 0 | 0.7856% |  | 0 | 1750.45 | 70645 | 24.6% | -6283 | 64362 | 22.41% | 0 |  | 416.23 | 19.21% | 416.23 | 19.21% | 285024.32 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878576 - DO NOT USE ALLEN, JOEL | WATER | WATER SUPPLY | 2018-07-17 | 2019-08-23 | 2018-03-22 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877562¦¦2020-03-31
UP | CJ | Yes | 877563 | 877562 | 49257 JOEL ALLEN TP WELL 2 | TRAMMELL, DUANE R. | 100% | 31942 | 0 | 31942 | 44.19 | 44.19 | 0 | 0 | 0 | 44.19 | 24171 | 1403 | 25574 | [7 empty] | 35.7 | 35.7 | [5 empty] | 8.49 | 0 | 0.1396% |  | 0 | 35.7 | 7771 | 24.33% | -1403 | 6368 | 19.94% | 0 |  | 8.49 | 19.21% | 8.49 | 19.21% | 31897.81 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878576 - DO NOT USE ALLEN, JOEL | WATER | WATER REPAIR & INSTALLATION | 2018-08-22 | 2019-09-04 | 2018-06-30 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877563¦¦2020-03-31
FP | LJ | Yes | 877566 |  | 49344 JUPITER PROD WELLS ACI | BRUGGER, CRAIG J. | 97.76% | 540100 | 20012 | 560112 | 656330.3824 | 626329.88 | 256986.14 | 0 | 62633 | 671368.88 | 391064 | 176071 | 567135 | 3398.59 | 1021.17 | 1770.82 |  | 471.68 |  | 134.92 | 780695.26 | 266853.82 | 114088.44 |  | 369210.96 | 27152.51 | 3389.53 | 0 | 154365.38 | 137.7% |  | 17888.07 | 798583.33 | 149036 | 27.59% | -156059 | -7023 | -1.254% | 0 |  | -127214.45 | -19.47% | -127214.45 | -18.95% | -93368.81 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878580 - JUPITER, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2018-04-02 | 2019-05-17 | 2018-04-02 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877566¦¦2020-03-31
FP | C | Yes | 877567 |  | 49442 EXXON REFINERY WELL 52 | ALBARADO, JORDAN A | 100% | 24820 | 0 | 24820 | 27790 | 27790 | 27790 | 0 | 0 | 27790 | 12325 | 0 | 12325 | 800.23 |  |  |  | 800.23 |  |  | 11315.48 | 6730.07 | 1148.4 |  | 3437.01 |  |  | 16474.52 | 0 | 91.81% |  | 0 | 11315.48 | 12495 | 50.34% | 0 | 12495 | 50.34% | 0 |  | 16474.52 | 59.28% | 16474.52 | 59.28% | -2970 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878581 - EXXON MOBIL REFINERY | WATER | WATER REPAIR & INSTALLATION | 2018-04-11 | 2019-04-30 | 2018-04-11 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877567¦¦2020-03-31
UP | CJ | Yes | 877569 |  | 49470 FILMORE RANCH BOOSTER & | GRACE, GARY L. | 100% | 26586 | 5691 | 32277 | 23252.5 | 23252.5 | 0 | 0 | 0 | 23252.5 | 17413 | 3927 | 21340 | [7 empty] | 14458.09 | 1550.54 | 150.02 |  | 12757.53 |  |  | 8794.41 | 0 | 67.75% |  | 0 | 14458.09 | 9173 | 34.5% | 1764 | 10937 | 33.88% | 0 |  | 8794.41 | 37.82% | 8794.41 | 37.82% | 9024.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878583 - FILLMORE VALLEY VIEW RANCH | WATER | WATER REPAIR & INSTALLATION | 2018-04-06 | 2019-04-30 | 2018-04-06 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877569¦¦2020-03-31
UP | C | Yes | 877570 |  | 49511 CLAWA RAG OIL CHANGE | BRASHEAR, DAVID M | 100% | 632 | 39396.48 | 40028.48 | 46937.78 | 46937.78 | 40152.53 | 0 | 0 | 46937.78 | 427 | 26893.23 | 27320.23 | [7 empty] | 40706.74 | 18115.41 | 2341.65 |  | 20214.68 | 35 |  | 6231.04 | 0 | 149% |  | 0 | 40706.74 | 205 | 32.44% | 12503.25 | 12708.25 | 31.75% | 0 |  | 6231.04 | 13.28% | 6231.04 | 13.28% | -6909.3 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878584 - CRESTLINE LAKE ARROWHEAD WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2018-04-18 | 2019-04-30 | 2018-04-18 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877570¦¦2020-03-31
FP | CJ | Yes | 877575 |  | 49603 MINEOLA NY WELL 1 AST | MCCARTNEY, JEFFREY C | 100% | 214750 | 0 | 214750 | 210562.5 | 210562.5 | 86112.5 | 4180 | 10528.13 | 210562.5 | 169207 | 0 | 169207 | 153.06 | 151.3 |  |  | 1.76 |  |  | 180595.63 | 23787.45 | 291.6 |  | 152266.58 | 4250 |  | 29966.87 | 0 | 106.7% |  | 0 | 180595.63 | 45543 | 21.21% | 0 | 45543 | 21.21% | 0 |  | 29966.87 | 14.23% | 29966.87 | 14.23% | 4187.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 878589 - PHILIP ROSS INDUSTRIES INC | WATER | WATER TREATMENT | 2018-04-24 | 2019-04-25 | 2018-04-24 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877575¦¦2020-03-31
FP | CJ | Yes | 877587 |  | 49718 PBHMD WELL 3 ANND 4 INST | SCHANAMAN, MIKE L. | 100% | 432390 | 0 | 432390 | 396871 | 396871 | 174935 | 0 | 0 | 396871 | 299859 | 1971 | 301830 | 2400 |  |  |  | 2400 |  |  | 249808.06 | 14399.29 | 3153 |  | 232255.77 |  |  | 147062.94 | 0 | 82.76% |  | 0 | 249808.06 | 132531 | 30.65% | -1971 | 130560 | 30.19% | 0 |  | 147062.94 | 37.06% | 147062.94 | 37.06% | 35519 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878597 - PAINT BRUSH HILLS METROPOLITAN DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2018-05-07 | 2019-04-30 | 2018-05-07 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877587¦¦2020-03-31
UP | CJ | Yes | 877589 |  | 49741 FILLMORE RANCH VFD | GRACE, GARY L. | 100% | 36927 | 0 | 36927 | 34560.81 | 34560.81 | 19253.81 | 0 | 0 | 34560.81 | 26255 | 0 | 26255 | [7 empty] | 30631.79 | 5036.3 | 1619.24 |  | 18460.48 | 5515.77 |  | 3929.02 | 0 | 116.7% |  | 0 | 30631.79 | 10672 | 28.9% | 0 | 10672 | 28.9% | 0 |  | 3929.02 | 11.37% | 3929.02 | 11.37% | 2366.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878583 - FILLMORE VALLEY VIEW RANCH | WATER | WATER REPAIR & INSTALLATION | 2018-05-31 | 2019-06-29 | 2018-05-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877589¦¦2020-03-31
FP | C | Yes | 877590 |  | 49748 BR WATER NEW WELL MONTES | LOPEZ-VASQUEZ, JUAN C. | 100% | 440000 | 66239 | 506239 | 509064 | 509064 | 57661.41 | 0 | 0 | 509064 | 361236 | 379264 | 740500 | [7 empty] | 825029.9 | 306869.38 | 166196.06 |  | 290090.37 | 61874.09 |  | 0 | 315965.9 | 111.4% |  | 0 | 825029.9 | 78764 | 17.9% | -313025 | -234261 | -46.27% | 0 |  | -315965.9 | -62.07% | -315965.9 | -62.07% | -2825 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER SUPPLY | 2018-05-04 | 2019-05-30 | 2018-05-04 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877590¦¦2020-03-31
TM | CJ | Yes | 877593 |  | 49838 PENDER NE WELL 2 | GANSEBOM, JASON W. | 100% | 5375 | 0 | 5375 | 3373.94 | 3373.94 | 0 | 0 | 0 | 3373.94 | 3225 | 0 | 3225 | 2441.18 | 1100.39 | 676.98 |  | 663.81 |  |  | 2725.79 | 1100.39 | 676.98 |  | 948.42 |  |  | 648.15 | 0 | 84.52% |  | 0 | 2725.79 | 2150 | 40% | 0 | 2150 | 40% | 0 |  | 648.15 | 19.21% | 648.15 | 19.21% | 2001.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878601 - PENDER UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2018-05-11 | 2019-06-30 | 2018-05-11 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877593¦¦2020-03-31
UP | C | Yes | 877600 |  | 50049 SANTA PAULA 2 BOOSTERS | GRACE, GARY L. | 100% | 9352 | 16934 | 26286 | 44988.34 | 44988.34 | 24043.88 | 0 | 0 | 44988.34 | 6872 | 10663 | 17535 | [7 empty] | 28925.01 | 10948.05 | 1529.84 |  | 16302.34 | 144.78 |  | 16063.33 | 0 | 165% |  | 0 | 28925.01 | 2480 | 26.52% | 6271 | 8751 | 33.29% | 0 |  | 16063.33 | 35.71% | 16063.33 | 35.71% | -18702.34 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878606 - SANTA PAULA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-04-13 | 2019-05-31 | 2018-04-13 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | PROFESSIONAL SERVICES | 877600¦¦2020-03-31
TM | CJ | Yes | 877601 |  | 50069 BRIGHTON WELL 11 SST PUM | SCHANAMAN, MIKE L. | 100% | 67763 | 0 | 67763 | 48852 | 48852 | 48852 | 0 | 0 | 48852 | 49579 | 0 | 49579 | [7 empty] | 41049 |  |  |  | 41049 |  |  | 7803 | 0 | 82.8% |  | 0 | 41049 | 18184 | 26.83% | 0 | 18184 | 26.83% | 0 |  | 7803 | 15.97% | 7803 | 15.97% | 18911 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878569 - BRIGHTON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-06-05 | 2019-10-31 | 2018-06-05 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 877601¦¦2020-03-31
TM | CJ | Yes | 877602 |  | 50071 BRIGHTON WELL 12 SST PUM | SCHANAMAN, MIKE L. | 100% | 73479 | 0 | 73479 | 73479 | 73479 | 54568.8 | 0 | 0 | 73479 | 54343 | 0 | 54343 | [7 empty] | 61934.14 |  |  |  | 61934.14 |  |  | 11544.86 | 0 | 114% |  | 0 | 61934.14 | 19136 | 26.04% | 0 | 19136 | 26.04% | 0 |  | 11544.86 | 15.71% | 11544.86 | 15.71% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878569 - BRIGHTON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-06-05 | 2019-10-31 | 2018-06-05 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 877602¦¦2020-03-31
TM | C | Yes | 877604 |  | 50074 WILLIAM KEFFER PR | BENNETT, MARK C. |  | 8000 | 0 | 8000 |  |  | 0 | 0 | 0 |  | 5000 | 0 | 5000 | [20 empty] | 3000 | 37.5% | 0 | 3000 | 37.5% | 0 | [5 empty] | 8000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878607 - DO NOT USE KEFFER, WILLIAM | WATER | WATER REPAIR & INSTALLATION | 2018-06-05 | 2019-05-31 | 2018-06-05 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877604¦¦2020-03-31
FP | LJ | Yes | 877607 |  | 50139 GULF POWER PLANT SMITH T | MARTINEZ, MIGUEL E | 95.11% | 7797286 | 0 | 7797286 | 7038201.1646 | 6293220.14 | 1745121.04 | 641950.38 | 629322.01 | 7400076 | 5347590 | 1970483 | 7318073 | 1090891.76 | 166994.73 | 130863.22 |  | 299371.42 | 114861.92 | 378800.47 | 15565782.63 | 3561255.75 | 4002786.03 |  | 3816880.39 | 3215172.79 | 969687.67 | 0 | 9272562.49 | 212.7% |  | 800327.37 | 16366110 | 2449696 | 31.42% | -1970483 | 479213 | 6.146% | 0 |  | -8966034 | -135.9% | -8966034 | -121.2% | 1197537.37 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878610 - GULF POWER COMPANY | WATER | WATER SPECIALTY DRILLING | 2018-06-18 | 2019-06-18 | 2018-06-18 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877607¦¦2020-03-31
TM | CJ | Yes | 877608 |  | 50144 NEBRASKA CITY WELL 2 TRE | GANSEBOM, JASON W. | 100% | 16947 | 51629.5 | 68576.5 | 64439.51 | 64439.51 | 0 | 0 | 0 | 64439.51 | 10168 | 51371.65 | 61539.65 | 9767.67 | 367.69 | 192.56 |  | 9207.42 |  |  | 52060.33 | 23532.16 | 7763.72 |  | 20764.45 |  |  | 12379.18 | 0 | 84.6% |  | 0 | 52060.33 | 6779 | 40% | 257.85 | 7036.85 | 10.26% | 0 |  | 12379.18 | 19.21% | 12379.18 | 19.21% | 4136.99 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878611 - NEBRASKA CITY UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2018-06-18 | 2019-06-30 | 2018-06-18 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 877608¦¦2020-03-31
FP | C | Yes | 877611 | 877612 | 50195 TARGA RESOURCES WELL 7 P | CALLAHAN, DANIEL E. | 100% | 222467 | 0 | 222467 | 220962.3 | 220962.3 | 181042.5 | 0 | 0 | 220962.3 | 150922 | 0 | 150922 | [7 empty] | 193945.03 | 55401.72 | 17380.34 |  | 101097.42 | 20065.55 |  | 27017.27 | 0 | 128.5% |  | 0 | 193945.03 | 71545 | 32.16% | 0 | 71545 | 32.16% | 0 |  | 27017.27 | 12.23% | 27017.27 | 12.23% | 1504.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 878614 - TARGA MIDSTREAM SERVICE LP | WATER | WATER REPAIR & INSTALLATION | 2018-06-15 | 2019-01-31 | 2018-06-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877611¦¦2020-03-31
FP | LJ | Yes | 877612 | 877612 | 50208 TARGA RESOURCES NEW WELL | LOPEZ-VASQUEZ, JUAN C. | 100% | 952533 | -2917 | 949616 | 949616 | 951810.2 | 0 | 0 | 0 | 949616 | 665860 | -105860 | 560000 | [7 empty] | 561096.03 | 211830.87 | 71553.89 |  | 247209.01 | 30502.26 |  | 390714.17 | 0 | 100.2% |  | 0 | 561096.03 | 286673 | 30.1% | 102943 | 389616 | 41.03% | 0 |  | 388519.97 | 40.91% | 388519.97 | 40.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878615 - TARGA DOWNSTREAM LLC HAA | WATER | WATER SUPPLY | 2018-06-15 | 2019-07-31 | 2018-06-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877612¦¦2020-03-31
FP | C | Yes | 877614 |  | 50230 DENKA LAPLACE RI WW 2 | LOPEZ-VASQUEZ, JUAN C. | 100% | 7500 | 38025 | 45525 | 43925 | 43925 | 1950 | 0 | 0 | 43925 | 5012 | 26376.7 | 31388.7 | [7 empty] | 28595.5 | 17011.67 | 2860.8 |  | 8323.03 | 400 |  | 15329.5 | 0 | 91.1% |  | 0 | 28595.5 | 2488 | 33.17% | 11648.3 | 14136.3 | 31.05% | 0 |  | 15329.5 | 34.9% | 15329.5 | 34.9% | 1600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878617 - DENKA PERFORMANCE ELASTOMERS | WATER | WATER REPAIR & INSTALLATION | 2018-06-23 | 2019-08-31 | 2018-06-23 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877614¦¦2020-03-31
UP | C | Yes | 877617 | 877617 | 50278 EMWD 205 DRILLING | TRAMMELL, DUANE R. | 100% | 1027904 | 55742 | 1083646 | 964346.65 | 964346.65 | 8169.39 | 0 | 0 | 964346.65 | 795158 | 411871 | 1207029 | [7 empty] | 1211639.34 | 364650.88 | 290736.16 |  | 519646.79 | 36605.51 |  | 0 | 247292.69 | 100.4% |  | 0 | 1211639.34 | 232746 | 22.64% | -356129 | -123383 | -11.39% | 0 |  | -247292.69 | -25.64% | -247292.69 | -25.64% | 119299.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878619 - EASTERN MUNICIPAL WATER DISTRICT | WATER | WATER SUPPLY | 2018-06-25 | 2019-10-31 | 2018-06-25 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877617¦¦2020-03-31
FP | C | Yes | 877618 | 877619 | 50286 RIO RANCHO NM WELL 13 TE | SCHANAMAN, MIKE L. | 100% | 259345 | 0 | 259345 | 0 | 0 | 0 | 0 | 0 | 0 | 207408 | 2123 | 209531 | [7 empty] | 222471.6 | 67823.62 | 46129.48 |  | 86824.9 | 21693.6 |  | 0 | 222471.6 | 106.2% |  | 0 | 222471.6 | 51937 | 20.03% | -2123 | 49814 | 19.21% | 0 |  | -222471.6 |  | -222471.6 |  | 259345 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878620 - RIO RANCHO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-06-26 | 2019-10-31 | 2018-06-26 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877618¦¦2020-03-31
FP | C | Yes | 877619 | 877619 | 50287 RIO RANCHO NM WELL 13 DR | DECKER, JASEN | 100% | 2393378 | -397435 | 1995943 | 2264167.78 | 2264167.78 | 382417.75 | 0 | 0 | 2264167.78 | 1914456 | 181946 | 2096402 | 50.34 |  |  |  | 50.34 |  |  | 2141367.33 | 447235.97 | 221141.66 |  | 1346986.16 | 126003.54 |  | 122800.45 | 0 | 102.1% |  | 0 | 2141367.33 | 478922 | 20.01% | -579381 | -100459 | -5.033% | 0 |  | 122800.45 | 5.424% | 122800.45 | 5.424% | -268224.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878620 - RIO RANCHO, CITY OF | WATER | WATER SUPPLY | 2018-06-26 | 2019-09-30 | 2018-06-26 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877619¦¦2020-03-31
FP | CJ | Yes | 877628 |  | 50374 DIXON IL WELL 3 WARRA | SNELTEN, BRIAN M | 100% | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 15000 | 0 | 15000 | [7 empty] | 14987.92 | 9137.37 | 1895 |  | 3802.55 | 153 |  | 0 | 14986.92 | 99.92% |  | 0 | 14987.92 | -14999 | -1499900% | 0 | -14999 | -1499900% | 0 |  | -14986.92 | -1498692% | -14986.92 | -1498692% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878628 - DIXON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-07-03 | 2019-08-24 | 2018-07-03 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 877628¦¦2020-03-31
FP | C | Yes | 877630 |  | 50411 SMITH LOGAN TODD | MIGUEL, SEAN J. | 100% | 193692 | 0 | 193692 | 193692 | 193692 | 0 | 0 | 0 | 193692 | 153408 | 0 | 153408 | [7 empty] | 162908.64 | 1506.69 | 539.34 |  | 160862.61 |  |  | 30783.36 | 0 | 106.2% |  | 0 | 162908.64 | 40284 | 20.8% | 0 | 40284 | 20.8% | 0 |  | 30783.36 | 15.89% | 30783.36 | 15.89% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878630 - SMITH CONTRACTORS INC | WATER | WATER EQUIPMENT SALES | 2018-07-05 | 2019-11-30 | 2018-07-05 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877630¦¦2020-03-31
FP | C | Yes | 877634 |  | 50452 CITY OF ARKANSAS CITY | BENNETT, MARK C. | 100% | 29465 | 0 | 29465 | 49881.87 | 49881.87 | 50455.21 | 0 | 0 | 49881.87 | 20465 | 0 | 20465 | [7 empty] | 44895.29 | 21211.23 | 3749.99 |  | 19613.57 | 320.5 |  | 4986.58 | 0 | 219.4% |  | 0 | 44895.29 | 9000 | 30.54% | 0 | 9000 | 30.54% | 0 |  | 4986.58 | 9.997% | 4986.58 | 9.997% | -20416.87 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878634 - ARKANSAS CITY, CITY OF | WATER | WATER EQUIPMENT SALES | 2018-07-10 | 2019-07-10 | 2018-07-10 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 877634¦¦2020-03-31
FP | C | Yes | 877637 |  | 50483 NLC WELL LOGGING SERVICE | MARTINEZ, MIGUEL E | 100% | 59500 | 14640 | 74140 | 74440 | 74440 | 9000 | 0 | 0 | 74440 | 34433 | 8567 | 43000 | 80.08 | 80.08 | [5 empty] | 40726.97 | 21089.99 | 5852.48 |  | 2699.5 | 11085 |  | 33713.03 | 0 | 94.71% |  | 0 | 40726.97 | 25067 | 42.13% | 6073 | 31140 | 42% | 0 |  | 33713.03 | 45.29% | 33713.03 | 45.29% | -300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878637 - LEE, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2018-07-19 | 2019-08-30 | 2018-07-19 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877637¦¦2020-03-31
UP | C | Yes | 877643 |  | 50530 LADWP R&I CONTRACT RENEW | BRASHEAR, DAVID M | 100% | 250000 | 225000 | 475000 | 582651.77 | 582651.77 | 238567.81 | 0 | 0 | 582651.77 | 187500 | 202000 | 389500 | [7 empty] | 547475.92 | 193348.69 | 54525.44 |  | 204111.08 | 95490.71 |  | 35175.85 | 0 | 140.6% |  | 0 | 547475.92 | 62500 | 25% | 23000 | 85500 | 18% | 0 |  | 35175.85 | 6.037% | 35175.85 | 6.037% | -107651.77 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878643 - LADWP | WATER | WATER REPAIR & INSTALLATION | 2018-07-20 | 2019-07-31 | 2018-07-20 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877643¦¦2020-03-31
UP | CJ | Yes | 877644 |  | 50538 PERC WATER WELL 5 DISCAH | BRASHEAR, DAVID M | 100% | 17081 | 0 | 17081 | 14838.75 | 14838.75 | 0 | 0 | 0 | 14838.75 | 10973 | 0 | 10973 | 0 |  |  |  | 0 |  |  | 12326.29 | 5160.68 | 896.98 |  | 6236.91 | 31.72 |  | 2512.46 | 0 | 112.3% |  | 0 | 12326.29 | 6108 | 35.76% | 0 | 6108 | 35.76% | 0 |  | 2512.46 | 16.93% | 2512.46 | 16.93% | 2242.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878644 - ADELANTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-07-19 | 2019-09-28 | 2018-07-19 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877644¦¦2020-03-31
TM | C | Yes | 877647 |  | 50558 50558 AK STEEL ACID PLA | SIMPSON, CARL L. | 100% | 4000 | 679345 | 683345 | 683345 | 683345 | 683345 | 0 | 0 | 683345 | 2800 | 500522 | 503322 | 16 | 16 | [5 empty] | 537704.81 | 146623.88 | 170621.4 |  | 201412.32 | 19047.21 |  | 145640.19 | 0 | 106.8% |  | 0 | 537704.81 | 1200 | 30% | 178823 | 180023 | 26.34% | 0 |  | 145640.19 | 21.31% | 145640.19 | 21.31% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2018-07-23 | 2019-07-31 | 2018-07-23 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877647¦¦2020-03-31
UP | C | Yes | 877654 |  | 50605 TOPA TOPA WEST WELL ELEC | GRACE, GARY L. | 100% | 29322 | 0 | 29322 | 24370.39 | 24370.39 | 0 | 0 | 0 | 24370.39 | 17820 | 0 | 17820 | [7 empty] | 13430.29 | 4499.14 | 911.47 |  | 2899.68 | 5120 |  | 10940.1 | 0 | 75.37% |  | 0 | 13430.29 | 11502 | 39.23% | 0 | 11502 | 39.23% | 0 |  | 10940.1 | 44.89% | 10940.1 | 44.89% | 4951.61 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878563 - TOPA TOPA RANCH & NURSERY LLC | WATER | WATER REPAIR & INSTALLATION | 2018-07-26 | 2019-08-30 | 2018-07-26 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877654¦¦2020-03-31
FP | CJ | Yes | 877656 |  | 50620 50620 NEW HAVEN WELLS 3 | BRECKENRIDGE, TERRY L. | 100% | 94253 | 143520 | 237773 | 108225.33 | 108225.33 | 72218 | 0 | 0 | 108225.33 | 72038 | 111945 | 183983 | 10715.4 | 3892.44 | 539.14 |  | 6283.82 |  |  | 87434.65 | 21624.65 | 9101.18 |  | 56708.82 |  |  | 20790.68 | 0 | 47.52% |  | 0 | 87434.65 | 22215 | 23.57% | 31575 | 53790 | 22.62% | 31575 |  | 20790.68 | 19.21% | 20790.68 | 19.21% | 129547.67 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 906304 - J F ALLEN COMPANY | WATER | WATER REPAIR & INSTALLATION | 2018-07-27 | 2019-08-30 | 2018-07-27 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877656¦¦2020-03-31
FP | C | Yes | 877657 |  | 50628 LAMBERTI NEW WELL | CALLAHAN, DANIEL E. | 100% | 172657 | 8850 | 181507 | 162657 | 162657 | 162657 | 0 | 0 | 162657 | 120525 | 15051.2 | 135576.2 | [7 empty] | 116033.37 | 4160.13 | 3025.4 |  | 6778.84 | 102069 |  | 46623.63 | 0 | 85.59% |  | 0 | 116033.37 | 52132 | 30.19% | -6201.2 | 45930.8 | 25.31% | 0 |  | 46623.63 | 28.66% | 46623.63 | 28.66% | 18850 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 878655 - LAMBERTI USA INC | WATER | WATER SUPPLY | 2018-07-24 | 2019-10-31 | 2018-07-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877657¦¦2020-03-31
UP | C | Yes | 877664 |  | 50694 RHCC NEW WELL | TRAMMELL, DUANE R. | 100% | 571170 | 149390.52 | 720560.52 | 704731.77 | 704731.77 | 281277.02 | 0 | 0 | 704731.77 | 427877 | 109242.4 | 537119.4 | [7 empty] | 609004.72 | 164326.2 | 64048.69 |  | 368945.57 | 11684.26 |  | 95727.05 | 0 | 113.4% |  | 0 | 609004.72 | 143293 | 25.09% | 40148.12 | 183441.12 | 25.46% | 0 |  | 95727.05 | 13.58% | 95727.05 | 13.58% | 15828.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878661 - ROLLING HILLS COUNTRY CLUB | WATER | WATER SUPPLY | 2018-07-31 | 2019-02-25 | 2018-07-31 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877664¦¦2020-03-31
UP | C | Yes | 877666 | 877617 | 50705 EMWD 205 TEST PUMPING | TRAMMELL, DUANE R. | 100% | 87885 | 10640 | 98525 | 83377 | 83377 | 0 | 0 | 0 | 83377 | 58788 | 90656 | 149444 | [7 empty] | 152905.49 | 100194.24 | 26504.89 |  | 17514.23 | 8692.13 |  | 0 | 69528.49 | 102.3% |  | 0 | 152905.49 | 29097 | 33.11% | -80016 | -50919 | -51.68% | 0 |  | -69528.49 | -83.39% | -69528.49 | -83.39% | 15148 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878619 - EASTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2018-06-25 | 2019-10-31 | 2018-06-25 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877666¦¦2020-03-31
UP | CJ | Yes | 877667 |  | 50720 WESTERN HEIGHTS WELL 9 | BRASHEAR, DAVID M | 100% | 23724 | 92267.98 | 115991.98 | 112895.31 | 112895.31 | 93543.25 | 0 | 0 | 112895.31 | 16712 | 68591.29 | 85303.29 | 1607.09 | 931.47 | 67.24 |  | 608.38 |  |  | 84557.15 | 25851.95 | 4820.09 |  | 53885.11 |  |  | 28338.16 | 0 | 99.13% |  | 0 | 84557.15 | 7012 | 29.56% | 23676.69 | 30688.69 | 26.46% | 676.67 | 676.67 | 28338.16 | 25.1% | 28338.16 | 25.1% | 3096.67 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878663 - WESTERN HEIGHTS WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2018-08-01 | 2019-10-31 | 2018-08-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877667¦¦2020-03-31
FP | C | Yes | 877672 |  | 50748 ARCONIC WELL 10 REHAB | MIGUEL, SEAN J. | 100% | 49200 | 49200 | 98400 | 100450 | 100450 | 51300 | 0 | 0 | 100450 | 32000 | 32000 | 64000 | [7 empty] | 79436.7 | 34042.53 | 15443.78 |  | 29900.89 | 49.5 |  | 21013.3 | 0 | 124.1% |  | 0 | 79436.7 | 17200 | 34.96% | 17200 | 34400 | 34.96% | 0 |  | 21013.3 | 20.92% | 21013.3 | 20.92% | -2050 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878667 - ARCONIC FORGINGS AND EXTRUSIONS | WATER | WATER REPAIR & INSTALLATION | 2018-07-31 | 2019-08-30 | 2018-07-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 877672¦¦2020-03-31
FP | CJ | Yes | 877673 |  | 50756 BAYOU LIBERTY TV CAMP VI | LOPEZ-VASQUEZ, JUAN C. | 100% | 7850 | 35428 | 43278 | 44488 | 44488 | 0 | 0 | 0 | 44488 | 4812 | 25364 | 30176 | [7 empty] | 33604.69 | 17283.34 | 2681.5 |  | 13164.85 | 475 |  | 10883.31 | 0 | 111.4% |  | 0 | 33604.69 | 3038 | 38.7% | 10064 | 13102 | 30.27% | 0 |  | 10883.31 | 24.46% | 10883.31 | 24.46% | -1210 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878648 - BAYOU LIBERTY WATER CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2018-08-08 | 2019-10-31 | 2018-08-08 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877673¦¦2020-03-31
UP | CJ | Yes | 877676 |  | 50796 AGP SGT BLUFF TEST WEL | GANSEBOM, JASON W. | 100% | 18124 | 0 | 18124 | 17504 | 17504 | 0 | 0 | 0 | 17504 | 10874 | 0 | 10874 | [7 empty] | 9785.03 | 5024.36 | 1892 |  | 1561.67 | 1307 |  | 7718.97 | 0 | 89.99% |  | 0 | 9785.03 | 7250 | 40% | 0 | 7250 | 40% | 0 |  | 7718.97 | 44.1% | 7718.97 | 44.1% | 620 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878670 - AG PROCESSING INC | WATER | WATER SUPPLY | 2018-08-13 | 2019-08-31 | 2018-08-13 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 877676¦¦2020-03-31
FP | LJ | Yes | 877680 |  | 50822 LEWIS & CLARK REGIONAL W | HEILIGER, TERENCE L. | 98.78% | 1178462 | -9687.45 | 1168774.55 | 1144689.2117 | 1158779.55 | 631614.84 | 161363.25 | 115877.97 | 1158779.55 | 947351 | 99949.63 | 1047300.63 | 0.3 | 0.3 |  |  | 0 |  | 0 | 1181057.75 | 402204.02 | 172496.81 |  | 561915.48 | 43979.54 | 461.9 | 0 | 22278.2 | 112.8% |  | 14538.01 | 1195595.76 | 231111 | 19.61% | -109637.08 | 121473.92 | 10.39% | 0 |  | -36816.21 | -3.218% | -36816.21 | -3.177% | 24533.01 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878673 - WELFL CONSTRUCTION | WATER | WATER SUPPLY | 2018-08-13 | 2019-10-31 | 2018-08-13 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877680¦¦2020-03-31
UP | CJ | Yes | 877684 |  | 50861 SUN PAC WELL 5 | GRACE, GARY L. | 100% | 17794 | 106087 | 123881 | 121747.37 | 121747.37 | 0 | 0 | 0 | 121747.37 | 13209 | 76829 | 90038 | [7 empty] | 91766.58 | 29760.06 | 7325.04 |  | 50631.48 | 4050 |  | 29980.79 | 0 | 101.9% |  | 0 | 91766.58 | 4585 | 25.77% | 29258 | 33843 | 27.32% | 0 |  | 29980.79 | 24.63% | 29980.79 | 24.63% | 2133.63 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878676 - SUN PACIFIC FARMS | WATER | WATER REPAIR & INSTALLATION | 2018-08-28 | 2019-08-31 | 2018-08-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877684¦¦2020-03-31
UP | C | Yes | 877686 |  | 50935 PRESTAGE FOODS PUMP HO | SNELTEN, BRIAN M | 100% | 1997722 | 342030.18 | 2339752.18 | 2339356.18 | 2339356.18 | 258423.93 | 0 | 0 | 2339356.18 | 1482088 | 463339 | 1945427 | 42.4 |  |  |  | 42.4 |  |  | 1947188.95 | 179576.09 | 98121.27 |  | 545256.23 | 1124235.36 |  | 392167.23 | 0 | 100.1% |  | 0 | 1947188.95 | 515634 | 25.81% | -121308.82 | 394325.18 | 16.85% | 0 |  | 392167.23 | 16.76% | 392167.23 | 16.76% | 396 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878481 - ISG | WATER | WATER SUPPLY | 2018-08-22 | 2019-12-31 | 2018-08-22 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877686¦¦2020-03-31
UP | C | Yes | 877689 |  | 50952 NICHOLS HILLS REPLACEMEN | EVANS, TRAVIS L | 100% | 641173 | 21022 | 662195 | 648374.89 | 648374.89 | 200537.3 | 0 | 0 | 648374.89 | 490467 | 15866 | 506333 | [7 empty] | 523285.72 | 64085.34 | 18269.57 |  | 107048.13 | 333882.68 |  | 125089.17 | 0 | 103.3% |  | 0 | 523285.72 | 150706 | 23.5% | 5156 | 155862 | 23.54% | 0 |  | 125089.17 | 19.29% | 125089.17 | 19.29% | 13820.11 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 878678 - NICHOLS HILLS, CITY OF | WATER | WATER SUPPLY | 2018-09-03 | 2019-01-31 | 2018-08-27 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 877689¦¦2020-03-31
UP | CJ | Yes | 877691 | 877698 | 50961 MMBAPEXAUCTIONEQUIPNEWWE | BRASHEAR, DAVID M | 100% | 57406 | 0 | 57406 | 24873.15 | 24873.15 | 0 | 0 | 0 | 24873.15 | 38247 | 0 | 38247 | -1349.64 |  |  |  | -1349.64 |  |  | 20094.88 | 383.73 |  |  | 19711.15 |  |  | 4778.27 | 0 | 52.54% |  | 0 | 20094.88 | 19159 | 33.37% | 0 | 19159 | 33.37% | 0 |  | 4778.27 | 19.21% | 4778.27 | 19.21% | 32532.85 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878679 - MMB APEX AUCTION LLC | WATER | WATER SUPPLY | 2018-09-19 | 2019-11-30 | 2018-09-19 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877691¦¦2020-03-31
UP | C | Yes | 877694 |  | 50985 SILVER LAKE CC WELL 10N | EISHA, JOSEPH J. | 100% | 2238 | 43190 | 45428 | 45464 | 45464 | 30757.72 | 0 | 0 | 45464 | 1500 | 33000 | 34500 | [7 empty] | 40491.51 | 27420.02 | 2326.72 |  | 10744.77 |  |  | 4972.49 | 0 | 117.4% |  | 0 | 40491.51 | 738 | 32.98% | 10190 | 10928 | 24.06% | 0 |  | 4972.49 | 10.94% | 4972.49 | 10.94% | -36 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878682 - SILVER LAKES COUNTRY CLUB | WATER | WATER REPAIR & INSTALLATION | 2018-09-22 | 2019-09-30 | 2018-09-22 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877694¦¦2020-03-31
UP | C | Yes | 877698 | 877698 | 51016 MMB APEXAUCTIONDRILLNEWW | TRAMMELL, DUANE R. | 100% | 364134 | 285205 | 649339 | 669613.63 | 669613.63 | 398061.24 | 0 | 0 | 669613.63 | 279271 | 350617 | 629888 | [7 empty] | 633081.29 | 173747 | 116371.03 |  | 316776.06 | 26187.2 |  | 36532.34 | 0 | 100.5% |  | 0 | 633081.29 | 84863 | 23.31% | -65412 | 19451 | 2.996% | 0 |  | 36532.34 | 5.456% | 36532.34 | 5.456% | -20274.63 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878679 - MMB APEX AUCTION LLC | WATER | WATER SUPPLY | 2018-09-19 | 2019-12-31 | 2018-09-19 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877698¦¦2020-03-31
FP | LJ | Yes | 877701 |  | 51040 BRWC DRILL GOVERNMENT ST | LOPEZ-VASQUEZ, JUAN C. | 100% | 738250 | 0 | 738250 | 727290 | 727290 | 155250 | 0 | 0 | 727290 | 562523 | 0 | 562523 | [7 empty] | 565267.62 | 191320.03 | 68630.1 |  | 268034.54 | 37282.95 |  | 162022.38 | 0 | 100.5% |  | 0 | 565267.62 | 175727 | 23.8% | 0 | 175727 | 23.8% | 0 |  | 162022.38 | 22.28% | 162022.38 | 22.28% | 10960 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER SUPPLY | 2018-08-31 | 2019-02-28 | 2018-08-31 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877701¦¦2020-03-31
UP | C | Yes | 877705 |  | 51072 OSWEGO WELL 10 | BALLUFF, WILLIAM O. | 100% | 8486 | 0 | 8486 | 11276.35 | 11276.35 | 11276.35 | 0 | 0 | 11276.35 | 5500 | 0 | 5500 | [7 empty] | 13695.13 | 7003.72 | 1280 |  | 5121.86 | 289.55 |  | 0 | 2418.78 | 249% |  | 0 | 13695.13 | 2986 | 35.19% | 0 | 2986 | 35.19% | 0 |  | -2418.78 | -21.45% | -2418.78 | -21.45% | -2790.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878689 - OSWEGO, VILLAGE OF | WATER | WATER EQUIPMENT SALES | 2018-08-27 | 2019-09-30 | 2018-08-27 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877705¦¦2020-03-31
UP | C | Yes | 877708 | 877708 | 51088 SRP WELL 31 3E 7 0N D | SEIDEN, ANDREW L. | 100% | 952728 | 237942 | 1190670 | 1190670.29 | 1190670.29 | 0 | 0 | 0 | 1190670.29 | 733271 | 317927 | 1051198 | [7 empty] | 1073020.46 | 294278.93 | 150195.61 |  | 571996.02 | 56549.9 |  | 117649.83 | 0 | 102.1% |  | 0 | 1073020.46 | 219457 | 23.03% | -79985 | 139472 | 11.71% | 0 |  | 117649.83 | 9.881% | 117649.83 | 9.881% | -0.29 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878691 - SALT RIVER PROJECT | WATER | WATER SUPPLY | 2018-09-21 | 2019-09-30 | 2018-09-21 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877708¦¦2020-03-31
FP | CJ | Yes | 877722 |  | 51220 SOUTHERN IONICS NEW WE | ALBARADO, JORDAN A | 100% | 255000 | 0 | 255000 | 254000 | 254000 | 254000 | 0 | 0 | 254000 | 203328 | -15000 | 188328 | 31.31 |  |  |  | 31.31 |  |  | 172883.19 | 78083.52 | 18111.05 |  | 70081.49 | 6607.13 |  | 81116.81 | 0 | 91.8% |  | 0 | 172883.19 | 51672 | 20.26% | 15000 | 66672 | 26.15% | 0 |  | 81116.81 | 31.94% | 81116.81 | 31.94% | 1000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 898039 - SOUTHERN IONICS INC | WATER | WATER SUPPLY | 2018-09-20 | 2019-12-31 | 2018-09-20 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877722¦¦2020-03-31
UP | CJ | Yes | 877723 |  | 51231 WATSON NY 16 X 10 WELLS | CROOK, CHARLES M | 100% | 127950 | 67345 | 195295 | 231503.5 | 231503.5 | 231503.5 | 14900 | 0 | 231503.5 | 90000 | 53362.06 | 143362.06 | 22810.19 | 14529.67 | 3763.33 |  | 4517.19 |  |  | 199365.66 | 86154.88 | 47165.28 |  | 66045.5 |  |  | 32137.84 | 0 | 139.1% |  | 0 | 199365.66 | 37950 | 29.66% | 13982.94 | 51932.94 | 26.59% | 7412.94 |  | 32137.84 | 13.88% | 32137.84 | 13.88% | -36208.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 878702 - HYDROSOURCE ASSOCIATES INC | WATER | WATER SUPPLY | 2018-11-25 | 2019-01-31 | 2018-09-21 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877723¦¦2020-03-31
FP | LJ | Yes | 877726 |  | 51243 RAMSEY IN LAYNEOX | MCCARTNEY, JEFFREY C | 98.17% | 697000 | 20777.5 | 717777.5 | 704633.4594 | 717777.5 | 121842.5 | 19267.5 | 34925.5 | 717777.5 | 490673 | 7884.15 | 498557.15 | 8021.13 | 2759.76 |  |  | 301.37 | 4960 |  | 530415.7 | 42525.69 | 1075.76 |  | 299819.25 | 186995 |  | 187361.8 | 0 | 106.4% |  | 9894.23 | 540309.93 | 206327 | 29.6% | 12893.35 | 219220.35 | 30.54% | 4333.5 | 4333.5 | 174217.76 | 24.72% | 177467.57 | 24.72% | 13144.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 878705 - THIENEMAN CONSTRUCTION INC | WATER | WATER TREATMENT | 2018-09-14 | 2019-09-30 | 2018-09-14 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877726¦¦2020-03-31
FP | C | Yes | 877728 |  | 51250 BASF WELL P 803 PULL PUM | LOPEZ-VASQUEZ, JUAN C. | 100% | 8500 | 70845 | 79345 | 79345 | 79345 | 26345 | 0 | 0 | 79345 | 4237 | 44879 | 49116 | [7 empty] | 44566.48 | 18787.03 | 5651.92 |  | 10918.44 | 9209.09 |  | 34778.52 | 0 | 90.74% |  | 0 | 44566.48 | 4263 | 50.15% | 25966 | 30229 | 38.1% | 0 |  | 34778.52 | 43.83% | 34778.52 | 43.83% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878707 - BASF CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2018-10-08 | 2019-11-30 | 2018-10-08 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877728¦¦2020-03-31
FP | LJ | Yes | 877732 |  | 51300 WC BRINE NEW WELL | ALBARADO, JORDAN A | 97.07% | 715200 | 25000 | 740200 | 718514.9507 | 738200 | 284080 | 0 | 0 | 740200 | 484771 | 12500 | 497271 | 0 |  | 0 |  |  |  |  | 508650.77 | 144455.56 | 60052.67 |  | 276618.57 | 27523.97 |  | 229549.23 | 0 | 102.3% |  | 15351.27 | 524002.04 | 230429 | 32.22% | 12500 | 242929 | 32.82% | 0 |  | 209864.18 | 29.21% | 216197.96 | 29.21% | 21685.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878710 - AXIALL CORPORATION | WATER | WATER SUPPLY | 2018-09-30 | 2019-12-31 | 2018-09-30 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877732¦¦2020-03-31
FP | C | Yes | 877737 |  | 51328 SPRING VALLEY METRO DIST | SCHANAMAN, MIKE L. | 100% | 110045 | 92990 | 203035 | 208035 | 208035 | 160265 | 0 | 0 | 208035 | 76590 | 71129 | 147719 | 0 |  |  |  | 0 |  |  | 150804.33 | 41056.64 | 18078 |  | 89669.69 | 2000 |  | 57230.67 | 0 | 102.1% |  | 0 | 150804.33 | 33455 | 30.4% | 21861 | 55316 | 27.24% | 0 |  | 57230.67 | 27.51% | 57230.67 | 27.51% | -5000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878715 - SPRING VALLEY METROPOLITAN DISTRICT 1 | WATER | WATER REPAIR & INSTALLATION | 2018-10-02 | 2019-12-31 | 2018-10-02 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877737¦¦2020-03-31
UP | CJ | Yes | 877738 |  | 51329 INNOVA | BRASHEAR, DAVID M | 100% | 20000 | 0 | 20000 | 20000 | 20000 | 3806 | 0 | 0 | 20000 | 14400 | 0 | 14400 | [7 empty] | 16377.16 | 878.08 |  |  | 13540.66 | 1958.42 |  | 3622.84 | 0 | 113.7% |  | 0 | 16377.16 | 5600 | 28% | 0 | 5600 | 28% | 0 |  | 3622.84 | 18.11% | 3622.84 | 18.11% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878716 - E WATER SOLUTIONS | WATER | WATER EQUIPMENT SALES | 2018-10-02 | 2019-10-31 | 2018-10-02 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877738¦¦2020-03-31
FP | C | Yes | 877744 |  | 51386 BLYTHEVILLE AR CITY OF W | BURGE, EVERETT E. | 100% | 1257575 | 0 | 1257575 | 1243895 | 1243895 | 1243895 | 0 | 0 | 1243895 | 950175 | 0 | 950175 | [7 empty] | 927537.46 | 212910.93 | 70456.54 |  | 377368.8 | 266801.19 |  | 316357.54 | 0 | 97.62% | 8.75 | 0 | 927537.46 | 307400 | 24.44% | 0 | 307400 | 24.44% | 0 |  | 316357.54 | 25.43% | 316357.54 | 25.43% | 13680 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878722 - BLYTHEVILLE WATER WORKS | WATER | WATER SUPPLY | 2018-10-08 | 2019-05-10 | 2018-10-08 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 877744¦¦2020-03-31
FP | CJ | Yes | 877747 |  | 51402 PHILLIPS 66 WELL 22 HE | GNAU, CASEY T | 100% | 14938 | 0 | 14938 | 14938 | 14938 | 0 | 0 | 0 | 14938 | 7469 | 0 | 7469 | 0 |  |  |  | 0 |  |  | 13559.54 | 1694.54 | 100 |  | 3997.18 | 7767.82 |  | 1378.46 | 0 | 181.5% |  | 0 | 13559.54 | 7469 | 50% | 0 | 7469 | 50% | 0 |  | 1378.46 | 9.228% | 1378.46 | 9.228% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878724 - PHILLIPS 66 | WATER | WATER REPAIR & INSTALLATION | 2018-10-10 | 2019-12-28 | 2018-10-10 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877747¦¦2020-03-31
UP | C | Yes | 877752 |  | 51445 SAN JACINTO LAKE PARK WE | BRASHEAR, DAVID M | 100% | 26595 | 191418 | 218013 | 218017.19 | 218017.19 | 0 | 0 | 0 | 218017.19 | 19933 | 140461 | 160394 | [7 empty] | 154887.43 | 53148.58 | 10073.79 |  | 81855.98 | 9809.08 |  | 63129.76 | 0 | 96.57% |  | 0 | 154887.43 | 6662 | 25.05% | 50957 | 57619 | 26.43% | 0 |  | 63129.76 | 28.96% | 63129.76 | 28.96% | -4.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878729 - SAN JACINTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-10-12 | 2019-12-31 | 2018-10-12 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 877752¦¦2020-03-31
FP | C | Yes | 877753 |  | 51449 ENTERGY CW 3 REHAB | HARTMAN, MICHAEL | 100% | 419300 | 0 | 419300 | 481610 | 481610 | 481610 | 0 | 0 | 481610 | 250000 | 0 | 250000 | 6.75 | 6.75 | 0 |  | 0 |  |  | 325979.38 | 122882.97 | 34217.38 |  | 128188.15 | 40690.88 |  | 155630.62 | 0 | 130.4% |  | 0 | 325979.38 | 169300 | 40.38% | 0 | 169300 | 40.38% | 0 |  | 155630.62 | 32.31% | 155630.62 | 32.31% | -62310 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 890293 - ENTERGY OPERATIONS GRAND GULF | WATER | WATER SUPPLY | 2018-10-16 | 2019-01-30 | 2018-10-16 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877753¦¦2020-03-31
FP | C | Yes | 877756 |  | 51490 GARDEN CITY PARK NY AST | CHESLEY, ANDREW J | 100% | 315000 | 0 | 315000 | 315000 | 315000 | 52879.55 | 0 | 0 | 315000 | 228730.64 | 0 | 228730.64 | [7 empty] | 238085.63 | 25623.49 |  |  | 209962.14 | 2500 |  | 76914.37 | 0 | 104.1% |  | 0 | 238085.63 | 86269.36 | 27.39% | 0 | 86269.36 | 27.39% | 0 |  | 76914.37 | 24.42% | 76914.37 | 24.42% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 878589 - PHILIP ROSS INDUSTRIES INC | WATER | WATER TREATMENT | 2018-10-16 | 2019-05-31 | 2018-10-16 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877756¦¦2020-03-31
FP | CJ | Yes | 877757 |  | 51509 KOCH SGT BLUFF NEW WE | HEILIGER, TERENCE L. | 100% | 83190 | 18805 | 101995 | 101995 | 101995 | 76137 | 0 | 0 | 101995 | 52717 | 11151 | 63868 | 1422.25 | 713.46 | 250.44 |  | 458.35 |  |  | 102654.39 | 22086.36 | 43000.47 |  | 35862.56 | 1705 |  | 0 | 659.39 | 160.7% |  | 0 | 102654.39 | 30473 | 36.63% | 7654 | 38127 | 37.38% | 0 |  | -659.39 | -0.6465% | -659.39 | -0.6465% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878732 - KOCH FERTILIZER SGT BLUFF LLC | WATER | WATER SUPPLY | 2018-10-22 | 2019-12-31 | 2018-10-22 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877757¦¦2020-03-31
FP | C | Yes | 877762 |  | 51539 SCWA NICHOLS RD WELLS 1A | RANFT, DONALD R | 100% | 599400 | -13280 | 586120 | 575400 | 575400 | 295558.5 | 0 | 0 | 575400 | 429000 | -5085.39 | 423914.61 | -183.1 |  |  |  | -183.1 |  |  | 474201.12 | 227413.34 | 67931.35 |  | 145583.43 | 33273 |  | 101198.88 | 0 | 111.9% |  | 0 | 474201.12 | 170400 | 28.43% | -8194.61 | 162205.39 | 27.67% | 0 |  | 101198.88 | 17.59% | 101198.88 | 17.59% | 10720 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878736 - SUFFOLK, COUNTY OF | WATER | WATER SUPPLY | 2018-10-28 | 2019-05-20 | 2018-10-28 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877762¦¦2020-03-31
FP | C | Yes | 877768 |  | 51558 LSR PUMP REPAIRS | LOPEZ-VASQUEZ, JUAN C. | 100% | 18414.18 | 12895 | 31309.18 | 31309 | 31309 | 22070.08 | 0 | 0 | 31309 | 10067.6 | 10823.5 | 20891.1 | [7 empty] | 22616.29 | 8019.69 | 1032.42 |  | 13564.18 |  |  | 8692.71 | 0 | 108.3% |  | 0 | 22616.29 | 8346.58 | 45.33% | 2071.5 | 10418.08 | 33.27% | -1610 |  | 8692.71 | 27.76% | 8692.71 | 27.76% | 0.18 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878741 - LOUISIANA SUGAR REFINING | WATER | WATER REPAIR & INSTALLATION | 2018-10-24 | 2019-04-30 | 2018-10-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877768¦¦2020-03-31
TM | CJ | Yes | 877769 |  | 51559 SEARCY WATER & SEWER RAW | BURGE, EVERETT E. | 100% | 14000 | 0 | 14000 | 448.12 | 448.12 | 0 | 0 | 0 | 448.12 | 9800 | 0 | 9800 | [7 empty] | 362.03 | 267.45 |  |  | 94.58 |  |  | 86.09 | 0 | 3.694% |  | 0 | 362.03 | 4200 | 30% | 0 | 4200 | 30% | 0 |  | 86.09 | 19.21% | 86.09 | 19.21% | 13551.88 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878604 - SEARCY WATER AND SEWER SYSTEM | WATER | WATER REPAIR & INSTALLATION | 2018-10-24 | 2019-02-28 | 2018-10-24 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877769¦¦2020-03-31
UP | CJ | Yes | 877770 |  | 51562 INGLEWOOD SERVICE CONTRA | GRACE, GARY L. | 100% | 9928 | 0 | 9928 | 1977.4 | 1977.4 | 0 | 0 | 0 | 1977.4 | 5610 | 0 | 5610 | [7 empty] | 1894.71 | 1274.99 | 235 |  | 384.72 |  |  | 82.69 | 0 | 33.77% |  | 0 | 1894.71 | 4318 | 43.49% | 0 | 4318 | 43.49% | 0 |  | 82.69 | 4.182% | 82.69 | 4.182% | 7950.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878505 - INGLEWOOD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-10-31 | 2019-02-28 | 2018-10-31 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877770¦¦2020-03-31
FP | CJ | Yes | 877771 |  | 51564 RAPIDES ISLAND 2 NEW W | ALBARADO, JORDAN A | 100% | 475000 | 0 | 475000 | 440359.5 | 440359.5 | 253571.45 | 0 | 22047.35 | 440359.5 | 372449 | 0 | 372449 | [7 empty] | 396346.17 | 214792.15 | 78953.78 |  | 98827.24 | 3773 |  | 44013.33 | 0 | 106.4% |  | 0 | 396346.17 | 102551 | 21.59% | 0 | 102551 | 21.59% | 0 |  | 44013.33 | 9.995% | 44013.33 | 9.995% | 34640.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878742 - RAPIDES ISLAND WATER ASSOCIATION INC | WATER | WATER SUPPLY | 2018-10-23 | 2019-12-31 | 2018-10-23 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877771¦¦2020-03-31
FP | CJ | Yes | 877773 |  | 51571 RAPIDES ISLAND R&I | ALBARADO, JORDAN A | 100% | 58923 | 0 | 58923 | 47725.81 | 47725.81 | 0 | 0 | 0 | 47725.81 | 46549 | 0 | 46549 | [7 empty] | 38557.42 | 16242.03 | 3075.79 |  | 19239.6 |  |  | 9168.39 | 0 | 82.83% |  | 0 | 38557.42 | 12374 | 21% | 0 | 12374 | 21% | 0 |  | 9168.39 | 19.21% | 9168.39 | 19.21% | 11197.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878742 - RAPIDES ISLAND WATER ASSOCIATION INC | WATER | WATER REPAIR & INSTALLATION | 2018-10-23 | 2019-12-31 | 2018-10-23 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 877773¦¦2020-03-31
UP | C | Yes | 877777 |  | 51604 MALIBU BYA 1 ELECTRICAL | GRACE, GARY L. | 100% | 19434 | 0 | 19434 | 0 | 0 | 0 | 0 | 0 | 0 | 14076 | 0 | 14076 | [7 empty] | 57.06 | 57.06 | [5 empty] | 0 | 57.06 | 0.4054% |  | 0 | 57.06 | 5358 | 27.57% | 0 | 5358 | 27.57% | 0 |  | -57.06 |  | -57.06 |  | 19434 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878747 - FUGRO CONSULTANTS INC VENTURA CA | WATER | WATER REPAIR & INSTALLATION | 2018-11-01 | 2019-11-30 | 2018-11-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877777¦¦2020-03-31
FP | CJ | Yes | 877786 |  | 51641 GEOSYNTEC AST PILOT | MCCARTNEY, JEFFREY C | 100% | 94400 | 4185 | 98585 | 98585 | 98585 | 98585 | 0 | 0 | 98585 | 62239.8 | 600 | 62839.8 | [7 empty] | 75251.53 | 24803.61 |  |  | 44640.42 | 5807.5 |  | 23333.47 | 0 | 119.8% |  | 0 | 75251.53 | 32160.2 | 34.07% | 3585 | 35745.2 | 36.26% | 0 |  | 23333.47 | 23.67% | 23333.47 | 23.67% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 878755 - STARKIST COMPANY | WATER | WATER TREATMENT | 2018-10-31 | 2019-01-31 | 2018-10-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877786¦¦2020-03-31
FP | CJ | Yes | 877787 |  | 51643 VULCAN MATERIALS DEEP WE | BRASHEAR, DAVID M | 100% | 75925 | 0 | 75925 | 10428.85 | 10428.85 | 0 | 0 | 0 | 10428.85 | 54598 | 0 | 54598 | [7 empty] | 10032.55 | 6946.54 | 1370 |  | 1716.01 |  |  | 396.3 | 0 | 18.38% |  | 0 | 10032.55 | 21327 | 28.09% | 0 | 21327 | 28.09% | 0 |  | 396.3 | 3.8% | 396.3 | 3.8% | 65496.15 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878756 - DO NOT USE VULCAN MATERIALS COMPANY | WATER | WATER REPAIR & INSTALLATION | 2018-03-05 | 2019-04-30 | 2018-03-05 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 877787¦¦2020-03-31
FP | C | Yes | 877788 |  | 51654 ENTERPRISE MT BELVIEU NE | CALLAHAN, DANIEL E. | 100% | 89562 | 0 | 89562 | 95087 | 95087 | 82945 | 0 | 0 | 95087 | 62693 | 0 | 62693 | 3950 |  |  |  |  | 3950 |  | 70760 |  |  |  |  | 70760 |  | 24327 | 0 | 112.9% |  | 0 | 70760 | 26869 | 30% | 0 | 26869 | 30% | 0 |  | 24327 | 25.58% | 24327 | 25.58% | -5525 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 878757 - ENTERPRISE PRODUCTS COMPANY | WATER | WATER SUPPLY | 2018-03-05 | 2019-11-30 | 2018-03-05 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877788¦¦2020-03-31
UP | CJ | Yes | 877789 |  | 51664 WAM FLOW METERS | BRASHEAR, DAVID M | 100% | 45037 | 0 | 45037 | 38468.25 | 38468.25 | 0 | 0 | 0 | 38468.25 | 31555 | 0 | 31555 | [7 empty] | 31078.29 | 7570.85 | 140 |  | 23367.44 |  |  | 7389.96 | 0 | 98.49% |  | 0 | 31078.29 | 13482 | 29.94% | 0 | 13482 | 29.94% | 0 |  | 7389.96 | 19.21% | 7389.96 | 19.21% | 6568.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878758 - WATER ASSET MANAGEMENT INC | WATER | WATER EQUIPMENT SALES | 2018-11-30 | 2019-12-31 | 2018-11-30 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877789¦¦2020-03-31
UP | CJ | Yes | 877797 |  | 51702 VILLISCA IA TEST HOLES | GANSEBOM, JASON W. | 100% | 46071 | 0 | 46071 | 11760.14 | 11760.14 | 0 | 0 | 0 | 11760.14 | 33736 | 0 | 33736 | [7 empty] | 9500.95 | 5264.11 | 1358 |  | 2878.84 |  |  | 2259.19 | 0 | 28.16% |  | 0 | 9500.95 | 12335 | 26.77% | 0 | 12335 | 26.77% | 0 |  | 2259.19 | 19.21% | 2259.19 | 19.21% | 34310.86 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878764 - VILLISCA, CITY OF | WATER | WATER SUPPLY | 2018-10-31 | 2019-12-14 | 2018-10-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 877797¦¦2020-03-31
FP | LJ | Yes | 877799 |  | 51706 WEST BATON ROUGE ARENA | LOPEZ-VASQUEZ, JUAN C. | 96.22% | 885984 | 0 | 885984 | 868636.4935 | 878144.25 | 878144.25 | 0 | 43907.21 | 902761.5 | 695497 | 0 | 695497 | 48.66 |  |  |  | 46.89 |  | 1.77 | 1100684.79 | 270890.83 | 205965.55 |  | 525570 | 86706.92 | 11551.49 | 0 | 222540.54 | 158.3% |  | 43241.19 | 1143925.98 | 190487 | 21.5% | 0 | 190487 | 21.5% | 0 |  | -241164.48 | -28.06% | -241164.48 | -26.71% | 26463.69 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878765 - WEST BATON ROUGE NAT GAS WATER | WATER | WATER SUPPLY | 2018-11-30 | 2019-05-31 | 2018-11-30 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877799¦¦2020-03-31
UP | C | Yes | 877800 |  | 51711 CONOCOPHILLIPS RIG SUPPL | LOPEZ-VASQUEZ, JUAN C. | 100% | 67755 | 63787 | 131542 | 131541.59 | 131541.59 | -11599.49 | 0 | 0 | 131541.59 | 59463.59 | 45136 | 104599.59 | [7 empty] | 101921.57 | 6617.31 | 3972.79 |  | 10756.47 | 80575 |  | 29620.02 | 0 | 97.44% |  | 0 | 101921.57 | 8291.41 | 12.24% | 18651 | 26942.41 | 20.48% | 0 |  | 29620.02 | 22.52% | 29620.02 | 22.52% | 0.41 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878766 - CONOCOPHILLIPS COMPANY LOUISIANA | WATER | WATER SUPPLY | 2018-08-06 | 2019-06-25 | 2018-08-06 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877800¦¦2020-03-31
FP | CJ | Yes | 877802 |  | 51718 IP RIVERDALE EMERGENCY | PARSLEY, TRISTAN S | 100% | 16730 | 154294.14 | 171024.14 | 128525.09 | 128525.09 | 0 | 0 | 0 | 128525.09 | 10147 | 92157 | 102304 | 181 |  |  |  | 181 |  |  | 103834.72 | 42527.33 | 2079.71 |  | 59227.68 |  |  | 24690.37 | 0 | 101.5% |  | 0 | 103834.72 | 6583 | 39.35% | 62137.14 | 68720.14 | 40.18% | 0 |  | 24690.37 | 19.21% | 24690.37 | 19.21% | 42499.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 878768 - INTERNATIONAL PAPER RIVERDALE | WATER | WATER REPAIR & INSTALLATION | 2018-11-07 | 2019-04-01 | 2018-11-07 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877802¦¦2020-03-31
TM | C | Yes | 877803 |  | 51720 WESTROCK PAINT ST 2019 | GAMBLE, BRAD F. | 100% | 18580 | 0 | 18580 | 18570 | 18570 | 10480 | 0 | 0 | 18570 | 11430 | 0 | 11430 | 0.03 | 0.03 |  |  | 0 |  |  | 12900.76 | 12465.36 | 77.56 |  | 357.84 |  |  | 5669.24 | 0 | 112.9% |  | 0 | 12900.76 | 7150 | 38.48% | 0 | 7150 | 38.48% | 0 |  | 5669.24 | 30.53% | 5669.24 | 30.53% | 10 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878769 - WESTROCK CORP | WATER | WATER SPECIALTY DRILLING | 2018-11-11 | 2019-12-30 | 2018-11-11 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877803¦¦2020-03-31
UP | C | Yes | 877804 |  | 51722 RCWD WELL 120 PUMP AND | BRASHEAR, DAVID M | 100% | 92717 | 28792 | 121509 | 117115.45 | 117115.45 | 0 | 0 | 0 | 117115.45 | 70565 | 20938 | 91503 | [7 empty] | 83366.02 | 23506.27 | 9155.82 |  | 41851.19 | 8852.74 |  | 33749.43 | 0 | 91.11% |  | 0 | 83366.02 | 22152 | 23.89% | 7854 | 30006 | 24.69% | 0 |  | 33749.43 | 28.82% | 33749.43 | 28.82% | 4393.55 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878683 - RANCHO CALIFORNIA WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2018-11-19 | 2019-12-31 | 2018-11-19 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877804¦¦2020-03-31
UP | C | Yes | 877806 |  | 51729 GSW CALIPATRIA BOOST | GRACE, GARY L. | 100% | 22610 | 10549 | 33159 | 36716.48 | 36716.48 | 37877.82 | 0 | 0 | 36716.48 | 14108 | 6620 | 20728 | [7 empty] | 40383.76 | 12413.01 | 1520.34 |  | 19124.57 | 7325.84 |  | 0 | 3667.28 | 194.8% |  | 0 | 40383.76 | 8502 | 37.6% | 3929 | 12431 | 37.49% | 0 |  | -3667.28 | -9.988% | -3667.28 | -9.988% | -3557.48 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878770 - GOLDEN STATE WATER COMPANY CALIPATRIA | WATER | WATER REPAIR & INSTALLATION | 2018-11-26 | 2019-12-03 | 2018-11-26 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877806¦¦2020-03-31
FP | C | Yes | 877807 |  | 51735 TID WELL 7 PUMP TEST | SEIDEN, ANDREW L. | 100% | 11982 | 0 | 11982 | 0 | 0 | 0 | 0 | 0 | 0 | 8592 | 0 | 8592 | [7 empty] | 82871.94 | 30650.58 | 12796.06 |  | 19202.95 | 20222.35 |  | 0 | 82871.94 | 964.5% |  | 0 | 82871.94 | 3390 | 28.29% | 0 | 3390 | 28.29% | 0 |  | -82871.94 |  | -82871.94 |  | 11982 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878771 - TRANQUILLITY IRRIGATION DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2018-11-09 | 2019-01-31 | 2018-11-09 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877807¦¦2020-03-31
UP | C | Yes | 877809 |  | 51738 WESTMONT BOOSTER PULL I | GRACE, GARY L. | 100% | 4860 | 32342.45 | 37202.45 | 37072.18 | 37072.18 | 33383.4 | 0 | 0 | 37072.18 | 3122 | 20799.62 | 23921.62 | [7 empty] | 28419.37 | 7866.67 | 719.56 |  | 14836.69 | 4996.45 |  | 8652.81 | 0 | 118.8% |  | 0 | 28419.37 | 1738 | 35.76% | 11542.83 | 13280.83 | 35.7% | 0 |  | 8652.81 | 23.34% | 8652.81 | 23.34% | 130.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878773 - WESTMONT COLLEGE | WATER | WATER REPAIR & INSTALLATION | 2018-11-12 | 2019-01-31 | 2018-11-12 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 877809¦¦2020-03-31
UP | C | Yes | 877811 |  | 51740 JG BOSWELL S 224 | BRASHEAR, DAVID M | 100% | 12975 | 30131 | 43106 | 41378.57 | 41378.57 | 0 | 0 | 0 | 41378.57 | 6723 | 19012 | 25735 | 190.4 |  |  |  |  | 190.4 |  | 22940.03 | 6824.83 | 3263 |  | 12661.8 | 190.4 |  | 18438.54 | 0 | 89.14% |  | 0 | 22940.03 | 6252 | 48.18% | 11119 | 17371 | 40.3% | 0 |  | 18438.54 | 44.56% | 18438.54 | 44.56% | 1727.43 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878568 - J G BOSWELL | WATER | WATER REPAIR & INSTALLATION | 2018-11-01 | 2019-01-31 | 2018-11-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877811¦¦2020-03-31
FP | LJ | Yes | 877812 |  | 51745 TX BRINE DRILL WELLS 6 A | LOPEZ-VASQUEZ, JUAN C. | 94.54% | 635000 | 0 | 635000 | 628651.0892 | 664925 | 127035 | 0 | 0 | 664925 | 481633 | -164991 | 316642 | 0 |  |  |  | 0 |  |  | 316999.4 | 123176.1 | 44020.72 |  | 146507.58 | 3295 |  | 347925.6 | 0 | 100.1% |  | 18291.24 | 335290.64 | 153367 | 24.15% | 164991 | 318358 | 50.14% | 0 |  | 311651.69 | 49.57% | 329634.36 | 49.57% | 6348.91 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878775 - TEXAS BRINE WHITE CASTLE COMPANY LLC | WATER | WATER SUPPLY | 2018-11-12 | 2019-05-15 | 2018-11-12 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877812¦¦2020-03-31
TM | C | Yes | 877813 |  | 51751 CHS MCPHERSON KS WELL 1 | WARTICK, LOGAN M | 100% | 10310 | 54035.75 | 64345.75 | 116951.75 | 116951.75 | 90446.88 | 14040 | 0 | 116951.75 | 6701.5 | 40811.42 | 47512.92 | 19607.21 | 9487.95 | 2649.4 |  | 6079.16 | 1390.7 |  | 118827.56 | 48721.45 | 10517.58 |  | 50901.59 | 8686.94 |  | 0 | 1875.81 | 250.1% |  | 0 | 118827.56 | 3608.5 | 35% | 13224.33 | 16832.83 | 26.16% | 0 |  | -1875.81 | -1.604% | -1875.81 | -1.604% | -52606 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 878776 - CHS MCPHERSON REFINERY INC | WATER | WATER REPAIR & INSTALLATION | 2018-11-12 | 2019-01-31 | 2018-11-12 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877813¦¦2020-03-31
UP | C | Yes | 877815 |  | 51763 CHENOA IL WELL NO 1 | EISHA, JOSEPH J. | 100% | 45000 | 0 | 45000 | 69517.3 | 69517.3 | 69517.3 | 26517.3 | 0 | 69517.3 | 30000 | 0 | 30000 | [7 empty] | 68785.79 | 30972.76 | 4474.86 |  | 8780.87 | 24557.3 |  | 731.51 | 0 | 229.3% |  | 0 | 68785.79 | 15000 | 33.33% | 0 | 15000 | 33.33% | 0 |  | 731.51 | 1.052% | 731.51 | 1.052% | -24517.3 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878778 - CHENOA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-11-26 | 2019-12-31 | 2018-11-26 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877815¦¦2020-03-31
UP | C | Yes | 877817 |  | 51768 SAN JUAN CAP STEEPLECH | BRASHEAR, DAVID M | 100% | 58535 | 1315 | 59850 | 59849.81 | 59849.81 | 0 | 0 | 0 | 59849.81 | 46204 | -8193 | 38011 | 0 |  |  |  | 0 |  |  | 41458.75 | 9978.81 | 845.84 |  | 30605.28 | 28.82 |  | 18391.06 | 0 | 109.1% |  | 0 | 41458.75 | 12331 | 21.07% | 9508 | 21839 | 36.49% | 0 |  | 18391.06 | 30.73% | 18391.06 | 30.73% | 0.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878779 - SAN JUAN CAPISTRANO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-11-19 | 2019-12-28 | 2018-11-19 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 877817¦¦2020-03-31
UP | CJ | Yes | 877821 |  | 51776 CAL WATER 020 01 ABANDON | GRACE, GARY L. | 100% | 44803 | 0 | 44803 | 24962.81 | 24962.81 | 8917.02 | 0 | 0 | 24962.81 | 33496 | 0 | 33496 | [7 empty] | 20167.32 | 10788.75 | 3005.5 |  | 4096.57 | 2276.5 |  | 4795.49 | 0 | 60.21% |  | 0 | 20167.32 | 11307 | 25.24% | 0 | 11307 | 25.24% | 0 |  | 4795.49 | 19.21% | 4795.49 | 19.21% | 19840.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878783 - CALIFORNIA WATER SERVICE COMPANY | WATER | WATER SUPPLY | 2018-12-15 | 2019-01-31 | 2018-12-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 877821¦¦2020-03-31
FP | C | Yes | 877832 | 877833 | 51840 ACWWA ELKHORN A2 TEST | SCHANAMAN, MIKE L. | 100% | 56745 | -25742 | 31003 | 31003 | 31003 | 0 | 0 | 0 | 31003 | 44050 | -23313 | 20737 | [7 empty] | 43451.27 | 19746.12 | 12102.35 |  | 11353.3 | 249.5 |  | 0 | 12448.27 | 209.5% |  | 0 | 43451.27 | 12695 | 22.37% | -2429 | 10266 | 33.11% | 0 |  | -12448.27 | -40.15% | -12448.27 | -40.15% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878792 - ARAPAHOE COUNTY WATER AND WASTEWATER AUT | WATER | WATER REPAIR & INSTALLATION | 2018-11-26 | 2019-02-28 | 2018-11-26 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877832¦¦2020-03-31
FP | C | Yes | 877833 | 877833 | 51844 ACWWA ELKHORN A2 DRILL | DECKER, JASEN | 100% | 478250 | 40868 | 519118 | 550121 | 550121 | 0 | 0 | 0 | 550121 | 373363 | 42452 | 415815 | [7 empty] | 416062.34 | 118375.6 | 85333.09 |  | 160195.22 | 52158.43 |  | 134058.66 | 0 | 100.1% |  | 0 | 416062.34 | 104887 | 21.93% | -1584 | 103303 | 19.9% | 0 |  | 134058.66 | 24.37% | 134058.66 | 24.37% | -31003 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878793 - ARAPAHOE COUNTY WATER AND WASTEWATER AUT | WATER | WATER SUPPLY | 2018-11-28 | 2019-02-28 | 2018-11-28 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877833¦¦2020-03-31
TM | C | Yes | 877834 |  | 51845 SOUTH FARM PR | BENNETT, MARK C. | 100% | 25000 | 0 | 25000 | 46787.98 | 46787.98 | 50297.13 | 0 | 0 | 46787.98 | 15000 | 0 | 15000 | [7 empty] | 39487.16 | 15428.84 | 3399.29 |  | 20659.03 |  |  | 7300.82 | 0 | 263.2% |  | 0 | 39487.16 | 10000 | 40% | 0 | 10000 | 40% | 0 |  | 7300.82 | 15.6% | 7300.82 | 15.6% | -21787.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878794 - SOUTH FARM | WATER | WATER REPAIR & INSTALLATION | 2018-11-28 | 2019-11-28 | 2018-11-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877834¦¦2020-03-31
UP | C | Yes | 877836 |  | 51861 EMWD 35 REHAB | BRASHEAR, DAVID M | 100% | 140252 | -4876 | 135376 | 135376.5 | 135376.5 | 0 | 0 | 0 | 135376.5 | 94363 | -11711 | 82652 | [7 empty] | 80195.71 | 37221.49 | 8982.21 |  | 33775.02 | 216.99 |  | 55180.79 | 0 | 97.03% |  | 0 | 80195.71 | 45889 | 32.72% | 6835 | 52724 | 38.95% | 0 |  | 55180.79 | 40.76% | 55180.79 | 40.76% | -0.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878619 - EASTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2018-11-28 | 2019-02-28 | 2018-11-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877836¦¦2020-03-31
UP | C | Yes | 877837 |  | 51863 JG BOSWELL EC 7 | BRASHEAR, DAVID M | 100% | 11775 | 128029 | 139804 | 137714 | 137714 | 128029 | 0 | 0 | 137714 | 7153 | 105599.48 | 112752.48 | [7 empty] | 118024.89 | 51443.65 | 27083.39 |  | 39497.85 |  |  | 19689.11 | 0 | 104.7% |  | 0 | 118024.89 | 4622 | 39.25% | 22429.52 | 27051.52 | 19.35% | 22429.52 |  | 19689.11 | 14.3% | 19689.11 | 14.3% | 2090 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878568 - J G BOSWELL | WATER | WATER REPAIR & INSTALLATION | 2018-11-27 | 2019-02-28 | 2018-11-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877837¦¦2020-03-31
UP | C | Yes | 877838 |  | 51864 EMWD 82 | BRASHEAR, DAVID M | 100% | 6645 | 32912 | 39557 | 38041.18 | 38041.18 | 0 | 0 | 0 | 38041.18 | 3977 | 28617 | 32594 | [7 empty] | 42094.73 | 14493.22 | 960 |  | 26598.24 | 43.27 |  | 0 | 4053.55 | 129.1% |  | 0 | 42094.73 | 2668 | 40.15% | 4295 | 6963 | 17.6% | 0 |  | -4053.55 | -10.66% | -4053.55 | -10.66% | 1515.82 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878619 - EASTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2018-11-29 | 2019-01-31 | 2018-11-29 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877838¦¦2020-03-31
UP | CJ | Yes | 877842 |  | 51871 BPI NEW WELL 1 | HEILIGER, TERENCE L. | 100% | 389492 | 0 | 389492 | 298754 | 298754 | 249919 | 0 | 0 | 298754 | 253170 | 0 | 253170 | [7 empty] | 224464.45 | 60626.95 | 17447.65 |  | 141924.85 | 4465 |  | 74289.55 | 0 | 88.66% |  | 0 | 224464.45 | 136322 | 35% | 0 | 136322 | 35% | 0 |  | 74289.55 | 24.87% | 74289.55 | 24.87% | 90738 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878799 - EMPIRICAL FOODS INC | WATER | WATER SUPPLY | 2018-11-27 | 2019-05-31 | 2018-11-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877842¦¦2020-03-31
TM | CJ | Yes | 877849 |  | 51895 LWC HSP 6 | MIGUEL, SEAN J. | 100% | 2000 | 104272 | 106272 | 106272 | 106272 | 8223 | 0 | 0 | 106272 | 1300 | 75010 | 76310 | 8052.96 | 3677.25 | 1188.71 |  | 2612 | 575 |  | 91070.62 | 31362.16 | 9351.96 |  | 39622.04 | 10734.46 |  | 15201.38 | 0 | 119.3% |  | 0 | 91070.62 | 700 | 35% | 29262 | 29962 | 28.19% | 0 |  | 15201.38 | 14.3% | 15201.38 | 14.3% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878555 - LOUISVILLE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2018-12-06 | 2019-01-30 | 2018-12-06 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877849¦¦2020-03-31
UP | C | Yes | 877850 |  | 51896 SILVERLAKESWELL 15PULLAN | BRASHEAR, DAVID M | 100% | 10511 | 20150 | 30661 | 30660.74 | 30660.74 | 0 | 0 | 0 | 30660.74 | 7380 | 13733 | 21113 | [7 empty] | 30120.57 | 12822.29 | 2394.64 |  | 14903.64 |  |  | 540.17 | 0 | 142.7% |  | 0 | 30120.57 | 3131 | 29.79% | 6417 | 9548 | 31.14% | 0 |  | 540.17 | 1.762% | 540.17 | 1.762% | 0.26 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878805 - SILVER LAKES ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2018-12-10 | 2019-01-31 | 2018-12-10 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 877850¦¦2020-03-31
UP | C | Yes | 877851 |  | 51899 SILVERLAKESBOOSTERSTATIO | BRASHEAR, DAVID M | 100% | 3246 | 18626 | 21872 | 21872.12 | 21872.12 | 0 | 0 | 0 | 21872.12 | 2045 | 11608 | 13653 | [7 empty] | 13843.06 | 5425.4 | 434 |  | 5493.18 | 2490.48 |  | 8029.06 | 0 | 101.4% |  | 0 | 13843.06 | 1201 | 37% | 7018 | 8219 | 37.58% | 0 |  | 8029.06 | 36.71% | 8029.06 | 36.71% | -0.12 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878805 - SILVER LAKES ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2018-12-10 | 2019-01-31 | 2018-12-10 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877851¦¦2020-03-31
UP | C | Yes | 877853 |  | 51904 PERC WTR BST 1 MOTOR | BRASHEAR, DAVID M | 100% | 19506 | 13263.54 | 32769.54 | 32769.1 | 32769.1 | 30947.12 | 0 | 0 | 32769.1 | 12196 | 9538.77 | 21734.77 | [7 empty] | 27012.64 | 8579.39 | 1417.05 |  | 16448.44 | 567.76 |  | 5756.46 | 0 | 124.3% |  | 0 | 27012.64 | 7310 | 37.48% | 3724.77 | 11034.77 | 33.67% | 0 |  | 5756.46 | 17.57% | 5756.46 | 17.57% | 0.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878644 - ADELANTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-12-17 | 2019-01-31 | 2018-12-17 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877853¦¦2020-03-31
UP | C | Yes | 877855 |  | 51932 SILVERLAKESWELLSELECTRIC | BRASHEAR, DAVID M | 100% | 3288 | 3007.5 | 6295.5 | 6295.53 | 6295.53 | 1711.6 | 0 | 0 | 6295.53 | 2305 | 3217.09 | 5522.09 | [7 empty] | 12249.96 | 5479.31 | 1102.69 |  | 5667.96 |  |  | 0 | 5954.43 | 221.8% |  | 0 | 12249.96 | 983 | 29.9% | -209.59 | 773.41 | 12.29% | 0 |  | -5954.43 | -94.58% | -5954.43 | -94.58% | -0.03 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878805 - SILVER LAKES ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2018-12-31 | 2019-01-31 | 2018-12-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877855¦¦2020-03-31
FP | CJ | Yes | 877865 |  | 51957 51957 GILES CHEMICAL NE | CURLEY, ROBERT E. | 100% | 105606 | 10000 | 115606 | 115606 | 115606 | 115606 | 0 | 0 | 115606 | 79204 | 7500 | 86704 | 0.15 | 0.15 |  |  | 0 |  |  | 137184.35 | 47938 | 34773.09 |  | 54473.26 |  |  | 0 | 21578.35 | 158.2% |  | 0 | 137184.35 | 26402 | 25% | 2500 | 28902 | 25% | 0 |  | -21578.35 | -18.67% | -21578.35 | -18.67% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878815 - GILES CHEMICAL | WATER | WATER SUPPLY | 2018-12-16 | 2019-03-28 | 2018-12-16 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877865¦¦2020-03-31
TM | CJ | Yes | 877869 |  | 51970 JONES HYDRO SERVICES | BENNETT, MARK C. | 100% | 8000 | 0 | 8000 | 29495.54 | 29495.54 | 19754.3 | 0 | 0 | 29495.54 | 5000 | 0 | 5000 | 4741.2 | 2074.48 | 65 |  | 2601.72 |  |  | 29717.77 | 15183.59 | 164 |  | 14370.18 |  |  | 0 | 222.23 | 594.4% |  | 0 | 29717.77 | 3000 | 37.5% | 0 | 3000 | 37.5% | 0 |  | -222.23 | -0.7534% | -222.23 | -0.7534% | -21495.54 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878818 - JONES HYDRO SERVICES INC | WATER | WATER REPAIR & INSTALLATION | 2018-12-17 | 2019-11-30 | 2018-12-17 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877869¦¦2020-03-31
UP | C | Yes | 877872 |  | 51984 ROCKFORD IL UW40 | KENNEDY, CHRISTOPHER C. | 100% | 50089 | 158096 | 208185 | 239717.25 | 239717.25 | 68820.75 | 0 | 0 | 239717.25 | 31556 | 113444 | 145000 | [7 empty] | 271746.16 | 175766.09 | 32833.95 |  | 62050.77 | 1095.35 |  | 0 | 32028.91 | 187.4% | 18904.08 | 0 | 271746.16 | 18533 | 37% | 44652 | 63185 | 30.35% | 0 |  | -32028.91 | -13.36% | -32028.91 | -13.36% | -31532.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878821 - ROCKFORD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-12-17 | 2019-02-28 | 2018-12-17 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877872¦¦2020-03-31
FP | C | Yes | 877875 |  | 51997 ROI PROPERTY GROUP | SCHANAMAN, MIKE L. | 100% | 31875 | 31875 | 63750 | 63750 | 63750 | 31875 | 31875 | 0 | 63750 | 21540 | 21540 | 43080 | [7 empty] | 31823.67 | 14970.87 | 8904.92 |  | 7947.88 |  |  | 31926.33 | 0 | 73.87% |  | 0 | 31823.67 | 10335 | 32.42% | 10335 | 20670 | 32.42% | 0 |  | 31926.33 | 50.08% | 31926.33 | 50.08% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878824 - ROI PROPERTY GROUP LLC | WATER | WATER REPAIR & INSTALLATION | 2018-12-18 | 2019-02-28 | 2018-12-18 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877875¦¦2020-03-31
UP | C | Yes | 877880 | 877880 | 52007 SRP WELL 5 4E 16 2N DR | SEIDEN, ANDREW L. | 100% | 990777 | -79018 | 911759 | 912886.06 | 912886.06 | 132615.69 | 0 | 0 | 912886.06 | 769213 | -40100 | 729113 | [7 empty] | 793870.41 | 241091.79 | 101899.75 |  | 392747.87 | 58131 |  | 119015.65 | 0 | 108.9% |  | 0 | 793870.41 | 221564 | 22.36% | -38918 | 182646 | 20.03% | 0 |  | 119015.65 | 13.04% | 119015.65 | 13.04% | -1127.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878691 - SALT RIVER PROJECT | WATER | WATER SUPPLY | 2019-01-28 | 2019-04-29 | 2018-12-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877880¦¦2020-03-31
UP | C | Yes | 877881 | 877880 | 52009 SRP WELL 5 4E 16 2N TP | VAN ALLEN, WESLEY C. | 100% | 26000 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 19304 | 0 | 19304 | [7 empty] | 25466.64 | 11644.74 | 3575.89 |  | 10246.01 |  |  | 0 | 25466.64 | 131.9% |  | 0 | 25466.64 | 6696 | 25.75% | 0 | 6696 | 25.75% | 0 |  | -25466.64 |  | -25466.64 |  | 26000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878691 - SALT RIVER PROJECT | WATER | WATER SUPPLY | 2019-01-28 | 2019-04-29 | 2018-12-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877881¦¦2020-03-31
FP | CJ | Yes | 877883 |  | 52016 HAMMOCK TEST WELL | ALBARADO, JORDAN A | 100% | 168000 | 0 | 168000 | 163000 | 163000 | 163000 | 0 | 16300 | 163000 | 134000 | 0 | 134000 | [7 empty] | 155662.38 | 67931.72 | 41909.65 |  | 42161.01 | 3660 |  | 7337.62 | 0 | 116.2% |  | 0 | 155662.38 | 34000 | 20.24% | 0 | 34000 | 20.24% | 0 |  | 7337.62 | 4.502% | 7337.62 | 4.502% | 5000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878829 - HAMMOCK WATER SYSTEM | WATER | WATER SUPPLY | 2019-01-14 | 2019-02-28 | 2018-12-31 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 877883¦¦2020-03-31
UP | LJ | Yes | 877884 |  | 52027 NORMAN CITY OF 6 WELLS | EVANS, TRAVIS L | 18.44% | 4714422 | 1607970.36 | 6322392.36 | 1138482.2163 | 930887.87 | 930887.87 | 0 | 50049.32 | 6172392.36 | 3771476 | 1666967 | 5438443 | 188748.37 | 63201.61 | 45741.38 |  | 51765.38 | 28040 |  | 1124707.59 | 336373.38 | 271072.87 | 1000 | 297049.95 | 219211.39 |  | 0 | 193819.72 | 20.68% |  | 4973004.29 | 6097711.88 | 942946 | 20% | -58996.64 | 883949.36 | 13.98% | -58996.64 |  | 13774.63 | 1.21% | 74680.48 | 1.21% | 5183910.14 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 878830 - NORMAN, CITY OF | WATER | WATER SUPPLY | 2018-10-29 | 2019-12-28 | 2018-10-29 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 877884¦¦2020-03-31
UP | LJ | Yes | 877885 |  | 52032 CDM SMITH 2 NEW WELL | MCMAHON, PERRY J | 0.2421% | 3622523 | 20283.44 | 3642806.44 | 8820.2968 |  | 0 | 0 | 0 | 3642806.44 | 2405912 | 15254.97 | 2421166.97 | 5592.07 | 2060.5 |  |  | 3531.57 |  |  | 7424.69 | 3541.6 |  |  | 3883.09 |  |  | 0 | 7424.69 | 0.3067% |  | 3058992.37 | 3066417.06 | 1216611 | 33.58% | 5028.47 | 1221639.47 | 33.54% | 5028.47 |  | 1395.61 | 15.82% | 576389.38 | 15.82% | 3633986.14 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878831 - DO NOT USE CDM SMITH CONSTRUCTION | WATER | WATER SUPPLY | 2019-04-08 | 2020-02-28 | 2018-12-31 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877885¦¦2020-03-31
TM | C | Yes | 877888 |  | 52043 CRETE NE WELL 5 NEW | GANSEBOM, JASON W. | 100% | 9140 | 57077.5 | 66217.5 | 62323.95 | 62323.95 | 25532.13 | 0 | 0 | 62323.95 | 6386.57 | 39965.25 | 46351.82 | [7 empty] | 63660.33 | 27690.17 | 5620.93 |  | 29601.87 | 747.36 |  | 0 | 1336.38 | 137.3% |  | 0 | 63660.33 | 2753.43 | 30.13% | 17112.25 | 19865.68 | 30% | 0 |  | -1336.38 | -2.144% | -1336.38 | -2.144% | 3893.55 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878833 - CRETE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-01-02 | 2019-01-31 | 2019-01-02 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877888¦¦2020-03-31
CPF | C | Yes | 877889 |  | 52044 INDEPENDENCE MO 2019 REH | WARTICK, LOGAN M | 100% | 220000 | 93892 | 313892 | 324101.85 | 324101.85 | 172663.44 | 0 | 0 | 324101.85 | 176000 | 114114.72 | 290114.72 | 312.49 | 312.49 |  |  | 0 |  |  | 337542.46 | 153114.27 | 44649.18 |  | 139779.01 |  |  | 0 | 13440.61 | 116.3% |  | 0 | 337542.46 | 44000 | 20% | -20222.72 | 23777.28 | 7.575% | 0 |  | -13440.61 | -4.147% | -13440.61 | -4.147% | -10209.85 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 878834 - INDEPENDENCE WATER DEPARTMENT | WATER | WATER REPAIR & INSTALLATION | 2019-01-10 | 2019-08-31 | 2019-01-10 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877889¦¦2020-03-31
TM | CJ | Yes | 877893 |  | 52052 HILLCREST CC WELL TEST I | GANSEBOM, JASON W. | 100% | 6955 | 39465 | 46420 | 71954.4 | 71954.4 | 74806.84 | 0 | 0 | 71954.4 | 4868.5 | 25133.82 | 30002.32 | 6735.48 | 798.47 | 392.3 |  | 5544.71 |  |  | 64249.68 | 17712.69 | 5366.12 |  | 41170.87 |  |  | 7704.72 | 0 | 214.1% |  | 0 | 64249.68 | 2086.5 | 30% | 14331.18 | 16417.68 | 35.37% | 0 |  | 7704.72 | 10.71% | 7704.72 | 10.71% | -25534.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878837 - HILLCREST COUNTRY CLUB | WATER | WATER REPAIR & INSTALLATION | 2019-01-02 | 2019-02-28 | 2019-01-02 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877893¦¦2020-03-31
FP | C | Yes | 877894 |  | 52055 MOSAIC HOOKERS PRAIRIE W | TORMOEHLEN, DAVID A. | 100% | 78000 | 0 | 78000 | 78000 | 78000 | 0 | 0 | 0 | 78000 | 47305 | 0 | 47305 | [7 empty] | 48487.38 | 4351.1 | 2484.45 |  | 41651.83 |  |  | 29512.62 | 0 | 102.5% |  | 0 | 48487.38 | 30695 | 39.35% | 0 | 30695 | 39.35% | 0 |  | 29512.62 | 37.84% | 29512.62 | 37.84% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878838 - MOSAIC BUSINESS SERVICES PLANT CITY FL | WATER | WATER REPAIR & INSTALLATION | 2019-01-30 | 2019-02-27 | 2019-01-30 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877894¦¦2020-03-31
FP | C | Yes | 877895 |  | 52056 STUTTGART WASTEWATER CLA | BURGE, EVERETT E. | 100% | 20000 | 0 | 20000 | 2392.48 | 2392.48 | 1728.22 | 0 | 0 | 2392.48 | 15000 | 0 | 15000 | [7 empty] | 1932.87 | 1135.17 | 83.56 |  | 714.14 |  |  | 459.61 | 0 | 12.89% |  | 0 | 1932.87 | 5000 | 25% | 0 | 5000 | 25% | 0 |  | 459.61 | 19.21% | 459.61 | 19.21% | 17607.52 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878545 - STUTTGART WATER WORKS | WATER | WATER REPAIR & INSTALLATION | 2019-01-03 | 2019-07-26 | 2019-01-03 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877895¦¦2020-03-31
TM | C | Yes | 877897 |  | 52066 EKP 2019 MAINTENANCE | MIGUEL, SEAN J. | 100% | 165000 | 121057.15 | 286057.15 | 245225.32 | 245225.32 | 172444.38 | 0 | 0 | 245225.32 | 115500 | 82150 | 197650 | [7 empty] | 174182.25 | 65687.56 | 32258.21 |  | 68930.48 | 7306 |  | 71043.07 | 0 | 88.13% |  | 0 | 174182.25 | 49500 | 30% | 38907.15 | 88407.15 | 30.91% | 0 |  | 71043.07 | 28.97% | 71043.07 | 28.97% | 40831.83 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878840 - EAST KENTUCKY POWER CO OP | WATER | WATER REPAIR & INSTALLATION | 2019-01-02 | 2019-12-30 | 2019-01-02 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877897¦¦2020-03-31
FP | C | Yes | 877898 |  | 52069 AK EAST SIDE | SIMPSON, CARL L. | 100% | 11850 | 177672 | 189522 | 201847 | 201847 | 166297 | 0 | 0 | 201847 | 8532 | 131709 | 140241 | 2.41 | 2.41 |  |  | 0 |  |  | 197197.13 | 79509.52 | 27450.54 |  | 73855.07 | 16382 |  | 4649.87 | 0 | 140.6% |  | 0 | 197197.13 | 3318 | 28% | 45963 | 49281 | 26% | 0 |  | 4649.87 | 2.304% | 4649.87 | 2.304% | -12325 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-01-01 | 2019-01-29 | 2019-01-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877898¦¦2020-03-31
TM | C | Yes | 877899 |  | 52070 AK IMS | SIMPSON, CARL L. | 100% | 20000 | 413353.55 | 433353.55 | 433930.61 | 433930.61 | 285812.19 | 0 | 0 | 433930.61 | 14400 | 294059 | 308459 | 58.47 | 8.52 |  |  | 49.95 |  |  | 322059.02 | 125069.29 | 39815.54 |  | 137150.45 | 20023.74 |  | 111871.59 | 0 | 104.4% |  | 0 | 322059.02 | 5600 | 28% | 119294.55 | 124894.55 | 28.82% | 0 |  | 111871.59 | 25.78% | 111871.59 | 25.78% | -577.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-01-01 | 2019-01-29 | 2019-01-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877899¦¦2020-03-31
FP | C | Yes | 877902 |  | 52083 COUNCIL BLUFFS WELL RE | GANSEBOM, JASON W. | 100% | 21618 | 87801 | 109419 | 136269.24 | 136269.24 | 26850.07 | 0 | 0 | 136269.24 | 14051.7 | 99948 | 113999.7 | 0 |  |  |  | 0 |  |  | 174161.07 | 83253.55 | 30847.41 |  | 59488.91 | 571.2 |  | 0 | 37891.83 | 152.8% |  | 0 | 174161.07 | 7566.3 | 35% | -12147 | -4580.7 | -4.186% | 0 |  | -37891.83 | -27.81% | -37891.83 | -27.81% | -26850.24 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878843 - COUNCIL BLUFFS WATER WORKS | WATER | WATER REPAIR & INSTALLATION | 2019-01-04 | 2019-03-31 | 2018-12-31 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | COST REIMBURSIBLE | 877902¦¦2020-03-31
UP | C | Yes | 877911 |  | 52116 FILLMORE 5 PULL INSP | GRACE, GARY L. | 100% | 12916 | 16503 | 29419 | 104137.44 | 104137.44 | 77720.97 | 0 | 0 | 104137.44 | 9475 | 12564 | 22039 | [7 empty] | 128288.51 | 65495.18 | 13806.8 |  | 46171.91 | 2814.62 |  | 0 | 24151.07 | 582.1% |  | 0 | 128288.51 | 3441 | 26.64% | 3939 | 7380 | 25.09% | 0 |  | -24151.07 | -23.19% | -24151.07 | -23.19% | -74718.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878851 - FILLMORE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-01-09 | 2019-01-17 | 2019-01-09 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877911¦¦2020-03-31
UP | CJ | Yes | 877916 |  | 52134 BANNING MULTI WELL PR | BRASHEAR, DAVID M | 100% | 179885 | 0 | 179885 | 166045.55 | 166045.55 | 117216.09 | 0 | 0 | 166045.55 | 127519 | 0 | 127519 | -0.01 | -0.01 |  |  | 0 |  |  | 122905.88 | 62497.06 | 8709.05 |  | 44603.11 | 7096.66 |  | 43139.67 | 0 | 96.38% |  | 0 | 122905.88 | 52366 | 29.11% | 0 | 52366 | 29.11% | 0 |  | 43139.67 | 25.98% | 43139.67 | 25.98% | 13839.45 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878855 - BANNING, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-01-21 | 2019-04-01 | 2019-01-11 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877916¦¦2020-03-31
FP | C | Yes | 877921 |  | 52146 KIOWA PUMP 3 | MIGUEL, SEAN J. | 100% | 43100 | 29395 | 72495 | 70595 | 70595 | 50495 | 0 | 0 | 70595 | 30000 | 20746 | 50746 | [7 empty] | 61863.39 | 26423.03 | 9077.57 |  | 25062.79 | 1300 |  | 8731.61 | 0 | 121.9% |  | 0 | 61863.39 | 13100 | 30.39% | 8649 | 21749 | 30% | 0 |  | 8731.61 | 12.37% | 8731.61 | 12.37% | 1900 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878860 - KIOWA POWER PARTNERS LLC | WATER | WATER REPAIR & INSTALLATION | 2019-01-17 | 2019-04-29 | 2019-01-17 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877921¦¦2020-03-31
TM | C | Yes | 877922 |  | 52148 PPG ROUTINE SERVICES | SIMPSON, CARL L. | 100% | 15000 | 0 | 15000 | 14510.84 | 14510.84 | 10737.43 | 0 | 0 | 14510.84 | 12300 | 0 | 12300 | [7 empty] | 11962.62 |  |  |  | 29.82 | 11932.8 |  | 2548.22 | 0 | 97.26% |  | 0 | 11962.62 | 2700 | 18% | 0 | 2700 | 18% | 0 |  | 2548.22 | 17.56% | 2548.22 | 17.56% | 489.16 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878532 - PPG INDUSTRIES INC | WATER | WATER REPAIR & INSTALLATION | 2019-01-06 | 2019-01-29 | 2019-01-06 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877922¦¦2020-03-31
UP | C | Yes | 877923 |  | 52150 JG BOSWELL S 204 | BRASHEAR, DAVID M | 100% | 11570 | 85908.75 | 97478.75 | 111123.75 | 111123.75 | 102185.09 | 0 | 0 | 111123.75 | 8508 | 68944.21 | 77452.21 | [7 empty] | 97563.87 | 20408.47 | 9419.55 |  | 67735.85 |  |  | 13559.88 | 0 | 126% |  | 0 | 97563.87 | 3062 | 26.46% | 16964.54 | 20026.54 | 20.54% | 0 |  | 13559.88 | 12.2% | 13559.88 | 12.2% | -13645 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878568 - J G BOSWELL | WATER | WATER REPAIR & INSTALLATION | 2019-01-14 | 2019-03-31 | 2019-01-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877923¦¦2020-03-31
FP | C | Yes | 877924 |  | 52153 PHILLIPS 66 COOLING PU | ALBARADO, JORDAN A | 100% | 59260 | 9250 | 68510 | 68510 | 68510 | 68510 | 0 | 0 | 68510 | 35554 | 4625 | 40179 | [7 empty] | 39766.42 | 2105.3 | 131.94 |  | 37129.18 | 400 |  | 28743.58 | 0 | 98.97% |  | 0 | 39766.42 | 23706 | 40% | 4625 | 28331 | 41.35% | 0 |  | 28743.58 | 41.96% | 28743.58 | 41.96% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878724 - PHILLIPS 66 | WATER | WATER EQUIPMENT SALES | 2019-01-14 | 2019-04-01 | 2019-01-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877924¦¦2020-03-31
FP | C | Yes | 877928 |  | 52165 CITGO PENTAIR PUMP | GNAU, CASEY T | 100% | 17900 | 0 | 17900 | 17900 | 17900 | 17900 | 0 | 0 | 17900 | 8950 | 0 | 8950 | [7 empty] | 7919.16 | 181.84 | 73.3 |  | 7664.02 |  |  | 9980.84 | 0 | 88.48% |  | 0 | 7919.16 | 8950 | 50% | 0 | 8950 | 50% | 0 |  | 9980.84 | 55.76% | 9980.84 | 55.76% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878864 - CITGO PETROLEUM CORP | WATER | WATER EQUIPMENT SALES | 2019-01-15 | 2019-06-01 | 2019-01-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877928¦¦2020-03-31
FP | CJ | Yes | 877929 |  | 52167 HICKSVILLE REHAB 5 2 AND | RANFT, DONALD R | 100% | 270100 | 6275 | 276375 | 235402.5 | 235402.5 | 235402.5 | 170108 | 11770.13 | 235402.5 | 185855 | 5961.25 | 191816.25 | 24385.5 | 13796.15 | 4742.91 |  | 5046.44 | 800 |  | 195748.61 | 39670 | 13664.69 |  | 137556.58 | 4857.34 |  | 39653.89 | 0 | 102.1% |  | 0 | 195748.61 | 84245 | 31.19% | 313.75 | 84558.75 | 30.6% | 313.75 |  | 39653.89 | 16.85% | 39653.89 | 16.85% | 40972.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878471 - BENSIN CONTRACTING INC | WATER | WATER REPAIR & INSTALLATION | 2019-01-27 | 2019-06-27 | 2019-01-22 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877929¦¦2020-03-31
FP | CJ | Yes | 877934 |  | 52185 SWOWC 2019 MONITORING | GAMBLE, BRAD F. | 100% | 6200 | 0 | 6200 | 4758.6 | 4758.6 | 0 | 0 | 0 | 4758.6 | 4200 | 0 | 4200 | [7 empty] | 3844.45 | 3834.85 |  |  | 9.6 |  |  | 914.15 | 0 | 91.53% |  | 0 | 3844.45 | 2000 | 32.26% | 0 | 2000 | 32.26% | 0 |  | 914.15 | 19.21% | 914.15 | 19.21% | 1441.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878870 - SOUTHWESTERN OHIO WATER COMPANY | WATER | WATER SUPPLY | 2019-01-16 | 2020-01-30 | 2019-01-16 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877934¦¦2020-03-31
TM | C | Yes | 877937 |  | 52194 52194 AK STEEL MAINTEN | SIMPSON, CARL L. | 100% | 12000 | 0 | 12000 | 23647.8 | 23647.8 | 18672.8 | 0 | 0 | 23647.8 | 8400 | 0 | 8400 | 1.15 | 1.15 | [5 empty] | 17777.31 | 8826.3 | 4325.16 |  | 4625.85 | 0 |  | 5870.49 | 0 | 211.6% |  | 0 | 17777.31 | 3600 | 30% | 0 | 3600 | 30% | 0 |  | 5870.49 | 24.82% | 5870.49 | 24.82% | -11647.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-01-06 | 2019-03-28 | 2019-01-06 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877937¦¦2020-03-31
TM | C | Yes | 877940 |  | 52200 BEARSKIN FARMS | BENNETT, MARK C. | 100% | 22500 | 0 | 22500 | 61333.64 | 61333.64 | 39700.34 | 0 | 0 | 61333.64 | 16000 | 0 | 16000 | [7 empty] | 68382.88 | 34659.03 | 10318.67 |  | 23405.18 |  |  | 0 | 7049.24 | 427.4% |  | 0 | 68382.88 | 6500 | 28.89% | 0 | 6500 | 28.89% | 0 |  | -7049.24 | -11.49% | -7049.24 | -11.49% | -38833.64 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878874 - BEARSKIN FARMS | WATER | WATER SUPPLY | 2019-01-18 | 2020-01-18 | 2019-01-18 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877940¦¦2020-03-31
TM | C | Yes | 877949 |  | 52235 52235 AK STEEL BOILER | SIMPSON, CARL L. | 100% | 200000 | 600000 | 800000 | 800000 | 800000 | 400000 | 0 | 0 | 800000 | 140000 | 380000 | 520000 | [7 empty] | 485624.44 | 89605.79 | 45687.79 |  | 349805.86 | 525 |  | 314375.56 | 0 | 93.39% |  | 0 | 485624.44 | 60000 | 30% | 220000 | 280000 | 35% | 0 |  | 314375.56 | 39.3% | 314375.56 | 39.3% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-01-27 | 2019-02-27 | 2019-01-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877949¦¦2020-03-31
FP | CJ | Yes | 877967 |  | 52283 ECO SERVICES FABRICATED | LOPEZ-VASQUEZ, JUAN C. | 100% | 16070 | 4120 | 20190 | 20190 | 20190 | 2661.86 | 0 | 0 | 20190 | 7797.5 | 2504.77 | 10302.27 | [7 empty] | 8600.27 | 2033.48 | 142.45 |  | 6424.34 |  |  | 11589.73 | 0 | 83.48% |  | 0 | 8600.27 | 8272.5 | 51.48% | 1615.23 | 9887.73 | 48.97% | 0 |  | 11589.73 | 57.4% | 11589.73 | 57.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878890 - ECO SERVICES OPERATIONS CORP | WATER | WATER EQUIPMENT SALES | 2019-01-28 | 2019-05-31 | 2019-01-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877967¦¦2020-03-31
UP | C | Yes | 877968 |  | 52287 FMI SIERRITA FFS 6 PUL | VAN ALLEN, WESLEY C. | 100% | 20676 | 76145 | 96821 | 94465.51 | 94465.51 | 75390 | 0 | 0 | 94465.51 | 14262 | 63480.42 | 77742.42 | -0.03 | -0.04 |  |  | 0.01 |  |  | 70261.58 | 23183.88 | 12457.32 |  | 34620.38 |  |  | 24203.93 | 0 | 90.38% |  | 0 | 70261.58 | 6414 | 31.02% | 12664.58 | 19078.58 | 19.71% | 9032.04 |  | 24203.93 | 25.62% | 24203.93 | 25.62% | 2355.49 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878891 - FREEPORT MCMORAN SIERRITA OPERATIONS | WATER | WATER REPAIR & INSTALLATION | 2019-02-04 | 2019-03-25 | 2019-02-04 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877968¦¦2020-03-31
FP | C | Yes | 877969 |  | 52288 IBERVILLE PUMP 4 RI | GNAU, CASEY T | 100% | 4170 | 5030 | 9200 | 9200 | 9200 | 9200 | 0 | 0 | 9200 | 2292 | 3163 | 5455 | [7 empty] | 4498.05 | 2412.78 | 262.8 |  | 1822.47 |  |  | 4701.95 | 0 | 82.46% |  | 0 | 4498.05 | 1878 | 45.04% | 1867 | 3745 | 40.71% | 0 |  | 4701.95 | 51.11% | 4701.95 | 51.11% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878892 - IBERVILLE PARISH UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-01-29 | 2019-02-28 | 2019-01-29 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877969¦¦2020-03-31
FP | CJ | Yes | 877972 |  | 52293 V&K WEST DES MOINES WW | HEILIGER, TERENCE L. | 100% | 242851 | 0 | 242851 | 216596.88 | 216596.88 | 216596.88 | 49702.23 | 0 | 216596.88 | 190453 | 0 | 190453 | 18684.98 |  | 2664 |  |  | 16020.98 |  | 198241.32 | 35693.52 | 38483.67 |  | 31004.13 | 93060 |  | 18355.56 | 0 | 104.1% |  | 0 | 198241.32 | 52398 | 21.58% | 0 | 52398 | 21.58% | 0 |  | 18355.56 | 8.475% | 18355.56 | 8.475% | 26254.12 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878894 - VEENSTRA & KIMM INC | WATER | WATER SUPPLY | 2019-01-30 | 2019-04-30 | 2019-01-30 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877972¦¦2020-03-31
UP | CJ | Yes | 877973 |  | 52294 CHANDLER ASR 6 PULL | VAN ALLEN, WESLEY C. | 100% | 5233 | 310384 | 315617 | 306132.22 | 306132.22 | 165973 | 0 | 0 | 306132.22 | 3262 | 263907.24 | 267169.24 | 51099.28 | 45.98 |  |  | 51053.3 |  |  | 247322.55 | 32036.42 | 27176.56 |  | 186759.57 | 1350 |  | 58809.67 | 0 | 92.57% |  | 0 | 247322.55 | 1971 | 37.66% | 46476.76 | 48447.76 | 15.35% | 0 |  | 58809.67 | 19.21% | 58809.67 | 19.21% | 9484.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-01-31 | 2019-03-04 | 2019-01-31 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 877973¦¦2020-03-31
FP | C | Yes | 877980 |  | 52307 WC PLAQ WELL 15B REHAB | GNAU, CASEY T | 100% | 117000 | 32430 | 149430 | 149430 | 149430 | 0 | 0 | 0 | 149430 | 61220 | 16216 | 77436 | 2396.86 |  |  |  |  | 2396.86 |  | 77373.98 | 32442.99 | 4445.26 |  | 34989.87 | 5495.86 |  | 72056.02 | 0 | 99.92% |  | 0 | 77373.98 | 55780 | 47.68% | 16214 | 71994 | 48.18% | 0 |  | 72056.02 | 48.22% | 72056.02 | 48.22% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878850 - AXIALL PLAQ GEORGIA GULF | WATER | WATER REPAIR & INSTALLATION | 2019-02-01 | 2019-03-15 | 2019-02-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877980¦¦2020-03-31
UP | LJ | Yes | 877982 |  | 52309 SIDNEY NY DRILLING | CROOK, CHARLES M | 63.52% | 508000 | 132053 | 640053 | 406571.0223 | 402105 | 402105 | 0 | 20105.25 | 640052 | 355610 | 105642.68 | 461252.68 | 4281.71 | 1877.37 | 195.12 |  | 2209.22 |  |  | 343016.43 | 134014.08 | 103723.7 |  | 105278.65 |  |  | 59088.57 | 0 | 74.37% |  | 196983.57 | 540000 | 152390 | 30% | 26410.32 | 178800.32 | 27.94% | 26410.32 |  | 63554.59 | 15.63% | 100052 | 15.63% | 233481.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 878902 - SIDNEY, VILLAGE OF | WATER | WATER SUPPLY | 2019-01-20 | 2020-04-09 | 2019-01-20 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 877982¦¦2020-03-31
UP | C | Yes | 877994 |  | 52337 VENTAVO WELL 1 PULL INSP | GRACE, GARY L. | 100% | 14641 | 120419.01 | 135060.01 | 134527.06 | 134527.06 | 33780.64 | 0 | 0 | 134527.06 | 10760 | 109493.32 | 120253.32 | [7 empty] | 142461.51 | 43808.93 | 15044.22 |  | 77877.5 | 5730.86 |  | 0 | 7934.45 | 118.5% |  | 0 | 142461.51 | 3881 | 26.51% | 10925.69 | 14806.69 | 10.96% | 0 |  | -7934.45 | -5.898% | -7934.45 | -5.898% | 532.95 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878912 - VENTAVO WATER GROUP | WATER | WATER REPAIR & INSTALLATION | 2019-02-05 | 2019-03-01 | 2019-02-05 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877994¦¦2020-03-31
UP | CJ | Yes | 877996 |  | 52339 SONY PULL PUMP AND VIDEO | GRACE, GARY L. | 100% | 8162 | 0 | 8162 | 8161.81 | 8161.81 | 0 | 0 | 0 | 8161.81 | 4880 | 0 | 4880 | [7 empty] | 4728.64 | 3243.52 | 110 |  | 1375.12 |  |  | 3433.17 | 0 | 96.9% |  | 0 | 4728.64 | 3282 | 40.21% | 0 | 3282 | 40.21% | 0 |  | 3433.17 | 42.06% | 3433.17 | 42.06% | 0.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878913 - DO NOT USE GREGG DRILLING & TESTING INC | WATER | WATER REPAIR & INSTALLATION | 2019-02-05 | 2019-03-15 | 2019-02-05 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 877996¦¦2020-03-31
TM | C | Yes | 878003 |  | 52353 REMINGTON ARMS WELL 4 | CROOK, CHARLES M | 100% | 27765 | 14285 | 42050 | 56160 | 56160 | 56160 | 0 | 0 | 56160 | 19436 | 9564 | 29000 | [7 empty] | 43025.32 | 15176.02 | 4281.97 |  | 23567.33 |  |  | 13134.68 | 0 | 148.4% |  | 0 | 43025.32 | 8329 | 30% | 4721 | 13050 | 31.03% | 0 |  | 13134.68 | 23.39% | 13134.68 | 23.39% | -14110 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 878919 - REMINGTON ARMS CO INC | WATER | WATER REPAIR & INSTALLATION | 2019-02-03 | 2019-02-24 | 2019-02-03 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878003¦¦2020-03-31
FP | CJ | Yes | 878004 |  | 52357 TIPTONVILLE TN NEW WE | ANDERSON, STEPHEN P. | 100% | 406967 | 25321 | 432288 | 438988 | 438988 | 177295.3 | 37831.5 | 0 | 438988 | 305237 | 19381.94 | 324618.94 | 4540.69 |  |  |  | 4540.69 |  |  | 350405.79 | 103545.12 | 30391.01 |  | 158490.66 | 57979 |  | 88582.21 | 0 | 107.9% |  | 0 | 350405.79 | 101730 | 25% | 5939.06 | 107669.06 | 24.91% | 0 |  | 88582.21 | 20.18% | 88582.21 | 20.18% | -6700 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 878920 - TIPTONVILLE, CITY OF | WATER | WATER SUPPLY | 2019-02-25 | 2019-06-24 | 2019-02-25 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 878004¦¦2020-03-31
FP | C | Yes | 878008 |  | 52367 NOBLE ENERGY MW TESTING | SCHANAMAN, MIKE L. |  | 21870 | 0 | 21870 |  |  | 0 | 0 | 0 |  | 16840 | 0 | 16840 | [20 empty] | 5030 | 23% | 0 | 5030 | 23% | 0 | [5 empty] | 21870 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878923 - OLSSON DENVER | WATER | WATER SPECIALTY DRILLING | 2019-02-07 | 2019-03-31 | 2019-02-07 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 878008¦¦2020-03-31
FP | C | Yes | 878011 |  | 52378 PIXELLE WELL 13 REHAB | HARTMAN, MICHAEL | 100% | 192300 | 22782 | 215082 | 215082 | 215082 | 215082 | 0 | 0 | 215082 | 124000 | 18225 | 142225 | 2.01 | 2.01 | [5 empty] | 337397.51 | 151043.46 | 48181.59 |  | 127815.16 | 10357.3 |  | 0 | 122315.51 | 237.2% |  | 0 | 337397.51 | 68300 | 35.52% | 4557 | 72857 | 33.87% | 0 |  | -122315.51 | -56.87% | -122315.51 | -56.87% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878886 - PIXELLE SPECIALTY SOLUTIONS | WATER | WATER SUPPLY | 2019-02-10 | 2019-06-30 | 2019-02-10 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878011¦¦2020-03-31
FP | C | Yes | 878012 |  | 52379 NOBLE ENERGY MW DRILL | DECKER, JASEN | 100% | 233855 | 0 | 233855 | 277093.95 | 277093.95 | 277093.95 | 0 | 0 | 277093.95 | 178608 | 0 | 178608 | 0 |  |  |  | 0 |  |  | 248179.22 | 85446.25 | 64545.09 |  | 96355.98 | 1831.9 |  | 28914.73 | 0 | 139% |  | 0 | 248179.22 | 55247 | 23.62% | 0 | 55247 | 23.62% | 0 |  | 28914.73 | 10.43% | 28914.73 | 10.43% | -43238.95 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878923 - OLSSON DENVER | WATER | WATER SPECIALTY DRILLING | 2019-02-08 | 2019-03-31 | 2019-02-08 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 878012¦¦2020-03-31
UP | C | Yes | 878021 |  | 52398 SAN JACINTO ARTESIA WEL | BRASHEAR, DAVID M | 100% | 12888 | 97286 | 110174 | 105531 | 105531 | 0 | 0 | 0 | 105531 | 11066 | 73019 | 84085 | [7 empty] | 97607.72 | 31689.27 | 3167.86 |  | 47036.52 | 15714.07 |  | 7923.28 | 0 | 116.1% |  | 0 | 97607.72 | 1822 | 14.14% | 24267 | 26089 | 23.68% | 0 |  | 7923.28 | 7.508% | 7923.28 | 7.508% | 4643 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878729 - SAN JACINTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-02-05 | 2019-04-30 | 2019-02-05 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | PROFESSIONAL SERVICES | 878021¦¦2020-03-31
FP | C | Yes | 878023 |  | 52409 NUTRIEN DRILL WELL GEI | LOPEZ-VASQUEZ, JUAN C. | 100% | 289400 | 0 | 289400 | 289400 | 289400 | 28445 | 0 | 0 | 289400 | 212141 | 0 | 212141 | [7 empty] | 156806.27 | 61632.61 | 24618 |  | 64039.91 | 6515.75 |  | 132593.73 | 0 | 73.92% |  | 0 | 156806.27 | 77259 | 26.7% | 0 | 77259 | 26.7% | 0 |  | 132593.73 | 45.82% | 132593.73 | 45.82% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878934 - NUTRIENT | WATER | WATER SUPPLY | 2019-02-08 | 2019-08-30 | 2019-02-08 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878023¦¦2020-03-31
UP | C | Yes | 878025 |  | 52412 BEV HILLS FIRE PUMP R&I | BRASHEAR, DAVID M | 100% | 14022 | 0 | 14022 | 13944.56 | 13944.56 | 14598.94 | 0 | 0 | 13944.56 | 10525 | 0 | 10525 | [7 empty] | 17100.06 | 6704.6 | 1682.26 |  | 8665.34 | 47.86 |  | 0 | 3155.5 | 162.5% |  | 0 | 17100.06 | 3497 | 24.94% | 0 | 3497 | 24.94% | 0 |  | -3155.5 | -22.63% | -3155.5 | -22.63% | 77.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878627 - BEVERLY HILLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-02-14 | 2019-04-30 | 2019-02-14 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 878025¦¦2020-03-31
FP | CJ | Yes | 878031 |  | 52424 SCIOTO IMPROVEMENTS | BARNES, MATTHEW D | 100% | 317500 | 0 | 317500 | 317500 | 317500 | 283771.8 | 0 | 29559.6 | 317500 | 246988 | 0 | 246988 | 1142.43 | 842.71 | 284.76 |  | 14.96 |  |  | 319855.16 | 84831.06 | 51847.02 |  | 135275.08 | 47902 |  | 0 | 2355.16 | 129.5% |  | 0 | 319855.16 | 70512 | 22.21% | 0 | 70512 | 22.21% | 0 |  | -2355.16 | -0.7418% | -2355.16 | -0.7418% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878940 - SCIOTO WATER INC | WATER | WATER REPAIR & INSTALLATION | 2019-02-07 | 2019-12-15 | 2019-02-07 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 878031¦¦2020-03-31
FP | LJ | Yes | 878032 |  | 52426 EXXON CHEMICAL NEW WELL | LOPEZ-VASQUEZ, JUAN C. | 76.03% | 2204260 | 0 | 2204260 | 1816997.1086 | 1985854 | 1985854 | 0 | 0 | 2389898 | 1532826 | 0 | 1532826 | 40926.22 | 17882.86 | 423.73 |  | 16666.91 | 5952.72 |  | 1365689.28 | 438764.72 | 282946.49 |  | 519995.88 | 123982.19 |  | 620164.72 | 0 | 89.1% |  | 430603.11 | 1796292.39 | 671434 | 30.46% | 0 | 671434 | 30.46% | 0 |  | 451307.83 | 24.84% | 593605.61 | 24.84% | 387262.89 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878941 - EXXON MOBIL CHEMICAL COMPANY | WATER | WATER SUPPLY | 2019-02-15 | 2020-06-30 | 2019-02-15 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 878032¦¦2020-03-31
FP | CJ | Yes | 878034 |  | 52430 PLAINVIEW MAINTENANCE CO | RANFT, DONALD R | 100% | 73070 | 0 | 73070 | 1652.08 | 1652.08 | 0 | 0 | 0 | 1652.08 | 55000 | 0 | 55000 | 246.98 | 177.9 | 23.32 |  | 45.76 |  |  | 1334.71 | 780.14 | 150.06 |  | 404.51 |  |  | 317.37 | 0 | 2.427% |  | 0 | 1334.71 | 18070 | 24.73% | 0 | 18070 | 24.73% | 0 |  | 317.37 | 19.21% | 317.37 | 19.21% | 71417.92 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878816 - PLAINVIEW WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-01-27 | 2019-12-30 | 2019-01-27 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 878034¦¦2020-03-31
UP | CJ | Yes | 878038 |  | 52448 PHILLIPS 66 RW19 | WHITE, CATHLEEN R | 100% | 306880 | 37680 | 344560 | 344560 | 344560 | 327332 | 0 | 32733.2 | 344560 | 200000 | 26695.94 | 226695.94 | 105718.01 | 53127.69 | 23537.54 |  | 29052.78 |  |  | 362435.29 | 152003.87 | 76397.56 |  | 134033.86 |  |  | 0 | 17875.29 | 159.9% |  | 0 | 362435.29 | 106880 | 34.83% | 10984.06 | 117864.06 | 34.21% | 10984.06 |  | -17875.29 | -5.188% | -17875.29 | -5.188% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878946 - PHILLIPS 66 WOOD RIVER REFINERY | WATER | WATER SUPPLY | 2019-03-04 | 2019-04-30 | 2019-02-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 878038¦¦2020-03-31
FP | C | Yes | 878045 |  | 52462 MADISON CO LOCI TESTING | BARNES, MATTHEW D | 100% | 10400 | 19110 | 29510 | 34090 | 34090 | 34090 | 0 | 0 | 34090 | 7280 | 13759 | 21039 | 5.44 | 0.45 |  |  | 4.99 |  |  | 23563.13 | 9546.12 | 4262.53 |  | 9754.48 |  |  | 10526.87 | 0 | 112% |  | 0 | 23563.13 | 3120 | 30% | 5351 | 8471 | 28.71% | 0 |  | 10526.87 | 30.88% | 10526.87 | 30.88% | -4580 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878952 - MADISON COUNTY SEWER AND WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-03-14 | 2019-05-14 | 2019-03-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 878045¦¦2020-03-31
UP | CJ | Yes | 878046 |  | 52463 MUD PLATTE S 2019 WELL R | GANSEBOM, JASON W. | 100% | 162000 | 0 | 162000 | 162000 | 162000 | 92964.82 | 0 | 0 | 162000 | 121500 | 0 | 121500 | 221.54 | 0.28 |  |  | 221.26 |  |  | 188623.55 | 58916.24 | 33679.88 |  | 96027.43 |  |  | 0 | 26623.55 | 155.2% |  | 0 | 188623.55 | 40500 | 25% | 0 | 40500 | 25% | 0 |  | -26623.55 | -16.43% | -26623.55 | -16.43% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878953 - METROPOLITAN UTILITIES DISTRICT NE | WATER | WATER REPAIR & INSTALLATION | 2019-02-14 | 2020-02-29 | 2019-02-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 878046¦¦2020-03-31
CR | C | Yes | 878047 |  | 52465 EMWD 55 | BRASHEAR, DAVID M | 100% | 112371 | 0 | 112371 | 190940.11 | 190940.11 | 179848.22 | 0 | 0 | 190940.11 | 85470 | 0 | 85470 | 4.73 |  |  |  | 4.73 |  |  | 192028.86 | 74759.2 | 32632.69 |  | 73501.88 | 11135.09 |  | 0 | 1088.75 | 224.7% |  | 0 | 192028.86 | 26901 | 23.94% | 0 | 26901 | 23.94% | 0 |  | -1088.75 | -0.5702% | -1088.75 | -0.5702% | -78569.11 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878619 - EASTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-02-22 | 2019-05-31 | 2019-02-22 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 878047¦¦2020-03-31
TM | CJ | Yes | 878049 |  | 52467 WALKER WATER ASSOCIATION | BURGE, EVERETT E. | 100% | 101300 | 19000 | 120300 | 101300 | 101300 | 101300 | 0 | 5065 | 101300 | 74000 | 24334.82 | 98334.82 | -2978.89 |  |  |  | 126.11 | -3105 |  | 90206.85 | 18304.29 | 1364.02 |  | 58291.04 | 12247.5 |  | 11093.15 | 0 | 91.73% |  | 0 | 90206.85 | 27300 | 26.95% | -5334.82 | 21965.18 | 18.26% | -5334.82 |  | 11093.15 | 10.95% | 11093.15 | 10.95% | 19000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878955 - WALKER WATER ASSOCIATION | WATER | WATER EQUIPMENT SALES | 2019-01-15 | 2019-04-26 | 2019-01-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 878049¦¦2020-03-31
FP | C | Yes | 878050 |  | 52475 MOSAIC PLANT CITY GEOPHY | TORMOEHLEN, DAVID A. | 100% | 33750 | 0 | 33750 | 33875 | 33875 | 0 | 0 | 0 | 33875 | 16875 | 0 | 16875 | [7 empty] | 9265.44 | 6128.45 | 1744.33 |  | 1392.66 |  |  | 24609.56 | 0 | 54.91% |  | 0 | 9265.44 | 16875 | 50% | 0 | 16875 | 50% | 0 |  | 24609.56 | 72.65% | 24609.56 | 72.65% | -125 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878838 - MOSAIC BUSINESS SERVICES PLANT CITY FL | WATER | WATER SUPPLY | 2019-02-24 | 2019-03-07 | 2019-02-24 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 878050¦¦2020-03-31
FP | LJ | Yes | 878052 |  | 52477 WARREN CO FILTER REHAB | WILLIAMS, DONALD G. | 99.7% | 669500 | 36224.68 | 705724.68 | 703595.884 | 699368.73 | 699368.73 | 0 | 34968.44 | 705724.68 | 538724 | 16681.58 | 555405.58 | 10196.92 | 6096.88 | 1941.95 |  | 2158.09 |  |  | 661823.59 | 158739.43 | 58121.26 |  | 220949.77 | 224013.13 |  | 37545.14 | 0 | 119.2% |  | 2002.41 | 663826 | 130776 | 19.53% | 19543.1 | 150319.1 | 21.3% | 1873.71 |  | 41772.29 | 5.937% | 41898.68 | 5.937% | 2128.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878956 - WARREN COUNTY WATER & SEWER DIST | WATER | WATER REPAIR & INSTALLATION | 2019-03-31 | 2020-02-02 | 2019-03-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 878052¦¦2020-03-31
UP | CJ | Yes | 878056 |  | 52485 EARTH CITY LEVEE RW TE | WHITE, CATHLEEN R | 100% | 92650 | 71289 | 163939 | 80169 | 80169 | 79065 | 0 | 0 | 80169 | 59650 | 49902.3 | 109552.3 | 1677.74 |  |  |  | 1677.74 |  |  | 67624.33 | 17591.88 | 1333.63 |  | 47491.08 | 1207.74 |  | 12544.67 | 0 | 61.73% |  | 0 | 67624.33 | 33000 | 35.62% | 21386.7 | 54386.7 | 33.17% | 0 |  | 12544.67 | 15.65% | 12544.67 | 15.65% | 83770 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878960 - EARTH CITY LEVEE DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-03-01 | 2019-04-01 | 2019-02-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 878056¦¦2020-03-31
FP | CJ | Yes | 878064 |  | 52505 ST TAMMANY PARISH FLOW | GREGORY, CRYSTAL N | 100% | 21600 | 0 | 21600 | 26790 | 26790 | 23190 | 6600 | 0 | 26790 | 15174 | 0 | 15174 | 0.01 |  |  |  | 0.01 |  |  | 10610.09 | 5844.57 | 2731.54 |  | 2033.98 |  |  | 16179.91 | 0 | 69.92% |  | 0 | 10610.09 | 6426 | 29.75% | 0 | 6426 | 29.75% | 0 |  | 16179.91 | 60.4% | 16179.91 | 60.4% | -5190 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878967 - ST TAMMANY PARISH GOVERNMENT | WATER | WATER REPAIR & INSTALLATION | 2019-04-01 | 2019-12-27 | 2019-04-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 878064¦¦2020-03-31
CR | C | Yes | 878065 |  | 52509 VIRGIN VALLEY WELL 28 R | BRASHEAR, DAVID M | 100% | 375356 | 0 | 375356 | 354268.48 | 354268.48 | 212978.88 | 0 | 0 | 354268.48 | 319860 | 0 | 319860 | [7 empty] | 272767.71 | 94575.35 | 15996.35 |  | 162196.01 |  |  | 81500.77 | 0 | 85.28% |  | 0 | 272767.71 | 55496 | 14.78% | 0 | 55496 | 14.78% | 0 |  | 81500.77 | 23.01% | 81500.77 | 23.01% | 21087.52 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878968 - VIRGIN VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-02-25 | 2019-05-31 | 2019-02-25 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 878065¦¦2020-03-31
FP | C | Yes | 878066 |  | 52513 ENTERGY CONSULTING | REED, MATTHEW T. | 100% | 40000 | 0 | 40000 | 30210.65 | 30210.65 | 30210.65 | 0 | 0 | 30210.65 | 25000 | 0 | 25000 | [7 empty] | 22927.67 | 22518.97 |  |  | 408.7 |  |  | 7282.98 | 0 | 91.71% |  | 0 | 22927.67 | 15000 | 37.5% | 0 | 15000 | 37.5% | 0 |  | 7282.98 | 24.11% | 7282.98 | 24.11% | 9789.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878969 - ENTERGY | WATER | WATER SUPPLY | 2019-02-27 | 2019-06-13 | 2019-02-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 878066¦¦2020-03-31
TM | C | Yes | 878069 |  | 52519 EVERGREEN PACKAGING WELL | BURGE, EVERETT E. | 100% | 24000 | 0 | 24000 | 50604.78 | 50604.78 | 36629.78 | 0 | 0 | 50604.78 | 16800 | 0 | 16800 | [7 empty] | 30708.44 | 13422.42 | 3203.29 |  | 14082.73 |  |  | 19896.34 | 0 | 182.8% |  | 0 | 30708.44 | 7200 | 30% | 0 | 7200 | 30% | 0 |  | 19896.34 | 39.32% | 19896.34 | 39.32% | -26604.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878972 - EVERGREEN PACKAGING INC | WATER | WATER REPAIR & INSTALLATION | 2019-02-28 | 2019-05-31 | 2019-02-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 878069¦¦2020-03-31
FP | C | Yes | 878070 |  | 52520 CLECO ST LANDRY REHAB | GNAU, CASEY T | 100% | 106000 | 21200 | 127200 | 127200 | 127200 | 0 | 0 | 0 | 127200 | 59012 | 10569 | 69581 | [7 empty] | 70999.75 | 35213.11 | 16021.6 |  | 15598.43 | 4166.61 |  | 56200.25 | 0 | 102% |  | 0 | 70999.75 | 46988 | 44.33% | 10631 | 57619 | 45.3% | 0 |  | 56200.25 | 44.18% | 56200.25 | 44.18% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878973 - CLECO POWER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-03-01 | 2019-03-29 | 2019-03-01 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 878070¦¦2020-03-31
FP | C | Yes | 878071 |  | 52521 COMPASS MINERALS FIRE | GNAU, CASEY T | 100% | 20900 | 18753 | 39653 | 39653 | 39653 | 22933 | 0 | 0 | 39653 | 10429 | 10359 | 20788 | [7 empty] | 21755.55 | 14277.89 | 2363.74 |  | 4713.92 | 400 |  | 17897.45 | 0 | 104.7% |  | 0 | 21755.55 | 10471 | 50.1% | 8394 | 18865 | 47.58% | 0 |  | 17897.45 | 45.14% | 17897.45 | 45.14% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878974 - COMPASS MINERALS | WATER | WATER REPAIR & INSTALLATION | 2019-03-01 | 2019-03-29 | 2019-03-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 878071¦¦2020-03-31
FP | C | Yes | 878073 |  | 52529 WELL 4 REPLACEMENT EQUIP | MARTINEZ, MIGUEL E | 100% | 93925 | 0 | 93925 | 93925 | 93925 | 93925 | 0 | 0 | 93925 | 61000 | 0 | 61000 | [7 empty] | 61386.04 |  |  |  | 61386.04 |  |  | 32538.96 | 0 | 100.6% |  | 0 | 61386.04 | 32925 | 35.05% | 0 | 32925 | 35.05% | 0 |  | 32538.96 | 34.64% | 32538.96 | 34.64% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878976 - DAVIE, TOWN OF | WATER | WATER EQUIPMENT SALES | 2019-02-28 | 2019-07-30 | 2019-02-28 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 878073¦¦2020-03-31
FP | C | Yes | 878074 |  | 52532 MOSAIC PLANT CITY WELL F | BRUGGER, CRAIG J. | 100% | 24539 | 17808 | 42347 | 42347 | 42347 | 0 | 0 | 0 | 42347 | 14724 | 1874 | 16598 | [7 empty] | 16603.38 | 9104.06 | 2688.68 |  | 3160.64 | 1650 |  | 25743.62 | 0 | 100% |  | 0 | 16603.38 | 9815 | 40% | 15934 | 25749 | 60.8% | 0 |  | 25743.62 | 60.79% | 25743.62 | 60.79% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878838 - MOSAIC BUSINESS SERVICES PLANT CITY FL | WATER | WATER SUPPLY | 2019-03-02 | 2019-03-30 | 2019-02-28 | 1900-01-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 878074¦¦2020-03-31
CPF | CJ | Yes | 878076 |  | 52544 WICHITA KS MLB STADIUM | WARTICK, LOGAN M | 100% | 32396 | 370838 | 403234 | 492735 | 492735 | 453839 | 0 | 22691.95 | 492735 | 21057.4 | 241826.12 | 262883.52 | 4505.26 | 3985.08 | 1304.8 |  | 3134.12 | -3918.74 |  | 239712.35 | 49744.38 | 39929.15 |  | 117882.58 | 32156.24 |  | 253022.65 | 0 | 91.19% |  | 0 | 239712.35 | 11338.6 | 35% | 129011.88 | 140350.48 | 34.81% | 0 |  | 253022.65 | 51.35% | 253022.65 | 51.35% | -89501 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 878978 - J E DUNN | WATER | WATER SUPPLY | 2019-01-31 | 2019-05-10 | 2019-01-31 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 878076¦¦2020-03-31
TM | CJ | Yes | 878078 |  | 52546 BASF | PARSLEY, TRISTAN S | 100% | 115160 | 0 | 115160 | 100415 | 100415 | 100415 | 0 | 0 | 100415 | 63733 | 0 | 63733 | [7 empty] | 59296.23 | 5398.51 | 246.31 |  | 53651.41 |  |  | 41118.77 | 0 | 93.04% |  | 0 | 59296.23 | 51427 | 44.66% | 0 | 51427 | 44.66% | 0 |  | 41118.77 | 40.95% | 41118.77 | 40.95% | 14745 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 878980 - BASF MCINTOSH PLANT | WATER | WATER REPAIR & INSTALLATION | 2019-03-02 | 2019-08-01 | 2019-03-02 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 878078¦¦2020-03-31
FP | C | Yes | 878086 |  | 52585 AUL 6 & 7 WELLS | SIMPSON, CARL L. | 100% | 56300 | 25492 | 81792 | 81792 | 81792 | 81792 | 0 | 0 | 81792 | 39000 | 17551 | 56551 | [7 empty] | 56640.23 | 17103.76 | 12384.46 |  | 24352.01 | 2800 |  | 25151.77 | 0 | 100.2% |  | 0 | 56640.23 | 17300 | 30.73% | 7941 | 25241 | 30.86% | 0 |  | 25151.77 | 30.75% | 25151.77 | 30.75% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889230 - CUSHMAN & WAKEFILED AUL | WATER | WATER REPAIR & INSTALLATION | 2019-03-07 | 2019-04-30 | 2019-03-07 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 878086¦¦2020-03-31
FP | C | Yes | 878090 |  | 52600 SHELL NORCO WELL 2 | LOPEZ-VASQUEZ, JUAN C. | 100% | 10150 | 130820 | 140970 | 130102.6 | 130102.6 | 109802.6 | 0 | 0 | 130102.6 | 6961 | 83442 | 90403 | [7 empty] | 108369.74 | 33317.52 | 10384.78 |  | 64667.44 |  |  | 21732.86 | 0 | 119.9% |  | 0 | 108369.74 | 3189 | 31.42% | 47378 | 50567 | 35.87% | 0 |  | 21732.86 | 16.7% | 21732.86 | 16.7% | 10867.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878988 - SHELL CHEMICAL LP | WATER | WATER REPAIR & INSTALLATION | 2019-03-11 | 2019-09-24 | 2019-03-11 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 878090¦¦2020-03-31
UP | C | Yes | 878095 |  | 52607 SUEZ RUSTIC 72 PUMP | CROOK, CHARLES M | 100% | 46275 | 0 | 46275 | 49840 | 49840 | 49840 | 0 | 0 | 49840 | 32394 | 0 | 32394 | 0 |  |  |  | 0 |  |  | 45818.4 | 11174.34 | 3636.42 |  | 30190.64 | 817 |  | 4021.6 | 0 | 141.4% |  | 0 | 45818.4 | 13881 | 30% | 0 | 13881 | 30% | 0 |  | 4021.6 | 8.069% | 4021.6 | 8.069% | -3565 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 898467 - SUEZ | WATER | WATER REPAIR & INSTALLATION | 2019-05-26 | 2019-07-14 | 2019-03-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 878095¦¦2020-03-31
TM | CJ | Yes | 878096 |  | 52608 RICE UNIVERSITY | CALLAHAN, DANIEL E. | 100% | 88270 | 0 | 88270 | 120407 | 120407 | 120407 | 24800 | 0 | 120407 | 61789 | 0 | 61789 | [7 empty] | 202032.86 | 55314.2 | 48470.12 |  | 96812.89 | 1435.65 |  | 0 | 81625.86 | 327% |  | 0 | 202032.86 | 26481 | 30% | 0 | 26481 | 30% | 0 |  | -81625.86 | -67.79% | -81625.86 | -67.79% | -32137 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 878993 - RICE UNIVERSITY | WATER | WATER REPAIR & INSTALLATION | 2019-03-25 | 2019-05-30 | 2019-03-25 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878096¦¦2020-03-31
FP | C | Yes | 878097 |  | 52612 GASPARILLA RO WTP MIT | MARTINEZ, MIGUEL E | 100% | 37593 | 0 | 37593 | 37593 | 37593 | 37593 | 0 | 0 | 37593 | 22556 | 0 | 22556 | 194.92 |  | 194.92 |  |  |  |  | 14856.34 | 5605.78 | 5286.28 |  | 3485.82 | 478.46 |  | 22736.66 | 0 | 65.86% |  | 0 | 14856.34 | 15037 | 40% | 0 | 15037 | 40% | 0 |  | 22736.66 | 60.48% | 22736.66 | 60.48% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878994 - GASPARILLA ISLAND WATER ASSOCIATION | WATER | WATER SUPPLY | 2019-05-01 | 2019-09-29 | 2019-08-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878097¦¦2020-03-31
UP | C | Yes | 878100 |  | 52619 LAKE VENTURA 2007 1 WELL | GANSEBOM, JASON W. | 100% | 16357 | 0 | 16357 | 25501.38 | 25501.38 | 26318.38 | 0 | 0 | 25501.38 | 11449.9 | 0 | 11449.9 | [7 empty] | 34243.72 | 9297.08 | 6888.61 |  | 17898.03 | 160 |  | 0 | 8742.34 | 299.1% |  | 0 | 34243.72 | 4907.1 | 30% | 0 | 4907.1 | 30% | 0 |  | -8742.34 | -34.28% | -8742.34 | -34.28% | -9144.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878995 - LAKE VENTURA SID 3 | WATER | WATER REPAIR & INSTALLATION | 2019-03-12 | 2019-06-30 | 2019-03-12 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 878100¦¦2020-03-31
FP | CJ | Yes | 878102 |  | 52630 BURNS MAC ENTERGY WW6 SU | GREGORY, CRYSTAL N | 100% | 47054 | 9461 | 56515 | 56480.15 | 56480.15 | 58273.28 | 1600.87 | 0 | 56480.15 | 27809.7 | 6858 | 34667.7 | 0 |  |  |  | 0 |  |  | 27747.72 | 9230 | 3086.77 |  | 15430.95 |  |  | 28732.43 | 0 | 80.04% |  | 0 | 27747.72 | 19244.3 | 40.9% | 2603 | 21847.3 | 38.66% | -2139 | -2139 | 28732.43 | 50.87% | 28732.43 | 50.87% | 34.85 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878996 - BURNS & MCDONNELL | WATER | WATER REPAIR & INSTALLATION | 2019-03-13 | 2019-04-01 | 2019-03-13 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | PROFESSIONAL SERVICES | 878102¦¦2020-03-31
FP | C | Yes | 878109 |  | 52645 WELL 5 REPLACEMENT EQUIP | MARTINEZ, MIGUEL E | 100% | 93925 | 0 | 93925 | 95875 | 95875 | 95875 | 0 | 0 | 95875 | 61000 | 0 | 61000 | [7 empty] | 61386.04 |  |  |  | 61386.04 |  |  | 34488.96 | 0 | 100.6% |  | 0 | 61386.04 | 32925 | 35.05% | 0 | 32925 | 35.05% | 0 |  | 34488.96 | 35.97% | 34488.96 | 35.97% | -1950 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878976 - DAVIE, TOWN OF | WATER | WATER EQUIPMENT SALES | 2019-03-14 | 2019-07-30 | 2019-03-14 | 1900-01-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 878109¦¦2020-03-31
FP | C | Yes | 878110 |  | 52647 ALCOA ACID TREATMENT | ELLIS, DYLAN MICHAEL DEWITT | 100% | 22996 | 31099 | 54095 | 54095.5 | 54095.5 | 31099 | 0 | 0 | 54095.5 | 15900 | 21266 | 37166 | [7 empty] | 43310.18 | 16218.01 | 4977.5 |  | 20314.67 | 1800 |  | 10785.32 | 0 | 116.5% |  | 0 | 43310.18 | 7096 | 30.86% | 9833 | 16929 | 31.29% | 0 |  | 10785.32 | 19.94% | 10785.32 | 19.94% | -0.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879002 - ALCOA AGC WARRICK STATION | WATER | WATER REPAIR & INSTALLATION | 2019-03-14 | 2019-05-30 | 2019-03-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 878110¦¦2020-03-31
CR | C | Yes | 878111 |  | 52649 WESTERN SPRINGS IL WELL | SNELTEN, BRIAN M | 100% | 1085180 | 0 | 1085180 | 1045267 | 1045267 | 1045267 | 152098.9 | 0 | 1045267 | 847424 | 0 | 847424 | 31.56 |  |  |  | 31.56 |  |  | 1179606.85 | 374182.7 | 397342.96 |  | 312820.51 | 95260.68 | 0 | 0 | 134339.85 | 139.2% |  | 0 | 1179606.85 | 237756 | 21.91% | 0 | 237756 | 21.91% | 0 |  | -134339.85 | -12.85% | -134339.85 | -12.85% | 39913 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 879003 - WESTERN SPRINGS, VILLAGE OF | WATER | WATER SUPPLY | 2019-03-15 | 2019-08-30 | 2019-03-15 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 878111¦¦2020-03-31
FP | C | Yes | 878113 |  | 52651 WESTLAKE CAVERN PUMPS | ANDERSON, STEPHEN P. | 100% | 46080 | 0 | 46080 | 23510 | 23510 | 0 | 0 | 0 | 23510 | 27648 | 0 | 27648 | [7 empty] | 11400.07 | 6889.93 | 1320 |  | 3190.14 |  |  | 12109.93 | 0 | 41.23% |  | 0 | 11400.07 | 18432 | 40% | 0 | 18432 | 40% | 0 |  | 12109.93 | 51.51% | 12109.93 | 51.51% | 22570 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879005 - DO NOT USE WESTLAKE C A & O CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-03-18 | 2019-03-31 | 2019-03-18 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 878113¦¦2020-03-31
UP | C | Yes | 878119 |  | 52664 MISSION SPRINGS WELL 24 | BRASHEAR, DAVID M | 100% | 12439 | 258996.53 | 271435.53 | 271436.2 | 271436.2 | 253438.78 | 0 | 0 | 271436.2 | 9321 | 222718.51 | 232039.51 | 0 |  |  |  | 0 |  |  | 292959.79 | 113481.16 | 33469.32 |  | 108796.9 | 37212.41 |  | 0 | 21523.59 | 126.3% |  | 0 | 292959.79 | 3118 | 25.07% | 36278.02 | 39396.02 | 14.51% | 0 |  | -21523.59 | -7.93% | -21523.59 | -7.93% | -0.67 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879011 - MISSION SPRINGS WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-03-19 | 2019-04-30 | 2019-03-19 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 878119¦¦2020-03-31
CR | C | Yes | 878123 |  | 52672 EXXON 4 | BALLUFF, WILLIAM O. | 100% | 100000 | 125246 | 225246 | 448492.75 | 448492.75 | 356095.25 | 0 | 0 | 448492.75 | 70000 | 88000 | 158000 | [7 empty] | 269884.2 | 99358.29 | 12179.85 |  | 157727.01 | 619.05 |  | 178608.55 | 0 | 170.8% |  | 0 | 269884.2 | 30000 | 30% | 37246 | 67246 | 29.85% | 0 |  | 178608.55 | 39.82% | 178608.55 | 39.82% | -223246.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 879014 - EXXONMOBIL OIL CORPORATION MKTG & REF US | WATER | WATER REPAIR & INSTALLATION | 2019-03-19 | 2019-05-24 | 2019-03-19 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 878123¦¦2020-03-31
TM | C | Yes | 878134 |  | 52685 DUPONT LA PORTE WELL 6 | CALLAHAN, DANIEL E. | 100% | 20600 | 297465 | 318065 | 299766 | 299766 | 299766 | 0 | 0 | 299766 | 13390 | 259737.87 | 273127.87 | 9752.64 | 3456.42 | 2556.91 |  | 3739.31 |  |  | 288173.82 | 63778.4 | 60015.96 |  | 156919.46 | 7460 |  | 11592.18 | 0 | 105.5% |  | 0 | 288173.82 | 7210 | 35% | 37727.13 | 44937.13 | 14.13% | -5793.8 |  | 11592.18 | 3.867% | 11592.18 | 3.867% | 18299 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 879025 - DUPONT | WATER | WATER REPAIR & INSTALLATION | 2019-03-20 | 2019-05-06 | 2019-03-20 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 878134¦¦2020-03-31
TM | CJ | Yes | 878138 |  | 52690 LEAVENWORTH WELL 1 04 | ELLIS, DYLAN MICHAEL DEWITT | 100% | 8796 | 0 | 8796 | 8590 | 8590 | 8590 | 0 | 0 | 8590 | 6116 | 0 | 6116 | 0 |  |  |  | 0 |  |  | 6923.55 | 1238.78 | 499.1 |  | 5185.67 |  |  | 1666.45 | 0 | 113.2% |  | 0 | 6923.55 | 2680 | 30.47% | 0 | 2680 | 30.47% | 0 |  | 1666.45 | 19.4% | 1666.45 | 19.4% | 206 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879027 - LEAVENWORTH, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-03-21 | 2019-05-30 | 2019-03-21 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878138¦¦2020-03-31
TM | C | Yes | 878141 |  | 52693 FORSYTH 2019 TEST HOLE | WHITE, CATHLEEN R | 100% | 33200 | 0 | 33200 | 33200 | 33200 | 33200 | 0 | 0 | 33200 | 23000 | 0 | 23000 | [7 empty] | 86839.87 | 39038.18 | 22711.84 |  | 25089.85 |  |  | 0 | 53639.87 | 377.6% |  | 0 | 86839.87 | 10200 | 30.72% | 0 | 10200 | 30.72% | 0 |  | -53639.87 | -161.6% | -53639.87 | -161.6% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 879030 - FORSYTH, VILLAGE OF | WATER | WATER SUPPLY | 2019-03-22 | 2019-05-31 | 2019-03-22 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878141¦¦2020-03-31
FP | C | Yes | 878144 |  | 52696 LEAVENWORTH KS ABANDONME | WARTICK, LOGAN M | 100% | 12945 | 0 | 12945 | 12945 | 12945 | 12945 | 0 | 0 | 12945 | 8338 | 0 | 8338 | 0 |  |  |  | 0 |  |  | 4483.78 | 1865.42 | 1188.13 |  | 1430.23 |  |  | 8461.22 | 0 | 53.78% |  | 0 | 4483.78 | 4607 | 35.59% | 0 | 4607 | 35.59% | 0 |  | 8461.22 | 65.36% | 8461.22 | 65.36% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 879033 - LEAVENWORTH WATERWORKS | WATER | WATER SUPPLY | 2019-03-22 | 2019-06-28 | 2019-03-22 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 878144¦¦2020-03-31
TM | C | Yes | 878151 |  | 52705 STERLING HILLS FARMLAND | GRACE, GARY L. | 100% | 30261 | 7734 | 37995 | 8721.29 | 8721.29 | 8721.29 | 0 | 0 | 8721.29 | 23605 | 5998 | 29603 | [7 empty] | 12811.52 | 6256.23 | 1080.81 |  | 4721.98 | 752.5 |  | 0 | 4090.23 | 43.28% |  | 0 | 12811.52 | 6656 | 22% | 1736 | 8392 | 22.09% | 0 |  | -4090.23 | -46.9% | -4090.23 | -46.9% | 29273.71 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878945 - STERLING HILLS GOLF CLUB | WATER | WATER REPAIR & INSTALLATION | 2019-03-31 | 2019-05-25 | 2019-03-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878151¦¦2020-03-31
FP | C | Yes | 878152 |  | 52706 REHOBOTH DE GAC CHANGEO | RANFT, DONALD R | 100% | 128779 | 0 | 128779 | 128779 | 128779 | 128779 | 0 | 0 | 128779 | 83703.95 | 0 | 83703.95 | [7 empty] | 87915.67 | 13632.83 | 1480.69 |  | 71923.65 | 878.5 |  | 40863.33 | 0 | 105% |  | 0 | 87915.67 | 45075.05 | 35% | 0 | 45075.05 | 35% | 0 |  | 40863.33 | 31.73% | 40863.33 | 31.73% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 879038 - REHOBOTH BEACH, CITY OF | WATER | WATER TREATMENT | 2019-03-25 | 2019-04-30 | 2019-03-22 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878152¦¦2020-03-31
FP | CJ | Yes | 878153 |  | 52707 HEMPSTEAD NY AST | CHESLEY, ANDREW J | 100% | 345000 | 0 | 345000 | 345000 | 345000 | 327750 | 57000 | 0 | 345000 | 253203.7 | 0 | 253203.7 | 2344.3 | 40.93 |  |  | 2303.37 |  |  | 376220.24 | 72350.09 | 10257.79 |  | 281388.73 | 12223.63 |  | 0 | 31220.24 | 148.6% |  | 0 | 376220.24 | 91796.3 | 26.61% | 0 | 91796.3 | 26.61% | 0 |  | -31220.24 | -9.049% | -31220.24 | -9.049% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 879039 - HEMPSTEAD, VILLAGE OF | WATER | WATER TREATMENT | 2019-04-03 | 2019-07-31 | 2019-03-25 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878153¦¦2020-03-31
FP | C | Yes | 878155 |  | 52716 SWIFT SCADA | MIGUEL, SEAN J. | 100% | 70498 | 0 | 70498 | 70498 | 70498 | 70498 | 0 | 0 | 70498 | 54500 | 0 | 54500 | [7 empty] | 61057.55 | 482.39 | 173.75 |  | 659.41 | 59742 |  | 9440.45 | 0 | 112% |  | 0 | 61057.55 | 15998 | 22.69% | 0 | 15998 | 22.69% | 0 |  | 9440.45 | 13.39% | 9440.45 | 13.39% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879041 - S & C RESALE SWIFT & COMPANY | WATER | WATER EQUIPMENT SALES | 2019-03-24 | 2019-06-13 | 2019-03-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878155¦¦2020-03-31
TM | C | Yes | 878158 |  | 52721 JG BOSWELL S 191 | BRASHEAR, DAVID M | 100% | 13375 | 0 | 13375 | 29550 | 29550 | 29550 | 0 | 0 | 29550 | 10202 | 0 | 10202 | 744.81 | 359.12 | 93.28 |  | 292.41 |  |  | 20274.33 | 11208.69 | 1013.28 |  | 8052.36 |  |  | 9275.67 | 0 | 198.7% |  | 0 | 20274.33 | 3173 | 23.72% | 0 | 3173 | 23.72% | 0 |  | 9275.67 | 31.39% | 9275.67 | 31.39% | -16175 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878568 - J G BOSWELL | WATER | WATER REPAIR & INSTALLATION | 2019-03-25 | 2019-07-31 | 2019-03-25 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878158¦¦2020-03-31
FP | CJ | Yes | 878159 |  | 52728 CULLIGAN OK LAYNERT SYS | MCCARTNEY, JEFFREY C | 100% | 268000 | 61800 | 329800 | 296820 | 296820 | 296820 | 296820 | 0 | 296820 | 185807.34 | 68553 | 254360.34 | 948.77 | 940.14 |  |  | 8.63 |  |  | 251821.45 | 20854.47 |  |  | 140753.78 | 90213.2 |  | 44998.55 | 0 | 99% |  | 0 | 251821.45 | 82192.66 | 30.67% | -6753 | 75439.66 | 22.87% | 0 |  | 44998.55 | 15.16% | 44998.55 | 15.16% | 32980 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 879043 - CULLIGAN WATER CONDITIONING CHICKASHA | WATER | WATER TREATMENT | 2019-03-25 | 2019-06-30 | 2019-03-25 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 878159¦¦2020-03-31
FP | C | Yes | 878160 |  | 52729 MOSAIC LITHIA WEST PUMP | TORMOEHLEN, DAVID A. | 100% | 1187 | 0 | 1187 | 1187 | 1187 | 0 | 0 | 0 | 1187 | 710 | 0 | 710 | [7 empty] | 682.45 |  |  |  | 682.45 |  |  | 504.55 | 0 | 96.12% |  | 0 | 682.45 | 477 | 40.19% | 0 | 477 | 40.19% | 0 |  | 504.55 | 42.51% | 504.55 | 42.51% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 879044 - MOSAIC RIVERVIEW | WATER | WATER EQUIPMENT SALES | 2019-02-13 | 2019-03-13 | 2019-02-13 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878160¦¦2020-03-31
TM | C | Yes | 878161 |  | 52734 COLLIER COUNTY NRWTP IW | BRUGGER, CRAIG J. | 100% | 36500 | 0 | 36500 | 36500 | 36500 | 0 | 0 | 0 | 36500 | 23103 | 0 | 23103 | [7 empty] | 12442.31 | 8861.21 | 1958 |  | 1153.14 | 469.96 |  | 24057.69 | 0 | 53.86% |  | 0 | 12442.31 | 13397 | 36.7% | 0 | 13397 | 36.7% | 0 |  | 24057.69 | 65.91% | 24057.69 | 65.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 879045 - COLLIER COUNTY PUBLIC UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-03-25 | 2019-05-30 | 2019-03-25 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878161¦¦2020-03-31
TM | C | Yes | 878165 |  | 52742 KIMBERLY CLARK WELL 1 | MIGUEL, SEAN J. | 100% | 16750 | 9200 | 25950 | 25950 | 25950 | 25950 | 0 | 0 | 25950 | 11750 | 6624 | 18374 | [7 empty] | 19098.65 | 7155.76 | 2409.25 |  | 8533.64 | 1000 |  | 6851.35 | 0 | 103.9% |  | 0 | 19098.65 | 5000 | 29.85% | 2576 | 7576 | 29.19% | 0 |  | 6851.35 | 26.4% | 6851.35 | 26.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879048 - KIMBERLY CLARK CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-03-24 | 2019-07-30 | 2019-03-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878165¦¦2020-03-31
TM | C | Yes | 878167 |  | 52744 GALESBURG CW REHAB | HARTMAN, MICHAEL | 100% | 296600 | 78760 | 375360 | 371560 | 371560 | 371560 | 0 | 0 | 371560 | 210000 | 55763 | 265763 | 0.51 | 0.51 | [5 empty] | 309486.61 | 167079.15 | 20290 |  | 95424.3 | 26693.16 |  | 62073.39 | 0 | 116.5% |  | 0 | 309486.61 | 86600 | 29.2% | 22997 | 109597 | 29.2% | 0 |  | 62073.39 | 16.71% | 62073.39 | 16.71% | 3800 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 879050 - GALESBURG, CITY OF | WATER | WATER SUPPLY | 2019-03-24 | 2019-06-27 | 2019-03-24 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 878167¦¦2020-03-31
FP | C | Yes | 878168 |  | 52745 FLAGLER COUNTYLINE DIW 1 | MARTINEZ, MIGUEL E | 100% | 5000 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 5000 | 2747 | -1478 | 1269 | [7 empty] | 1268.62 | 629.66 | 220 |  | 418.96 |  |  | 3731.38 | 0 | 99.97% |  | 0 | 1268.62 | 2253 | 45.06% | 1478 | 3731 | 74.62% | 0 |  | 3731.38 | 74.63% | 3731.38 | 74.63% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 879051 - DO NOT USE COUNTYLINE 2 LLC | WATER | WATER REPAIR & INSTALLATION | 2019-03-28 | 2019-03-28 | 2019-03-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878168¦¦2020-03-31
TM | C | Yes | 878169 |  | 52748 VICTORVILLE WELL 126 | BRASHEAR, DAVID M | 100% | 11862 | 149886.03 | 161748.03 | 161747.32 | 161747.32 | 159290.41 | 0 | 0 | 161747.32 | 8862 | 109810.47 | 118672.47 | [7 empty] | 148642.37 | 47035.16 | 9487.31 |  | 92054.3 | 65.6 |  | 13104.95 | 0 | 125.3% |  | 0 | 148642.37 | 3000 | 25.29% | 40075.56 | 43075.56 | 26.63% | 0 |  | 13104.95 | 8.102% | 13104.95 | 8.102% | 0.71 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878903 - VICTORVILLE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-03-28 | 2019-05-31 | 2019-03-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878169¦¦2020-03-31
TM | C | Yes | 878177 |  | 52758 OXBOW 3 STUFFING BOX | GNAU, CASEY T | 100% | 18770 | 0 | 18770 | 17270 | 17270 | 17270 | 0 | 0 | 17270 | 11664 | 0 | 11664 | 2428.22 |  |  |  | 2428.22 |  |  | 10647.09 | 3960.06 |  |  | 6687.03 |  |  | 6622.91 | 0 | 91.28% |  | 0 | 10647.09 | 7106 | 37.86% | 0 | 7106 | 37.86% | 0 |  | 6622.91 | 38.35% | 6622.91 | 38.35% | 1500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879058 - OXBOW CALCINING LLC | WATER | WATER REPAIR & INSTALLATION | 2019-03-29 | 2019-04-30 | 2019-03-29 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878177¦¦2020-03-31
TM | C | Yes | 878186 |  | 52770 WESTROCK WELL 1 | ALBARADO, JORDAN A | 100% | 34200 | 0 | 34200 | 34200 | 34200 | 34200 | 0 | 0 | 34200 | 17101 | 0 | 17101 | [7 empty] | 15642.66 | 5520.19 | 1069 |  | 6955.51 | 2097.96 |  | 18557.34 | 0 | 91.47% |  | 0 | 15642.66 | 17099 | 50% | 0 | 17099 | 50% | 0 |  | 18557.34 | 54.26% | 18557.34 | 54.26% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2019-03-29 | 2019-04-26 | 2019-03-29 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878186¦¦2020-03-31
TM | C | Yes | 878189 |  | 52773 WC PLAQ REHAB WELL 9 | GNAU, CASEY T | 100% | 109000 | 8680 | 117680 | 117680 | 117680 | 117680 | 0 | 0 | 117680 | 51352 | 4340 | 55692 | [7 empty] | 41200.82 | 25510.47 | 7064.64 |  | 8625.71 |  |  | 76479.18 | 0 | 73.98% |  | 0 | 41200.82 | 57648 | 52.89% | 4340 | 61988 | 52.68% | 0 |  | 76479.18 | 64.99% | 76479.18 | 64.99% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878850 - AXIALL PLAQ GEORGIA GULF | WATER | WATER REPAIR & INSTALLATION | 2019-04-01 | 2019-05-03 | 2019-04-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878189¦¦2020-03-31
TM | C | Yes | 878197 |  | 52796 CHILLICOTHE PIXELLE 2019 | BELL, JAMES J. | 100% | 10900 | 0 | 10900 | 10900 | 10900 | 10900 | 2725 | 0 | 10900 | 7000 | 0 | 7000 | 0.03 | 0.03 |  |  | 0 |  |  | 6979.56 | 6124.13 | 75.79 |  | 779.64 |  |  | 3920.44 | 0 | 99.71% |  | 0 | 6979.56 | 3900 | 35.78% | 0 | 3900 | 35.78% | 0 |  | 3920.44 | 35.97% | 3920.44 | 35.97% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878886 - PIXELLE SPECIALTY SOLUTIONS | WATER | WATER SUPPLY | 2019-04-03 | 2020-01-30 | 2019-04-03 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878197¦¦2020-03-31
TM | C | Yes | 878201 |  | 52802 WOODWARD OK 2019 WELL W | WARTICK, LOGAN M | 100% | 3850 | 137544.5 | 141394.5 | 174410.41 | 174410.41 | 174410.41 | 0 | 0 | 174410.41 | 3080 | 132548.91 | 135628.91 | 16258.43 | 8499.78 | 2570.45 |  | 6799.42 | -1611.22 |  | 137484.3 | 38294.47 | 13797.56 |  | 60878.19 | 24514.08 |  | 36926.11 | 0 | 101.4% |  | 0 | 137484.3 | 770 | 20% | 4995.59 | 5765.59 | 4.078% | -11401.54 |  | 36926.11 | 21.17% | 36926.11 | 21.17% | -33015.91 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 879076 - WOODWARD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-02 | 2019-08-01 | 2019-04-02 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 878201¦¦2020-03-31
TM | C | Yes | 878211 |  | 52814 NORTH CHESHIRE CT WELL | CROOK, CHARLES M | 100% | 40825 | 32725 | 73550 | 73550 | 73550 | 73550 | 0 | 0 | 73550 | 28581 | 23589.17 | 52170.17 | [7 empty] | 50125.67 | 19843.9 | 4226.93 |  | 26054.84 |  |  | 23424.33 | 0 | 96.08% |  | 0 | 50125.67 | 12244 | 29.99% | 9135.83 | 21379.83 | 29.07% | 0 |  | 23424.33 | 31.85% | 23424.33 | 31.85% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 879082 - SOUTH CENTRAL CT REGIONAL WATER AUTH | WATER | WATER REPAIR & INSTALLATION | 2019-04-03 | 2019-06-03 | 2019-04-03 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878211¦¦2020-03-31
FP | C | Yes | 878213 |  | 52816 DARDANELLE AR CLARIFIER | BURGE, EVERETT E. | 100% | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 0 | 24500 | -1530 |  |  |  | -1530 |  |  | 2229.61 | 1219.05 | 86.28 |  | 924.28 |  |  | 0 | 2229.61 | 9.1% |  | 0 | 2229.61 | 10500 | 30% | 0 | 10500 | 30% | 0 |  | -2229.61 |  | -2229.61 |  | 35000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879083 - DARDANELLE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-03 | 2019-08-16 | 2019-04-03 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878213¦¦2020-03-31
TM | C | Yes | 878215 |  | 52818 LAYNE MOTOR STOCK | BENNETT, MARK C. | 100% | 24000 | 0 | 24000 | 11079.9 | 11079.9 | 8044.92 | 0 | 0 | 11079.9 | 20000 | 0 | 20000 | 7630.32 | 4162.48 |  |  | 3467.84 |  |  | 74991.87 | 34418.62 | 758.36 |  | 39814.89 |  |  | 0 | 63911.97 | 375% |  | 0 | 74991.87 | 4000 | 16.67% | 0 | 4000 | 16.67% | 0 |  | -63911.97 | -576.8% | -63911.97 | -576.8% | 12920.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879085 - DO NOT USE LAYNE CHRISTENSEN STUTTGART | WATER | WATER EQUIPMENT SALES | 2019-04-03 | 2020-04-03 | 2019-04-03 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878215¦¦2020-03-31
FP | C | Yes | 878218 |  | 52821 BORMANN FARMS | BENNETT, MARK C. | 100% | 18000 | 0 | 18000 | 60076.17 | 60076.17 | 62725.65 | 0 | 0 | 60076.17 | 10000 | 0 | 10000 | [7 empty] | 85508.37 | 22803.74 | 13584.94 |  | 47654.69 | 1465 |  | 0 | 25432.2 | 855.1% |  | 0 | 85508.37 | 8000 | 44.44% | 0 | 8000 | 44.44% | 0 |  | -25432.2 | -42.33% | -25432.2 | -42.33% | -42076.17 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879087 - BORMANN FARMS | WATER | WATER REPAIR & INSTALLATION | 2019-04-04 | 2020-04-04 | 2019-04-04 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878218¦¦2020-03-31
TM | C | Yes | 878223 |  | 52827 WC LC REHAB WELL 34 | GNAU, CASEY T | 100% | 131000 | 8950 | 139950 | 139950 | 139950 | 139950 | 0 | 0 | 139950 | 65034 | 3840 | 68874 | 0 |  |  |  | 0 |  |  | 67701.69 | 30190.45 | 5152.88 |  | 16561.65 | 15796.71 |  | 72248.31 | 0 | 98.3% |  | 0 | 67701.69 | 65966 | 50.36% | 5110 | 71076 | 50.79% | 0 |  | 72248.31 | 51.62% | 72248.31 | 51.62% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878710 - AXIALL CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-04-04 | 2019-05-10 | 2019-04-04 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878223¦¦2020-03-31
TM | C | Yes | 878231 |  | 52844 P 8 & P 9 SPARE PUMP EQU | VAN ALLEN, WESLEY C. | 100% | 359519 | 0 | 359519 | 351408.2 | 351408.2 | 351408.2 | 0 | 0 | 351408.2 | 237341 | 0 | 237341 | [7 empty] | 228140.59 | 1004.16 |  |  | 221136.43 | 6000 |  | 123267.61 | 0 | 96.12% |  | 0 | 228140.59 | 122178 | 33.98% | 0 | 122178 | 33.98% | 0 |  | 123267.61 | 35.08% | 123267.61 | 35.08% | 8110.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 879023 - FMI SAFFORD | WATER | WATER REPAIR & INSTALLATION | 2019-04-02 | 2019-12-31 | 2019-04-02 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878231¦¦2020-03-31
TM | C | Yes | 878233 |  | 52846 GRAYSON CO QTRLY TEST | MIESNER, EMILY E. | 100% | 510 | 0 | 510 | 510 | 510 | 0 | 0 | 0 | 510 | 350 | 0 | 350 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 509.99 | 0 | 0.002857% |  | 0 | 0.01 | 160 | 31.37% | 0 | 160 | 31.37% | 0 |  | 509.99 | 100% | 509.99 | 100% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879099 - GRAYSON, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-04 | 2019-04-29 | 2019-04-04 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878233¦¦2020-03-31
TM | C | Yes | 878238 |  | 52853 CORONA RECLAIM BOOSTER | GRACE, GARY L. | 100% | 6993 | 23207.5 | 30200.5 | 30200.5 | 30200.5 | 24029.74 | 0 | 0 | 30200.5 | 3904 | 15219.79 | 19123.79 | [7 empty] | 29854.1 | 12530.22 | 1726.25 |  | 15597.63 |  |  | 346.4 | 0 | 156.1% |  | 0 | 29854.1 | 3089 | 44.17% | 7987.71 | 11076.71 | 36.68% | 0 |  | 346.4 | 1.147% | 346.4 | 1.147% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878883 - CORONA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-08 | 2019-06-18 | 2019-04-08 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878238¦¦2020-03-31
TM | CJ | Yes | 878240 |  | 52857 DUKE ENERGY WELL 3 | ELLIS, DYLAN MICHAEL DEWITT | 100% | 1667 | 46506 | 48173 | 30200.74 | 30200.74 | 14768 | 0 | 0 | 30200.74 | 1150 | 35125 | 36275 | 9501.75 | 2122.86 | 702.46 |  | 6676.43 |  |  | 24399.01 | 8021.24 | 2603.44 |  | 13774.33 |  |  | 5801.73 | 0 | 67.26% |  | 0 | 24399.01 | 517 | 31.01% | 11381 | 11898 | 24.7% | 6853 | 6853 | 5801.73 | 19.21% | 5801.73 | 19.21% | 17972.26 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879103 - DUKE ENERGY CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-04-07 | 2019-05-30 | 2019-04-07 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878240¦¦2020-03-31
TM | C | Yes | 878242 |  | 52860 CW4 DISINFECTION | VAN ALLEN, WESLEY C. | 100% | 10644 | 26595.44 | 37239.44 | 35609.34 | 35609.34 | 36354.18 | 0 | 0 | 35609.34 | 7648 | 19201.25 | 26849.25 | [7 empty] | 23698.89 | 6628.21 | 2683.59 |  | 12587.09 | 1800 |  | 11910.45 | 0 | 88.27% |  | 0 | 23698.89 | 2996 | 28.15% | 7394.19 | 10390.19 | 27.9% | 0 |  | 11910.45 | 33.45% | 11910.45 | 33.45% | 1630.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 879105 - INFRAMARK | WATER | WATER REPAIR & INSTALLATION | 2019-04-08 | 2019-06-01 | 2019-04-08 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878242¦¦2020-03-31
TM | C | Yes | 878246 |  | 52865 RIVERDALE WELL 1 PULL | GANSEBOM, JASON W. | 100% | 2100 | 0 | 2100 | 15070 | 15070 | 15472.99 | 0 | 0 | 15070 | 1648 | 0 | 1648 | 83.95 |  |  |  | 83.95 |  |  | 31689.67 | 12034.6 | 4930.39 |  | 14724.68 |  |  | 0 | 16619.67 | 1923% |  | 0 | 31689.67 | 452 | 21.52% | 0 | 452 | 21.52% | 0 |  | -16619.67 | -110.3% | -16619.67 | -110.3% | -12970 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 879109 - RIVERDALE, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-09 | 2019-05-31 | 2019-04-09 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 878246¦¦2020-03-31
FP | C | Yes | 878249 |  | 52869 ERIC SCHERM | BENNETT, MARK C. | 100% | 7500 | 0 | 7500 | 10927.9 | 10927.9 | 11169.18 | 0 | 0 | 10927.9 | 6000 | 0 | 6000 | [7 empty] | 7265.57 | 1353.3 | 450 |  | 5047.27 | 415 |  | 3662.33 | 0 | 121.1% |  | 0 | 7265.57 | 1500 | 20% | 0 | 1500 | 20% | 0 |  | 3662.33 | 33.51% | 3662.33 | 33.51% | -3427.9 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879111 - SCHERM, ERIC | WATER | WATER REPAIR & INSTALLATION | 2019-04-09 | 2020-04-09 | 2019-04-09 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878249¦¦2020-03-31
FP | C | Yes | 878253 |  | 52875 BAYER FARMS & WILDLIFE C | BENNETT, MARK C. | 100% | 15000 | 0 | 15000 | 15386.32 | 15386.32 | 16540.33 | 0 | 0 | 15386.32 | 11500 | 0 | 11500 | [7 empty] | 36754.87 | 10464.42 | 8317.61 |  | 17972.84 |  |  | 0 | 21368.55 | 319.6% |  | 0 | 36754.87 | 3500 | 23.33% | 0 | 3500 | 23.33% | 0 |  | -21368.55 | -138.9% | -21368.55 | -138.9% | -386.32 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879114 - MONSANTO WILDLIFE & FARM MANAGEMENT CENT | WATER | WATER REPAIR & INSTALLATION | 2019-04-10 | 2020-04-10 | 2019-04-10 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878253¦¦2020-03-31
TM | C | Yes | 878254 |  | 52876 DELAWARE 2019 MONITORING | BELL, JAMES J. | 100% | 10142 | 0 | 10142 | 10012.4 | 10012.4 | 10012.4 | 0 | 0 | 10012.4 | 6600 | 0 | 6600 | 0.01 | 0.01 |  |  | 0 |  |  | 2464.18 | 2420.53 |  |  | 43.65 |  |  | 7548.22 | 0 | 37.34% |  | 0 | 2464.18 | 3542 | 34.92% | 0 | 3542 | 34.92% | 0 |  | 7548.22 | 75.39% | 7548.22 | 75.39% | 129.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 879115 - DELAWARE, CITY OF | WATER | WATER SUPPLY | 2019-04-10 | 2020-01-30 | 2019-04-10 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 878254¦¦2020-03-31
UP | C | Yes | 906032 |  | 49242 HDWD 4 VTP BOOSTER S | BRASHEAR, DAVID M | 100% | 238484 | 0 | 238484 | 234485 | 234485 | 0 | 0 | 0 | 234485 | 178583 | 501 | 179084 | [7 empty] | 185650.76 | 9385.37 | 228.26 |  | 171966.73 | 4070.4 |  | 48834.24 | 0 | 103.7% |  | 0 | 185650.76 | 59901 | 25.12% | -501 | 59400 | 24.91% | 0 |  | 48834.24 | 20.83% | 48834.24 | 20.83% | 3999 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878494 - HI DESERT WATER DISTRICT | WATER | WATER EQUIPMENT SALES | 2018-03-26 | 2019-08-20 | 2018-03-26 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 906032¦¦2020-03-31
TM | C | Yes | 906033 |  | 49318 GRAND LAKE PWA PUMP INST | EVANS, TRAVIS L | 100% | 123528 | 0 | 123528 | 139728 | 139728 | 50480.25 | 0 | 0 | 139728 | 93228 | 0 | 93228 | [7 empty] | 91420.96 | 12050.12 | 6022.95 |  | 22934.89 | 50413 |  | 48307.04 | 0 | 98.06% |  | 0 | 91420.96 | 30300 | 24.53% | 0 | 30300 | 24.53% | 0 |  | 48307.04 | 34.57% | 48307.04 | 34.57% | -16200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 891480 - GRAND LAKE PWA | WATER | WATER EQUIPMENT SALES | 2018-04-09 | 2019-05-04 | 2018-04-09 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 906033¦¦2020-03-31
TM | C | Yes | 906034 |  | 49335 VAN WERT CITY OF | SIMPSON, CARL L. | 100% | 1500 | 31733 | 33233 | 33233 | 33233 | 21758 | 0 | 0 | 33233 | 1050 | 42820 | 43870 | 0.6 | 0.6 | [5 empty] | 42738.89 | 14482.26 | 2964.16 |  | 25292.47 |  |  | 0 | 9505.89 | 97.42% |  | 0 | 42738.89 | 450 | 30% | -11087 | -10637 | -32.01% | 0 |  | -9505.89 | -28.6% | -9505.89 | -28.6% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 899576 - VAN WERT, OH, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2018-04-02 | 2019-04-30 | 2018-04-02 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906034¦¦2020-03-31
TM | C | Yes | 906039 |  | 50062 EVONIK HAYSVILLE KS PU | WARTICK, LOGAN M | 100% | 18122.72 | 22585.01 | 40707.73 | 25132.87 | 25132.87 | 0 | 0 | 0 | 25132.87 | 10873.63 | 13550.6 | 24424.23 | [7 empty] | 17436.51 | 6397.63 | 340 |  | 10698.88 |  |  | 7696.36 | 0 | 71.39% |  | 0 | 17436.51 | 7249.09 | 40% | 9034.41 | 16283.5 | 40% | 0 |  | 7696.36 | 30.62% | 7696.36 | 30.62% | 15574.86 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 890481 - EVONIK CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2018-06-04 | 2019-05-31 | 2018-06-04 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906039¦¦2020-03-31
UP | C | Yes | 906040 |  | 50100 GRIC PMIP BW 1 BW 2 | TRAMMELL, DUANE R. | 100% | 2393055 | 66585.93 | 2459640.93 | 2465908.51 | 2465908.51 | 896118.85 | 0 | 0 | 2465908.51 | 1922531 | 184154.93 | 2106685.93 | [7 empty] | 2142845.22 | 244921.27 | 174203.66 |  | 872801.91 | 850918.38 |  | 323063.29 | 0 | 101.7% |  | 0 | 2142845.22 | 470524 | 19.66% | -117569 | 352955 | 14.35% | 0 |  | 323063.29 | 13.1% | 323063.29 | 13.1% | -6267.58 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 891252 - GILA RIVER INDIAN COMMUNITY | WATER | WATER SUPPLY | 2018-06-25 | 2019-07-31 | 2018-06-25 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 906040¦¦2020-03-31
TM | LJ | Yes | 906042 |  | 50168 MLGW 2018 WELLS | ANDERSON, STEPHEN P. | 86.47% | 3940405 | 85188 | 4025593 | 3518719.9123 | 3383037 | 876135 | 0 | 22568.45 | 4069133 | 2898283 | 155808.67 | 3054091.67 | 241829.86 | 62913.22 | 89748.35 |  | 89168.29 |  |  | 2920537.19 | 925303.99 | 445629.52 |  | 1531904.16 | 17699.52 |  | 462499.81 | 0 | 95.63% |  | 456842.81 | 3377380 | 1042122 | 26.45% | -70620.67 | 971501.33 | 24.13% | 260239.33 |  | 598182.72 | 17% | 691753 | 17% | 506873.09 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879104 - MEMPHIS, CITY OF | WATER | WATER SUPPLY | 2018-06-26 | 2019-02-28 | 2018-06-26 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906042¦¦2020-03-31
TM | CJ | Yes | 906044 |  | 50291 GRANITEVALLEYWELLSTEMPWE | MAI, JONATHAN | 100% | 47063 | 639808.18 | 686871.18 | 826633.29 | 826633.29 | 470318.3 | 149313.12 | 0 | 826633.29 | 31657 | 515044.94 | 546701.94 | 979.65 | -16.6 |  |  | 996.25 |  |  | 582117.33 | 220287.1 | 58872.6 |  | 277515.36 | 25442.27 |  | 244515.96 | 0 | 106.5% |  | 0 | 582117.33 | 15406 | 32.73% | 124763.24 | 140169.24 | 20.41% | 0 |  | 244515.96 | 29.58% | 244515.96 | 29.58% | -139762.11 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 891515 - GRANITE CONSTRUCTION INDIO BRANCH | WATER | WATER REPAIR & INSTALLATION | 2018-06-27 | 2019-07-31 | 2018-06-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906044¦¦2020-03-31
FP | CJ | Yes | 906047 |  | 50550 EAST FISHKILL NY CANON | CROOK, CHARLES M | 100% | 79015 | 2885 | 81900 | 81900 | 81900 | 41900 | 40150 | 0 | 81900 | 55304 | -3304 | 52000 | 522.84 | 515.89 |  |  | 6.95 |  |  | 69737.73 | 26561.95 | 3459.47 |  | 39716.31 |  |  | 12162.27 | 0 | 134.1% |  | 0 | 69737.73 | 23711 | 30.01% | 6189 | 29900 | 36.51% | 0 |  | 12162.27 | 14.85% | 12162.27 | 14.85% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 891558 - GREEN ACRES EXCAVATING & CONTRACTING COR | WATER | WATER REPAIR & INSTALLATION | 2018-07-23 | 2019-08-31 | 2018-07-23 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906047¦¦2020-03-31
UP | C | Yes | 906048 |  | 50581 LEHIGH ACRES WWTP | BRUGGER, CRAIG J. | 100% | 79904 | 667 | 80571 | 80571 | 80571 | 0 | 0 | 0 | 80571 | 43947 | 0 | 43947 | [7 empty] | 41675.76 | 5811.16 | 958 |  | 33158.12 | 1748.48 |  | 38895.24 | 0 | 94.83% |  | 0 | 41675.76 | 35957 | 45% | 667 | 36624 | 45.46% | 0 |  | 38895.24 | 48.27% | 38895.24 | 48.27% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 899491 - US WATER SERVICES CORP | WATER | WATER EQUIPMENT SALES | 2018-07-24 | 2019-09-29 | 2018-07-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906048¦¦2020-03-31
UP | LJ | Yes | 906049 | 906049 | 50594 CAVE CREEK LANDFILL IW | DECKER, JASEN | 99.98% | 1336659 | 0 | 1336659 | 2737941.2989 | 2410787.35 | 2410787.35 | 176676.2 | 0 | 2738387.35 | 1081710 | 15994 | 1097704 | 44580.42 | 274.92 | 823.55 |  | -401.34 | 45980.5 | -2097.21 | 2788697.53 | 438403.72 | 876574.91 |  | 1284375.84 | 189334.64 | 8.42 | 0 | 377910.18 | 254% | 198171.52 | 454.32 | 2789151.85 | 254949 | 19.07% | -15994 | 238955 | 17.88% | 0 |  | -50764.5 | -1.854% | -50764.5 | -1.854% | -1401274.03 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 900469 - WOOD ENVIRONMENTAL AND INFRASTRUCTURE SO | WATER | WATER SUPPLY | 2018-07-27 | 2019-11-30 | 2018-07-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906049¦¦2020-03-31
UP | C | Yes | 906050 | 906049 | 50600 CAVE CREEK LANDFILL IW | VAN ALLEN, WESLEY C. | 100% | 59213 | 0 | 59213 | 0 | 0 | 0 | 0 | 0 | 0 | 46219 | 1787 | 48006 | -412.7 | 136.3 | -549 |  | 0 |  |  | -3116.71 | 1092.07 | 388.29 |  | -6259.68 | 1662.61 |  | 3116.71 | 0 | -6.492% |  | 0 | -3116.71 | 12994 | 21.94% | -1787 | 11207 | 18.93% | 0 |  | 3116.71 |  | 3116.71 |  | 59213 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 900469 - WOOD ENVIRONMENTAL AND INFRASTRUCTURE SO | WATER | WATER SUPPLY | 2017-07-27 | 2019-12-31 | 2018-07-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906050¦¦2020-03-31
TM | C | Yes | 906052 |  | 50721 GALLANT EP NEW WELL | CALLAHAN, DANIEL E. | 100% | 83978 | 4200 | 88178 | 84178 | 84178 | 15275.1 | 0 | 0 | 84178 | 58785 | 3150 | 61935 | [7 empty] | 56305 |  |  |  |  | 56305 |  | 27873 | 0 | 90.91% |  | 0 | 56305 | 25193 | 30% | 1050 | 26243 | 29.76% | 0 |  | 27873 | 33.11% | 27873 | 33.11% | 4000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 891012 - GALLANT BUILDERS LLC | WATER | WATER SUPPLY | 2018-08-01 | 2019-07-31 | 2018-08-01 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906052¦¦2020-03-31
UP | C | Yes | 906054 |  | 50860 GRIC PMIP 8 1 8 2 8 3 | DECKER, JASEN | 100% | 1887494 | -246818 | 1640676 | 1713644.35 | 1713644.35 | 970218.7 | 0 | 0 | 1713644.35 | 1500841 | -140518 | 1360323 | 0 |  |  |  | 0 |  |  | 1350451.85 | 156775.95 | 105965.17 |  | 404308.66 | 683402.07 |  | 363192.5 | 0 | 99.27% |  | 0 | 1350451.85 | 386653 | 20.48% | -106300 | 280353 | 17.09% | 0 |  | 363192.5 | 21.19% | 363192.5 | 21.19% | -72968.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 891252 - GILA RIVER INDIAN COMMUNITY | WATER | WATER SUPPLY | 2018-08-27 | 2019-04-30 | 2018-08-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906054¦¦2020-03-31
UP | C | Yes | 906055 | 877708 | 51089 SRP WELL 31 3E 7 0N | VAN ALLEN, WESLEY C. | 100% | 35193 | 11507 | 46700 | 46700 | 46700 | 0 | 0 | 0 | 46700 | 26816 | 6184 | 33000 | [7 empty] | 34167.93 | 17769.68 | 3631 |  | 12767.25 |  |  | 12532.07 | 0 | 103.5% |  | 0 | 34167.93 | 8377 | 23.8% | 5323 | 13700 | 29.34% | 0 |  | 12532.07 | 26.84% | 12532.07 | 26.84% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878691 - SALT RIVER PROJECT | WATER | WATER SUPPLY | 2018-09-21 | 2019-09-30 | 2018-09-21 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | MATOC/MACC/GWAC | 906055¦¦2020-03-31
FP | C | Yes | 906059 |  | 51306 ROXBURY NY PRODUCTION WE | CROOK, CHARLES M | 100% | 71750 | 37215.5 | 108965.5 | 108965.5 | 108965.5 | 23066.99 | 0 | 0 | 108965.5 | 51000 | 44600 | 95600 | [7 empty] | 101107.47 | 64176.25 | 17096.59 |  | 19834.63 |  |  | 7858.03 | 0 | 105.8% |  | 0 | 101107.47 | 20750 | 28.92% | -7384.5 | 13365.5 | 12.27% | 0 |  | 7858.03 | 7.211% | 7858.03 | 7.211% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 897275 - ROXBURY, NY, TOWN OF | WATER | WATER SUPPLY | 2018-10-02 | 2019-10-31 | 2018-10-02 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 906059¦¦2020-03-31
FP | C | Yes | 906060 |  | 51421 ROTTERDAM NY WELL 3 PU | CROOK, CHARLES M | 100% | 11000 | 11700 | 22700 | 19950 | 19950 | 8500 | 0 | 0 | 19950 | 7700 | 8300 | 16000 | [7 empty] | 15720.2 | 9331.01 | 3299.32 |  | 3089.87 |  |  | 4229.8 | 0 | 98.25% |  | 0 | 15720.2 | 3300 | 30% | 3400 | 6700 | 29.52% | 0 |  | 4229.8 | 21.2% | 4229.8 | 21.2% | 2750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 897260 - ROTTERDAM, NY, TOWN OF | WATER | WATER EQUIPMENT SALES | 2018-10-11 | 2019-10-28 | 2018-10-11 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 906060¦¦2020-03-31
TM | C | Yes | 906061 |  | 51514 SUEZ 97 RVWF CASING EXTE | CROOK, CHARLES M | 100% | 29300 | 0 | 29300 | 29300 | 29300 | 13690 | 0 | 0 | 29300 | 20550 | 0 | 20550 | [7 empty] | 31990.67 | 16759.66 | 4841.99 |  | 10389.02 |  |  | 0 | 2690.67 | 155.7% |  | 0 | 31990.67 | 8750 | 29.86% | 0 | 8750 | 29.86% | 0 |  | -2690.67 | -9.183% | -2690.67 | -9.183% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 892817 - J FLETCHER CREAMER & SON, INC | WATER | WATER REPAIR & INSTALLATION | 2018-10-22 | 2019-10-31 | 2018-10-22 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906061¦¦2020-03-31
TM | C | Yes | 906062 |  | 51591 PPG RW2 | SIMPSON, CARL L. | 100% | 5000 | 46175 | 51175 | 58406 | 58406 | 58406 | 0 | 0 | 58406 | 3000 | 35381 | 38381 | 0.12 | 0.12 |  |  | 0 |  |  | 51837.55 | 22782.71 | 11108.12 |  | 16795.52 | 1151.2 |  | 6568.45 | 0 | 135.1% |  | 0 | 51837.55 | 2000 | 40% | 10794 | 12794 | 25% | 0 |  | 6568.45 | 11.25% | 6568.45 | 11.25% | -7231 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878532 - PPG INDUSTRIES INC | WATER | WATER REPAIR & INSTALLATION | 2018-10-23 | 2019-10-31 | 2018-10-23 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906062¦¦2020-03-31
UP | C | Yes | 906064 |  | 51642 BLYTHE NRG WELL 1 REHA | GRACE, GARY L. | 100% | 89563 | 0 | 89563 | 89562.1 | 89562.1 | 0 | 0 | 0 | 89562.1 | 49923 | 0 | 49923 | 1162.8 |  |  |  | 1162.8 |  |  | 48524.71 | 13130.81 | 3475.5 |  | 31375.9 | 542.5 |  | 41037.39 | 0 | 97.2% |  | 0 | 48524.71 | 39640 | 44.26% | 0 | 39640 | 44.26% | 0 |  | 41037.39 | 45.82% | 41037.39 | 45.82% | 0.9 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887234 - BLYTHE ENERGY INC | WATER | WATER REPAIR & INSTALLATION | 2018-11-05 | 2019-12-21 | 2018-11-05 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906064¦¦2020-03-31
UP | C | Yes | 906070 |  | 51842 PHILLIPS 66 NEW WELL W | MCMAHON, PERRY J | 100% | 1178950 | -17053 | 1161897 | 1170485 | 1170485 | 62736.5 | 0 | 0 | 1170485 | 806964 | -16679 | 790285 | [7 empty] | 718192.84 | 159761.99 | 56822.91 |  | 463201.67 | 38406.27 |  | 452292.16 | 0 | 90.88% |  | 0 | 718192.84 | 371986 | 31.55% | -374 | 371612 | 31.98% | 0 |  | 452292.16 | 38.64% | 452292.16 | 38.64% | -8588 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 896284 - PHILLIPS 66 CARSON | WATER | WATER SUPPLY | 2018-11-27 | 2019-04-30 | 2018-11-27 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906070¦¦2020-03-31
TM | C | Yes | 906078 |  | 51962 51962 FIRSTENERGY SAMMIS | CURLEY, ROBERT E. | 100% | 8154 | 0 | 8154 | 1008 | 1008 | 0 | 0 | 0 | 1008 | 5707 | 0 | 5707 | [7 empty] | 1185.93 | 740.56 | 166.53 |  |  | 278.84 |  | 0 | 177.93 | 20.78% |  | 0 | 1185.93 | 2447 | 30.01% | 0 | 2447 | 30.01% | 0 |  | -177.93 | -17.65% | -177.93 | -17.65% | 7146 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 890659 - FIRSTENERGY GENERATION CORP | WATER | WATER REPAIR & INSTALLATION | 2018-12-12 | 2019-01-31 | 2018-12-12 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906078¦¦2020-03-31
TM | C | Yes | 906080 |  | 52063 CCUA MCPHERSON KS WELL | WARTICK, LOGAN M | 100% | 1 | 69845 | 69846 | 94943 | 94943 | 72890 | 0 | 0 | 94943 | 1680 | 52834.11 | 54514.11 | 60 |  |  |  | 60 |  |  | 72078.46 | 30859.95 | 9010.18 |  | 30524.53 | 1683.8 |  | 22864.54 | 0 | 132.2% |  | 0 | 72078.46 | -1679 | -167900% | 17010.89 | 15331.89 | 21.95% | 0 |  | 22864.54 | 24.08% | 22864.54 | 24.08% | -25097 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 888364 - CHISHOLM CREEK UTILITY AUTHORITY | WATER | WATER REPAIR & INSTALLATION | 2019-01-03 | 2019-02-08 | 2018-12-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906080¦¦2020-03-31
FP | C | Yes | 906081 |  | 52071 EAST FORK PROBE&REP | WILLIAMS, DONALD G. | 100% | 10200 | 8700 | 18900 | 14550 | 14550 | 10650 | 0 | 0 | 14550 | 7997 | 120 | 8117 | [7 empty] | 4597.96 | 3383.77 | 775.88 |  | 438.31 |  |  | 9952.04 | 0 | 56.65% |  | 0 | 4597.96 | 2203 | 21.6% | 8580 | 10783 | 57.05% | 0 |  | 9952.04 | 68.4% | 9952.04 | 68.4% | 4350 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878557 - EAST FORK WATER INC | WATER | WATER REPAIR & INSTALLATION | 2019-01-03 | 2019-08-29 | 2019-01-03 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906081¦¦2020-03-31
UP | CJ | Yes | 906084 |  | 52105 SHARONDALE MHP CONTROL | BRASHEAR, DAVID M | 100% | 46518 | 0 | 46518 | 47200.27 | 47200.27 | 49199.01 | 0 | 0 | 47200.27 | 31561 | 0 | 31561 | 0.01 | 0.01 |  |  | 0 |  |  | 28473.56 | 4954.46 | 1454.16 |  | 22064.94 |  |  | 18726.71 | 0 | 90.22% |  | 0 | 28473.56 | 14957 | 32.15% | 0 | 14957 | 32.15% | 0 |  | 18726.71 | 39.68% | 18726.71 | 39.68% | -682.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 906306 - SHARONDALE MESA OWNERS ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2019-01-08 | 2019-02-28 | 2019-01-08 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906084¦¦2020-03-31
TM | C | Yes | 906086 |  | 52149 GULF POWER MIT | MARTINEZ, MIGUEL E | 100% | 143662 | -3662 | 140000 | 140000 | 140000 | 70000 | 0 | 0 | 140000 | 94817 | -14817 | 80000 | [7 empty] | 82446.62 | 48031.24 | 10024.93 |  | 23920.49 | 469.96 |  | 57553.38 | 0 | 103.1% |  | 0 | 82446.62 | 48845 | 34% | 11155 | 60000 | 42.86% | 0 |  | 57553.38 | 41.11% | 57553.38 | 41.11% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 888196 - CH2M HILL ENGINEERS, INC | WATER | WATER REPAIR & INSTALLATION | 2019-01-09 | 2019-04-29 | 2019-01-09 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906086¦¦2020-03-31
TM | C | Yes | 906088 |  | 52163 MADISON CO LOCI HS | BARNES, MATTHEW D | 100% | 5200 | 17750 | 22950 | 22950 | 22950 | 5003 | 0 | 0 | 22950 | 3395 | 11670 | 15065 | 80.93 |  |  |  | 80.93 |  |  | 18953.35 | 7937.13 | 1437.89 |  | 9578.33 |  |  | 3996.65 | 0 | 125.8% |  | 0 | 18953.35 | 1805 | 34.71% | 6080 | 7885 | 34.36% | 0 |  | 3996.65 | 17.41% | 3996.65 | 17.41% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878952 - MADISON COUNTY SEWER AND WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-01-16 | 2019-02-27 | 2019-01-16 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906088¦¦2020-03-31
TM | C | Yes | 906099 |  | 52341 SAVANNAH MO WELL 2 REPAI | WARTICK, LOGAN M | 100% | 31717.29 | 4845 | 36562.29 | 36562.29 | 36562.29 | 0 | 0 | 0 | 36562.29 | 22202.1 | 10998 | 33200.1 | -0.01 |  |  |  | -0.01 |  |  | 37313.1 | 19039.69 | 6574.62 |  | 11698.79 |  |  | 0 | 750.81 | 112.4% |  | 0 | 37313.1 | 9515.19 | 30% | -6153 | 3362.19 | 9.196% | 0 |  | -750.81 | -2.054% | -750.81 | -2.054% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 897532 - SAVANNAH, MO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-02-06 | 2019-05-31 | 2019-02-06 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 906099¦¦2020-03-31
CR | C | Yes | 906100 |  | 52358 PINE ISLAND MIT | MARTINEZ, MIGUEL E | 100% | 22696 | 0 | 22696 | 22696 | 22696 | 0 | 0 | 0 | 22696 | 12029 | -5824 | 6205 | [7 empty] | 6235.67 | 3557.25 | 1070 |  | 1608.42 |  |  | 16460.33 | 0 | 100.5% |  | 0 | 6235.67 | 10667 | 47% | 5824 | 16491 | 72.66% | 0 |  | 16460.33 | 72.53% | 16460.33 | 72.53% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 891545 - GREATER PINE ISLAND WATER ASSOCIATION | WATER | WATER SUPPLY | 2019-03-03 | 2019-03-07 | 2019-02-28 | 2019-04-30 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906100¦¦2020-03-31
TM | C | Yes | 906102 |  | 52372 MOSAIC PLANT CITY PUMP R | BRUGGER, CRAIG J. | 100% | 23750 | 0 | 23750 | 31111 | 31111 | 7361 | 0 | 0 | 31111 | 16382 | 0 | 16382 | [7 empty] | 26954.76 | 11059.29 | 7491.1 |  | 8104.37 | 300 |  | 4156.24 | 0 | 164.5% |  | 0 | 26954.76 | 7368 | 31.02% | 0 | 7368 | 31.02% | 0 |  | 4156.24 | 13.36% | 4156.24 | 13.36% | -7361 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878838 - MOSAIC BUSINESS SERVICES PLANT CITY FL | WATER | WATER REPAIR & INSTALLATION | 2019-02-03 | 2019-02-27 | 2019-02-03 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 906102¦¦2020-03-31
TM | C | Yes | 906106 |  | 52405 EVONIK TROUBLESHOOT | MIGUEL, SEAN J. | 100% | 2250 | 36941 | 39191 | 79278 | 79278 | 76028 | 0 | 0 | 79278 | 1575 | 26340 | 27915 | 0 |  | 0 |  |  |  |  | 97290.76 | 32434.15 | 26087.37 |  | 38769.24 |  |  | 0 | 18012.76 | 348.5% |  | 0 | 97290.76 | 675 | 30% | 10601 | 11276 | 28.77% | 0 |  | -18012.76 | -22.72% | -18012.76 | -22.72% | -40087 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 890483 - EVONIK DEGUSSA CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-02-05 | 2019-03-30 | 2019-02-05 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906106¦¦2020-03-31
TM | C | Yes | 906110 |  | 52421 MANHATTAN KS 2019 WELL | WARTICK, LOGAN M | 100% | 56688 | 52389 | 109077 | 124311 | 124311 | 79472.8 | 0 | 0 | 124311 | 51019.2 | 46110.34 | 97129.54 | 151.12 |  |  |  | 151.12 |  |  | 117073.88 | 55128.44 | 10461.8 |  | 51197.9 | 285.74 |  | 7237.12 | 0 | 120.5% |  | 0 | 117073.88 | 5668.8 | 10% | 6278.66 | 11947.46 | 10.95% | 0 |  | 7237.12 | 5.822% | 7237.12 | 5.822% | -15234 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 894147 - MANHATTAN, KS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-02-04 | 2019-03-31 | 2019-02-04 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906110¦¦2020-03-31
FP | CJ | Yes | 906112 |  | 52428 52428 AK STEEL COKE PLA | SIMPSON, CARL L. | 100% | 1500 | 0 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 1500 | 1080 | 0 | 1080 | 0.22 | 0.22 |  |  | 0 |  |  | 4753.64 | 2906.28 | 506.5 |  | 736.86 | 604 |  | 0 | 3253.64 | 440.2% |  | 0 | 4753.64 | 420 | 28% | 0 | 420 | 28% | 0 |  | -3253.64 | -216.9% | -3253.64 | -216.9% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-02-03 | 2019-02-06 | 2019-02-03 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 906112¦¦2020-03-31
FP | CJ | Yes | 906121 |  | 52493 CATALINA MONTHLY | BARNES, MATTHEW D | 100% | 2880 | 0 | 2880 | 2400 | 2400 | 1920 | 0 | 0 | 2400 | 2016 | 144 | 2160 | [7 empty] | 1620 |  |  |  |  | 1620 |  | 780 | 0 | 75% |  | 0 | 1620 | 864 | 30% | -144 | 720 | 25% | 0 |  | 780 | 32.5% | 780 | 32.5% | 480 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 888039 - CATALINA MANUFACTURED HOME COMMUNITY | WATER | WATER REPAIR & INSTALLATION | 2019-02-28 | 2019-07-30 | 2019-02-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 906121¦¦2020-03-31
FP | C | Yes | 906130 |  | 52531 MOSAIC FOUR CORNERS DEEP | BRUGGER, CRAIG J. | 100% | 34450 | 0 | 34450 | 34469 | 34469 | 17234.5 | 0 | 0 | 34469 | 21656 | 0 | 21656 | [7 empty] | 9330.94 | 4783.31 | 1051.4 |  | 3496.23 |  |  | 25138.06 | 0 | 43.09% |  | 0 | 9330.94 | 12794 | 37.14% | 0 | 12794 | 37.14% | 0 |  | 25138.06 | 72.93% | 25138.06 | 72.93% | -19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895010 - MOSAIC BUSINESS SERVICES | WATER | WATER REPAIR & INSTALLATION | 2019-02-28 | 2019-04-29 | 2019-02-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906130¦¦2020-03-31
TM | C | Yes | 906184 |  | 52859 P66 WELL MAINTENANCE 041 | WHITE, CATHLEEN R | 100% | 10000 | 0 | 10000 | 32527 | 32527 | 32527 | 0 | 0 | 32527 | 7000 | 0 | 7000 | 260.31 |  |  |  | 260.31 |  |  | 40742.54 | 22338.56 | 5840.03 |  | 12563.95 |  |  | 0 | 8215.54 | 582% |  | 0 | 40742.54 | 3000 | 30% | 0 | 3000 | 30% | 0 |  | -8215.54 | -25.26% | -8215.54 | -25.26% | -22527 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878946 - PHILLIPS 66 WOOD RIVER REFINERY | WATER | WATER REPAIR & INSTALLATION | 2019-04-09 | 2019-05-31 | 2019-04-09 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 906184¦¦2020-03-31
TM | C | Yes | 906186 |  | 52868 ARKANSAS ELECTRIC COOP | BENNETT, MARK C. | 100% | 12000 | 0 | 12000 | 5694.44 | 5694.44 | 5694.44 | 0 | 0 | 5694.44 | 8000 | 0 | 8000 | [7 empty] | 110577.94 | 55741.62 | 8602.19 |  | 46234.13 |  |  | 0 | 104883.5 | 1382% |  | 0 | 110577.94 | 4000 | 33.33% | 0 | 4000 | 33.33% | 0 |  | -104883.5 | -1842% | -104883.5 | -1842% | 6305.56 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 886478 - ARKANSAS ELECTRIC COOPERATIVE CORP | WATER | WATER REPAIR & INSTALLATION | 2019-04-09 | 2020-04-09 | 2019-04-09 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906186¦¦2020-03-31
FP | C | Yes | 906187 |  | 52878 NEEDLESCITYSERVICECALL | BRASHEAR, DAVID M | 100% | 4716 | 0 | 4716 | 0 | 0 | 0 | 0 | 0 | 0 | 3153 | 0 | 3153 | [7 empty] | 5924.37 | 3312.29 | 540 |  | 2072.08 |  |  | 0 | 5924.37 | 187.9% |  | 0 | 5924.37 | 1563 | 33.14% | 0 | 1563 | 33.14% | 0 |  | -5924.37 |  | -5924.37 |  | 4716 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 888536 - CITY OF NEEDLES | WATER | WATER REPAIR & INSTALLATION | 2019-04-15 | 2019-04-12 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906187¦¦2020-03-31
TM | C | Yes | 906190 |  | 52882 LEE COUNTY PINEWOODS RO | TORMOEHLEN, DAVID A. | 100% | 9550 | 0 | 9550 | 9550 | 9550 | 9550 | 0 | 0 | 9550 | 5921 | 0 | 5921 | [7 empty] | 16330.43 | 3552.24 | 3269.68 |  | 9508.51 |  |  | 0 | 6780.43 | 275.8% |  | 0 | 16330.43 | 3629 | 38% | 0 | 3629 | 38% | 0 |  | -6780.43 | -71% | -6780.43 | -71% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878637 - LEE, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-03-12 | 2019-04-29 | 2019-03-12 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906190¦¦2020-03-31
TM | C | Yes | 906191 |  | 52883 PPG RW3 | SIMPSON, CARL L. | 100% | 44435 | 0 | 44435 | 93730 | 93730 | 93730 | 0 | 0 | 93730 | 31000 | 0 | 31000 | 56.47 |  |  |  | 56.47 |  |  | 86717.62 | 26795.65 | 24228.07 |  | 35693.9 |  |  | 7012.38 | 0 | 279.7% |  | 0 | 86717.62 | 13435 | 30.24% | 0 | 13435 | 30.24% | 0 |  | 7012.38 | 7.481% | 7012.38 | 7.481% | -49295 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878532 - PPG INDUSTRIES INC | WATER | WATER REPAIR & INSTALLATION | 2019-04-14 | 2019-05-02 | 2019-04-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906191¦¦2020-03-31
TM | C | Yes | 906192 |  | 52884 MOSAIC WELL RW5 REHABILI | BRUGGER, CRAIG J. | 100% | 37984 | 0 | 37984 | 71421 | 71421 | 71421 | 0 | 0 | 71421 | 23260 | 0 | 23260 | [7 empty] | 38688.32 | 20266.8 | 6798.82 |  | 11622.7 |  |  | 32732.68 | 0 | 166.3% |  | 0 | 38688.32 | 14724 | 38.76% | 0 | 14724 | 38.76% | 0 |  | 32732.68 | 45.83% | 32732.68 | 45.83% | -33437 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878838 - MOSAIC BUSINESS SERVICES PLANT CITY FL | WATER | WATER REPAIR & INSTALLATION | 2019-04-10 | 2019-05-10 | 2019-04-10 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906192¦¦2020-03-31
TM | C | Yes | 906194 |  | 52887 CITY OF ST PETE MIT NWR | MARTINEZ, MIGUEL E | 100% | 42500 | 0 | 42500 | 42500 | 42500 | 42500 | 0 | 0 | 42500 | 27533 | 0 | 27533 | [7 empty] | 19130.68 | 7020.65 | 7060.95 |  | 2850.11 | 2198.97 |  | 23369.32 | 0 | 69.48% |  | 0 | 19130.68 | 14967 | 35.22% | 0 | 14967 | 35.22% | 0 |  | 23369.32 | 54.99% | 23369.32 | 54.99% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 886574 - ASRUS LLC | WATER | WATER REPAIR & INSTALLATION | 2019-04-10 | 2019-05-30 | 2019-04-10 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906194¦¦2020-03-31
TM | C | Yes | 906196 |  | 52889 GREENSBURG PUMP REPAIR | LOPEZ-VASQUEZ, JUAN C. | 100% | 25960 | 100420 | 126380 | 126900 | 126900 | 126900 | 0 | 0 | 126900 | 17912.5 | 71079.5 | 88992 | 0 |  |  |  | 0 |  |  | 96752.5 | 42302.51 | 16530.95 |  | 37156.84 | 762.2 |  | 30147.5 | 0 | 108.7% |  | 0 | 96752.5 | 8047.5 | 31% | 29340.5 | 37388 | 29.58% | 0 |  | 30147.5 | 23.76% | 30147.5 | 23.76% | -520 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 891585 - GREENSBURG, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-22 | 2019-08-02 | 2019-04-22 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906196¦¦2020-03-31
CR | LJ | Yes | 906204 |  | 52902 SYNGENTA DRILL INDUSTRIA | LOPEZ-VASQUEZ, JUAN C. | 50.37% | 542600 | 0 | 542600 | 273303.7326 | 344100 | 344100 | 0 | 0 | 542600 | 364965 | 0 | 364965 | 3658.31 | 417.61 | 505.57 |  | 235.13 | 2500 |  | 208284.15 | 66303.43 | 38019.97 |  | 96905.35 | 7055.4 |  | 135815.85 | 0 | 57.07% |  | 205230.07 | 413514.22 | 177635 | 32.74% | 0 | 177635 | 32.74% | 0 |  | 65019.58 | 23.79% | 129085.78 | 23.79% | 269296.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 898608 - SYNGENTA CROP PROTECTION, LLC | WATER | WATER SUPPLY | 2019-05-01 | 2019-10-05 | 2019-06-28 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 906204¦¦2020-03-31
CR | CJ | Yes | 906205 |  | 52903 MONOLITH MATERIALS NEW W | HEILIGER, TERENCE L. | 100% | 107481 | 0 | 107481 | 128379 | 128379 | 128379 | 0 | 0 | 128379 | 71881 | 0 | 71881 | 2447 | 1332.31 | 450.88 |  | 663.81 |  |  | 121840.52 | 28921.14 | 45955.59 |  | 46963.79 |  |  | 6538.48 | 0 | 169.5% |  | 0 | 121840.52 | 35600 | 33.12% | 0 | 35600 | 33.12% | 0 |  | 6538.48 | 5.093% | 6538.48 | 5.093% | -20898 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 894893 - MONOLITH MATERIALS | WATER | WATER SUPPLY | 2019-04-11 | 2019-07-31 | 2019-04-11 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906205¦¦2020-03-31
CR | C | Yes | 906209 |  | 52912 SEYMOUR CT PRODUCTION WE | CROOK, CHARLES M | 100% | 458315 | -42840 | 415475 | 401755 | 401755 | 401755 | 0 | 20087.75 | 401755 | 340000 | -30000 | 310000 | 0 |  |  |  | 0 |  |  | 357036.1 | 110982.2 | 68699.82 |  | 177354.08 |  |  | 44718.9 | 0 | 115.2% |  | 0 | 357036.1 | 118315 | 25.82% | -12840 | 105475 | 25.39% | 0 |  | 44718.9 | 11.13% | 44718.9 | 11.13% | 13720 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 893290 - KOVACS CONSTRUCTION CORP OXFORD, CT | WATER | WATER SUPPLY | 2019-02-24 | 2019-12-26 | 2019-04-12 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906209¦¦2020-03-31
FP | C | Yes | 906220 |  | 52925 EVERGREEN PACKAGING WELL | BURGE, EVERETT E. | 100% | 24800 | 0 | 24800 | 28244.15 | 28244.15 | 28244.15 | 0 | 0 | 28244.15 | 17360 | 0 | 17360 | 0 |  |  |  | 0 |  |  | 19947.57 | 8337.53 | 1615.46 |  | 9994.58 |  |  | 8296.58 | 0 | 114.9% |  | 0 | 19947.57 | 7440 | 30% | 0 | 7440 | 30% | 0 |  | 8296.58 | 29.37% | 8296.58 | 29.37% | -3444.15 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878972 - EVERGREEN PACKAGING INC | WATER | WATER REPAIR & INSTALLATION | 2019-04-15 | 2019-07-26 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906220¦¦2020-03-31
FP | C | Yes | 906222 |  | 52929 OCALA WELL 6 AND 2 | PARSLEY, TRISTAN S | 100% | 10000 | 112240 | 122240 | 122240 | 122240 | 122240 | 0 | 0 | 122240 | 7000 | 73505 | 80505 | [7 empty] | 94654.68 | 18766.38 | 6030.84 |  | 69857.46 |  |  | 27585.32 | 0 | 117.6% |  | 0 | 94654.68 | 3000 | 30% | 38735 | 41735 | 34.14% | 0 |  | 27585.32 | 22.57% | 27585.32 | 22.57% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 895661 - OCALA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-15 | 2019-06-30 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906222¦¦2020-03-31
FP | CJ | Yes | 906223 |  | 52931 KOCH FERTILIZER FT DODGE | HEILIGER, TERENCE L. | 100% | 27409 | 61270 | 88679 | 215048 | 215048 | 215048 | 0 | 0 | 215048 | 15880 | 44573.61 | 60453.61 | 8023.81 | 859.85 | 10.5 |  | 653.06 | 6500.4 |  | 129150.4 | 17451.15 | 7009.36 | 608.21 | 68097.28 | 35984.4 |  | 85897.6 | 0 | 213.6% |  | 0 | 129150.4 | 11529 | 42.06% | 16696.39 | 28225.39 | 31.83% | 0 |  | 85897.6 | 39.94% | 85897.6 | 39.94% | -126369 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 893267 - KOCH FERTILIZER FT DODGE, LLC | WATER | WATER REPAIR & INSTALLATION | 2019-04-15 | 2019-06-30 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906223¦¦2020-03-31
TM | C | Yes | 906228 |  | 52940 ASE INDIANSPRINGSPRISONE | BRASHEAR, DAVID M | 100% | 146286 | 76719.23 | 223005.23 | 223006.31 | 223006.31 | 237149.61 | 11857.48 | 0 | 223006.31 | 95452 | 49701.1 | 145153.1 | 2754.64 |  |  |  | 2754.64 |  |  | 129187.18 | 15607.62 | 5719.06 |  | 107860.5 |  |  | 93819.13 | 0 | 89% |  | 0 | 129187.18 | 50834 | 34.75% | 27018.13 | 77852.13 | 34.91% | 0 |  | 93819.13 | 42.07% | 93819.13 | 42.07% | -1.08 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 906308 - AMERICAN SOUTHWEST ELECTRIC | WATER | WATER REPAIR & INSTALLATION | 2019-04-15 | 2019-08-30 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906228¦¦2020-03-31
FP | C | Yes | 906229 |  | 52941 CHEMOURS RWP | MIGUEL, SEAN J. | 100% | 276928 | 0 | 276928 | 272291.5 | 272291.5 | 272291.5 | 0 | 0 | 272291.5 | 196618 | 0 | 196618 | [7 empty] | 211902.38 | 25849.17 | 9014.06 |  | 177039.15 |  |  | 60389.12 | 0 | 107.8% |  | 0 | 211902.38 | 80310 | 29% | 0 | 80310 | 29% | 0 |  | 60389.12 | 22.18% | 60389.12 | 22.18% | 4636.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888287 - CHEMOURS LOUISVILLE WORKS | WATER | WATER REPAIR & INSTALLATION | 2019-04-15 | 2019-07-30 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906229¦¦2020-03-31
FP | C | Yes | 906233 |  | 52948 MOSAIC FOUR CORNERS DW 1 | BRUGGER, CRAIG J. | 100% | 35719 | 0 | 35719 | 35719 | 35719 | 35719 | 0 | 0 | 35719 | 21635 | 0 | 21635 | [7 empty] | 19545.15 | 965.69 | -38.12 |  | 18617.58 |  |  | 16173.85 | 0 | 90.34% |  | 0 | 19545.15 | 14084 | 39.43% | 0 | 14084 | 39.43% | 0 |  | 16173.85 | 45.28% | 16173.85 | 45.28% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 906311 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-04-15 | 2019-05-30 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906233¦¦2020-03-31
TM | C | Yes | 906239 |  | 52957 CALTRANS WHITEWATER | BRASHEAR, DAVID M | 100% | 3641 | 0 | 3641 | 0 | 0 | 0 | 0 | 0 | 0 | 1503 | 0 | 1503 | [7 empty] | 952.26 | 359.82 |  |  | 592.44 |  |  | 0 | 952.26 | 63.36% |  | 0 | 952.26 | 2138 | 58.72% | 0 | 2138 | 58.72% | 0 |  | -952.26 |  | -952.26 |  | 3641 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 906314 - CALTRANS WHITEWATER REST STOP | WATER | WATER REPAIR & INSTALLATION | 2019-04-19 | 2019-04-30 | 2019-04-19 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906239¦¦2020-03-31
CR | LJ | Yes | 906240 |  | 52958 BIG RIVER STEEL WELLS 3 | BURGE, EVERETT E. | 98.17% | 2000735 | 0 | 2000735 | 1912111.0734 | 1986268.55 | 1986268.55 | 0 | 0 | 1947735 | 1315760 | 0 | 1315760 | 0 |  | 0 |  |  |  |  | 1338967.34 | 337986.38 | 308008.91 |  | 644009.3 | 48962.75 |  | 647301.21 | 0 | 101.8% |  | 24945.87 | 1363913.21 | 684975 | 34.24% | 0 | 684975 | 34.24% | 0 |  | 573143.73 | 29.97% | 583821.79 | 29.97% | 88623.93 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887104 - BIG RIVER STEEL LLC | WATER | WATER SUPPLY | 2019-04-15 | 2019-12-15 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906240¦¦2020-03-31
FP | C | Yes | 906246 |  | 52967 CHARLES F SMITH JR FAR | BENNETT, MARK C. | 100% | 22000 | 0 | 22000 | 37947.79 | 37947.79 | 38903.88 | 0 | 0 | 37947.79 | 16000 | 0 | 16000 | [7 empty] | 30710.43 | 9049.18 | 2236.5 |  | 19239.75 | 185 |  | 7237.36 | 0 | 191.9% |  | 0 | 30710.43 | 6000 | 27.27% | 0 | 6000 | 27.27% | 0 |  | 7237.36 | 19.07% | 7237.36 | 19.07% | -15947.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 888236 - CHARLES F SMITH JR FARMS | WATER | WATER SUPPLY | 2019-04-18 | 2020-04-18 | 2019-04-18 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906246¦¦2020-03-31
FP | C | Yes | 906249 |  | 52973 WESTROCK SPARE 12 PUMP | ALBARADO, JORDAN A | 100% | 15800 | 0 | 15800 | 15800 | 15800 | 15800 | 0 | 0 | 15800 | 7900 | 0 | 7900 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 15799.99 | 0 | 0.0001266% |  | 0 | 0.01 | 7900 | 50% | 0 | 7900 | 50% | 0 |  | 15799.99 | 100% | 15799.99 | 100% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2019-04-18 | 2019-05-09 | 2019-04-18 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906249¦¦2020-03-31
FP | LJ | Yes | 906255 |  | 52987 NYAW 24 2A TEST WELL | RANFT, DONALD R | 85.85% | 194900 | 601445 | 796345 | 683634.9748 | 595575 | 595575 | 0 | 29778.75 | 796345 | 132500 | 527347.53 | 659847.53 | 2349.7 | 288.68 | -591.88 |  | 2652.9 |  |  | 592294.21 | 226205.46 | 120168.18 |  | 244680.57 | 1240 |  | 3280.79 | 0 | 89.76% |  | 97650.79 | 689945 | 62400 | 32.02% | 74097.47 | 136497.47 | 17.14% | 15202.14 |  | 91340.76 | 13.36% | 106400 | 13.36% | 112710.03 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878512 - NEW YORK AMERICAN WATER | WATER | WATER SUPPLY | 2019-04-21 | 2019-08-15 | 2019-04-21 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906255¦¦2020-03-31
FP | C | Yes | 906258 |  | 52990 WELL 5 PUMP PULL AND INS | BRUGGER, CRAIG J. | 100% | 16367 | 0 | 16367 | 16367 | 16367 | 16367 | 0 | 0 | 16367 | 9827 | 0 | 9827 | [7 empty] | 9136.63 | 4376.77 | 2515.62 |  | 2244.24 |  |  | 7230.37 | 0 | 92.97% |  | 0 | 9136.63 | 6540 | 39.96% | 0 | 6540 | 39.96% | 0 |  | 7230.37 | 44.18% | 7230.37 | 44.18% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878976 - DAVIE, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-08-04 | 2019-07-14 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 906258¦¦2020-03-31
FP | C | Yes | 906271 |  | 53009 EVERGREEN PACKAGING WELL | BURGE, EVERETT E. | 100% | 628310 | 0 | 628310 | 706194 | 706194 | 392039 | 0 | 0 | 706194 | 435100 | 0 | 435100 | 117437.47 | 25272.43 | 21134.28 |  | 73784.31 |  | -2753.55 | 811852.83 | 261892.83 | 121160.63 |  | 428799.37 |  | 0 | 0 | 105658.83 | 186.6% |  | 0 | 811852.83 | 193210 | 30.75% | 0 | 193210 | 30.75% | 0 |  | -105658.83 | -14.96% | -105658.83 | -14.96% | -77884 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878972 - EVERGREEN PACKAGING INC | WATER | WATER SUPPLY | 2019-04-19 | 2019-12-02 | 2019-04-19 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906271¦¦2020-03-31
CR | C | Yes | 906275 |  | 53014 WESTBOROUGH MA AERATOR | CHESLEY, ANDREW J | 100% | 83500 | 0 | 83500 | 83500 | 83500 | 83500 | 0 | 0 | 83500 | 63047.21 | 0 | 63047.21 | [7 empty] | 57694.6 | 5362.67 |  |  | 52331.93 |  |  | 25805.4 | 0 | 91.51% |  | 0 | 57694.6 | 20452.79 | 24.49% | 0 | 20452.79 | 24.49% | 0 |  | 25805.4 | 30.9% | 25805.4 | 30.9% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 906323 - WATERLINE INDUSTRIES CORPORATION | WATER | WATER TREATMENT | 2019-04-19 | 2019-08-30 | 2019-04-17 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906275¦¦2020-03-31
TM | CJ | Yes | 906277 |  | 53017 CARAUSTAR PWM S | GRACE, GARY L. | 100% | 2390 | 0 | 2390 | 0 | 0 | 0 | 0 | 0 | 0 | 1531 | 0 | 1531 | 0.01 |  |  |  | 0.01 |  |  | -581.98 | 99.09 | -69.96 |  | -611.11 |  |  | 581.98 | 0 | -38.01% |  | 0 | -581.98 | 859 | 35.94% | 0 | 859 | 35.94% | 0 |  | 581.98 |  | 581.98 |  | 2390 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 906325 - GREIF | WATER | WATER REPAIR & INSTALLATION | 2019-04-22 | 2019-05-06 | 2019-04-22 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906277¦¦2020-03-31
CR | CJ | Yes | 906278 |  | 53024 WMWD JEFFERSON BSTER 2 A | SEIDEN, ANDREW L. | 100% | 31605 | 11481.6 | 43086.6 | 52196.6 | 52196.6 | 54770.52 | 0 | 0 | 52196.6 | 24157 | 6656.32 | 30813.32 | 2.62 |  |  |  | 2.62 |  |  | 62407.62 | 18270.33 | 3772.66 |  | 38788.95 | 1575.68 |  | 0 | 10211.02 | 202.5% |  | 0 | 62407.62 | 7448 | 23.57% | 4825.28 | 12273.28 | 28.49% | 0 |  | -10211.02 | -19.56% | -10211.02 | -19.56% | -9110 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 900107 - WESTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-04-23 | 2019-06-30 | 2019-04-23 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 906278¦¦2020-03-31
TM | C | Yes | 906280 |  | 53026 OBG GE EVENDALE PIPE CLE | BARNES, MATTHEW D | 100% | 39261 | 32239 | 71500 | 68596 | 68596 | 68596 | 1035 | 0 | 68596 | 21245 | 21751 | 42996 | 0.02 | 0.02 | [5 empty] | 41311.63 | 15272.36 | 11963.07 |  | 14076.2 |  |  | 27284.37 | 0 | 96.08% |  | 0 | 41311.63 | 18016 | 45.89% | 10488 | 28504 | 39.87% | 0 |  | 27284.37 | 39.78% | 27284.37 | 39.78% | 2904 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 895659 - RAMBOLL | WATER | WATER REPAIR & INSTALLATION | 2019-03-31 | 2019-05-31 | 2019-03-31 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906280¦¦2020-03-31
FP | C | Yes | 906282 |  | 53031 EMWD 85 | BRASHEAR, DAVID M | 100% | 10956 | 0 | 10956 | 10851.9 | 10851.9 | 10851.9 | 0 | 0 | 10851.9 | 7566 | 0 | 7566 | [7 empty] | 10709.51 | 5237.48 | 535.79 |  | 4936.24 |  |  | 142.39 | 0 | 141.5% |  | 0 | 10709.51 | 3390 | 30.94% | 0 | 3390 | 30.94% | 0 |  | 142.39 | 1.312% | 142.39 | 1.312% | 104.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878619 - EASTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-04-15 | 2019-06-27 | 2019-04-15 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | PROFESSIONAL SERVICES | 906282¦¦2020-03-31
TM | C | Yes | 906284 |  | 53034 GOODYEAR KS NEW HSP | WARTICK, LOGAN M | 100% | 10905 | 0 | 10905 | 28233 | 28233 | 28233 | 0 | 0 | 28233 | 8724 | 0 | 8724 | [7 empty] | 40890.34 | 12619.28 | 4993.18 |  | 23277.88 |  |  | 0 | 12657.34 | 468.7% |  | 0 | 40890.34 | 2181 | 20% | 0 | 2181 | 20% | 0 |  | -12657.34 | -44.83% | -12657.34 | -44.83% | -17328 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 891420 - GOODYEAR TOPEKA PLANT | WATER | WATER SUPPLY | 2019-04-24 | 2019-07-05 | 2019-04-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906284¦¦2020-03-31
CR | C | Yes | 906285 |  | 53035 HELZBERG DEWATERING WELL | WARTICK, LOGAN M | 100% | 266303 | 136040.5 | 402343.5 | 402343.25 | 402343.25 | 402343.25 | 0 | 0 | 402343.25 | 219351 | 212856.41 | 432207.41 | [7 empty] | 348070.3 | 70252.28 | 22637.15 |  | 79604.65 | 175576.22 |  | 54272.95 | 0 | 80.53% |  | 0 | 348070.3 | 46952 | 17.63% | -76815.91 | -29863.91 | -7.422% | 0 |  | 54272.95 | 13.49% | 54272.95 | 13.49% | 0.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 892005 - HELZBERG DIAMONDS | WATER | WATER SUPPLY | 2019-04-24 | 2019-06-06 | 2019-04-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 906285¦¦2020-03-31
TM | C | Yes | 906292 |  | 53050 KCPL LAKE ROAD TEST DRIL | WARTICK, LOGAN M | 100% | 13677 | 0 | 13677 |  |  | 0 | 0 | 0 |  | 10941 | 0 | 10941 | [7 empty] | 1750 |  |  |  |  | 1750 |  | 0 | 1750 | 15.99% |  | 0 | 1750 | 2736 | 20% | 0 | 2736 | 20% | 0 |  | -1750 |  | -1750 |  | 13677 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 893032 - EVERGY | WATER | WATER SUPPLY | 2019-04-25 | 2019-06-30 | 2019-04-25 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906292¦¦2020-03-31
FP | C | Yes | 906293 |  | 53052 GSW BELLHAVEN 3 | SEIDEN, ANDREW L. | 100% | 40253 | 0 | 40253 | 40253 | 40253 | 43126.56 | 0 | 0 | 40253 | 29949 | 0 | 29949 | [7 empty] | 39351.71 | 5713.82 | 1499.6 |  | 32138.29 |  |  | 901.29 | 0 | 131.4% |  | 0 | 39351.71 | 10304 | 25.6% | 0 | 10304 | 25.6% | 0 |  | 901.29 | 2.239% | 901.29 | 2.239% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 891366 - GOLDEN STATE WATER CO | WATER | WATER REPAIR & INSTALLATION | 2019-04-25 | 2019-06-30 | 2019-04-25 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 906293¦¦2020-03-31
FP | C | Yes | 906294 |  | 53053 BENTON UTILITIES PR | BENNETT, MARK C. | 100% | 25000 | 0 | 25000 | 73058.72 | 73058.72 | 79908.01 | 0 | 0 | 73058.72 | 17500 | 0 | 17500 | [7 empty] | 53948.18 | 21528.53 | 6048.73 |  | 22877.23 | 3493.69 |  | 19110.54 | 0 | 308.3% | 62.85 | 0 | 53948.18 | 7500 | 30% | 0 | 7500 | 30% | 0 |  | 19110.54 | 26.16% | 19110.54 | 26.16% | -48058.72 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887011 - BENTON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-25 | 2020-04-25 | 2019-04-25 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 906294¦¦2020-03-31
UP | C | Yes | 906297 |  | 53057 WICHITA KS 2019 WELL RE | WARTICK, LOGAN M | 100% | 752244 | 0 | 752244 | 746945.55 | 746945.55 | 746945.55 | 0 | 0 | 746945.55 | 661974 | 0 | 661974 | 0.55 | 0.55 | [5 empty] | 712398.86 | 213502.61 | 113658.46 |  | 351357.9 | 33879.89 |  | 34546.69 | 0 | 107.6% |  | 0 | 712398.86 | 90270 | 12% | 0 | 90270 | 12% | 0 |  | 34546.69 | 4.625% | 34546.69 | 4.625% | 5298.45 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 900297 - WICHITA, KS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-02 | 2019-11-30 | 2019-04-02 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 906297¦¦2020-03-31
FP | C | Yes | 907653 |  | WILL TARKINGTON | SCHERM, LOGAN M | 100% | 22500 | 0 | 22500 | 28121 | 28121 | 28121 | 0 | 0 | 28121 | 15750 | 0 | 15750 | [7 empty] | 20779.24 | 4718.5 | 1062.08 |  | 13298.66 | 1700 |  | 7341.76 | 0 | 131.9% |  | 0 | 20779.24 | 6750 | 30% | 0 | 6750 | 30% | 0 |  | 7341.76 | 26.11% | 7341.76 | 26.11% | -5621 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 900365 - WILL TARKINGTON | WATER | WATER REPAIR & INSTALLATION | 2019-04-29 | 2019-08-01 | 1900-01-01 | 2019-08-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 907653¦¦2020-03-31
UP | C | Yes | 907662 |  | ST JOHN SEMINARY WELL ABANDON | GRACE, GARY L. | 100% | 3032.48 | 6131.32 | 9163.8 | 7494.66 | 7494.66 | 7494.66 | 0 | 0 | 7494.66 | 1971.54 | 3765.31 | 5736.85 | [7 empty] | 8176.47 | 4219.15 | 427.94 |  | 3529.38 |  |  | 0 | 681.81 | 142.5% |  | 0 | 8176.47 | 1060.94 | 34.99% | 2366.01 | 3426.95 | 37.4% | 0 |  | -681.81 | -9.097% | -681.81 | -9.097% | 1669.14 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 291753 - SHEA HOMES | WATER | WATER REPAIR & INSTALLATION | 2019-04-22 | 2019-05-01 | 2019-04-22 | 2019-05-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 907662¦¦2020-03-31
UP | CJ | Yes | 907673 |  | LONG BEACH WELL 16 NEW PUMP | RANFT, DONALD R | 100% | 103650 | 0 | 103650 | 148850 | 148850 | 148850 | 0 | 6182.5 | 148850 | 77130 | 0 | 77130 | 0 |  |  |  | 0 |  |  | 127537.25 | 51818.92 | 18083.2 |  | 55735.13 | 1900 |  | 21312.75 | 0 | 165.4% |  | 0 | 127537.25 | 26520 | 25.59% | 0 | 26520 | 25.59% | 0 |  | 21312.75 | 14.32% | 21312.75 | 14.32% | -45200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 893883 - LONG BEACH, NY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-28 | 2019-05-31 | 2019-04-28 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 907673¦¦2020-03-31
UP | CJ | Yes | 907746 |  | ELGIN IL WELL 4A | HEALY, THOMAS P. | 100% | 468191 | 0 | 468191 | 396079.5 | 396079.5 | 396079.5 | 0 | 0 | 396079.5 | 355825 | 0 | 355825 | 0 |  |  |  | 0 |  |  | 325842.78 | 91413.52 | 14262 |  | 218517.26 | 1650 |  | 70236.72 | 0 | 91.57% |  | 0 | 325842.78 | 112366 | 24% | 0 | 112366 | 24% | 0 |  | 70236.72 | 17.73% | 70236.72 | 17.73% | 72111.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 890121 - ELGIN, CITY OF WATER DEPT | WATER | WATER REPAIR & INSTALLATION | 2019-04-25 | 2019-11-30 | 1900-01-01 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 907746¦¦2020-03-31
TM | C | Yes | 907750 |  | NKWD ORPS 1 - PUMP 4 | MIGUEL, SEAN J. | 100% | 144750 | 23645 | 168395 | 168395 | 168395 | 168395 | 0 | 0 | 168395 | 114985 | 18207 | 133192 | 650.55 |  |  |  | 650.55 |  |  | 127299.01 | 23625.07 | 5093.76 |  | 91012.88 | 7567.3 |  | 41095.99 | 0 | 95.58% |  | 0 | 127299.01 | 29765 | 20.56% | 5438 | 35203 | 20.91% | 0 |  | 41095.99 | 24.4% | 41095.99 | 24.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 1001607 - GLENWOOD ELECTRIC INC | WATER | WATER REPAIR & INSTALLATION | 2019-04-29 | 2019-05-31 | 2019-04-29 | 2019-05-31 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 907750¦¦2020-03-31
FP | C | Yes | 907809 |  | LVVWD BBWD NEW WELL | MCMAHON, PERRY J | 100% | 629870 | 0 | 629870 | 643481.39 | 643481.39 | 643481.39 | 0 | 0 | 643481.39 | 544583.2 | 0 | 544583.2 | [7 empty] | 1207062.79 | 319228.68 | 337129.04 |  | 441867.88 | 108837.19 |  | 0 | 563581.4 | 221.6% |  | 0 | 1207062.79 | 85286.8 | 13.54% | 0 | 85286.8 | 13.54% | 0 |  | -563581.4 | -87.58% | -563581.4 | -87.58% | -13611.39 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 893513 - LAS VEGAS VALLEY WATER DISTRICT | WATER | WATER SUPPLY | 2019-04-24 | 2019-07-24 | 1900-01-01 | 2019-07-24 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 907809¦¦2020-03-31
CR | C | Yes | 908167 |  | PCA DERIDDER - TEST | ALBARADO, JORDAN A | 100% | 9750 | 0 | 9750 | 9750 | 9750 | 9750 | 0 | 0 | 9750 | 3574 | 0 | 3574 | [7 empty] | 5255.73 | 3217.36 | 773.3 |  | 1265.07 |  |  | 4494.27 | 0 | 147.1% |  | 0 | 5255.73 | 6176 | 63.34% | 0 | 6176 | 63.34% | 0 |  | 4494.27 | 46.1% | 4494.27 | 46.1% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895966 - PACKAGING CORPORATION OF AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-05-31 | 2019-05-01 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 908167¦¦2020-03-31
TM | CJ | Yes | 908168 |  | ST MARYS GLACIER WELL | SCHANAMAN, MIKE L. | 100% | 159995 | 0 | 159995 | 186326 | 186326 | 186326 | 0 | 9316.3 | 186326 | 113596 | 0 | 113596 | 0 |  |  |  | 0 |  |  | 160557.02 | 67494.41 | 17304.61 |  | 75306 | 452 |  | 25768.98 | 0 | 141.3% |  | 0 | 160557.02 | 46399 | 29% | 0 | 46399 | 29% | 0 |  | 25768.98 | 13.83% | 25768.98 | 13.83% | -26331 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 909424 - ST MARYS GLACIER WATER AND SANITATION | WATER | WATER SUPPLY | 2019-05-01 | 2019-06-29 | 2019-05-01 | 2019-06-29 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 908168¦¦2020-03-31
CR | C | Yes | 908171 |  | EXXON REFINERY 52 P&A | GNAU, CASEY T | 100% | 54460 | 0 | 54460 | 54460 | 54460 | 54460 | 0 | 0 | 54460 | 21785 | 0 | 21785 | 0 |  |  |  | 0 |  |  | 22054.27 | 10269.82 | 6537.19 |  | 5247.26 |  |  | 32405.73 | 0 | 101.2% |  | 0 | 22054.27 | 32675 | 60% | 0 | 32675 | 60% | 0 |  | 32405.73 | 59.5% | 32405.73 | 59.5% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 890523 - EXXONMOBIL REFINING & MARKETING | WATER | WATER REPAIR & INSTALLATION | 2019-04-25 | 2019-07-31 | 2019-04-25 | 2019-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 908171¦¦2020-03-31
CR | C | Yes | 908177 |  | EXXON 53 TV SURVEY | GNAU, CASEY T | 100% | 21200 | 51965 | 73165 | 73165 | 73165 | 73165 | 0 | 0 | 73165 | 11940 | 22346 | 34286 | [7 empty] | 34368.67 | 8962.06 | 3636.67 |  | 6492.82 | 15277.12 |  | 38796.33 | 0 | 100.2% |  | 0 | 34368.67 | 9260 | 43.68% | 29619 | 38879 | 53.14% | 0 |  | 38796.33 | 53.03% | 38796.33 | 53.03% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 890524 - EXXONMOBIL REFINING & MARKETING DIV EMC | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-05-31 | 1900-01-01 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 908177¦¦2020-03-31
FP | C | Yes | 908659 |  | 49534 JONESBORO CWL MEDALLION | BURGE, EVERETT E. | 100% | 269477 | 0 | 269477 | 274454.4 | 274454.4 | 85326.6 | 0 | 0 | 274454.4 | 204197 | 0 | 204197 | [7 empty] | 223910.07 | 85602.11 | 14890.56 |  | 118944.4 | 4473 |  | 50544.33 | 0 | 109.7% |  | 0 | 223910.07 | 65280 | 24.22% | 0 | 65280 | 24.22% | 0 |  | 50544.33 | 18.42% | 50544.33 | 18.42% | -4977.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892917 - JONESBORO, CITY WATER & LIGHT | WATER | WATER REPAIR & INSTALLATION | 2018-04-18 | 2019-02-22 | 2018-04-18 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 908659¦¦2020-03-31
TM | C | Yes | 908669 |  | 51756 ELEVATOR WARRANTY | BRANHAM, DAVID W. | 100% | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  | 5000 | 0 | 5000 | 0 |  |  |  | 0 |  |  | 28250.48 | 21307.34 | 9325.83 |  | -59071.85 | 56689.16 |  | 0 | 28250.48 | 565% |  | 0 | 28250.48 | -4999 | -499900% | 0 | -4999 | -499900% | 0 |  | -28250.48 |  | -28250.48 |  | 1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 908718 - LAYNE CHRISTENSEN HOUSTON, TX | WATER | WATER REPAIR & INSTALLATION | 2018-11-14 | 2019-03-29 | 2018-11-14 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 908669¦¦2020-03-31
TM | C | Yes | 908693 |  | 52624 PECO FOODS POCAHONTAS MO | BURGE, EVERETT E. | 100% | 5000 | 0 | 5000 | 46031.76 | 46031.76 | 44887.3 | 0 | 0 | 46031.76 | 3750 | 0 | 3750 | 0 |  |  |  | 0 |  |  | 33524.16 | 11721.76 | 2333.83 |  | 19468.57 |  |  | 12507.6 | 0 | 894% |  | 0 | 33524.16 | 1250 | 25% | 0 | 1250 | 25% | 0 |  | 12507.6 | 27.17% | 12507.6 | 27.17% | -41031.76 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 896164 - PECO FOODS, INC | WATER | WATER EQUIPMENT SALES | 2019-03-13 | 2019-06-14 | 2019-03-13 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 908693¦¦2020-03-31
FP | CJ | Yes | 908705 |  | 52965 LEITCHFIELD KY WTP | MIGUEL, SEAN J. | 100% | 481410 | 0 | 481410 | 10321.89 | 10321.89 | 0 | 0 | 0 | 10321.89 | 346615 | 0 | 346615 | [7 empty] | 8339 |  |  |  | 8339 |  |  | 1982.89 | 0 | 2.406% |  | 0 | 8339 | 134795 | 28% | 0 | 134795 | 28% | 0 |  | 1982.89 | 19.21% | 1982.89 | 19.21% | 471088.11 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878630 - SMITH CONTRACTORS INC | WATER | WATER REPAIR & INSTALLATION | 2019-04-17 | 2020-01-30 | 2019-04-17 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 908705¦¦2020-03-31
FP | C | Yes | 908711 |  | 53028 BRANTLEY FARMING CO WS | BENNETT, MARK C. | 100% | 24000 | 59000 | 83000 | 118364.73 | 118364.73 | 118642.95 | 0 | 0 | 118364.73 | 18000 | 31433.1 | 49433.1 | 27698.53 | 6746.9 | 8032.39 |  | 12919.24 |  |  | 150109.03 | 39719.22 | 22427.9 |  | 87961.91 |  |  | 0 | 31744.3 | 303.7% |  | 0 | 150109.03 | 6000 | 25% | 27566.9 | 33566.9 | 40.44% | 0 |  | -31744.3 | -26.82% | -31744.3 | -26.82% | -35364.73 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878621 - BRANTLEY FARMING COMPANY | WATER | WATER SUPPLY | 2019-04-24 | 2020-04-24 | 2019-04-24 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 908711¦¦2020-03-31
UP | C | Yes | 908712 |  | 53030 53030 SPRING VALLEY CONT | BARNES, MATTHEW D | 100% | 4890 | 0 | 4890 | 4890 | 4890 | 4890 | 0 | 0 | 4890 | 2934 | 0 | 2934 | [7 empty] | 3142.71 | 1372.41 | 251.65 |  | 1518.65 |  |  | 1747.29 | 0 | 107.1% |  | 0 | 3142.71 | 1956 | 40% | 0 | 1956 | 40% | 0 |  | 1747.29 | 35.73% | 1747.29 | 35.73% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 906393 - SPRING VALLEY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-05 | 2019-05-09 | 2019-05-05 | 1900-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 908712¦¦2020-03-31
TM | C | Yes | 908714 |  | 53047 SBC CALICO RO UNLOAD & I | BRASHEAR, DAVID M | 100% | 36670 | 38718.51 | 75388.51 | 72477.65 | 72477.65 | 74246.05 | 0 | 0 | 72477.65 | 21438 | 28967.16 | 50405.16 | [7 empty] | 77016.66 | 31730.68 | 7363.37 |  | 37922.61 |  |  | 0 | 4539.01 | 152.8% |  | 0 | 77016.66 | 15232 | 41.54% | 9751.35 | 24983.35 | 33.14% | 0 |  | -4539.01 | -6.263% | -4539.01 | -6.263% | 2910.86 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878787 - SAN BERNARDINO SPECIAL DISTRICT COUNTY | WATER | WATER TREATMENT | 2019-02-04 | 2019-02-08 | 2019-02-04 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 908714¦¦2020-03-31
TM | C | Yes | 908715 |  | 53049 SAN JACINTO BATH WELL | BRASHEAR, DAVID M | 100% | 8982 | 0 | 8982 | 9782.26 | 9782.26 | 9782.26 | 0 | 0 | 9782.26 | 6749 | 0 | 6749 | 1161.6 | 787.96 |  |  | 373.64 |  |  | 11041.06 | 5644.57 | 1406.88 |  | 3239.61 | 750 |  | 0 | 1258.8 | 163.6% |  | 0 | 11041.06 | 2233 | 24.86% | 0 | 2233 | 24.86% | 0 |  | -1258.8 | -12.87% | -1258.8 | -12.87% | -800.26 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878729 - SAN JACINTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-04-25 | 2019-06-30 | 2019-04-25 | 1900-01-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 908715¦¦2020-03-31
TM | CJ | Yes | 909034 |  | CATHOLIC CEMETARIES | RANFT, DONALD R | 100% | 250 | 0 | 250 | 2810 | 2810 | 2810 | 0 | 0 | 2810 | 156 | 0 | 156 | 226.8 | 151.58 | 29.32 |  | 45.9 |  |  | 3133.28 | 1793.43 | 381.16 |  | 958.69 |  |  | 0 | 323.28 | 2009% |  | 0 | 3133.28 | 94 | 37.6% | 0 | 94 | 37.6% | 0 |  | -323.28 | -11.5% | -323.28 | -11.5% | -2560 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 888044 - CATHOLIC CEMETERIES | WATER | WATER REPAIR & INSTALLATION | 2019-05-03 | 2019-05-30 | 2019-05-03 | 2019-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 909034¦¦2020-03-31
CR | CJ | Yes | 909046 |  | MORGANFIELD GOLF-DUININCK WELL | ALBARADO, JORDAN A | 100% | 298500 | 0 | 298500 | 298500 | 298500 | 298500 | 0 | 0 | 298500 | 201488 | 0 | 201488 | [7 empty] | 244060.06 | 87040.74 | 60378.1 |  | 87727.61 | 8913.61 |  | 54439.94 | 0 | 121.1% |  | 0 | 244060.06 | 97012 | 32.5% | 0 | 97012 | 32.5% | 0 |  | 54439.94 | 18.24% | 54439.94 | 18.24% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 889824 - DUININCK BROTHERS GOLF, INC | WATER | WATER SUPPLY | 2019-05-03 | 2019-05-31 | 2019-05-03 | 2019-05-31 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 909046¦¦2020-03-31
CR | C | Yes | 909048 |  | LA PEDRERA SUB PULL | NARWOLD, TIMOTHY L. | 100% | 10502.01 | 3287.52 | 13789.53 | 13729.84 | 13729.84 | 13848.71 | 0 | 0 | 13729.84 | 7812.35 | 1965.94 | 9778.29 | [7 empty] | 9098.36 | 2896.07 | 859.43 |  | 5342.86 |  |  | 4631.48 | 0 | 93.05% |  | 0 | 9098.36 | 2689.66 | 25.61% | 1321.58 | 4011.24 | 29.09% | 0 |  | 4631.48 | 33.73% | 4631.48 | 33.73% | 59.69 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 933894 - LA PEDRERA LLC | WATER | WATER REPAIR & INSTALLATION | 2019-05-02 | 2019-05-31 | 2019-05-02 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 909048¦¦2020-03-31
TM | C | Yes | 909052 |  | WOOD CREEK HSP 3 | MIGUEL, SEAN J. | 100% | 5000 | 8945 | 13945 | 14609 | 14609 | 14609 | 0 | 0 | 14609 | 3500 | 6711 | 10211 | [7 empty] | 10256.07 | 4179.11 | 1073.13 |  | 4297.78 | 706.05 |  | 4352.93 | 0 | 100.4% |  | 0 | 10256.07 | 1500 | 30% | 2234 | 3734 | 26.78% | 0 |  | 4352.93 | 29.8% | 4352.93 | 29.8% | -664 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 900468 - WOOD CREEK WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-05-03 | 2019-06-28 | 2019-05-03 | 2019-06-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 909052¦¦2020-03-31
CR | C | Yes | 909056 |  | SCOTTSBURG PMS | MIGUEL, SEAN J. | 100% | 714 | 0 | 714 | 714 | 714 | 714 | 0 | 0 | 714 | 506 | 0 | 506 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 713.99 | 0 | 0.001976% |  | 0 | 0.01 | 208 | 29.13% | 0 | 208 | 29.13% | 0 |  | 713.99 | 100% | 713.99 | 100% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 897619 - SCOTTSBURG, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-03 | 2019-05-31 | 2019-05-03 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 909056¦¦2020-03-31
CR | CJ | Yes | 909057 |  | WELL 33 AIRLINE REPLACEMENT | PARSLEY, TRISTAN S |  | 4298 | 0 | 4298 |  |  | 0 | 0 | 0 |  | 1498 | 0 | 1498 | [20 empty] | 2800 | 65.15% | 0 | 2800 | 65.15% | 0 | [5 empty] | 4298 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 879056 - INTERNATIONAL PAPER CANTONMENT | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-05-31 | 2019-05-02 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 909057¦¦2020-03-31
CR | C | Yes | 909062 |  | RICHARD GREY PULL AND INSPECT | GRACE, GARY L. | 100% | 7560.08 | 0 | 7560.08 | 81244.12 | 81244.12 | 83851.67 | 0 | 0 | 81244.12 | 5738.55 | 0 | 5738.55 | [7 empty] | 59166.03 | 18645.1 | 6239.34 |  | 34281.59 |  |  | 22078.09 | 0 | 1031% |  | 0 | 59166.03 | 1821.53 | 24.09% | 0 | 1821.53 | 24.09% | 0 |  | 22078.09 | 27.18% | 22078.09 | 27.18% | -73684.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 919325 - GREY, RICHARD | WATER | WATER REPAIR & INSTALLATION | 2019-04-29 | 2019-05-31 | 2019-04-29 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 909062¦¦2020-03-31
CR | C | Yes | 909487 |  | CARAUSTAR PULL INSPECT VIDEO | GRACE, GARY L. | 100% | 9855 | 69752.79 | 79607.79 | 101578.62 | 101578.62 | 104680.92 | 0 | 0 | 101578.62 | 7290.69 | 48625.29 | 55915.98 | -0.01 |  |  |  | -0.01 |  |  | 90920.33 | 20236.42 | 8478.61 |  | 59756.99 | 2448.31 |  | 10658.29 | 0 | 162.6% |  | 0 | 90920.33 | 2564.31 | 26.02% | 21127.5 | 23691.81 | 29.76% | 0 |  | 10658.29 | 10.49% | 10658.29 | 10.49% | -21970.83 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 937528 - CSAR MILL LOS ANGELES | WATER | WATER REPAIR & INSTALLATION | 2019-04-30 | 2019-05-31 | 1900-01-01 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 909487¦¦2020-03-31
FP | C | Yes | 909857 |  | OMU - WELL REHABS | MIGUEL, SEAN J. | 100% | 52875 | 29416 | 82291 | 82291 | 82291 | 82291 | 0 | 0 | 82291 | 39656 | 23341 | 62997 | [7 empty] | 116415.92 | 33734.13 | 28516.23 |  | 54165.56 |  |  | 0 | 34124.92 | 184.8% |  | 0 | 116415.92 | 13219 | 25% | 6075 | 19294 | 23.45% | 0 |  | -34124.92 | -41.47% | -34124.92 | -41.47% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895920 - OWENSBORO MUNICIPAL UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-06-30 | 2019-04-30 | 2019-06-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 909857¦¦2020-03-31
FP | C | Yes | 909917 |  | EVANSVILLE PHASE 3 | GAMBLE, BRAD F. | 100% | 18130 | 0 | 18130 | 24829 | 24829 | 24829 | 0 | 0 | 24829 | 11900 | 0 | 11900 | [7 empty] | 13597.05 | 11117.32 |  |  | 1987.73 | 492 |  | 11231.95 | 0 | 114.3% |  | 0 | 13597.05 | 6230 | 34.36% | 0 | 6230 | 34.36% | 0 |  | 11231.95 | 45.24% | 11231.95 | 45.24% | -6699 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 892161 - HNTB CORPORATION | WATER | WATER SUPPLY | 2019-05-09 | 2019-05-08 | 2019-05-13 | 2019-09-30 | SUBCONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 909917¦¦2020-03-31
TM | C | Yes | 910395 |  | LA CUMBRE WELL 21 PULL REPLACE | NARWOLD, TIMOTHY L. | 100% | 6357.66 | 38930.56 | 45288.22 | 45903.02 | 45903.02 | 47646.2 | 0 | 0 | 45903.02 | 5217.32 | 27314.96 | 32532.28 | [7 empty] | 33530.43 | 9858.87 | 3439.75 |  | 20231.81 |  |  | 12372.59 | 0 | 103.1% |  | 0 | 33530.43 | 1140.34 | 17.94% | 11615.6 | 12755.94 | 28.17% | 0 |  | 12372.59 | 26.95% | 12372.59 | 26.95% | -614.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879040 - LA CUMBRE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-05-07 | 2019-05-31 | 2019-05-07 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 910395¦¦2020-03-31
UP | C | Yes | 910400 |  | TXB WC WATER SAMPLING | LOPEZ-VASQUEZ, JUAN C. | 100% | 2200 | 0 | 2200 | 2700 | 2700 | 2700 | 0 | 0 | 2700 | 1268 | 0 | 1268 | [7 empty] | 1224.36 | 424.24 | 193.33 |  | 193.79 | 413 |  | 1475.64 | 0 | 96.56% |  | 0 | 1224.36 | 932 | 42.36% | 0 | 932 | 42.36% | 0 |  | 1475.64 | 54.65% | 1475.64 | 54.65% | -500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878775 - TEXAS BRINE WHITE CASTLE COMPANY LLC | WATER | WATER SUPPLY | 2019-05-07 | 2019-05-31 | 2019-05-07 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 910400¦¦2020-03-31
FP | CJ | Yes | 910972 |  | XCEL ENERGY WELL 5 | OMAN, TIMOTHY S. | 100% | 13945 | 0 | 13945 | 17445 | 17445 | 17445 | 0 | 0 | 17445 | 7484 | 0 | 7484 | 5795.15 | 2962.9 | 1060.92 |  | 1771.33 |  |  | 11753.29 | 4443.98 | 2186.78 |  | 5122.53 |  |  | 5691.71 | 0 | 157% |  | 0 | 11753.29 | 6461 | 46.33% | 0 | 6461 | 46.33% | 0 |  | 5691.71 | 32.63% | 5691.71 | 32.63% | -3500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 900557 - XCEL ENERGY | WATER | WATER SUPPLY | 2019-05-01 | 2019-05-31 | 2019-05-01 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 910972¦¦2020-03-31
TM | C | Yes | 910978 |  | LIBERTY HILLS GC MO WELL 1 | WARTICK, LOGAN M | 100% | 2352 | 0 | 2352 | 2352 | 2352 | 2352 | 2352 | 0 | 2352 | 1999 | 0 | 1999 | [7 empty] | 2526.9 | 1408.37 | 406 |  | 712.53 |  |  | 0 | 174.9 | 126.4% |  | 0 | 2526.9 | 353 | 15.01% | 0 | 353 | 15.01% | 0 |  | -174.9 | -7.436% | -174.9 | -7.436% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 893725 - LIBERTY HILLS COUNTRY CLUB | WATER | WATER REPAIR & INSTALLATION | 2019-05-09 | 2019-05-31 | 2019-04-26 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 910978¦¦2020-03-31
TM | C | Yes | 911022 |  | DARDANELLE WATER | SCHERM, LOGAN M | 100% | 7000 | 0 | 7000 | 20203.77 | 20203.77 | 22299.92 | 0 | 0 | 20203.77 | 4900 | 0 | 4900 | [7 empty] | 18422.34 | 4201.97 | 2295.12 |  | 11925.25 |  |  | 1781.43 | 0 | 376% |  | 0 | 18422.34 | 2100 | 30% | 0 | 2100 | 30% | 0 |  | 1781.43 | 8.817% | 1781.43 | 8.817% | -13203.77 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879083 - DARDANELLE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-08 | 2019-05-31 | 2019-05-08 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 911022¦¦2020-03-31
TM | C | Yes | 911185 |  | JURUPA WELL 42 | SEIDEN, ANDREW L. | 100% | 12229 | 0 | 12229 | 15333.35 | 15333.35 | 15333.35 | 0 | 0 | 15333.35 | 7993.33 | 0 | 7993.33 | [7 empty] | 17874.71 | 6289.18 | 704.41 |  | 10881.12 |  |  | 0 | 2541.36 | 223.6% |  | 0 | 17874.71 | 4235.67 | 34.64% | 0 | 4235.67 | 34.64% | 0 |  | -2541.36 | -16.57% | -2541.36 | -16.57% | -3104.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892972 - JURUPA COMMUNITY SERVICES DIST | WATER | WATER SUPPLY | 2019-05-01 | 2019-05-31 | 2019-05-01 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 911185¦¦2020-03-31
TM | C | Yes | 911358 |  | HI SPEED INDUSTRIAL | SCHERM, LOGAN M | 100% | 2500 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 2500 | 1800 | 0 | 1800 | [7 empty] | 2765.12 | 1502.33 |  |  | 1262.79 |  |  | 0 | 265.12 | 153.6% |  | 0 | 2765.12 | 700 | 28% | 0 | 700 | 28% | 0 |  | -265.12 | -10.6% | -265.12 | -10.6% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892150 - HI SPEED INDUSTRIAL SERVICE | WATER | WATER REPAIR & INSTALLATION | 2019-05-10 | 2019-05-31 | 2019-05-10 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 911358¦¦2020-03-31
TM | CJ | Yes | 911372 |  | POLAND TWO NEW WELLS | ALBARADO, JORDAN A | 100% | 475000 | 0 | 475000 | 317488.46 | 317488.46 | 0 | 0 | 0 | 317488.46 | 373827.64 | 0 | 373827.64 | 0.13 |  |  |  | 0.13 |  |  | 256497.19 | 110235.05 | 68170.44 |  | 77060 | 1031.7 |  | 60991.27 | 0 | 68.61% |  | 0 | 256497.19 | 101172.36 | 21.3% | 0 | 101172.36 | 21.3% | 0 |  | 60991.27 | 19.21% | 60991.27 | 19.21% | 157511.54 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 910215 - MEYER MEYER LACROIX AND HIXSON INC | WATER | WATER SUPPLY | 2019-05-01 | 2019-05-31 | 2019-05-01 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 911372¦¦2020-03-31
TM | C | Yes | 911376 |  | RIPLEY TN PWM TESTING | ANDERSON, STEPHEN P. | 100% | 2500 | 0 | 2500 | 2000 | 2000 | 2000 | 0 | 0 | 2000 | 2375 | 0 | 2375 | 4086.48 | 2160.92 | 185.5 |  | 1740.06 |  |  | 7691.29 | 3974.12 | 845.5 |  | 2871.67 |  |  | 0 | 5691.29 | 323.8% |  | 0 | 7691.29 | 125 | 5% | 0 | 125 | 5% | 0 |  | -5691.29 | -284.6% | -5691.29 | -284.6% | 500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 897057 - RIPLEY WATER & GAS | WATER | WATER REPAIR & INSTALLATION | 2019-05-03 | 2019-05-31 | 2019-05-03 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 911376¦¦2020-03-31
TM | C | Yes | 911377 |  | PICKENS MS PWM TESTING | ANDERSON, STEPHEN P. | 100% | 713 | 0 | 713 | 712.5 | 712.5 | 712.5 | 0 | 0 | 712.5 | 677 | 0 | 677 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 712.49 | 0 | 0.001477% |  | 0 | 0.01 | 36 | 5.049% | 0 | 36 | 5.049% | 0 |  | 712.49 | 100% | 712.49 | 100% | 0.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 896301 - PICKENS, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-03 | 2019-05-31 | 2019-05-03 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 911377¦¦2020-03-31
TM | C | Yes | 911420 |  | FMI SAFFORD PUMP INTAKE | VAN ALLEN, WESLEY C. | 100% | 19361.19 | 0 | 19361.19 | 19361.19 | 19361.19 | 19361.19 | 0 | 0 | 19361.19 | 12972 | 0 | 12972 | [7 empty] | 12972 |  |  |  | 12972 |  |  | 6389.19 | 0 | 100% |  | 0 | 12972 | 6389.19 | 33% | 0 | 6389.19 | 33% | 0 |  | 6389.19 | 33% | 6389.19 | 33% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878738 - FREEPORT MCMORAN SAFFORD OPERATIONS | WATER | WATER EQUIPMENT SALES | 2019-05-09 | 2019-05-31 | 2019-05-09 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 911420¦¦2020-03-31
TM | CJ | Yes | 911421 |  | EXXON 78 TV SURVEY | GNAU, CASEY T | 100% | 23550 | 0 | 23550 | 23550 | 23550 | 23550 | 0 | 0 | 23550 | 15747 | 0 | 15747 | [7 empty] | 9486.04 | 3622.59 | 3151.5 |  | 2711.95 |  |  | 14063.96 | 0 | 60.24% |  | 0 | 9486.04 | 7803 | 33.13% | 0 | 7803 | 33.13% | 0 |  | 14063.96 | 59.72% | 14063.96 | 59.72% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 890523 - EXXONMOBIL REFINING & MARKETING | WATER | WATER REPAIR & INSTALLATION | 2019-05-10 | 2019-05-31 | 2019-05-10 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 911421¦¦2020-03-31
FP | C | Yes | 911449 |  | RANNEY WESTROCK | BARNES, MATTHEW D | 100% | 33984 | 4108 | 38092 | 38092 | 38092 | 38092 | 0 | 0 | 38092 | 22089 | 2809 | 24898 | 0.18 | 0.18 | [5 empty] | 27460.37 | 9936.8 | 7605.63 |  | 9917.94 |  |  | 10631.63 | 0 | 110.3% |  | 0 | 27460.37 | 11895 | 35% | 1299 | 13194 | 34.64% | 0 |  | 10631.63 | 27.91% | 10631.63 | 27.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878769 - WESTROCK CORP | WATER | WATER REPAIR & INSTALLATION | 2019-05-10 | 2019-06-30 | 2019-05-13 | 2019-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 911449¦¦2020-03-31
TM | C | Yes | 911528 |  | PHILLIPS 66 WELL 11 | GNAU, CASEY T | 100% | 23100 | 60354 | 83454 | 83454 | 83454 | 83454 | 0 | 0 | 83454 | 11525 | 32683 | 44208 | 0 |  |  |  | 0 |  |  | 48075.62 | 12755.15 | 3646.17 |  | 31274.3 | 400 |  | 35378.38 | 0 | 108.7% |  | 0 | 48075.62 | 11575 | 50.11% | 27671 | 39246 | 47.03% | 0 |  | 35378.38 | 42.39% | 35378.38 | 42.39% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 530545 - PHILLIPS 66 COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-05-10 | 2019-05-31 | 2019-05-10 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 911528¦¦2020-03-31
TM | CJ | Yes | 911530 |  | PCA DERIDDER WELL 12 | ALBARADO, JORDAN A | 100% | 25000 | 14025.3 | 39025.3 | 39025.3 | 39025.3 | 39025.3 | 0 | 0 | 39025.3 | 12500 | 7012.65 | 19512.65 | 326.1 |  |  |  | 0 | 326.1 |  | 10242.76 | 7119.54 | 263.7 |  | 2533.42 | 326.1 |  | 28782.54 | 0 | 52.49% |  | 0 | 10242.76 | 12500 | 50% | 7012.65 | 19512.65 | 50% | 0 |  | 28782.54 | 73.75% | 28782.54 | 73.75% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895966 - PACKAGING CORPORATION OF AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-05-14 | 2019-05-31 | 2019-05-14 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 911530¦¦2020-03-31
TM | C | Yes | 911534 |  | TYSON FRESH MEATS PERRY IOWA | HEILIGER, TERENCE L. | 100% | 16000 | 88442.5 | 104442.5 | 104442.5 | 104442.5 | 104442.5 | 0 | 0 | 104442.5 | 10301 | 76326.03 | 86627.03 | -11990 |  |  |  | -11990 |  |  | 76567.37 | 22496.14 | 4998.15 |  | 49073.08 |  |  | 27875.13 | 0 | 88.39% |  | 0 | 76567.37 | 5699 | 35.62% | 12116.47 | 17815.47 | 17.06% | 0 |  | 27875.13 | 26.69% | 27875.13 | 26.69% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 899269 - TYSON FRESH MEATS PERRY | WATER | WATER REPAIR & INSTALLATION | 2019-05-14 | 2019-05-31 | 2019-05-14 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 911534¦¦2020-03-31
TM | CJ | Yes | 911748 |  | FAYETTE MS WELL WORK | ANDERSON, STEPHEN P. | 100% | 440159 | -229307 | 210852 | 210852 | 210852 | 200379 | 0 | 20037.9 | 210852 | 346048 | -147048.7 | 198999.3 | 441.21 |  |  |  | 441.21 |  |  | 222204.73 | 47639.46 | 17789.8 |  | 156300.87 | 474.6 |  | 0 | 11352.73 | 111.7% |  | 0 | 222204.73 | 94111 | 21.38% | -82258.3 | 11852.7 | 5.621% | 0 |  | -11352.73 | -5.384% | -11352.73 | -5.384% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 911567 - FAYETTE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-05-31 | 2019-05-01 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 911748¦¦2020-03-31
TM | C | Yes | 911750 |  | HIGHLAND VILLAGE REHAB HS | CALLAHAN, DANIEL E. | 100% | 320030 | 0 | 320030 | 207710 | 207710 | 207710 | 0 | 0 | 207710 | 270500 | 0 | 270500 | 0 |  |  |  | 0 |  |  | 166570.18 | 29332.7 | 16445.63 | 3900 | 113243.1 | 3648.75 |  | 41139.82 | 0 | 61.58% |  | 0 | 166570.18 | 49530 | 15.48% | 0 | 49530 | 15.48% | 0 |  | 41139.82 | 19.81% | 41139.82 | 19.81% | 112320 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 892093 - HIGHLAND VILLAGE, TX, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-09 | 2019-05-31 | 2019-05-09 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 911750¦¦2020-03-31
TM | C | Yes | 912462 |  | CANYON RV PARK | SEIDEN, ANDREW L. | 100% | 7272.62 | 17538.14 | 24810.76 | 24810.53 | 24810.53 | 25469.28 | 0 | 0 | 24810.53 | 5293 | 13518.13 | 18811.13 | [7 empty] | 21862.85 | 7198.45 | 742.98 |  | 13921.42 |  |  | 2947.68 | 0 | 116.2% |  | 0 | 21862.85 | 1979.62 | 27.22% | 4020.01 | 5999.63 | 24.18% | 0 |  | 2947.68 | 11.88% | 2947.68 | 11.88% | 0.23 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887896 - CANYON RV PARK | WATER | WATER REPAIR & INSTALLATION | 2019-05-16 | 2019-05-31 | 2019-05-16 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 912462¦¦2020-03-31
TM | C | Yes | 912465 |  | WELL 13 SILVER LAKES | BRASHEAR, DAVID M | 100% | 6870.54 | 70025.77 | 76896.31 | 79896.35 | 79896.35 | 83315.42 | 0 | 0 | 79896.35 | 4905 | 60367.33 | 65272.33 | [7 empty] | 62564.3 | 8059.23 | 2302 |  | 42703.07 | 9500 |  | 17332.05 | 0 | 95.85% |  | 0 | 62564.3 | 1965.54 | 28.61% | 9658.44 | 11623.98 | 15.12% | 0 |  | 17332.05 | 21.69% | 17332.05 | 21.69% | -3000.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878805 - SILVER LAKES ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2019-05-15 | 2019-05-31 | 2019-05-15 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 912465¦¦2020-03-31
TM | C | Yes | 912466 |  | WELL 15 MOTOR AND BOWL | BRASHEAR, DAVID M | 100% | 33688.49 | 0 | 33688.49 | 31322.97 | 31322.97 | 33688.5 | 0 | 0 | 31322.97 | 24818 | 0 | 24818 | [7 empty] | 26385.91 | 61.21 |  |  | 26324.7 |  |  | 4937.06 | 0 | 106.3% |  | 0 | 26385.91 | 8870.49 | 26.33% | 0 | 8870.49 | 26.33% | 0 |  | 4937.06 | 15.76% | 4937.06 | 15.76% | 2365.52 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 888536 - CITY OF NEEDLES | WATER | WATER EQUIPMENT SALES | 2019-05-15 | 2019-05-31 | 2019-05-15 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 912466¦¦2020-03-31
FP | CJ | Yes | 912469 |  | PHILLIPS 66 NP 5 TREATMENTS | WHITE, CATHLEEN R | 100% | 161250 | 0 | 161250 | 140872.14 | 140872.14 | 96750 | 0 | 0 | 140872.14 | 112875 | 0 | 112875 | 0.06 |  |  |  | 0.06 |  |  | 113809.83 | 55564.97 | 13170.76 |  | 45074.1 |  |  | 27062.31 | 0 | 100.8% |  | 0 | 113809.83 | 48375 | 30% | 0 | 48375 | 30% | 0 |  | 27062.31 | 19.21% | 27062.31 | 19.21% | 20377.86 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878946 - PHILLIPS 66 WOOD RIVER REFINERY | WATER | WATER REPAIR & INSTALLATION | 2019-05-16 | 2019-06-28 | 2019-05-16 | 2019-06-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 912469¦¦2020-03-31
TM | LJ | Yes | 912493 |  | KIEWIT 3 NEW WELLS | ALBARADO, JORDAN A | 76.85% | 1257101 | 101250 | 1358351 | 1043928.1054 | 779811.15 | 779811.15 | 701830.03 | 77981.12 | 1358351.12 | 997310.95 | 60135 | 1057445.95 | 17744.43 | 5788.13 | 598.84 |  | 7357.46 | 4000 |  | 788147.97 | 244251.27 | 266302.8 | 67.77 | 261526.13 | 16000 |  | 0 | 8336.82 | 74.53% | 0 | 237384.03 | 1025532 | 259790.05 | 20.67% | 41115 | 300905.05 | 22.15% | 0 |  | 255780.14 | 24.5% | 332819.12 | 24.5% | 314422.89 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 893134 - KIEWIT | WATER | WATER SUPPLY | 2019-05-09 | 2019-06-30 | 2019-05-09 | 2019-06-30 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 912493¦¦2020-03-31
TM | CJ | Yes | 913385 |  | PCA DERIDDER WELL 23 | ALBARADO, JORDAN A | 100% | 25000 | 114423.93 | 139423.93 | 139422.93 | 139422.93 | 139422.93 | 0 | 0 | 139422.93 | 12500 | 57211.97 | 69711.97 | 0 |  |  |  | 0 |  |  | 69597.02 | 16001.5 | 2573.03 |  | 50296.39 | 726.1 |  | 69825.91 | 0 | 99.84% |  | 0 | 69597.02 | 12500 | 50% | 57211.96 | 69711.96 | 50% | 0 |  | 69825.91 | 50.08% | 69825.91 | 50.08% | 1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895966 - PACKAGING CORPORATION OF AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-05-15 | 2019-05-31 | 2019-05-15 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 913385¦¦2020-03-31
TM | CJ | Yes | 913389 |  | HORSESHOE 11 P AND A | RICHARDSON, DARA | 100% | 3512 | 0 | 3512 | 6962 | 6962 | 7536.37 | 0 | 0 | 6962 | 2458 | 0 | 2458 | [7 empty] | 2607.96 | 2604.55 |  |  | 3.41 |  |  | 4354.04 | 0 | 106.1% |  | 0 | 2607.96 | 1054 | 30.01% | 0 | 1054 | 30.01% | 0 |  | 4354.04 | 62.54% | 4354.04 | 62.54% | -3450 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 866 - WRD MIDLAND | MIDLAND - WA | 887074 - BHP BILLITON | WATER | WATER SUPPLY | 2019-05-01 | 2019-05-31 | 2019-05-01 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 913389¦¦2020-03-31
FP | C | Yes | 913390 |  | GRANDVIEW NEW WELL | WILLIAMS, DONALD G. | 100% | 260589 | -26081 | 234508 | 235118 | 235118 | 235118 | 0 | 0 | 235118 | 229400 | -26081 | 203319 | 735.38 |  |  |  | 735.38 |  |  | 221239.47 | 61268.9 | 21886.57 |  | 92326.09 | 45757.91 |  | 13878.53 | 0 | 108.8% |  | 0 | 221239.47 | 31189 | 11.97% | 0 | 31189 | 13.3% | 0 |  | 13878.53 | 5.903% | 13878.53 | 5.903% | -610 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 891500 - GRANDVIEW, TOWN OF | WATER | WATER SUPPLY | 2019-05-02 | 2019-10-31 | 2019-05-17 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 913390¦¦2020-03-31
TM | C | Yes | 913394 |  | SAN BERNARDINO RIXES DISCHARGE | SEIDEN, ANDREW L. | 100% | 47508 | 0 | 47508 | 47508 | 47508 | 47508 | 0 | 0 | 47508 | 40719 | 0 | 40719 | [7 empty] | 34150.1 | 16810.73 | 5024.26 |  | 12315.11 |  |  | 13357.9 | 0 | 83.87% |  | 0 | 34150.1 | 6789 | 14.29% | 0 | 6789 | 14.29% | 0 |  | 13357.9 | 28.12% | 13357.9 | 28.12% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878706 - SAN BERNARDINO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-14 | 2019-05-31 | 2019-05-14 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 913394¦¦2020-03-31
TM | C | Yes | 913660 |  | RCWD SENGA BOOSTER | BRASHEAR, DAVID M | 100% | 34981 | 0 | 34981 | 34987.74 | 34987.74 | 37934.98 | 0 | 0 | 34987.74 | 28159 | 0 | 28159 | [7 empty] | 29316.28 | 1017.11 |  |  | 28299.17 |  |  | 5671.46 | 0 | 104.1% |  | 0 | 29316.28 | 6822 | 19.5% | 0 | 6822 | 19.5% | 0 |  | 5671.46 | 16.21% | 5671.46 | 16.21% | -6.74 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878683 - RANCHO CALIFORNIA WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-05-21 | 2019-06-28 | 2019-05-21 | 2019-06-28 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 913660¦¦2020-03-31
TM | C | Yes | 913664 |  | BOYS REPUBLIC WELL PUMP | SEIDEN, ANDREW L. | 100% | 4655 | 0 | 4655 | 35864 | 35864 | 36996.98 | 0 | 0 | 35864 | 4028 | 0 | 4028 | 0 |  |  |  | 0 |  |  | 30037.04 | 9760.06 | 1116.66 |  | 19160.32 |  |  | 5826.96 | 0 | 745.7% |  | 0 | 30037.04 | 627 | 13.47% | 0 | 627 | 13.47% | 0 |  | 5826.96 | 16.25% | 5826.96 | 16.25% | -31209 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887335 - BOYS REPUBLIC | WATER | WATER REPAIR & INSTALLATION | 2019-05-13 | 2019-05-31 | 2019-05-13 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 913664¦¦2020-03-31
TM | C | Yes | 913825 | 913825 | ELEVATION MIDSTREAM WELL | DECKER, JASEN | 100% | 67247 | 0 | 67247 | 90005.05 | 90005.05 | 90005.05 | 0 | 0 | 90005.05 | 52169 | 0 | 52169 | [7 empty] | 11049.43 | 2815.43 | 349.8 |  | 6209.2 | 1675 |  | 78955.62 | 0 | 21.18% |  | 0 | 11049.43 | 15078 | 22.42% | 0 | 15078 | 22.42% | 0 |  | 78955.62 | 87.72% | 78955.62 | 87.72% | -22758.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 948805 - ELEVATION MIDSTREAM LLC | WATER | WATER REPAIR & INSTALLATION | 2019-05-22 | 2019-06-30 | 2019-05-22 | 2019-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 913825¦¦2020-03-31
TM | C | Yes | 913826 | 913825 | ELEVATION MIDSTREAM TEST | DECKER, JASEN | 100% | 17862 | 0 | 17862 |  |  | 0 | 0 | 0 |  | 13634 | 0 | 13634 | [7 empty] | 53240.11 | 16429.38 | 18140.4 |  | 16869.38 | 1800.95 |  | 0 | 53240.11 | 390.5% |  | 0 | 53240.11 | 4228 | 23.67% | 0 | 4228 | 23.67% | 0 |  | -53240.11 |  | -53240.11 |  | 17862 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 913576 - TRC SOLUTIONS | WATER | WATER REPAIR & INSTALLATION | 2019-05-22 | 2019-06-30 | 2019-05-22 | 2019-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 913826¦¦2020-03-31
TM | C | Yes | 913827 |  | AVI RESORT AND CASINO | BRASHEAR, DAVID M | 100% | 32027 | 0 | 32027 | 28404.12 | 28404.12 | 28404.12 | 0 | 0 | 28404.12 | 22600 | 0 | 22600 | [7 empty] | 11329.48 | 5699.35 | 364.52 |  | 5265.61 |  |  | 17074.64 | 0 | 50.13% |  | 0 | 11329.48 | 9427 | 29.43% | 0 | 9427 | 29.43% | 0 |  | 17074.64 | 60.11% | 17074.64 | 60.11% | 3622.88 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 886682 - AVI RESORT & CASINO | WATER | WATER REPAIR & INSTALLATION | 2019-05-07 | 2019-05-31 | 2019-05-08 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 913827¦¦2020-03-31
TM | C | Yes | 913828 |  | HESPERIA LAKES WELL 2 SOCCER | BRASHEAR, DAVID M | 100% | 7854 | 0 | 7854 | 7824.94 | 7824.94 | 7980.98 | 0 | 0 | 7824.94 | 5554 | 0 | 5554 | [7 empty] | 3.83 |  |  |  | 3.83 |  |  | 7821.11 | 0 | 0.06896% |  | 0 | 3.83 | 2300 | 29.28% | 0 | 2300 | 29.28% | 0 |  | 7821.11 | 99.95% | 7821.11 | 99.95% | 29.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 913574 - HESPERIA RECREATION AND PARKS DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-05-31 | 2019-05-01 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 913828¦¦2020-03-31
TM | C | Yes | 913830 |  | ASSOCIATED ELECTRIC PR | SCHERM, LOGAN M | 100% | 8665 | 44925 | 53590 | 96425.49 | 96425.49 | 96425.49 | 0 | 0 | 96425.49 | 6865 | 63281.47 | 70146.47 | 7608 |  |  |  | 7608 |  |  | 87779.33 | 31563.21 | 22205.71 |  | 34010.41 |  |  | 8646.16 | 0 | 125.1% |  | 0 | 87779.33 | 1800 | 20.77% | -18356.47 | -16556.47 | -30.89% | 0 |  | 8646.16 | 8.967% | 8646.16 | 8.967% | -42835.49 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 886579 - ASSOCIATED ELECTRIC COOPERATIVE INC | WATER | WATER REPAIR & INSTALLATION | 2019-05-20 | 2019-11-20 | 2019-05-20 | 2019-11-20 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 913830¦¦2020-03-31
TM | C | Yes | 913831 |  | APPLE VALLEY BOOSTER 2 | BRASHEAR, DAVID M | 100% | 1548.95 | 0 | 1548.95 | 4010.93 | 4010.93 | 4057.43 | 0 | 0 | 4010.93 | 1333 | 0 | 1333 | [7 empty] | 3606.22 | 1478.67 | 319.4 |  | 1808.15 |  |  | 404.71 | 0 | 270.5% |  | 0 | 3606.22 | 215.95 | 13.94% | 0 | 215.95 | 13.94% | 0 |  | 404.71 | 10.09% | 404.71 | 10.09% | -2461.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 886362 - APPLE VALLEY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-16 | 2019-05-31 | 2019-05-16 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 913831¦¦2020-03-31
TM | CJ | Yes | 913836 |  | CAL PAR 1 WELL 7 REHAB | ALBARADO, JORDAN A | 100% | 68905 | 0 | 68905 | 98710 | 98710 | 98710 | 0 | 0 | 98710 | 46855 | 0 | 46855 | [7 empty] | 67821.53 | 28890.75 | 9816.07 |  | 28314.71 | 800 |  | 30888.47 | 0 | 144.7% |  | 0 | 67821.53 | 22050 | 32% | 0 | 22050 | 32% | 0 |  | 30888.47 | 31.29% | 30888.47 | 31.29% | -29805 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 887728 - CALCASIEU PARISH WWD 1 | WATER | WATER REPAIR & INSTALLATION | 2019-05-14 | 2019-05-31 | 2019-05-14 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 913836¦¦2020-03-31
TM | CJ | Yes | 913837 |  | WC PLAQ NEW WELL | ALBARADO, JORDAN A | 100% | 325000 | 0 | 325000 | 307989.88 | 307989.88 | 243750 | 0 | 0 | 307989.88 | 195000 | 0 | 195000 | 196.99 |  |  |  | 196.99 |  |  | 248823.34 | 86806.08 | 55207.86 |  | 106809.4 |  |  | 59166.54 | 0 | 127.6% |  | 0 | 248823.34 | 130000 | 40% | 0 | 130000 | 40% | 0 |  | 59166.54 | 19.21% | 59166.54 | 19.21% | 17010.12 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 886694 - AXIALL WESTLAKE PLAQUEMINE | WATER | WATER SUPPLY | 2019-05-22 | 2019-05-31 | 2019-05-22 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 913837¦¦2020-03-31
TM | CJ | Yes | 914211 |  | DESERT CENTER EMERGENCY | TRAMMELL, DUANE R. | 100% | 490000 | 0 | 490000 | 725107.7 | 725107.7 | 725107.7 | 381739.36 | 0 | 725107.7 | 409128 | 0 | 409128 | 52523.65 |  | 1000 |  | 2281.4 | 49242.25 |  | 690893.18 | 200567 | 162841.47 |  | 148901.81 | 178582.9 |  | 34214.52 | 0 | 168.9% |  | 0 | 690893.18 | 80872 | 16.5% | 0 | 80872 | 16.5% | 0 |  | 34214.52 | 4.719% | 34214.52 | 4.719% | -235107.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 891515 - GRANITE CONSTRUCTION INDIO BRANCH | WATER | WATER REPAIR & INSTALLATION | 2019-05-03 | 2019-09-13 | 2019-05-03 | 2019-09-13 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 914211¦¦2020-03-31
TM | C | Yes | 914306 |  | DOMINION WRD TESTING | COMBS, TAYLOR E. | 100% | 27750 | 0 | 27750 | 26414 | 26414 | 26414 | 0 | 0 | 26414 | 20317 | 0 | 20317 | [7 empty] | 20645.66 | 8438.42 | 1343.29 |  | 10764.45 | 99.5 |  | 5768.34 | 0 | 101.6% |  | 0 | 20645.66 | 7433 | 26.79% | 0 | 7433 | 26.79% | 0 |  | 5768.34 | 21.84% | 5768.34 | 21.84% | 1336 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 914110 - DOMINION WATER & SANITATION DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-06-30 | 2019-05-01 | 2019-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 914306¦¦2020-03-31
TM | C | Yes | 914310 |  | IN LIMESTONE PUMP | WILLIAMS, DONALD G. | 100% | 3000 | 45670 | 48670 | 48670 | 48670 | 48670 | 0 | 0 | 48670 | 1950 | 34065 | 36015 | 0 |  |  |  | 0 |  |  | 32876.75 | 4620.74 | 412.77 |  | 27843.24 |  |  | 15793.25 | 0 | 91.29% |  | 0 | 32876.75 | 1050 | 35% | 11605 | 12655 | 26% | 6023 |  | 15793.25 | 32.45% | 15793.25 | 32.45% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 892507 - INDIANA LIMESTONE COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-05-22 | 2019-06-30 | 2019-05-22 | 2019-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 914310¦¦2020-03-31
UP | CJ | Yes | 914313 |  | MSD PREVENTATIVE MAINTENANCE | MIGUEL, SEAN J. | 100% | 100000 | 0 | 100000 | 85898.33 | 85898.33 | 63229 | 0 | 0 | 85898.33 | 65000 | 0 | 65000 | 13620.08 | 4949.69 | 3536.34 |  | 5134.05 |  |  | 69396.79 | 23739.12 | 15056.66 |  | 29561.51 | 1039.5 |  | 16501.54 | 0 | 106.8% |  | 0 | 69396.79 | 35000 | 35% | 0 | 35000 | 35% | 0 |  | 16501.54 | 19.21% | 16501.54 | 19.21% | 14101.67 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 893944 - METROPOLITAN SEWER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-05-23 | 2020-05-20 | 2019-05-23 | 2020-05-20 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 914313¦¦2020-03-31
TM | CJ | Yes | 914690 |  | VANDERBILT PWM TESTING | ANDERSON, STEPHEN P. | 100% | 2750 | 0 | 2750 | 3350 | 3350 | 3350 | 0 | 0 | 3350 | 2340 | 0 | 2340 | [7 empty] | 7069.11 | 3413.76 | 1275.19 |  | 2380.16 |  |  | 0 | 3719.11 | 302.1% |  | 0 | 7069.11 | 410 | 14.91% | 0 | 410 | 14.91% | 0 |  | -3719.11 | -111% | -3719.11 | -111% | -600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 899566 - VANDERBILT CHEMICAL | WATER | WATER REPAIR & INSTALLATION | 2019-05-24 | 2019-05-31 | 2019-05-24 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 914690¦¦2020-03-31
TM | C | Yes | 914691 |  | WALNUT PARK WELL 11 | GRACE, GARY L. | 100% | 10867 | 131167.36 | 142034.36 | 200619.62 | 200619.62 | 202997.42 | 0 | 0 | 200619.62 | 10857 | 98952.98 | 109809.98 | [7 empty] | 180795.13 | 38703.76 | 16882.36 |  | 54380.01 | 70829 |  | 19824.49 | 0 | 164.6% |  | 0 | 180795.13 | 10 | 0.09202% | 32214.38 | 32224.38 | 22.69% | 0 |  | 19824.49 | 9.882% | 19824.49 | 9.882% | -58585.26 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 899811 - WALNUT PARK MUTUAL WATER CO | WATER | WATER REPAIR & INSTALLATION | 2019-05-28 | 2019-05-31 | 2019-05-28 | 2019-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 914691¦¦2020-03-31
TM | C | Yes | 914692 |  | CLECO CAJUN 1 WELL 1 | GNAU, CASEY T | 100% | 18055 | 116065 | 134120 | 134120 | 134120 | 134120 | 0 | 0 | 134120 | 9026 | 74851 | 83877 | [7 empty] | 84082.72 | 30126.54 | 9035.98 |  | 44520.2 | 400 |  | 50037.28 | 0 | 100.2% |  | 0 | 84082.72 | 9029 | 50.01% | 41214 | 50243 | 37.46% | 0 |  | 50037.28 | 37.31% | 50037.28 | 37.31% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 914432 - NRG BIG CAJUN 1 | WATER | WATER REPAIR & INSTALLATION | 2019-05-22 | 2019-08-31 | 2019-05-22 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 914692¦¦2020-03-31
TM | CJ | Yes | 914694 |  | KU GHENT WELL 1 1 | MIGUEL, SEAN J. | 100% | 11895 | 84033 | 95928 | 62378 | 62378 | 62378 | 0 | 0 | 62378 | 8900 | 65458 | 74358 | 436.88 | 353.7 | 76.78 |  | 6.4 |  |  | 57086.33 | 22426.1 | 9057.34 |  | 24002.89 | 1600 |  | 5291.67 | 0 | 76.77% |  | 0 | 57086.33 | 2995 | 25.18% | 18575 | 21570 | 22.49% | 7914 |  | 5291.67 | 8.483% | 5291.67 | 8.483% | 33550 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 893306 - KU GHENT GENERATING STATION | WATER | WATER REPAIR & INSTALLATION | 2019-05-24 | 2019-06-30 | 2019-05-24 | 2019-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 914694¦¦2020-03-31
TM | C | Yes | 915323 |  | WEIBRING GC WELL NO 2 | HEALY, THOMAS P. | 100% | 60665 | 0 | 60665 | 54671 | 54671 | 54671 | 0 | 0 | 54671 | 43500 | 0 | 43500 | [7 empty] | 38257.89 | 17814.65 | 4966.14 |  | 15090.43 | 386.67 |  | 16413.11 | 0 | 87.95% |  | 0 | 38257.89 | 17165 | 28.29% | 0 | 17165 | 28.29% | 0 |  | 16413.11 | 30.02% | 16413.11 | 30.02% | 5994 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 892469 - ILLINOIS STATE UNIVERSITY WEIBRING GC | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-07-31 | 2019-05-01 | 2019-07-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 915323¦¦2020-03-31
TM | CJ | Yes | 915324 |  | GRACE 3137 | STUCKEY, WILLIAM C. | 100% | 70900 | 0 | 70900 | 69482 | 69482 | 69482 | 0 | 0 | 69482 | 31500 | 0 | 31500 | [7 empty] | 19307.54 | 3157 | 1197.2 |  | 14953.34 |  |  | 50174.46 | 0 | 61.29% |  | 0 | 19307.54 | 39400 | 55.57% | 0 | 39400 | 55.57% | 0 |  | 50174.46 | 72.21% | 50174.46 | 72.21% | 1418 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879019 - W R GRACE & CO CONN | WATER | WATER REPAIR & INSTALLATION | 2019-05-23 | 2019-05-31 | 2019-05-23 | 2019-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 915324¦¦2020-03-31
TM | C | Yes | 915371 |  | CITY OF SUMTER SC WELL 3PLANT5 | PARSLEY, TRISTAN S | 100% | 24833 | 174167 | 199000 | 202434.94 | 202434.94 | 204895.64 | 0 | 0 | 202434.94 | 24833 | 114827 | 139660 | [7 empty] | 189041.6 | 64461.6 | 42368.69 |  | 82211.31 |  |  | 13393.34 | 0 | 135.4% |  | 0 | 189041.6 | 0 | 0% | 59340 | 59340 | 29.82% | 0 |  | 13393.34 | 6.616% | 13393.34 | 6.616% | -3434.94 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 898504 - SUMTER COUNTY | WATER | WATER REPAIR & INSTALLATION | 2019-05-28 | 2019-07-31 | 2019-05-27 | 2019-07-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 915371¦¦2020-03-31
TM | C | Yes | 915934 |  | OTTER LAKE PUMP 2 | WHITE, CATHLEEN R | 100% | 34939 | 0 | 34939 | 34939 | 34939 | 34939 | 0 | 0 | 34939 | 22727 | 0 | 22727 | 0 |  |  |  | 0 |  |  | 49160.15 | 18081.36 | 7653.81 |  | 23424.98 |  |  | 0 | 14221.15 | 216.3% |  | 0 | 49160.15 | 12212 | 34.95% | 0 | 12212 | 34.95% | 0 |  | -14221.15 | -40.7% | -14221.15 | -40.7% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 895902 - OTTER LAKE WATER COMMISSION | WATER | WATER REPAIR & INSTALLATION | 2019-05-28 | 2019-07-31 | 2019-05-28 | 2019-07-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 915934¦¦2020-03-31
FP | C | Yes | 915935 |  | WAYNESVILLE PRVS | BARNES, MATTHEW D | 100% | 22825 | 0 | 22825 | 16885.5 | 16885.5 | 16885.5 | 0 | 0 | 16885.5 | 16040 | 0 | 16040 | -2.91 |  |  |  | -2.91 |  |  | 15870.01 | 4497.81 | 1031.67 |  | 10340.53 |  |  | 1015.49 | 0 | 98.94% |  | 0 | 15870.01 | 6785 | 29.73% | 0 | 6785 | 29.73% | 0 |  | 1015.49 | 6.014% | 1015.49 | 6.014% | 5939.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 912058 - WAYNESVILLE, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-30 | 2019-07-31 | 2019-05-30 | 2019-07-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 915935¦¦2020-03-31
TM | C | Yes | 915938 |  | BOOSTER SO CALIF GAS | BRASHEAR, DAVID M | 100% | 21537 | 1004.29 | 22541.29 | 22541.73 | 22541.73 | 24123.95 | 0 | 0 | 22541.73 | 15076 | 703 | 15779 | [7 empty] | 16251.07 | 333.72 | 209.88 |  | 15707.47 |  |  | 6290.66 | 0 | 103% |  | 0 | 16251.07 | 6461 | 30% | 301.29 | 6762.29 | 30% | 0 |  | 6290.66 | 27.91% | 6290.66 | 27.91% | -0.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 352503 - SOUTHERN CALIFORNIA GAS CO | WATER | WATER REPAIR & INSTALLATION | 2019-05-27 | 2019-06-28 | 2019-05-27 | 2019-06-28 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 915938¦¦2020-03-31
TM | C | Yes | 916459 |  | RCWD SENGA 4 | BRASHEAR, DAVID M | 100% | 34981 | 0 | 34981 | 34987.74 | 34987.74 | 37934.98 | 0 | 0 | 34987.74 | 28159 | 0 | 28159 | [7 empty] | 31086.76 | 1982.65 | 168.99 |  | 28935.12 |  |  | 3900.98 | 0 | 110.4% |  | 0 | 31086.76 | 6822 | 19.5% | 0 | 6822 | 19.5% | 0 |  | 3900.98 | 11.15% | 3900.98 | 11.15% | -6.74 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878683 - RANCHO CALIFORNIA WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-05-01 | 2019-06-30 | 2019-05-01 | 2019-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 916459¦¦2020-03-31
TM | CJ | Yes | 916461 |  | ASHGROVE CEMENT | GANSEBOM, JASON W. | 100% | 42058 | 0 | 42058 | 88275.38 | 88275.38 | 89919.39 | 0 | 0 | 88275.38 | 23973 | 0 | 23973 | 0.04 | 0.04 | [5 empty] | 78524.36 | 25536.67 | 11961.66 |  | 41026.03 |  |  | 9751.02 | 0 | 327.6% |  | 0 | 78524.36 | 18085 | 43% | 0 | 18085 | 43% | 0 |  | 9751.02 | 11.05% | 9751.02 | 11.05% | -46217.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 886558 - ASH GROVE CEMENT | WATER | WATER REPAIR & INSTALLATION | 2019-05-29 | 2019-07-30 | 2019-05-29 | 2019-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 916461¦¦2020-03-31
TM | C | Yes | 916484 |  | BURKETT FARMS OF STUTTGART | SCHERM, LOGAN M | 100% | 5000 | 0 | 5000 | 8115.19 | 8115.19 | 8723.83 | 0 | 0 | 8115.19 | 3000 | 0 | 3000 | [7 empty] | 1731.36 | 885.02 | 116.93 |  | 729.41 |  |  | 6383.83 | 0 | 57.71% |  | 0 | 1731.36 | 2000 | 40% | 0 | 2000 | 40% | 0 |  | 6383.83 | 78.67% | 6383.83 | 78.67% | -3115.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887624 - BURKETT, B & R FARM PARTNERSHI | WATER | WATER REPAIR & INSTALLATION | 2019-05-29 | 2019-06-30 | 2019-05-29 | 2019-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 916484¦¦2020-03-31
UP | C | Yes | 917742 |  | ALIQUIPPA NEW PUMP | BARNES, MATTHEW D | 100% | 16179 | 20719 | 36898 | 36898 | 36898 | 36898 | 0 | 0 | 36898 | 9807 | 12672 | 22479 | 0.33 | 0.33 | [5 empty] | 24055.18 | 2381.11 | 685.24 |  | 20988.83 |  |  | 12842.82 | 0 | 107% |  | 0 | 24055.18 | 6372 | 39.38% | 8047 | 14419 | 39.08% | 0 |  | 12842.82 | 34.81% | 12842.82 | 34.81% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878528 - MUNICIPAL WATER AUTHORITY OF ALIQUIPPA | WATER | WATER REPAIR & INSTALLATION | 2019-06-03 | 2019-08-30 | 2019-06-03 | 2019-08-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 917742¦¦2020-03-31
FP | C | Yes | 917767 |  | BELLS TN WELL 1 | ANDERSON, STEPHEN P. | 100% | 6360 | 30560 | 36920 | 37055 | 37055 | 37055 | 0 | 0 | 37055 | 4452 | 23483.08 | 27935.08 | 104.68 |  |  |  | 104.68 |  |  | 33031.78 | 9801.12 | 3579.72 |  | 19650.94 |  |  | 4023.22 | 0 | 118.2% |  | 0 | 33031.78 | 1908 | 30% | 7076.92 | 8984.92 | 24.34% | 0 |  | 4023.22 | 10.86% | 4023.22 | 10.86% | -135 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 886971 - BELLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-07-17 | 2019-06-01 | 2019-07-17 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 917767¦¦2020-03-31
FP | C | Yes | 917769 |  | PEARL PLACE CO PHASE 2 | CHESLEY, ANDREW J | 100% | 60420 | 23721 | 84141 | 84141 | 84141 | 84141 | 11525.4 | 0 | 84141 | 42640.25 | 14323.61 | 56963.86 | 218.93 | 214.53 |  |  | 4.4 |  |  | 92935.13 | 17025.98 | 86.28 |  | 49860.83 | 25962.04 |  | 0 | 8794.13 | 163.1% |  | 0 | 92935.13 | 17779.75 | 29.43% | 9397.39 | 27177.14 | 32.3% | 1142.76 |  | -8794.13 | -10.45% | -8794.13 | -10.45% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 267691 - SAUNDERS CONSTRUCTION INC | WATER | WATER TREATMENT | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 917769¦¦2020-03-31
UP | C | Yes | 917770 |  | NUTRIEN SWIFT CREEK SOUTH WELL | PARSLEY, TRISTAN S | 100% | 78576 | 0 | 78576 | 74350 | 74350 | 74350 | 0 | 0 | 74350 | 39288 | 0 | 39288 | [7 empty] | 60211.99 | 30431.93 | 9062.96 |  | 20717.1 |  |  | 14138.01 | 0 | 153.3% |  | 0 | 60211.99 | 39288 | 50% | 0 | 39288 | 50% | 0 |  | 14138.01 | 19.02% | 14138.01 | 19.02% | 4226 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 896144 - PCS PHOSPHATE WHITE SPRINGS | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-08-31 | 2019-06-01 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 917770¦¦2020-03-31
TM | C | Yes | 918177 |  | APACHE PARK PUMP STATION HIGH | VAN ALLEN, WESLEY C. |  | 3700 | 0 | 3700 |  |  | 0 | 0 | 0 |  | 2724 | 0 | 2724 | [20 empty] | 976 | 26.38% | 0 | 976 | 26.38% | 0 | [5 empty] | 3700 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-06-19 | 2019-06-01 | 2019-06-19 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 918177¦¦2020-03-31
TM | C | Yes | 918178 |  | APACHE PARK PUMP STATION BOOST | VAN ALLEN, WESLEY C. | 100% | 3700 | 18283.75 | 21983.75 | 19458.71 | 19458.71 | 19458.71 | 0 | 0 | 19458.71 | 2724 | 14190.01 | 16914.01 | [7 empty] | 15569.75 | 1703.66 | 527.24 |  | 13338.85 |  |  | 3888.96 | 0 | 92.05% |  | 0 | 15569.75 | 976 | 26.38% | 4093.74 | 5069.74 | 23.06% | 0 |  | 3888.96 | 19.99% | 3888.96 | 19.99% | 2525.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-06-19 | 2019-06-01 | 2019-06-19 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 918178¦¦2020-03-31
TM | C | Yes | 918179 |  | BUSH WAY BOOSTER PUMP STATION | VAN ALLEN, WESLEY C. | 100% | 3700 | 24377.71 | 28077.71 | 25688.68 | 25688.68 | 25688.68 | 0 | 0 | 25688.68 | 2724 | 20635.39 | 23359.39 | 987.28 |  |  |  | 987.28 |  |  | 22487.7 | 4990.48 | 1316.47 |  | 13990.74 | 2190.01 |  | 3200.98 | 0 | 96.27% |  | 0 | 22487.7 | 976 | 26.38% | 3742.32 | 4718.32 | 16.8% | 0 |  | 3200.98 | 12.46% | 3200.98 | 12.46% | 2389.03 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-06-19 | 2019-06-01 | 2019-06-19 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 918179¦¦2020-03-31
TM | C | Yes | 918180 |  | MURPHREE WATER TREATMENT PLANT | PARSLEY, TRISTAN S | 100% | 8519 | 0 | 8519 | 24687.5 | 24687.5 | 24687.5 | 0 | 0 | 24687.5 | 5537 | 0 | 5537 | [7 empty] | 16347.69 | 6844.62 | 1849.6 |  | 7653.47 |  |  | 8339.81 | 0 | 295.2% |  | 0 | 16347.69 | 2982 | 35% | 0 | 2982 | 35% | 0 |  | 8339.81 | 33.78% | 8339.81 | 33.78% | -16168.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 891007 - GAINESVILLE REGIONAL UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-07-31 | 2019-06-01 | 2019-07-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 918180¦¦2020-03-31
TM | C | Yes | 918181 |  | MURPHREE WATER TRTMT WELL 14 | PARSLEY, TRISTAN S | 100% | 8518 | 0 | 8518 | 12724.39 | 12724.39 | 12724.39 | 0 | 0 | 12724.39 | 5537 | 0 | 5537 | [7 empty] | 7551.85 | 3690.05 | 1085.52 |  | 2776.28 |  |  | 5172.54 | 0 | 136.4% |  | 0 | 7551.85 | 2981 | 35% | 0 | 2981 | 35% | 0 |  | 5172.54 | 40.65% | 5172.54 | 40.65% | -4206.39 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 891007 - GAINESVILLE REGIONAL UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-07-31 | 2019-06-01 | 2019-07-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 918181¦¦2020-03-31
TM | CJ | Yes | 918184 |  | OLIN LC P AND A | GNAU, CASEY T | 100% | 14941 | 14927 | 29868 | 29868 | 29868 | 29868 | 0 | 0 | 29868 | 14927 | 0 | 14927 | [7 empty] | 9246.67 | 2123.1 | 632.46 |  | 1306.01 | 5185.1 |  | 20621.33 | 0 | 61.95% |  | 0 | 9246.67 | 14 | 0.0937% | 14927 | 14941 | 50.02% | 0 |  | 20621.33 | 69.04% | 20621.33 | 69.04% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 917357 - SOUTHLAND ENVIRONMENTAL LLC | WATER | WATER REPAIR & INSTALLATION | 2019-06-03 | 2019-06-30 | 2019-06-03 | 2019-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 918184¦¦2020-03-31
TM | CJ | Yes | 918185 |  | JG BOSWELL S 237 PERM PUMP | BRASHEAR, DAVID M | 100% | 23669 | 0 | 23669 | 23669 | 23669 | 20253.65 | 0 | 0 | 23669 | 16164 | 0 | 16164 | [7 empty] | 20810.72 | 7978.21 | 3242.2 |  | 9590.31 |  |  | 2858.28 | 0 | 128.7% |  | 0 | 20810.72 | 7505 | 31.71% | 0 | 7505 | 31.71% | 0 |  | 2858.28 | 12.08% | 2858.28 | 12.08% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878568 - J G BOSWELL | WATER | WATER REPAIR & INSTALLATION | 2019-06-03 | 2019-08-31 | 2019-06-03 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 918185¦¦2020-03-31
TM | C | Yes | 918263 |  | WELLS 31 AND 33 VIRGIN VALLEY | BRASHEAR, DAVID M | 100% | 47860 | 0 | 47860 | 47859.82 | 47859.82 | 47859.82 | 0 | 0 | 47859.82 | 34687 | 0 | 34687 | 0 |  |  |  | 0 |  |  | 36706.12 | 996.02 |  |  | 35710.1 |  |  | 11153.7 | 0 | 105.8% |  | 0 | 36706.12 | 13173 | 27.52% | 0 | 13173 | 27.52% | 0 |  | 11153.7 | 23.3% | 11153.7 | 23.3% | 0.18 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 899720 - VIRGIN VALLEY WATER DISTRICT | WATER | WATER EQUIPMENT SALES | 2019-06-01 | 2019-07-31 | 2019-06-01 | 2019-07-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 918263¦¦2020-03-31
FP | C | Yes | 918271 |  | CORTLAND NY WELL 5 MOTOR | CROOK, CHARLES M | 100% | 37000 | 61385 | 98385 | 59555 | 59555 | 59555 | 0 | 0 | 59555 | 22000 | 45100 | 67100 | 17535.69 | 1517.52 | 77.52 |  | 15165.65 | 775 |  | 55298.35 | 15739.12 | 3001.55 |  | 35782.68 | 775 |  | 4256.65 | 0 | 82.41% |  | 0 | 55298.35 | 15000 | 40.54% | 16285 | 31285 | 31.8% | 7785 |  | 4256.65 | 7.147% | 4256.65 | 7.147% | 38830 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 917930 - M HUBBARD CONSTRUCTION | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-08-30 | 2019-05-30 | 2019-08-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 918271¦¦2020-03-31
FP | CJ | Yes | 918272 |  | HUMBOLDT TN NEW WELL | ANDERSON, STEPHEN P. | 100% | 402631 | -65754 | 336877 | 277893 | 277893 | 277893 | 28017.4 | 13894.65 | 277893 | 336893 | -53916 | 282977 | 20582.25 | 782.96 | 259.7 |  | 1539.59 | 18000 |  | 236580.36 | 59537.37 | 43172.1 |  | 111289.29 | 22581.6 |  | 41312.64 | 0 | 83.6% |  | 0 | 236580.36 | 65738 | 16.33% | -11838 | 53900 | 16% | 0 |  | 41312.64 | 14.87% | 41312.64 | 14.87% | 58984 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 917862 - HUMBOLDT UTILITIES | WATER | WATER SUPPLY | 2019-06-01 | 2019-08-31 | 2019-06-01 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 918272¦¦2020-03-31
TM | CJ | Yes | 918881 |  | ERM LILLY T1465 | MIGUEL, SEAN J. | 100% | 2199 | 0 | 2199 | 13260.5 | 13260.5 | 13260.5 | 1062.5 | 0 | 13260.5 | 1580 | 0 | 1580 | 674.36 | 407.88 | 89 |  | 177.48 |  |  | 10530.03 | 4049.16 | 1778.3 |  | 4702.57 |  |  | 2730.47 | 0 | 666.5% |  | 0 | 10530.03 | 619 | 28.15% | 0 | 619 | 28.15% | 0 |  | 2730.47 | 20.59% | 2730.47 | 20.59% | -11061.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 918468 - ERM | WATER | WATER REPAIR & INSTALLATION | 2019-06-04 | 2019-07-31 | 2019-06-04 | 2019-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 918881¦¦2020-03-31
FP | C | Yes | 918888 |  | UTTR HILL AFB | COMBS, TAYLOR E. | 100% | 92715 | 87635 | 180350 | 179740 | 179740 | 179740 | 0 | 0 | 179740 | 69536 | 32361.35 | 101897.35 | 0 |  |  |  | 0 |  |  | 399737.34 | 118192.77 | 140327.84 |  | 141216.73 |  |  | 0 | 219997.34 | 392.3% |  | 0 | 399737.34 | 23179 | 25% | 55273.65 | 78452.65 | 43.5% | 0 |  | -219997.34 | -122.4% | -219997.34 | -122.4% | 610 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 885935 - AECOM | WATER | WATER REPAIR & INSTALLATION | 2019-06-06 | 2019-07-31 | 2019-06-06 | 2019-07-31 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 918888¦¦2020-03-31
FP | C | Yes | 918889 |  | MATHESON TRI GAS | BRUGGER, CRAIG J. | 100% | 111357 | 0 | 111357 | 111357 | 111357 | 111357 | 0 | 0 | 111357 | 68315 | 0 | 68315 | [7 empty] | 68891.78 |  | 0 |  | 68891.78 |  |  | 42465.22 | 0 | 100.8% |  | 0 | 68891.78 | 43042 | 38.65% | 0 | 43042 | 38.65% | 0 |  | 42465.22 | 38.13% | 42465.22 | 38.13% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 894336 - MATHESON TRI GAS | WATER | WATER EQUIPMENT SALES | 2019-06-01 | 2019-09-30 | 2019-06-01 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 918889¦¦2020-03-31
TM | C | Yes | 918902 |  | COCA COLA APOPKA FL WELL 2 | TORMOEHLEN, DAVID A. | 100% | 19830 | 0 | 19830 | 26548 | 26548 | 26548 | 0 | 0 | 26548 | 15259 | 0 | 15259 | [7 empty] | 18937.14 | 7133.75 | 1962.1 |  | 9841.29 |  |  | 7610.86 | 0 | 124.1% |  | 0 | 18937.14 | 4571 | 23.05% | 0 | 4571 | 23.05% | 0 |  | 7610.86 | 28.67% | 7610.86 | 28.67% | -6718 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 888715 - COCA COLA ANAHEIM | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-06-17 | 2019-06-01 | 2019-06-17 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 918902¦¦2020-03-31
FP | C | Yes | 918904 |  | PIMA UTILITIES WELL 32REPLACE | VAN ALLEN, WESLEY C. | 100% | 62456.2 | 0 | 62456.2 | 59344 | 59344 | 61857.7 | 0 | 0 | 59344 | 46435 | 0 | 46435 | [7 empty] | 42132.34 | 5207.3 | 1738.22 |  | 35186.82 |  |  | 17211.66 | 0 | 90.73% |  | 0 | 42132.34 | 16021.2 | 25.65% | 0 | 16021.2 | 25.65% | 0 |  | 17211.66 | 29% | 17211.66 | 29% | 3112.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 896326 - PIMA UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-06-05 | 2019-06-24 | 2019-06-05 | 2019-06-24 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 918904¦¦2020-03-31
FP | C | Yes | 918905 |  | COCA COLA APOPKA WELL 1 | TORMOEHLEN, DAVID A. | 100% | 19830 | 0 | 19830 | 49815 | 49815 | 49815 | 0 | 0 | 49815 | 15259 | 0 | 15259 | [7 empty] | 36292.26 | 11182.93 | 6234.42 |  | 18874.91 |  |  | 13522.74 | 0 | 237.8% |  | 0 | 36292.26 | 4571 | 23.05% | 0 | 4571 | 23.05% | 0 |  | 13522.74 | 27.15% | 13522.74 | 27.15% | -29985 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 919781 - COCA COLA NORTH AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-06-17 | 2019-06-01 | 2019-06-17 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 918905¦¦2020-03-31
TM | C | Yes | 918953 |  | SAN BERNARDINO XC 31 | BRASHEAR, DAVID M | 100% | 43506 | 0 | 43506 | 36566.35 | 36566.35 | 37732.45 | 0 | 0 | 36566.35 | 32205 | 0 | 32205 | [7 empty] | 54052.01 | 16013.87 | 2984.92 |  | 31403.22 | 3650 |  | 0 | 17485.66 | 167.8% |  | 0 | 54052.01 | 11301 | 25.98% | 0 | 11301 | 25.98% | 0 |  | -17485.66 | -47.82% | -17485.66 | -47.82% | 6939.65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878706 - SAN BERNARDINO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-07-15 | 2019-06-01 | 2019-07-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 918953¦¦2020-03-31
TM | C | Yes | 918955 |  | PW LAYTON R AND I | LOPEZ-VASQUEZ, JUAN C. | 100% | 6750 | 269849 | 276599 | 276599 | 276599 | 279966.58 | 0 | 0 | 276599 | 4687 | 223576 | 228263 | 0 |  |  |  | 0 |  |  | 223333.3 | 78315.28 | 36801.88 |  | 108216.14 |  |  | 53265.7 | 0 | 97.84% |  | 0 | 223333.3 | 2063 | 30.56% | 46273 | 48336 | 17.48% | 0 |  | 53265.7 | 19.26% | 53265.7 | 19.26% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 879024 - PARISH WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-06-06 | 2019-08-31 | 2019-06-06 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 918955¦¦2020-03-31
TM | CJ | Yes | 919065 |  | EGAN MOTOR | ALBARADO, JORDAN A | 100% | 8500 | 0 | 8500 | 7700 | 7700 | 7700 | 0 | 0 | 7700 | 4250 | 0 | 4250 | [7 empty] | 462.4 | 242.76 | 71.23 |  | 148.41 |  |  | 7237.6 | 0 | 10.88% |  | 0 | 462.4 | 4250 | 50% | 0 | 4250 | 50% | 0 |  | 7237.6 | 93.99% | 7237.6 | 93.99% | 800 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 918995 - EGAN WATER CORP | WATER | WATER REPAIR & INSTALLATION | 2019-06-06 | 2019-06-07 | 2019-06-06 | 2019-06-07 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 919065¦¦2020-03-31
FP | C | Yes | 919247 |  | CITY OF SOLEDAD WELL 7 | SEIDEN, ANDREW L. | 100% | 176917 | 8258.95 | 185175.95 | 185176.87 | 185176.87 | 185176.87 | 0 | 0 | 185176.87 | 150052 | 5096.64 | 155148.64 | [7 empty] | 307247.91 | 84143.21 | 67285.66 |  | 127769.5 | 28049.54 |  | 0 | 122071.04 | 198% |  | 0 | 307247.91 | 26865 | 15.19% | 3162.31 | 30027.31 | 16.22% | 0 |  | -122071.04 | -65.92% | -122071.04 | -65.92% | -0.92 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 120200 - SOLEDAD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 919247¦¦2020-03-31
TM | C | Yes | 919934 |  | GSWC DESERT VIEW WELL 2 | BRASHEAR, DAVID M | 100% | 22107.32 | 1932.35 | 24039.67 | 24039.65 | 24039.65 | 24625.03 | 0 | 0 | 24039.65 | 15757 | 1449.26 | 17206.26 | [7 empty] | 18487.01 | 5536.49 | 1717.58 |  | 11232.94 |  |  | 5552.64 | 0 | 107.4% |  | 0 | 18487.01 | 6350.32 | 28.72% | 483.09 | 6833.41 | 28.43% | 0 |  | 5552.64 | 23.1% | 5552.64 | 23.1% | 0.02 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 231962 - GOLDEN STATE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-06-10 | 2019-07-31 | 2019-06-10 | 2019-07-31 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 919934¦¦2020-03-31
UP | C | Yes | 919936 |  | HAMILTON REHAB 3 AND 8 | BARNES, MATTHEW D | 100% | 111854 | 0 | 111854 | 111543 | 111543 | 111543 | 0 | 11154.3 | 111543 | 59668 | 0 | 59668 | 3.88 | 3.88 |  |  | 0 |  |  | 111841.27 | 47105.88 | 18525.83 |  | 45291.56 | 918 |  | 0 | 298.27 | 187.4% |  | 0 | 111841.27 | 52186 | 46.66% | 0 | 52186 | 46.66% | 0 |  | -298.27 | -0.2674% | -298.27 | -0.2674% | 311 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 891760 - HAMILTON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-05-03 | 2019-09-30 | 2019-06-10 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 919936¦¦2020-03-31
FP | C | Yes | 919938 |  | GSW IMPERIAL 1 | SEIDEN, ANDREW L. | 100% | 47094 | 10216.2 | 57310.2 | 49350.2 | 49350.2 | 49350.2 | 0 | 0 | 49350.2 | 37198 | 9617.27 | 46815.27 | [7 empty] | 42998.15 | 6978.82 | 4226.84 |  | 28767.49 | 3025 |  | 6352.05 | 0 | 91.85% |  | 0 | 42998.15 | 9896 | 21.01% | 598.93 | 10494.93 | 18.31% | 0 |  | 6352.05 | 12.87% | 6352.05 | 12.87% | 7960 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878675 - GOLDEN STATE WATER CO ONTARIO | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-08-22 | 2019-06-01 | 2019-08-22 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 919938¦¦2020-03-31
TM | C | Yes | 919942 |  | AK OUTFALL 006 | SIMPSON, CARL L. | 100% | 30000 | 29930 | 59930 | 59930 | 59930 | 59930 | 22445 | 0 | 59930 | 19000 | 23569 | 42569 | 0.07 | 0.07 |  |  | 0 |  |  | 53106.54 | 15272.02 | 9231.93 |  | 17518.94 | 11083.65 |  | 6823.46 | 0 | 124.8% |  | 0 | 53106.54 | 11000 | 36.67% | 6361 | 17361 | 28.97% | 4489 |  | 6823.46 | 11.39% | 6823.46 | 11.39% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-06-07 | 2019-07-31 | 2019-06-07 | 2019-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 919942¦¦2020-03-31
TM | C | Yes | 919944 |  | BRW OLOL WARRANTY | LOPEZ-VASQUEZ, JUAN C. | 100% | [5 empty] | 0 | 0 | 0 |  | 2040 | 0 | 2040 | 0 |  |  |  | 0 |  |  | 3854.47 | 1329.95 | 176.23 |  | 2348.29 |  |  | 0 | 3854.47 | 188.9% |  | 0 | 3854.47 | -2040 |  | 0 | -2040 |  | 0 |  | -3854.47 |  | -3854.47 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER SUPPLY | 2019-06-10 | 2019-07-07 | 2019-06-10 | 2019-07-07 | PRIME CONTRACTOR | PRIVATE | EXPENSE JOB | 919944¦¦2020-03-31
TM | C | Yes | 919965 |  | MEMPHIS NE PUMP REPLACE | GANSEBOM, JASON W. | 100% | 6479 | 0 | 6479 | 10552.96 | 10552.96 | 10881.04 | 0 | 0 | 10552.96 | 3639 | 0 | 3639 | [7 empty] | 8938.98 | 2489.41 | 958.56 |  | 5491.01 |  |  | 1613.98 | 0 | 245.6% |  | 0 | 8938.98 | 2840 | 43.83% | 0 | 2840 | 43.83% | 0 |  | 1613.98 | 15.29% | 1613.98 | 15.29% | -4073.96 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 919738 - MEMPHIS, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-10 | 2019-07-30 | 2019-06-10 | 2019-07-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 919965¦¦2020-03-31
TM | C | Yes | 920151 |  | WEST VALLEY WELL 39 | SEIDEN, ANDREW L. | 100% | 1285 | 0 | 1285 | 1285 | 1285 | 1285 | 0 | 0 | 1285 | 900 | 0 | 900 | [7 empty] | 1508.35 | 943.37 | 185.76 |  | 379.22 |  |  | 0 | 223.35 | 167.6% |  | 0 | 1508.35 | 385 | 29.96% | 0 | 385 | 29.96% | 0 |  | -223.35 | -17.38% | -223.35 | -17.38% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 900202 - WEST VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 920151¦¦2020-03-31
TM | C | Yes | 920498 |  | ARAPAHOE PARK A1 REPAIR | SCHANAMAN, MIKE L. | 100% | 131577 | 0 | 131577 | 153077.24 | 153077.24 | 156670 | 0 | 0 | 153077.24 | 93489 | 0 | 93489 | [7 empty] | 120266.04 | 24502.29 | 17051.04 |  | 76712.71 | 2000 |  | 32811.2 | 0 | 128.6% |  | 0 | 120266.04 | 38088 | 28.95% | 0 | 38088 | 28.95% | 0 |  | 32811.2 | 21.43% | 32811.2 | 21.43% | -21500.24 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 886404 - ARAPAHOE PARK | WATER | WATER REPAIR & INSTALLATION | 2019-06-12 | 2019-07-30 | 2019-06-12 | 2019-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 920498¦¦2020-03-31
TM | C | Yes | 920499 |  | BRW OLOL R AND I | LOPEZ-VASQUEZ, JUAN C. | 100% | 7050 | 30364.25 | 37414.25 | 37414.25 | 37414.25 | 39774.82 | 0 | 0 | 37414.25 | 8307 | 19285 | 27592 | [7 empty] | 32472.62 | 9196.75 | 3227.38 |  | 19800.49 | 248 |  | 4941.63 | 0 | 117.7% |  | 0 | 32472.62 | -1257 | -17.83% | 11079.25 | 9822.25 | 26.25% | 0 |  | 4941.63 | 13.21% | 4941.63 | 13.21% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER SUPPLY | 2019-06-12 | 2019-08-17 | 2019-06-12 | 2019-08-17 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 920499¦¦2020-03-31
TM | C | Yes | 920501 |  | JG BOSWELL S238 PERM PUMP | BRASHEAR, DAVID M | 100% | 19819 | 0 | 19819 | 19828 | 19828 | 19905.12 | 0 | 0 | 19828 | 14379 | 0 | 14379 | [7 empty] | 23437.87 | 6653.56 | 2766.77 |  | 14017.54 |  |  | 0 | 3609.87 | 163% |  | 0 | 23437.87 | 5440 | 27.45% | 0 | 5440 | 27.45% | 0 |  | -3609.87 | -18.21% | -3609.87 | -18.21% | -9 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878568 - J G BOSWELL | WATER | WATER REPAIR & INSTALLATION | 2019-06-07 | 2019-08-31 | 2019-06-07 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 920501¦¦2020-03-31
FP | C | Yes | 921749 |  | CASS COUNTY 2 WARRANTY PLUS | GANSEBOM, JASON W. | 100% |  |  |  | 16108.62 | 16108.62 | 16808.69 | 0 | 0 | 16108.62 | 4000 | 0 | 4000 | [7 empty] | 18109.29 | 3829.49 | 1360.65 |  | 12862.15 | 57 |  | 0 | 2000.67 | 452.7% |  | 0 | 18109.29 | -4000 |  | 0 | -4000 |  | 0 |  | -2000.67 | -12.42% | -2000.67 | -12.42% | -16108.62 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 888020 - CASS COUNTY RWD 2 | WATER | WATER REPAIR & INSTALLATION | 2019-06-13 | 2019-07-31 | 2019-06-13 | 2019-07-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 921749¦¦2020-03-31
FP | C | Yes | 921753 |  | KEENE NY PUMP AND PITLESS | CROOK, CHARLES M | 100% | 39620 | 0 | 39620 | 39300 | 39300 | 39300 | 0 | 0 | 39300 | 25620 | 0 | 25620 | 636.68 | 352.36 | 117.28 |  | 167.04 |  |  | 24883.58 | 6825.81 | 1749.3 |  | 16308.47 |  |  | 14416.42 | 0 | 97.13% |  | 0 | 24883.58 | 14000 | 35.34% | 0 | 14000 | 35.34% | 0 |  | 14416.42 | 36.68% | 14416.42 | 36.68% | 320 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 893040 - KEENE, NY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-10 | 2019-08-23 | 2019-06-10 | 2019-08-23 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 921753¦¦2020-03-31
TM | CJ | Yes | 922585 |  | WELL 26 VVWD RENTAL PUMP | BRASHEAR, DAVID M | 100% | 52636 | 0 | 52636 | 62134.85 | 62134.85 | 62134.85 | 0 | 0 | 62134.85 | 33642 | 0 | 33642 | 1.87 |  |  |  | 1.87 |  |  | 38444.57 | 15332.77 | 7419.09 |  | 15692.71 |  |  | 23690.28 | 0 | 114.3% |  | 0 | 38444.57 | 18994 | 36.09% | 0 | 18994 | 36.09% | 0 |  | 23690.28 | 38.13% | 23690.28 | 38.13% | -9498.85 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 899720 - VIRGIN VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-06-14 | 2019-09-30 | 2019-06-14 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 922585¦¦2020-03-31
FP | C | Yes | 922588 |  | CITY OF UPLAND WEST BOOSTER3 | SEIDEN, ANDREW L. | 100% | 35093 | 0 | 35093 | 32680 | 32680 | 34648.12 | 0 | 0 | 32680 | 25611 | 0 | 25611 | [7 empty] | 28354.87 | 4026.77 | 1109.64 |  | 23218.46 |  |  | 4325.13 | 0 | 110.7% |  | 0 | 28354.87 | 9482 | 27.02% | 0 | 9482 | 27.02% | 0 |  | 4325.13 | 13.23% | 4325.13 | 13.23% | 2413 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 899386 - UPLAND, CA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-08-25 | 2019-06-01 | 2019-08-25 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 922588¦¦2020-03-31
TM | CJ | Yes | 924061 |  | TESI TRAPPEY ROAD | ALBARADO, JORDAN A |  | 10904 | 0 | 10904 |  |  | 0 | 0 | 0 |  | 5452 | 0 | 5452 | [20 empty] | 5452 | 50% | 0 | 5452 | 50% | 0 | [5 empty] | 10904 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 898763 - TESI | WATER | WATER REPAIR & INSTALLATION | 2019-06-07 | 2019-06-07 | 2019-06-07 | 2019-06-07 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 924061¦¦2020-03-31
FP | CJ | Yes | 924068 |  | ABIE NE WELL 1 | GANSEBOM, JASON W. | 100% | 23943 | 42210 | 66153 | 67712 | 67712 | 67712 | 0 | 0 | 67712 | 16936 | 34496.99 | 51432.99 | 887.79 |  |  |  | 887.79 |  |  | 65764.43 | 18306.62 | 10699.59 |  | 36110.62 | 647.6 |  | 1947.57 | 0 | 127.9% |  | 0 | 65764.43 | 7007 | 29.27% | 7713.01 | 14720.01 | 22.25% | 0 |  | 1947.57 | 2.876% | 1947.57 | 2.876% | -1559 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 885859 - ABIE, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-17 | 2019-08-30 | 2019-06-17 | 2019-08-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 924068¦¦2020-03-31
TM | CJ | Yes | 924070 |  | WOODSTOCK NY GRAVEL PACK WELL | CROOK, CHARLES M | 100% | 52925 | 0 | 52925 | 52925 | 52925 | 43875 | 0 | 0 | 52925 | 36925 | 0 | 36925 | 0 |  |  |  | 0 |  |  | 55884.31 | 24728.15 | 22633.12 |  | 8523.04 |  |  | 0 | 2959.31 | 151.3% |  | 0 | 55884.31 | 16000 | 30.23% | 0 | 16000 | 30.23% | 0 |  | -2959.31 | -5.592% | -2959.31 | -5.592% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 922596 - WOODSTOCK, TOWN OF | WATER | WATER SUPPLY | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 924070¦¦2020-03-31
FP | C | Yes | 924106 |  | GREEN PLAINS HSP 1 | ANDERSON, STEPHEN P. | 100% | 4725 | 5035 | 9760 | 5035 | 5035 | 5035 | 0 | 0 | 5035 | 3307 | 4525.49 | 7832.49 | 1356.33 | 706.11 | 70.2 |  | 580.02 |  |  | 6630.98 | 3038.92 | 1174.67 |  | 2417.39 |  |  | 0 | 1595.98 | 84.66% |  | 0 | 6630.98 | 1418 | 30.01% | 509.51 | 1927.51 | 19.75% | 0 |  | -1595.98 | -31.7% | -1595.98 | -31.7% | 4725 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879091 - GREEN PLAINS OBION LLC | WATER | WATER REPAIR & INSTALLATION | 2019-06-17 | 2019-08-05 | 2019-06-17 | 2019-08-05 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 924106¦¦2020-03-31
FP | C | Yes | 924107 |  | GREEN PLAINS HSP 2 | ANDERSON, STEPHEN P. | 100% | 4725 | 0 | 4725 |  |  | 0 | 0 | 0 |  | 3307 | 0 | 3307 | 0 |  |  |  | 0 |  |  | 9066.88 | 4632.72 | 926.4 |  | 3507.76 |  |  | 0 | 9066.88 | 274.2% |  | 0 | 9066.88 | 1418 | 30.01% | 0 | 1418 | 30.01% | 0 |  | -9066.88 |  | -9066.88 |  | 4725 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879091 - GREEN PLAINS OBION LLC | WATER | WATER REPAIR & INSTALLATION | 2019-06-17 | 2019-09-09 | 2019-06-17 | 2019-09-09 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 924107¦¦2020-03-31
FP | C | Yes | 924110 |  | ALLSTATE PWM TESTING | KENNEDY, CHRISTOPHER C. | 100% | 6270 | 66960 | 73230 | 95033 | 95033 | 98330.65 | 0 | 0 | 95033 | 5000 | 50046.87 | 55046.87 | [7 empty] | 90096.67 | 40064.23 | 9420.95 |  | 40611.49 |  |  | 4936.33 | 0 | 163.7% |  | 0 | 90096.67 | 1270 | 20.26% | 16913.13 | 18183.13 | 24.83% | 0 |  | 4936.33 | 5.194% | 4936.33 | 5.194% | -21803 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 886118 - ALLSTATE INSURANCE COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-06-14 | 2019-06-14 | 2019-06-14 | 2019-06-14 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 924110¦¦2020-03-31
FP | C | Yes | 924111 |  | TRUE TEMPER HSP REPAIR | ANDERSON, STEPHEN P. | 100% | 2650 | 18704 | 21354 | 21354 | 21354 | 21354 | 0 | 0 | 21354 | 1855 | 13092 | 14947 | [7 empty] | 18360.8 | 5472.39 | 1822.55 |  | 11065.86 |  |  | 2993.2 | 0 | 122.8% |  | 0 | 18360.8 | 795 | 30% | 5612 | 6407 | 30% | 0 |  | 2993.2 | 14.02% | 2993.2 | 14.02% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 899175 - TRUE TEMPER CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-06-17 | 2019-08-05 | 2019-06-17 | 2019-08-05 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 924111¦¦2020-03-31
TM | C | Yes | 924114 |  | FPM HEAT TREATING WELL | KENNEDY, CHRISTOPHER C. | 100% | 333866 | 12083 | 345949 | 332172 | 332172 | 332172 | 33217.2 | 0 | 332172 | 241932 | 9666 | 251598 | -690.2 |  | -690.2 |  | 0 |  |  | 292746.27 | 106298.42 | 101930.84 |  | 83397.01 | 1120 |  | 39425.73 | 0 | 116.4% |  | 0 | 292746.27 | 91934 | 27.54% | 2417 | 94351 | 27.27% | 0 |  | 39425.73 | 11.87% | 39425.73 | 11.87% | 13777 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 922747 - SCANDROLI CONSTRUCTION | WATER | WATER SUPPLY | 2019-06-04 | 2019-09-20 | 2019-06-04 | 2019-09-20 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 924114¦¦2020-03-31
FP | C | Yes | 924320 |  | BETA PLANT WELL 3 | BRASHEAR, DAVID M | 100% | 110568 | 239623.53 | 350191.53 | 350191.44 | 350191.44 | 359907.42 | 0 | 0 | 350191.44 | 77397 | 166112.52 | 243509.52 | [7 empty] | 242838.89 | 24405.67 | 77212.25 |  | 141220.97 |  |  | 107352.55 | 0 | 99.72% |  | 0 | 242838.89 | 33171 | 30% | 73511.01 | 106682.01 | 30.46% | 0 |  | 107352.55 | 30.66% | 107352.55 | 30.66% | 0.09 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 648672 - MOJAVE SOLAR LLC | WATER | WATER REPAIR & INSTALLATION | 2019-06-14 | 2019-07-31 | 2019-06-14 | 2019-07-31 | PRIME CONTRACTOR | PRIVATE | CONST MANAGER/GEN CONTRACTOR | 924320¦¦2020-03-31
TM | C | Yes | 924321 |  | DURR HEAVY PLUG TIMES PICYUNE | LOPEZ-VASQUEZ, JUAN C. | 100% | 28544 | 0 | 28544 | 28544 | 28544 | 28544 | 0 | 0 | 28544 | 18838 | 0 | 18838 | [7 empty] | 18191.78 | 6722.5 | 1936.74 |  | 3718.36 | 5814.18 |  | 10352.22 | 0 | 96.57% |  | 0 | 18191.78 | 9706 | 34% | 0 | 9706 | 34% | 0 |  | 10352.22 | 36.27% | 10352.22 | 36.27% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 917868 - DURR HEAVY CONSTRUCTION LLC | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-07-17 | 2019-06-01 | 2019-07-17 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 924321¦¦2020-03-31
TM | CJ | Yes | 924328 |  | ARB MIDSTREAM WELL | DECKER, JASEN | 100% | 299750 | 0 | 299750 | 409076 | 409076 | 409076 | 0 | 0 | 409076 | 251998 | 0 | 251998 | 988.76 |  |  |  | 913.76 | 75 |  | 389376.06 | 83412.37 | 131066.22 |  | 161092.37 | 13805.1 |  | 19699.94 | 0 | 154.5% |  | 0 | 389376.06 | 47752 | 15.93% | 0 | 47752 | 15.93% | 0 |  | 19699.94 | 4.816% | 19699.94 | 4.816% | -109326 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 924268 - ARB MIDSTREAM LLC | WATER | WATER SUPPLY | 2019-06-18 | 2019-07-30 | 2019-06-18 | 2019-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 924328¦¦2020-03-31
TM | C | Yes | 924334 |  | RMNG WOLF CREEK SURGACE CASING | DECKER, JASEN | 100% | 1436970 | 0 | 1436970 | 1535568.75 | 1535568.75 | 1535568.75 | 0 | 0 | 1535568.75 | 1055196 | 0 | 1055196 | [7 empty] | 1626657.98 | 230440.35 | 517221.04 | 118.03 | 604044.09 | 274834.47 |  | 0 | 91089.23 | 154.2% |  | 0 | 1626657.98 | 381774 | 26.57% | 0 | 381774 | 26.57% | 0 |  | -91089.23 | -5.932% | -91089.23 | -5.932% | -98598.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 924266 - ROCKY MOUNTAIN NATURAL GAS | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-09-30 | 2019-06-01 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 924334¦¦2020-03-31
TM | CJ | Yes | 924571 |  | HERRERA FARMING CO PUMP | BENNETT, MARK C. | 100% | 10000 | 0 | 10000 | 10000 | 10000 | 9950 | 9950 | 0 | 10000 | 7000 | 0 | 7000 | 6479.05 | 2838.5 | 44 |  | 3531.55 | 65 |  | 13746.3 | 4528.03 | 93.25 |  | 9060.02 | 65 |  | 0 | 3746.3 | 196.4% |  | 0 | 13746.3 | 3000 | 30% | 0 | 3000 | 30% | 0 |  | -3746.3 | -37.46% | -3746.3 | -37.46% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892049 - HERRERA FARMING CO | WATER | WATER EQUIPMENT SALES | 2019-06-19 | 2019-09-30 | 2019-06-19 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 924571¦¦2020-03-31
TM | C | Yes | 924572 |  | BEVERLY HILLS FIRE PUMP | BRASHEAR, DAVID M | 100% | 14670 | 0 | 14670 | 14672.38 | 14672.38 | 15359.33 | 0 | 0 | 14672.38 | 10974 | 0 | 10974 | [7 empty] | 13629.29 | 3410.26 | 1513.9 |  | 8705.13 |  |  | 1043.09 | 0 | 124.2% |  | 0 | 13629.29 | 3696 | 25.19% | 0 | 3696 | 25.19% | 0 |  | 1043.09 | 7.109% | 1043.09 | 7.109% | -2.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878627 - BEVERLY HILLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-09-02 | 2019-06-01 | 2019-09-02 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 924572¦¦2020-03-31
TM | CJ | Yes | 925042 |  | WILL TARKINGTON PR | BENNETT, MARK C. | 100% | 18000 | 0 | 18000 | 18000 | 18000 | 15674.64 | 0 | 0 | 18000 | 12800 | 0 | 12800 | 0.17 |  |  |  | 0.17 |  |  | 18351.65 | 5608 | 883.44 |  | 11860.21 |  |  | 0 | 351.65 | 143.4% |  | 0 | 18351.65 | 5200 | 28.89% | 0 | 5200 | 28.89% | 0 |  | -351.65 | -1.954% | -351.65 | -1.954% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 1009080 - EF INC | WATER | WATER REPAIR & INSTALLATION | 2019-06-20 | 2019-09-30 | 2019-06-20 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 925042¦¦2020-03-31
TM | C | Yes | 925043 |  | MONSANTO FARM AND WILDLIFE PR | BENNETT, MARK C. | 100% | 18000 | 0 | 18000 | 68001.11 | 68001.11 | 69329.46 | 0 | 0 | 68001.11 | 12600 | 0 | 12600 | [7 empty] | 63907.54 | 15597.87 | 5221.76 |  | 43087.91 |  |  | 4093.57 | 0 | 507.2% |  | 0 | 63907.54 | 5400 | 30% | 0 | 5400 | 30% | 0 |  | 4093.57 | 6.02% | 4093.57 | 6.02% | -50001.11 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879114 - MONSANTO WILDLIFE & FARM MANAGEMENT CENT | WATER | WATER REPAIR & INSTALLATION | 2019-06-20 | 2019-09-30 | 2019-06-20 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 925043¦¦2020-03-31
TM | C | Yes | 925044 |  | BEVERLY HILLS REV4 BSTER2MOTOR | BRASHEAR, DAVID M | 100% | 8140 | 0 | 8140 | 8140 | 8140 | 8913.3 | 0 | 0 | 8140 | 6512 | 0 | 6512 | [7 empty] | 9145.19 | 938.97 | 184.91 |  | 8021.31 |  |  | 0 | 1005.19 | 140.4% |  | 0 | 9145.19 | 1628 | 20% | 0 | 1628 | 20% | 0 |  | -1005.19 | -12.35% | -1005.19 | -12.35% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878627 - BEVERLY HILLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-10 | 2019-07-25 | 2019-06-10 | 2019-07-25 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 925044¦¦2020-03-31
FP | C | Yes | 925046 |  | HAYS KS 2019 WELL WORK | WARTICK, LOGAN M | 100% | 67230 | 52668.85 | 119898.85 | 119898.85 | 119898.85 | 119898.85 | 0 | 0 | 119898.85 | 53784 | 42293.52 | 96077.52 | [7 empty] | 125047.35 | 36395.24 | 24119.19 |  | 51776.87 | 12756.05 |  | 0 | 5148.5 | 130.2% |  | 0 | 125047.35 | 13446 | 20% | 10375.33 | 23821.33 | 19.87% | 0 |  | -5148.5 | -4.294% | -5148.5 | -4.294% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 891930 - HAYS, KS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-21 | 2019-07-30 | 2019-06-21 | 2019-07-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 925046¦¦2020-03-31
TM | C | Yes | 925047 |  | FIELD PACKING REHAB 1 | MIGUEL, SEAN J. | 100% | 16631 | 6096 | 22727 | 22727 | 22727 | 22727 | 0 | 0 | 22727 | 13067 | 4267 | 17334 | [7 empty] | 23388.89 | 7619.47 | 4089.55 |  | 11679.87 |  |  | 0 | 661.89 | 134.9% |  | 0 | 23388.89 | 3564 | 21.43% | 1829 | 5393 | 23.73% | 0 |  | -661.89 | -2.912% | -661.89 | -2.912% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 890641 - FIELD PACKING COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-06-18 | 2019-08-31 | 2019-06-18 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 925047¦¦2020-03-31
TM | CJ | Yes | 925056 |  | WELL 33 RIO TINTO BORON | BRASHEAR, DAVID M | 100% | 11844 | 46140.68 | 57984.68 | 48378.11 | 48378.11 | 37311.96 | 25468.42 | 0 | 48378.11 | 8650 | 33608.32 | 42258.32 | 1330.37 | 691.93 | 247.68 |  | 390.76 |  |  | 39084.41 | 13443.22 | 5457.4 |  | 20183.79 |  |  | 9293.7 | 0 | 92.49% |  | 0 | 39084.41 | 3194 | 26.97% | 12532.36 | 15726.36 | 27.12% | 0 |  | 9293.7 | 19.21% | 9293.7 | 19.21% | 9606.57 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 897054 - RIO TINTO MINERALS BORON OPERATIONS | WATER | WATER REPAIR & INSTALLATION | 2019-06-17 | 2019-08-31 | 2019-06-17 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 925056¦¦2020-03-31
TM | C | Yes | 925066 |  | CAM PAR 10 TEST 2 WELLS | ALBARADO, JORDAN A | 100% | 1200 | 0 | 1200 | 1200 | 1200 | 1200 | 0 | 0 | 1200 | 800 | 0 | 800 | [7 empty] | 1758.61 | 1164.05 | 153.93 |  | 440.63 |  |  | 0 | 558.61 | 219.8% |  | 0 | 1758.61 | 400 | 33.33% | 0 | 400 | 33.33% | 0 |  | -558.61 | -46.55% | -558.61 | -46.55% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 887834 - CAMERON PARISH WATERWORKS DISTRICT 10 | WATER | WATER REPAIR & INSTALLATION | 2019-06-21 | 2019-07-24 | 2019-06-21 | 2019-07-24 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 925066¦¦2020-03-31
FP | CJ | Yes | 925271 |  | GSW FAIRHAVEN 3 PUMP EQUIPING | SEIDEN, ANDREW L. | 100% | 153153 | 0 | 153153 | 151053 | 151053 | 151053 | 2100 | 7552.65 | 151053 | 117986 | 0 | 117986 | 2701.88 | 1317.52 |  |  | 1384.36 |  |  | 132093.98 | 6968.41 | 1300.33 |  | 123825.24 |  |  | 18959.02 | 0 | 112% |  | 0 | 132093.98 | 35167 | 22.96% | 0 | 35167 | 22.96% | 0 |  | 18959.02 | 12.55% | 18959.02 | 12.55% | 2100 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 301724 - CORA CONSTRUCTORS | WATER | WATER REPAIR & INSTALLATION | 2019-06-20 | 2020-01-31 | 1900-01-01 | 2020-01-31 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 925271¦¦2020-03-31
TM | C | Yes | 926318 |  | INDIAN RIVER ECO DISTRICT 2019 | BRUGGER, CRAIG J. | 100% | 25465 | 0 | 25465 | 25465 | 25465 | 25465 | 0 | 0 | 25465 | 16140 | 0 | 16140 | [7 empty] | 10401.86 | 4112.32 | 4986.25 |  | 1303.29 |  |  | 15063.14 | 0 | 64.45% |  | 0 | 10401.86 | 9325 | 36.62% | 0 | 9325 | 36.62% | 0 |  | 15063.14 | 59.15% | 15063.14 | 59.15% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 925348 - INDIAN RIVER ECO DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-06-21 | 2019-07-01 | 1900-01-01 | 2019-07-01 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 926318¦¦2020-03-31
TM | CJ | Yes | 926325 |  | R360 - PUMP REPAIRS | ALBARADO, JORDAN A | 100% | 8000 | 0 | 8000 | 2638.01 | 2638.01 | 0 | 0 | 0 | 2638.01 | 4000 | 0 | 4000 | [7 empty] | 2131.23 | 645.22 |  |  | 1486.01 |  |  | 506.78 | 0 | 53.28% |  | 0 | 2131.23 | 4000 | 50% | 0 | 4000 | 50% | 0 |  | 506.78 | 19.21% | 506.78 | 19.21% | 5361.99 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 896722 - R360 ENVIRONMENTAL SOLUTIONS | WATER | WATER REPAIR & INSTALLATION | 2019-06-24 | 2019-06-28 | 1900-01-01 | 2019-06-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 926325¦¦2020-03-31
TM | C | Yes | 926446 |  | ALFRED NY WELL 1 REHAB PUMP | CROOK, CHARLES M | 100% | 34655 | 0 | 34655 | 42495 | 42495 | 42495 | 0 | 0 | 42495 | 24655 | 0 | 24655 | [7 empty] | 30857.81 | 15245.75 | 5188.43 |  | 9223.63 | 1200 |  | 11637.19 | 0 | 125.2% |  | 0 | 30857.81 | 10000 | 28.86% | 0 | 10000 | 28.86% | 0 |  | 11637.19 | 27.38% | 11637.19 | 27.38% | -7840 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 886067 - ALFRED, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-18 | 2019-09-06 | 1900-01-01 | 2019-09-06 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 926446¦¦2020-03-31
TM | CJ | Yes | 927435 |  | TITAN TIRE-MECHANICAL SEAL | ANDERSON, STEPHEN P. | 100% | 1400 | 4530 | 5930 | 3974.06 | 3974.06 | 1400 | 0 | 0 | 3974.06 | 980 | 3171 | 4151 | [7 empty] | 3210.62 | 564.88 | 407 |  | 2238.74 |  |  | 763.44 | 0 | 77.35% |  | 0 | 3210.62 | 420 | 30% | 1359 | 1779 | 30% | 0 |  | 763.44 | 19.21% | 763.44 | 19.21% | 1955.94 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 898969 - TITAN TIRE UNION CITY | WATER | WATER REPAIR & INSTALLATION | 2019-06-20 | 2019-07-07 | 1900-01-01 | 2019-07-07 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 927435¦¦2020-03-31
TM | C | Yes | 927442 |  | SOLAR LAND CO- PUMP REPAIR | BENNETT, MARK C. | 100% | 8000 | 0 | 8000 | 22571.34 | 22571.34 | 24264.25 | 0 | 0 | 22571.34 | 5600 | 0 | 5600 | [7 empty] | 27826.54 | 8034.12 | 1204.78 |  | 18587.64 |  |  | 0 | 5255.2 | 496.9% |  | 0 | 27826.54 | 2400 | 30% | 0 | 2400 | 30% | 0 |  | -5255.2 | -23.28% | -5255.2 | -23.28% | -14571.34 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 897974 - SOLLARS BROTHERS | WATER | WATER REPAIR & INSTALLATION | 2019-06-24 | 2019-09-30 | 1900-01-01 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 927442¦¦2020-03-31
TM | CJ | Yes | 927443 |  | CITY OF BEVERLY HILLS WELL 2 | SEIDEN, ANDREW L. | 100% | 13384.85 | 60897 | 74281.85 | 74281.52 | 74281.52 | 78763.7 | 0 | 0 | 74281.52 | 10526 | 49606.72 | 60132.72 | 7553.06 | 4768.88 | 495.9 |  | 2288.28 |  |  | 72706.15 | 15810.69 | 2905.02 |  | 53990.44 |  |  | 1575.37 | 0 | 120.9% |  | 0 | 72706.15 | 2858.85 | 21.36% | 11290.28 | 14149.13 | 19.05% | 0 |  | 1575.37 | 2.121% | 1575.37 | 2.121% | 0.33 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878627 - BEVERLY HILLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-24 | 2019-09-11 | 1900-01-01 | 2019-09-11 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 927443¦¦2020-03-31
TM | CJ | Yes | 927445 |  | PLATTSMIER HULIN - GEAR DRIVE | ALBARADO, JORDAN A | 100% | 6000 | 0 | 6000 | 12.37 | 12.37 | 0 | 0 | 0 | 12.37 | 3000 | 0 | 3000 | [7 empty] | 9.99 |  |  |  | 9.99 |  |  | 2.38 | 0 | 0.333% |  | 0 | 9.99 | 3000 | 50% | 0 | 3000 | 50% | 0 |  | 2.38 | 19.24% | 2.38 | 19.24% | 5987.63 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 896405 - PLATTSMIER HULIN | WATER | WATER REPAIR & INSTALLATION | 2019-06-10 | 2019-06-24 | 1900-01-01 | 2019-06-24 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 927445¦¦2020-03-31
UP | C | Yes | 927614 |  | WAPPINGERS FALLS NY PWM | CROOK, CHARLES M | 100% | 2250 | 0 | 2250 | 2250 | 2250 | 2250 | 0 | 0 | 2250 | 1550 | 0 | 1550 | 0 |  |  |  | 0 |  |  | 2167.22 | 1386.88 | 227.23 |  | 553.11 |  |  | 82.78 | 0 | 139.8% |  | 0 | 2167.22 | 700 | 31.11% | 0 | 700 | 31.11% | 0 |  | 82.78 | 3.679% | 82.78 | 3.679% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 899837 - WAPPINGERS FALLS, NY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-24 | 2019-09-10 | 1900-01-01 | 2019-09-10 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 927614¦¦2020-03-31
TM | C | Yes | 927639 |  | EXXON ANCHORAGE P-10 | GNAU, CASEY T | 100% | 14930 | 26760 | 41690 | 41690 | 41690 | 41690 | 0 | 0 | 41690 | 8958 | 13380 | 22338 | [7 empty] | 20644.28 | 6807.49 | 531.09 |  | 13305.7 |  |  | 21045.72 | 0 | 92.42% |  | 0 | 20644.28 | 5972 | 40% | 13380 | 19352 | 46.42% | 0 |  | 21045.72 | 50.48% | 21045.72 | 50.48% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 890523 - EXXONMOBIL REFINING & MARKETING | WATER | WATER REPAIR & INSTALLATION | 2019-06-25 | 2019-08-30 | 1900-01-01 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 927639¦¦2020-03-31
TM | C | Yes | 927947 |  | WMWD HILLSIDE BOOSTER 4 | SEIDEN, ANDREW L. | 100% | 3045 | 23347.63 | 26392.63 | 26392.63 | 26392.63 | 27746.76 | 0 | 0 | 26392.63 | 2745 | 15944.94 | 18689.94 | [7 empty] | 19398.52 | 3363.12 | 707.83 |  | 14825.57 | 502 |  | 6994.11 | 0 | 103.8% |  | 0 | 19398.52 | 300 | 9.852% | 7402.69 | 7702.69 | 29.19% | 0 |  | 6994.11 | 26.5% | 6994.11 | 26.5% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 900107 - WESTERN MUNICIPAL WATER DISTRICT | WATER | DAM / RESERVOIR | 2019-06-17 | 2019-07-30 | 1900-01-01 | 2019-07-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 927947¦¦2020-03-31
TM | CJ | Yes | 928182 |  | TESI GIROURARD | ALBARADO, JORDAN A | 100% | 8137 | 0 | 8137 | 2743.65 | 2743.65 | 0 | 0 | 0 | 2743.65 | 4068 | 0 | 4068 | [7 empty] | 2216.58 |  |  |  | 2216.58 |  |  | 527.07 | 0 | 54.49% |  | 0 | 2216.58 | 4069 | 50.01% | 0 | 4069 | 50.01% | 0 |  | 527.07 | 19.21% | 527.07 | 19.21% | 5393.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 898763 - TESI | WATER | WATER REPAIR & INSTALLATION | 2019-06-25 | 2019-06-25 | 1900-01-01 | 2019-06-25 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 928182¦¦2020-03-31
TM | CJ | Yes | 928184 |  | WESTROCK 23-WATER WELL REPAIR | GNAU, CASEY T | 100% | 29300 | 171030 | 200330 | 200330 | 200330 | 200330 | 0 | 0 | 200330 | 16465 | 85769 | 102234 | [7 empty] | 100683.7 | 29956.7 | 10275.11 |  | 52823.94 | 7627.95 |  | 99646.3 | 0 | 98.48% |  | 0 | 100683.7 | 12835 | 43.81% | 85261 | 98096 | 48.97% | 0 |  | 99646.3 | 49.74% | 99646.3 | 49.74% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2019-06-26 | 2019-07-15 | 1900-01-01 | 2019-07-15 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 928184¦¦2020-03-31
TM | C | Yes | 928185 |  | ALEXANDRIA 928 | GNAU, CASEY T | 100% | 43717.2 | -13245.2 | 30472 | 29183.8 | 29183.8 | 29183.8 | 0 | 0 | 29183.8 | 30602 | -8357 | 22245 | [7 empty] | 22921.04 | 3824.09 | 1158.6 |  | 17035.39 | 902.96 |  | 6262.76 | 0 | 103% |  | 0 | 22921.04 | 13115.2 | 30% | -4888.2 | 8227 | 27% | 0 |  | 6262.76 | 21.46% | 6262.76 | 21.46% | 1288.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 910215 - MEYER MEYER LACROIX AND HIXSON INC | WATER | WATER REPAIR & INSTALLATION | 2019-06-07 | 2019-09-08 | 1900-01-01 | 2019-09-08 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 928185¦¦2020-03-31
TM | C | Yes | 928224 |  | AK COSHOCTON WELL 1 | BARNES, MATTHEW D | 100% | 26940 | 12131 | 39071 | 39071 | 39071 | 39071 | 0 | 0 | 39071 | 18850 | 9704 | 28554 | [7 empty] | 54283.96 | 18767.32 | 16644.41 |  | 18872.23 |  |  | 0 | 15212.96 | 190.1% |  | 0 | 54283.96 | 8090 | 30.03% | 2427 | 10517 | 26.92% | 0 |  | -15212.96 | -38.94% | -15212.96 | -38.94% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER SUPPLY | 2019-06-27 | 2019-08-30 | 2019-06-27 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 928224¦¦2020-03-31
TM | C | Yes | 928269 |  | ALEXANDRIA 1292 | GNAU, CASEY T | 100% | 195187.76 | -28668.58 | 166519.18 | 166519.42 | 166519.42 | 166519.42 | 0 | 0 | 166519.42 | 136632 | -20068 | 116564 | [7 empty] | 118046.7 | 35594.45 | 38670.12 |  | 43382.13 | 400 |  | 48472.72 | 0 | 101.3% |  | 0 | 118046.7 | 58555.76 | 30% | -8600.58 | 49955.18 | 30% | 0 |  | 48472.72 | 29.11% | 48472.72 | 29.11% | -0.24 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 910215 - MEYER MEYER LACROIX AND HIXSON INC | WATER | WATER REPAIR & INSTALLATION | 2019-06-07 | 2019-09-08 | 1900-01-01 | 2019-09-08 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 928269¦¦2020-03-31
TM | C | Yes | 928299 |  | COLOG BOREHOLE TOOL RENTAL | TORMOEHLEN, DAVID A. | 100% | 3500 | 0 | 3500 | 3500 | 3500 | 3500 | 0 | 0 | 3500 | [10 empty] | 1.72 |  |  |  | 1.72 |  |  | 3498.28 | 0 |  |  | 0 | 1.72 | 3500 | 100% | 0 | 3500 | 100% | 0 |  | 3498.28 | 99.95% | 3498.28 | 99.95% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 888783 - COLOG INC | WATER | WATER EQUIPMENT SALES | 2019-06-01 | 2009-06-10 | 1900-01-01 | 2019-06-10 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 928299¦¦2020-03-31
TM | C | Yes | 929484 |  | MOSAIC NEW WALES WELL PB-4 RPR | BRUGGER, CRAIG J. | 100% | 21500 | 0 | 21500 | 21070 | 21070 | 21070 | 0 | 0 | 21070 | 14685 | 0 | 14685 | [7 empty] | 12545.85 | 5594.05 | 4016.78 |  | 2935.02 |  |  | 8524.15 | 0 | 85.43% |  | 0 | 12545.85 | 6815 | 31.7% | 0 | 6815 | 31.7% | 0 |  | 8524.15 | 40.46% | 8524.15 | 40.46% | 430 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895020 - MOSAIC NEW WALES | WATER | WATER REPAIR & INSTALLATION | 2019-06-28 | 2019-07-10 | 1900-01-01 | 2019-07-10 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 929484¦¦2020-03-31
TM | CJ | Yes | 930153 |  | DEKALB IL WELL 10 | BALLUFF, WILLIAM O. | 100% | 30000 | 119975 | 149975 | 101880.4 | 101880.4 | 101880.4 | 17866 | 0 | 101880.4 | 22500 | 96329.57 | 118829.57 | 9014.26 | 5143.46 | 320.21 |  | 3550.59 |  |  | 82937.38 | 40380.84 | 7327.63 |  | 35228.91 |  |  | 18943.02 | 0 | 69.8% |  | 0 | 82937.38 | 7500 | 25% | 23645.43 | 31145.43 | 20.77% | 0 |  | 18943.02 | 18.59% | 18943.02 | 18.59% | 48094.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 889433 - DEKALB, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-02 | 2019-08-16 | 1900-01-01 | 2019-08-16 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 930153¦¦2020-03-31
TM | C | Yes | 930217 |  | PERU IL WELL 9 | BALLUFF, WILLIAM O. | 100% | 35000 | 151391 | 186391 | 186204.5 | 186204.5 | 186204.5 | 0 | 0 | 186204.5 | 26250 | 114409.15 | 140659.15 | 685.18 | 471.85 | 87.43 |  | 125.9 |  |  | 142590.96 | 61828.37 | 7208.07 |  | 73477.72 | 76.8 |  | 43613.54 | 0 | 101.4% |  | 0 | 142590.96 | 8750 | 25% | 36981.85 | 45731.85 | 24.54% | 0 |  | 43613.54 | 23.42% | 43613.54 | 23.42% | 186.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 896232 - PERU, IL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-01 | 2019-08-16 | 1900-01-01 | 2019-08-16 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 930217¦¦2020-03-31
FP | CJ | Yes | 930336 |  | NJAW NAZARETH WELL PILOT | CHESLEY, ANDREW J | 100% | 98600 | 0 | 98600 | 98600 | 98600 | 53205.88 | 2665.63 | 0 | 98600 | 66719.52 | 0 | 66719.52 | 1158.84 | 1034.49 |  |  | 124.35 |  |  | 98995.93 | 27218.76 | 1677.19 |  | 56215.88 | 13884.1 |  | 0 | 395.93 | 148.4% |  | 0 | 98995.93 | 31880.48 | 32.33% | 0 | 31880.48 | 32.33% | 0 |  | -395.93 | -0.4016% | -395.93 | -0.4016% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 895316 - NEW JERSEY AMERICAN WATER | WATER | WATER TREATMENT | 2019-07-01 | 2020-07-31 | 1900-01-01 | 2020-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 930336¦¦2020-03-31
FP | C | Yes | 930450 |  | MADISON CO WTP VALVES | BARNES, MATTHEW D | 100% | 32247 | 0 | 32247 | 32247 | 32247 | 32247 | 0 | 0 | 32247 | 20900 | 0 | 20900 | [7 empty] | 23887.25 | 1800.83 | 344.89 |  | 21741.53 |  |  | 8359.75 | 0 | 114.3% |  | 0 | 23887.25 | 11347 | 35.19% | 0 | 11347 | 35.19% | 0 |  | 8359.75 | 25.92% | 8359.75 | 25.92% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878952 - MADISON COUNTY SEWER AND WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-07-02 | 2019-10-31 | 2019-07-02 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 930450¦¦2020-03-31
FP | CJ | Yes | 930454 |  | GREEN RIVER PM | MIGUEL, SEAN J. | 100% | 2925 | 69801 | 72726 | 75014 | 75014 | 75014 | 0 | 0 | 75014 | 2025 | 51265 | 53290 | 0 |  |  |  | 0 |  |  | 50087.34 | 12069.45 | 3984.25 |  | 26991.58 | 7042.06 |  | 24926.66 | 0 | 93.99% |  | 0 | 50087.34 | 900 | 30.77% | 18536 | 19436 | 26.72% | 0 |  | 24926.66 | 33.23% | 24926.66 | 33.23% | -2288 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 891577 - GREEN RIVER VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-07-03 | 2019-09-30 | 2019-07-03 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 930454¦¦2020-03-31
TM | C | Yes | 930593 |  | MONROVIA B1-3 | SEIDEN, ANDREW L. | 100% | 1327.5 | 0 | 1327.5 | 1327.5 | 1327.5 | 1327.5 | 0 | 0 | 1327.5 | 1062 | 0 | 1062 | [7 empty] | 145.79 | 143.42 |  |  | 2.37 |  |  | 1181.71 | 0 | 13.73% |  | 0 | 145.79 | 265.5 | 20% | 0 | 265.5 | 20% | 0 |  | 1181.71 | 89.02% | 1181.71 | 89.02% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879074 - MONROVIA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-17 | 2019-06-28 | 2019-06-27 | 2019-06-28 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 930593¦¦2020-03-31
UP | C | Yes | 930625 |  | DRILL TWO PRODUCTION WELLS PM | COMBS, TAYLOR E. | 100% | 749960.6 | 0 | 749960.6 | 733590.96 | 733590.96 | 733590.96 | 0 | 0 | 733590.96 | 601513.94 | 0 | 601513.94 | [7 empty] | 819698.4 | 163633.77 | 344207.31 |  | 292177.32 | 19680 |  | 0 | 86107.44 | 136.3% |  | 0 | 819698.4 | 148446.66 | 19.79% | 0 | 148446.66 | 19.79% | 0 |  | -86107.44 | -11.74% | -86107.44 | -11.74% | 16369.64 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 899186 - TUCSON, CITY OF | WATER | WATER SUPPLY | 2019-06-01 | 2019-10-08 | 1900-01-01 | 2019-10-08 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 930625¦¦2020-03-31
FP | C | Yes | 930637 |  | US WATER LEHIGH ACRES WELL | BRUGGER, CRAIG J. | 100% | 9614 | 0 | 9614 | 9614 | 9614 | 9614 | 0 | 0 | 9614 | 6175 | 0 | 6175 | [7 empty] | 2168.55 | 1165.95 | 454.21 |  | 548.39 |  |  | 7445.45 | 0 | 35.12% |  | 0 | 2168.55 | 3439 | 35.77% | 0 | 3439 | 35.77% | 0 |  | 7445.45 | 77.44% | 7445.45 | 77.44% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 899491 - US WATER SERVICES CORP | WATER | WATER REPAIR & INSTALLATION | 2019-06-12 | 2019-07-15 | 1900-01-01 | 2019-07-15 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 930637¦¦2020-03-31
UP | C | Yes | 930746 |  | N LEE CO WATER TRT PLANT WELL | MCCULLERS, BLAKE E. | 100% | 136518 | 0 | 136518 | 136518 | 136518 | 136518 | 0 | 0 | 136518 | 103168 | 0 | 103168 | [7 empty] | 79973.57 | 13473.34 | 7939.96 |  | 56535.27 | 2025 |  | 56544.43 | 0 | 77.52% |  | 0 | 79973.57 | 33350 | 24.43% | 0 | 33350 | 24.43% | 0 |  | 56544.43 | 41.42% | 56544.43 | 41.42% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878637 - LEE, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-06-27 | 2019-09-30 | 2019-07-15 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 930746¦¦2020-03-31
TM | C | Yes | 931338 |  | APPLE VALLEY GOLF COURSE BOOST | BRASHEAR, DAVID M | 100% | 6879 | 0 | 6879 | 6878.52 | 6878.52 | 7021.11 | 0 | 0 | 6878.52 | 5159 | 0 | 5159 | 0 |  |  |  | 0 |  |  | 7205.54 | 2841.95 | 806.5 |  | 3557.09 |  |  | 0 | 327.02 | 139.7% |  | 0 | 7205.54 | 1720 | 25% | 0 | 1720 | 25% | 0 |  | -327.02 | -4.754% | -327.02 | -4.754% | 0.48 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 886362 - APPLE VALLEY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-05 | 2019-07-22 | 2019-07-05 | 2019-07-22 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 931338¦¦2020-03-31
TM | CJ | Yes | 931340 |  | BEVERLY HILLS WELL 6 | SEIDEN, ANDREW L. | 100% | 44151 | 61231.57 | 105382.57 | 97397.83 | 97397.83 | 101911.83 | 0 | 0 | 97397.83 | 36108 | 49608.45 | 85716.45 | 10792.93 | 6258.33 | 1391.54 |  | 3143.06 |  |  | 78883.19 | 19669.84 | 8796.4 |  | 50416.95 |  |  | 18514.64 | 0 | 92.03% |  | 0 | 78883.19 | 8043 | 18.22% | 11623.12 | 19666.12 | 18.66% | 0 |  | 18514.64 | 19.01% | 18514.64 | 19.01% | 7984.74 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878627 - BEVERLY HILLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-08-25 | 2019-07-03 | 2019-08-25 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 931340¦¦2020-03-31
FP | C | Yes | 931343 |  | SASOL TEST 6 WELLS | ALBARADO, JORDAN A | 100% | 7500 | 0 | 7500 | 7500 | 7500 | 7500 | 0 | 0 | 7500 | 3750 | 0 | 3750 | 0 |  |  |  | 0 |  |  | 3490.82 | 2046.79 | 773.3 |  | 670.73 |  |  | 4009.18 | 0 | 93.09% |  | 0 | 3490.82 | 3750 | 50% | 0 | 3750 | 50% | 0 |  | 4009.18 | 53.46% | 4009.18 | 53.46% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878901 - SASOL NORTH AMERICA INC | WATER | WATER REPAIR & INSTALLATION | 2019-07-08 | 2019-08-31 | 2019-07-08 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 931343¦¦2020-03-31
TM | C | Yes | 931346 |  | LEE COUNTY ASR2 CORKSCREW WELL | MCCULLERS, BLAKE E. | 100% | 46263 | 0 | 46263 | 46263 | 46263 | 46263 | 0 | 0 | 46263 | 34389 | 0 | 34389 | [7 empty] | 29114.51 | 10023.8 | 3314.98 |  | 14800.73 | 975 |  | 17148.49 | 0 | 84.66% |  | 0 | 29114.51 | 11874 | 25.67% | 0 | 11874 | 25.67% | 0 |  | 17148.49 | 37.07% | 17148.49 | 37.07% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878637 - LEE, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-08 | 2019-09-30 | 2019-07-08 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 931346¦¦2020-03-31
TM | C | Yes | 931347 |  | WELL 7A DBR MCAGCC 29 PALMS | BRASHEAR, DAVID M | 100% | 153075 | 21588.97 | 174663.97 | 174664.4 | 174664.4 | 181938.83 | 0 | 0 | 174664.4 | 110273 | 14650.22 | 124923.22 | [7 empty] | 163345.44 | 45754.63 | 15797.28 |  | 100443.53 | 1350 |  | 11318.96 | 0 | 130.8% |  | 0 | 163345.44 | 42802 | 27.96% | 6938.75 | 49740.75 | 28.48% | 0 |  | 11318.96 | 6.48% | 11318.96 | 6.48% | -0.43 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 930898 - DBR GENERAL ENGINEERING | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-10-31 | 2019-06-20 | 2019-10-31 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 931347¦¦2020-03-31
FP | C | Yes | 931369 |  | REDHILL FOREST | SCHANAMAN, MIKE L. | 100% | 16779 | 0 | 16779 | 16306.13 | 16306.13 | 16779 | 0 | 0 | 16306.13 | 11035 | 0 | 11035 | [7 empty] | 11113.89 | 415.99 |  |  | 10697.9 |  |  | 5192.24 | 0 | 100.7% |  | 0 | 11113.89 | 5744 | 34.23% | 0 | 5744 | 34.23% | 0 |  | 5192.24 | 31.84% | 5192.24 | 31.84% | 472.87 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 906313 - REDHILL FOREST POMWACA | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-08-31 | 2019-07-01 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 931369¦¦2020-03-31
TM | CJ | Yes | 931371 |  | DUDA FARMS 20 PWMS | SEIDEN, ANDREW L. | 100% | 61100 | 0 | 61100 | 5092.5 | 5092.5 | 5092.5 | 0 | 0 | 5092.5 | 45919 | 0 | 45919 | 0 |  |  |  | 0 |  |  | 1793.46 | 1106.79 |  |  | 686.67 |  |  | 3299.04 | 0 | 3.906% |  | 0 | 1793.46 | 15181 | 24.85% | 0 | 15181 | 24.85% | 0 |  | 3299.04 | 64.78% | 3299.04 | 64.78% | 56007.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 930908 - DUDA FARM FRESH FOODS | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-07-21 | 2019-07-01 | 2019-07-21 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 931371¦¦2020-03-31
UP | C | Yes | 931372 |  | BONITA SPRINGS WELL 38 | MARTINEZ, MIGUEL E | 100% | 44970 | 0 | 44970 | 44970 | 44970 | 44970 | 0 | 0 | 44970 | 33177 | 0 | 33177 | [7 empty] | 29601.84 | 13882.48 | 5975.94 |  | 9743.42 |  |  | 15368.16 | 0 | 89.22% |  | 0 | 29601.84 | 11793 | 26.22% | 0 | 11793 | 26.22% | 0 |  | 15368.16 | 34.17% | 15368.16 | 34.17% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 930906 - BONITA SPRINGS UTILITIES INC | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-09-02 | 2019-07-01 | 2019-09-02 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 931372¦¦2020-03-31
TM | CJ | Yes | 931739 |  | CITY OF OAKLAND HS PUMP PULL | GANSEBOM, JASON W. | 100% | 12966 | 0 | 12966 | 12966 | 12966 | 6686.3 | 0 | 0 | 12966 | 7836 | 0 | 7836 | [7 empty] | 11195.54 | 3427.53 | 633.29 |  | 7134.72 |  |  | 1770.46 | 0 | 142.9% |  | 0 | 11195.54 | 5130 | 39.57% | 0 | 5130 | 39.57% | 0 |  | 1770.46 | 13.65% | 1770.46 | 13.65% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 895621 - OAKLAND , CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-03 | 2019-09-01 | 2019-07-03 | 2019-09-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 931739¦¦2020-03-31
TM | CJ | Yes | 931740 |  | TIBURON WELL 4 PUMP PULL | GANSEBOM, JASON W. | 100% | 12118 | 0 | 12118 | 19392.8 | 19392.8 | 19925.9 | 19925.9 | 0 | 19392.8 | 7559 | 0 | 7559 | 5918.07 | 2910.4 | 864.57 |  | 2143.1 |  |  | 16503.01 | 4807.56 | 1797.64 |  | 9897.81 |  |  | 2889.79 | 0 | 218.3% |  | 0 | 16503.01 | 4559 | 37.62% | 0 | 4559 | 37.62% | 0 |  | 2889.79 | 14.9% | 2889.79 | 14.9% | -7274.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 898941 - TIBURON SID 158 | WATER | WATER REPAIR & INSTALLATION | 2019-07-03 | 2019-09-30 | 2019-07-03 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 931740¦¦2020-03-31
FP | CJ | Yes | 931741 |  | DENISON IA 2019 REHAB 3 5 AND7 | GANSEBOM, JASON W. | 100% | 44195 | 0 | 44195 | 70573.45 | 70573.45 | 70573.45 | 0 | 0 | 70573.45 | 28727 | 0 | 28727 | 8018.25 | 3181.79 | 1580.05 |  | 2446.41 | 810 |  | 78300.72 | 27318.83 | 14290.08 |  | 35065.81 | 1626 |  | 0 | 7727.27 | 272.6% |  | 0 | 78300.72 | 15468 | 35% | 0 | 15468 | 35% | 0 |  | -7727.27 | -10.95% | -7727.27 | -10.95% | -26378.45 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 889499 - DENISON MUNICIPAL UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-07-02 | 2019-09-30 | 2019-07-02 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 931741¦¦2020-03-31
TM | C | Yes | 931742 |  | MEMPHIS CELLULOSE WELL 8 | ANDERSON, STEPHEN P. | 100% | 24460 | 30058 | 54518 | 54230.22 | 54230.22 | 54230.22 | 0 | 0 | 54230.22 | 17122 | 22581.04 | 39703.04 | 0 |  |  |  | 0 |  |  | 58050.62 | 20250.42 | 6199.75 |  | 31600.45 |  |  | 0 | 3820.4 | 146.2% |  | 0 | 58050.62 | 7338 | 30% | 7476.96 | 14814.96 | 27.17% | 0 |  | -3820.4 | -7.045% | -3820.4 | -7.045% | 287.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 878877 - MEMPHIS CELLULOSE LLC | WATER | WATER REPAIR & INSTALLATION | 2019-07-08 | 2019-09-26 | 2019-07-08 | 2019-09-26 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 931742¦¦2020-03-31
TM | CJ | Yes | 931744 |  | FIRST TRUST WELL 2 R AND I | MIGUEL, SEAN J. | 100% | 27250 | -10500 | 16750 | 16750 | 16750 | 16750 | 0 | 0 | 16750 | 19075 | -7350 | 11725 | [7 empty] | 9328.45 | 3333.22 | 835.63 |  | 4974.1 | 185.5 |  | 7421.55 | 0 | 79.56% |  | 0 | 9328.45 | 8175 | 30% | -3150 | 5025 | 30% | 0 |  | 7421.55 | 44.31% | 7421.55 | 44.31% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 931451 - CUSHMAN AND WAKEFIELD | WATER | WATER REPAIR & INSTALLATION | 2019-07-02 | 2019-08-02 | 2019-07-02 | 2019-08-02 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 931744¦¦2020-03-31
UP | CJ | Yes | 931745 |  | HDR LAWRENCE AVIATION | RANFT, DONALD R | 100% | 128520 | 128480 | 257000 | 93000 | 93000 | 93000 | 0 | 0 | 93000 | 74183 | 112953.1 | 187136.1 | 0 |  |  |  | 0 |  |  | 70418.05 | 30880.59 | 19680.63 |  | 16381.83 | 3475 |  | 22581.95 | 0 | 37.63% |  | 0 | 70418.05 | 54337 | 42.28% | 15526.9 | 69863.9 | 27.18% | 0 |  | 22581.95 | 24.28% | 22581.95 | 24.28% | 164000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 891958 - HDR, INC DENVER | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2020-04-04 | 2019-07-01 | 2020-04-04 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 931745¦¦2020-03-31
TM | C | Yes | 932215 |  | WOODWORTH TEST 2 WELLS | GNAU, CASEY T | 100% | 1200 | 0 | 1200 | 1200 | 1200 | 1200 | 0 | 0 | 1200 | 800 | 0 | 800 | [7 empty] | 246.74 | 181.68 |  |  | 65.06 |  |  | 953.26 | 0 | 30.84% |  | 0 | 246.74 | 400 | 33.33% | 0 | 400 | 33.33% | 0 |  | 953.26 | 79.44% | 953.26 | 79.44% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 900500 - WOODWORTH, LA, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-10 | 2019-08-31 | 2019-07-10 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 932215¦¦2020-03-31
TM | CJ | Yes | 932216 |  | SAPP BROTHERS PERCIVAL IA | GANSEBOM, JASON W. | 100% | 25815 | 0 | 25815 | 62217.79 | 62217.79 | 62217.79 | 0 | 0 | 62217.79 | 16169 | 0 | 16169 | 9746.68 | 2869.47 | 1224.31 |  | 5652.9 |  |  | 59369.29 | 19746.74 | 7693.62 |  | 31848.93 | 80 |  | 2848.5 | 0 | 367.2% |  | 0 | 59369.29 | 9646 | 37.37% | 0 | 9646 | 37.37% | 0 |  | 2848.5 | 4.578% | 2848.5 | 4.578% | -36402.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 897824 - SID I 29 AND HIGHWAY 2 | WATER | WATER REPAIR & INSTALLATION | 2019-07-10 | 2019-08-30 | 2019-07-10 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 932216¦¦2020-03-31
TM | C | Yes | 932409 |  | PINE PRARIE WELL 2 | GNAU, CASEY T | 100% | 41890 | 0 | 41890 | 41890 | 41890 | 41890 | 0 | 0 | 41890 | 25130 | 0 | 25130 | [7 empty] | 24049.07 | 6747.18 | 1258.3 |  | 16043.59 |  |  | 17840.93 | 0 | 95.7% |  | 0 | 24049.07 | 16760 | 40.01% | 0 | 16760 | 40.01% | 0 |  | 17840.93 | 42.59% | 17840.93 | 42.59% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879029 - EVANGELINE PAR WWD 1 | WATER | WATER REPAIR & INSTALLATION | 2019-07-10 | 2019-08-31 | 2019-07-10 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 932409¦¦2020-03-31
TM | C | Yes | 932576 |  | OWENS CORNING WELL 7 REHAB | WARTICK, LOGAN M | 100% | 12349 | 0 | 12349 | 49447 | 49447 | 49447 | 11099 | 0 | 49447 | 10496 | 0 | 10496 | [7 empty] | 44415.9 | 20403.31 | 8624.35 |  | 15388.24 |  |  | 5031.1 | 0 | 423.2% |  | 0 | 44415.9 | 1853 | 15.01% | 0 | 1853 | 15.01% | 0 |  | 5031.1 | 10.17% | 5031.1 | 10.17% | -37098 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 895921 - OWENS CORNING | WATER | WATER REPAIR & INSTALLATION | 2019-07-02 | 2019-09-30 | 2019-07-02 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 932576¦¦2020-03-31
TM | C | Yes | 933632 |  | PLEASANT GROVE AR CITY OF EQ | BURGE, EVERETT E. | 100% | 10000 | 0 | 10000 | 10654.02 | 10654.02 | 11453.07 | 0 | 0 | 10654.02 | 7500 | 0 | 7500 | 0 |  |  |  | 0 |  |  | 10971.86 | 2934.36 | 672.4 |  | 7365.1 |  |  | 0 | 317.84 | 146.3% |  | 0 | 10971.86 | 2500 | 25% | 0 | 2500 | 25% | 0 |  | -317.84 | -2.983% | -317.84 | -2.983% | -654.02 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 896408 - PLEASANT GROVE, AR, CITY OF | WATER | WATER EQUIPMENT SALES | 2019-07-01 | 2019-09-27 | 2019-07-01 | 2019-09-27 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 933632¦¦2020-03-31
TM | C | Yes | 933634 |  | R14 INVESTMENTS KETT ENG | VAN ALLEN, WESLEY C. | 100% | 5749 | 11869 | 17618 | 17618 | 17618 | 17618 | 0 | 0 | 17618 | 4399 | 17251.06 | 21650.06 | [7 empty] | 21676.92 | 5588.09 | 3335.45 |  | 12753.38 |  |  | 0 | 4058.92 | 100.1% |  | 0 | 21676.92 | 1350 | 23.48% | -5382.06 | -4032.06 | -22.89% | 0 |  | -4058.92 | -23.04% | -4058.92 | -23.04% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 931924 - KETT ENGINEERING R14 INVESTMENTS | WATER | WATER REPAIR & INSTALLATION | 2019-07-10 | 2019-07-18 | 2019-07-10 | 2019-07-18 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 933634¦¦2020-03-31
FP | C | Yes | 933636 |  | SCVWD BOOSTER REPAIR B18 | GRACE, GARY L. | 100% | 10529 | 0 | 10529 | 10528.6 | 10528.6 | 11275.87 | 0 | 0 | 10528.6 | 7498 | 0 | 7498 | [7 empty] | 8531.88 | 979.16 | 196.94 |  | 7355.78 |  |  | 1996.72 | 0 | 113.8% |  | 0 | 8531.88 | 3031 | 28.79% | 0 | 3031 | 28.79% | 0 |  | 1996.72 | 18.96% | 1996.72 | 18.96% | 0.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878930 - SANTA CLARITA VALLEY WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-08-12 | 2019-07-01 | 2019-08-12 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 933636¦¦2020-03-31
FP | C | Yes | 933637 |  | SCVWD BOOSTER REPL PINE TREE | GRACE, GARY L. | 100% | 14897 | 0 | 14897 | 14896.93 | 14896.93 | 15971.76 | 0 | 0 | 14896.93 | 11043 | 0 | 11043 | [7 empty] | 10988.1 | 672.06 | 46.8 |  | 10269.24 |  |  | 3908.83 | 0 | 99.5% |  | 0 | 10988.1 | 3854 | 25.87% | 0 | 3854 | 25.87% | 0 |  | 3908.83 | 26.24% | 3908.83 | 26.24% | 0.07 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 897478 - SANTA CLARITA VALLEY WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2019-07-12 | 2019-08-12 | 2019-07-12 | 2019-08-12 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 933637¦¦2020-03-31
TM | C | Yes | 933744 |  | ARKEMA WELL 1 | PARSLEY, TRISTAN S | 100% | 1800 | 11500 | 13300 | 13300 | 13300 | 13300 | 0 | 0 | 13300 | 1078 | 7610 | 8688 | [7 empty] | 16674.28 | 5475.74 | 4180.85 |  | 6267.69 | 750 |  | 0 | 3374.28 | 191.9% |  | 0 | 16674.28 | 722 | 40.11% | 3890 | 4612 | 34.68% | 0 |  | -3374.28 | -25.37% | -3374.28 | -25.37% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 886488 - ARKEMA INC | WATER | WATER REPAIR & INSTALLATION | 2019-07-13 | 2019-08-30 | 2019-07-11 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 933744¦¦2020-03-31
FP | C | Yes | 933745 |  | SCVWD PRESELY BOOSTER B42 | GRACE, GARY L. | 100% | 19271 | 0 | 19271 | 19271.06 | 19271.06 | 20593.81 | 0 | 0 | 19271.06 | 14132 | 0 | 14132 | [7 empty] | 16364.36 | 1725.2 | 178.54 |  | 14460.62 |  |  | 2906.7 | 0 | 115.8% |  | 0 | 16364.36 | 5139 | 26.67% | 0 | 5139 | 26.67% | 0 |  | 2906.7 | 15.08% | 2906.7 | 15.08% | -0.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878930 - SANTA CLARITA VALLEY WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2019-07-11 | 2019-08-12 | 2019-07-11 | 2019-08-12 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 933745¦¦2020-03-31
FP | C | Yes | 933862 |  | WC PETRO TEST 2 WELLS | ALBARADO, JORDAN A | 100% | 3000 | 0 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 3000 | 1500 | 0 | 1500 | [7 empty] | 1477.36 | 849.66 | 244.2 |  | 383.5 |  |  | 1522.64 | 0 | 98.49% |  | 0 | 1477.36 | 1500 | 50% | 0 | 1500 | 50% | 0 |  | 1522.64 | 50.75% | 1522.64 | 50.75% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 900146 - WESTLAKE PETROCHEMICALS LP | WATER | WATER REPAIR & INSTALLATION | 2019-07-15 | 2019-07-31 | 2019-07-15 | 2019-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 933862¦¦2020-03-31
FP | C | Yes | 933864 |  | NOURYON MOTOR CLUTCH | ANDERSON, STEPHEN P. | 100% | 1362 | 0 | 1362 | 1362 | 1362 | 1362 | 0 | 0 | 1362 | 953 | 0 | 953 | [7 empty] | 693.84 | 71.92 | 23.4 |  | 598.52 |  |  | 668.16 | 0 | 72.81% |  | 0 | 693.84 | 409 | 30.03% | 0 | 409 | 30.03% | 0 |  | 668.16 | 49.06% | 668.16 | 49.06% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 927621 - NOURYON PULP AND PERFORMANCE CHEM LLC | WATER | WATER REPAIR & INSTALLATION | 2019-07-15 | 2019-07-31 | 2019-07-15 | 2019-07-31 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 933864¦¦2020-03-31
FP | C | Yes | 933866 |  | FOUNTAIN WELL 4 VFD | SCHANAMAN, MIKE L. | 100% | 7760 | 0 | 7760 | 7760 | 7760 | 7760 | 0 | 0 | 7760 | 5188 | 0 | 5188 | [7 empty] | 517.58 | 315.01 | 46.64 |  | 155.93 |  |  | 7242.42 | 0 | 9.976% |  | 0 | 517.58 | 2572 | 33.14% | 0 | 2572 | 33.14% | 0 |  | 7242.42 | 93.33% | 7242.42 | 93.33% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 890822 - FOUNTAIN, CO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-15 | 2019-08-31 | 2019-07-15 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | CONST MANAGER/GEN CONTRACTOR | 933866¦¦2020-03-31
FP | C | Yes | 933881 |  | OLIVE BRANCH HSP REPAIRS | ANDERSON, STEPHEN P. | 100% | 4230 | 21652 | 25882 | 25882 | 25882 | 25882 | 0 | 0 | 25882 | 2961 | 15156 | 18117 | 0 |  |  |  | 0 |  |  | 20174.89 | 6490.04 | 1885.97 |  | 11798.88 |  |  | 5707.11 | 0 | 111.4% |  | 0 | 20174.89 | 1269 | 30% | 6496 | 7765 | 30% | 0 |  | 5707.11 | 22.05% | 5707.11 | 22.05% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895759 - OLIVE BRANCH, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-15 | 2019-08-30 | 2019-07-15 | 2019-08-30 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 933881¦¦2020-03-31
TM | C | Yes | 934268 |  | ALPHA RANCH PULL INSPECT VIDEO | SEIDEN, ANDREW L. | 100% | 7427 | 17045.27 | 24472.27 | 26451.8 | 26451.8 | 26451.8 | 5451.8 | 0 | 26451.8 | 5080 | 15050.71 | 20130.71 | [7 empty] | 61845.75 | 25036.49 | 13543.74 |  | 23265.52 |  |  | 0 | 35393.95 | 307.2% |  | 0 | 61845.75 | 2347 | 31.6% | 1994.56 | 4341.56 | 17.74% | 0 |  | -35393.95 | -133.8% | -35393.95 | -133.8% | -1979.53 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 931807 - ALPHA RANCH | WATER | WATER REPAIR & INSTALLATION | 2019-07-09 | 2019-07-13 | 2019-07-09 | 2019-07-13 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 934268¦¦2020-03-31
TM | C | Yes | 934269 |  | LEAD FORK LLC | BENNETT, MARK C. | 100% | 75279 | 0 | 75279 | 102201.63 | 102201.63 | 102572.88 | 0 | 0 | 102201.63 | 60223 | 0 | 60223 | [7 empty] | 154668.84 | 39335.8 | 28868.98 |  | 86464.06 |  |  | 0 | 52467.21 | 256.8% |  | 0 | 154668.84 | 15056 | 20% | 0 | 15056 | 20% | 0 |  | -52467.21 | -51.34% | -52467.21 | -51.34% | -26922.63 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878949 - LEAD FORK FARM | WATER | WATER SUPPLY | 2019-07-15 | 2019-09-30 | 2019-07-15 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 934269¦¦2020-03-31
FP | C | Yes | 934274 |  | BASF P804 FLOWTEST | GREGORY, CRYSTAL N | 100% | 2650 | 0 | 2650 |  |  | 0 | 0 | 0 |  | 2095 | 0 | 2095 | [7 empty] | 182 |  |  |  | 182 |  |  | 0 | 182 | 8.687% |  | 0 | 182 | 555 | 20.94% | 0 | 555 | 20.94% | 0 |  | -182 |  | -182 |  | 2650 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878707 - BASF CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-07-15 | 2019-09-30 | 2019-07-15 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 934274¦¦2020-03-31
TM | CJ | Yes | 934275 |  | WHARTON SMITH SHELL CREEK WTP | BRUGGER, CRAIG J. | 100% | 90028 | 0 | 90028 | 132152 | 132152 | 132152 | 9267.03 | 0 | 132152 | 57495 | 0 | 57495 | 2980.64 | 1106.84 | 564.79 |  | 1309.01 |  |  | 63226.78 | 23543.44 | 13374.06 |  | 26309.28 |  |  | 68925.22 | 0 | 110% |  | 0 | 63226.78 | 32533 | 36.14% | 0 | 32533 | 36.14% | 0 |  | 68925.22 | 52.16% | 68925.22 | 52.16% | -42124 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 900236 - WHARTON SMITH, INC | WATER | WATER REPAIR & INSTALLATION | 2019-07-15 | 2019-10-30 | 2019-07-15 | 2019-10-30 | SUBCONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 934275¦¦2020-03-31
FP | C | Yes | 934276 |  | LIBERTY UTILITIE JOPLIN MO2019 | WARTICK, LOGAN M | 100% | 316650 | 470268.5 | 786918.5 | 904704 | 904704 | 904704 | 0 | 0 | 904704 | 252675 | 380237.38 | 632912.38 | 87.8 |  | 0 |  | 87.8 |  |  | 945870.16 | 255590.81 | 219907.59 | 2700 | 414426.63 | 53245.13 | 0 | 0 | 41166.16 | 149.4% |  | 0 | 945870.16 | 63975 | 20.2% | 90031.12 | 154006.12 | 19.57% | 0 |  | -41166.16 | -4.55% | -41166.16 | -4.55% | -117785.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 890230 - EMPIRE DISTRICT ELECTRIC STATELINE | WATER | WATER SUPPLY | 2019-07-15 | 2019-10-31 | 2019-07-15 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 934276¦¦2020-03-31
FP | CJ | Yes | 934683 |  | WEKIVA FALLS RV RESORT WELL | BRUGGER, CRAIG J. | 100% | 65360 | 0 | 65360 | 65360 | 65360 | 65360 | 0 | 0 | 65360 | 43502 | 0 | 43502 | [7 empty] | 18163.79 | 4618.02 | 2061.73 |  | 7471.54 | 4012.5 |  | 47196.21 | 0 | 41.75% |  | 0 | 18163.79 | 21858 | 33.44% | 0 | 21858 | 33.44% | 0 |  | 47196.21 | 72.21% | 47196.21 | 72.21% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 934340 - TOWNSEND HOME SALES LLC | WATER | WATER REPAIR & INSTALLATION | 2019-07-15 | 2019-08-30 | 2019-07-15 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 934683¦¦2020-03-31
TM | C | Yes | 934776 |  | JASPER WCID NO 1 BOOSTER | CALLAHAN, DANIEL E. | 100% | 12365 | 0 | 12365 | 10060 | 10060 | 10060 | 0 | 0 | 10060 | 10203 | 0 | 10203 | [7 empty] | 13407.34 | 1335.71 | 345.27 |  | 11726.36 |  |  | 0 | 3347.34 | 131.4% |  | 0 | 13407.34 | 2162 | 17.48% | 0 | 2162 | 17.48% | 0 |  | -3347.34 | -33.27% | -3347.34 | -33.27% | 2305 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 933943 - JASPER, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-10 | 2019-08-09 | 2019-07-10 | 2019-08-09 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 934776¦¦2020-03-31
FP | C | Yes | 934777 |  | MINNEAPOLIS KS WELL 15 | WARTICK, LOGAN M | 100% | 14575 | 0 | 14575 | 28142.16 | 28142.16 | 28142.16 | 0 | 0 | 28142.16 | 11660 | 0 | 11660 | 43.3 |  |  |  | 43.3 |  |  | 28306.99 | 10316.86 | 5354.63 |  | 12635.5 |  |  | 0 | 164.83 | 242.8% |  | 0 | 28306.99 | 2915 | 20% | 0 | 2915 | 20% | 0 |  | -164.83 | -0.5857% | -164.83 | -0.5857% | -13567.16 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 894780 - MINNEAPOLIS, KS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-16 | 2019-10-31 | 2019-07-16 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 934777¦¦2020-03-31
FP | C | Yes | 934779 |  | KINROSS ROUND MOUNTAIN 2019 | COMBS, TAYLOR E. | 100% | 588563 | 0 | 588563 | 914114.86 | 914114.86 | 914114.86 | 0 | 0 | 914114.86 | 468630 | 0 | 468630 | [7 empty] | 667207.43 | 191250.48 | 146469.26 |  | 329487.69 |  |  | 246907.43 | 0 | 142.4% |  | 0 | 667207.43 | 119933 | 20.38% | 0 | 119933 | 20.38% | 0 |  | 246907.43 | 27.01% | 246907.43 | 27.01% | -325551.86 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 893187 - KINROSS ROUND MOUNTAIN GOLD CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-07-08 | 2019-08-30 | 2019-07-08 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 934779¦¦2020-03-31
TM | CJ | Yes | 934844 |  | MONEE WELL NO 5 PUMP | EISHA, JOSEPH J. | 100% | 78890 | 0 | 78890 | 76714.78 | 76714.78 | 60000 | 0 | 6000 | 76714.78 | 50890 | 0 | 50890 | 0.03 |  |  |  | 0.03 |  |  | 61977.45 | 17011.36 | 830.91 |  | 44135.18 |  |  | 14737.33 | 0 | 121.8% |  | 0 | 61977.45 | 28000 | 35.49% | 0 | 28000 | 35.49% | 0 |  | 14737.33 | 19.21% | 14737.33 | 19.21% | 2175.22 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 1002762 - GASKILL & WALTON CONSTRUCTION CO | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-10-30 | 2019-07-01 | 2019-10-30 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 934844¦¦2020-03-31
FP | CJ | Yes | 934906 |  | WAGNN MAINTENANCE | GRECKI, ROBERT | 100% | 2455 | 0 | 2455 | 2455 | 2455 | 2455 | 0 | 0 | 2455 | 1800 | 0 | 1800 | [7 empty] | 2299.02 | 1421.45 | 293.2 |  | 584.37 |  |  | 155.98 | 0 | 127.7% |  | 0 | 2299.02 | 655 | 26.68% | 0 | 655 | 26.68% | 0 |  | 155.98 | 6.354% | 155.98 | 6.354% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 899895 - WATER AUTHORITY OF GREAT NECK NORTH | WATER | WATER REPAIR & INSTALLATION | 2019-07-17 | 2019-08-31 | 2019-07-17 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 934906¦¦2020-03-31
TM | CJ | Yes | 934907 |  | ELWOOD WELL 8 | KENNEDY, CHRISTOPHER C. | 100% | 496907 | 0 | 496907 | 320841.1 | 320841.1 | 202852 | 0 | 20285.2 | 320841.1 | 397500 | 0 | 397500 | 1.24 |  |  |  | 1.24 |  |  | 259205.77 | 75477.13 | 37353.37 |  | 84989.72 | 61385.55 |  | 61635.33 | 0 | 65.21% |  | 0 | 259205.77 | 99407 | 20.01% | 0 | 99407 | 20.01% | 0 |  | 61635.33 | 19.21% | 61635.33 | 19.21% | 176065.9 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 890207 - ELWOOD, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2020-05-22 | 2019-07-01 | 2020-05-22 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 934907¦¦2020-03-31
TM | C | Yes | 934909 |  | DESERT VIEW MEMORIAL IRRIGATIO | BRASHEAR, DAVID M | 100% | 8347 | 0 | 8347 | 0 | 0 | 0 | 0 | 0 | 0 | 6677 | 0 | 6677 | [7 empty] | 15360.39 | 5584.13 | 1404.9 |  | 8371.36 |  |  | 0 | 15360.39 | 230% |  | 0 | 15360.39 | 1670 | 20.01% | 0 | 1670 | 20.01% | 0 |  | -15360.39 |  | -15360.39 |  | 8347 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 889556 - DESERT VIEW MEMORIAL PARK | WATER | WATER REPAIR & INSTALLATION | 2019-07-15 | 2019-07-30 | 2019-07-15 | 2019-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 934909¦¦2020-03-31
TM | C | Yes | 934953 |  | VANDENBERG WL TO OL CROSSOVER | GRACE, GARY L. | 100% | 74999 | 0 | 74999 | 104294.8 | 104294.8 | 107296.41 | 0 | 0 | 104294.8 | 46854 | 0 | 46854 | [7 empty] | 98726.1 | 31656.2 | 15432.11 |  | 51637.79 |  |  | 5568.7 | 0 | 210.7% |  | 0 | 98726.1 | 28145 | 37.53% | 0 | 28145 | 37.53% | 0 |  | 5568.7 | 5.339% | 5568.7 | 5.339% | -29295.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879053 - AMERICAN WATER ENTERPRISES | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-08-30 | 2019-07-01 | 2019-08-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 934953¦¦2020-03-31
FP | CJ | Yes | 935192 |  | HILLSBORO KS BOOSTER PUMP | WARTICK, LOGAN M | 100% | 5301 | 0 | 5301 | 5301 | 5301 | 5301 | 5301 | 0 | 5301 | 4241 | 0 | 4241 | 1620.81 | 655.44 | 329.74 |  | 253.16 | 382.47 |  | 11363.58 | 4501.27 | 1323.8 |  | 5156.04 | 382.47 |  | 0 | 6062.58 | 267.9% |  | 0 | 11363.58 | 1060 | 20% | 0 | 1060 | 20% | 0 |  | -6062.58 | -114.4% | -6062.58 | -114.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 892124 - HILLSBORO, KS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-02 | 2019-09-30 | 2019-07-02 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 935192¦¦2020-03-31
FP | C | Yes | 935447 |  | OWENS CORNING PM | ANDERSON, STEPHEN P. | 100% | 1150 | 0 | 1150 | 1450 | 1450 | 1450 | 0 | 0 | 1450 | 862 | 0 | 862 | [7 empty] | 1138.86 | 386.88 | 300 |  | 301.98 | 150 |  | 311.14 | 0 | 132.1% |  | 0 | 1138.86 | 288 | 25.04% | 0 | 288 | 25.04% | 0 |  | 311.14 | 21.46% | 311.14 | 21.46% | -300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895921 - OWENS CORNING | WATER | WATER REPAIR & INSTALLATION | 2019-07-18 | 2019-09-09 | 2019-07-22 | 2019-09-19 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 935447¦¦2020-03-31
FP | CJ | Yes | 935786 |  | EDMOND WELL SERVICES | EVANS, TRAVIS L | 100% | 100000 | 225000 | 325000 | 201732.95 | 201732.95 | 201732.95 | 0 | 0 | 201732.95 | 70000 | 150500 | 220500 | 11996.96 | 3813.86 | 1669.11 |  | 6513.99 |  |  | 189896.19 | 65545.44 | 33166.39 |  | 91184.36 |  |  | 11836.76 | 0 | 86.12% |  | 0 | 189896.19 | 30000 | 30% | 74500 | 104500 | 32.15% | 0 |  | 11836.76 | 5.868% | 11836.76 | 5.868% | 123267.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 890051 - EDMOND, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2020-06-30 | 2019-07-01 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 935786¦¦2020-03-31
TM | C | Yes | 935787 |  | HARDINSBURG HENNING BP | MIGUEL, SEAN J. | 100% | 4500 | 4913 | 9413 | 11095 | 11095 | 11095 | 0 | 0 | 11095 | 3500 | 3845 | 7345 | 0 |  |  |  | 0 |  |  | 7991.78 | 1710.82 | 441.66 |  | 5236.3 | 603 |  | 3103.22 | 0 | 108.8% |  | 0 | 7991.78 | 1000 | 22.22% | 1068 | 2068 | 21.97% | 1068 |  | 3103.22 | 27.97% | 3103.22 | 27.97% | -1682 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878784 - HARDINSBURG, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-18 | 2019-08-31 | 2019-07-18 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 935787¦¦2020-03-31
TM | C | Yes | 935789 |  | JS TARKINGTON PR | BENNETT, MARK C. | 100% | 7000 | 0 | 7000 | 9800 | 9800 | 9800 | 0 | 0 | 9800 | 5000 | 0 | 5000 | 11.23 |  |  |  | 11.23 |  |  | 10923.23 | 3365.39 | 615.19 |  | 6942.65 |  |  | 0 | 1123.23 | 218.5% |  | 0 | 10923.23 | 2000 | 28.57% | 0 | 2000 | 28.57% | 0 |  | -1123.23 | -11.46% | -1123.23 | -11.46% | -2800 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892953 - J S TARKINGTON FARMS | WATER | WATER REPAIR & INSTALLATION | 2019-07-19 | 2019-09-30 | 2019-07-19 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | MULTI CUSTOM JOB | 935789¦¦2020-03-31
FP | C | Yes | 935790 |  | PINE PRAIRIE WELL 1 MOTOR | GNAU, CASEY T | 100% | 10500 | 500 | 11000 | 11000 | 11000 | 11000 | 0 | 0 | 11000 | 5124 | 250 | 5374 | [7 empty] | 5722.03 | 1659.39 | 528.21 |  | 3534.43 |  |  | 5277.97 | 0 | 106.5% |  | 0 | 5722.03 | 5376 | 51.2% | 250 | 5626 | 51.15% | 0 |  | 5277.97 | 47.98% | 5277.97 | 47.98% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879029 - EVANGELINE PAR WWD 1 | WATER | WATER REPAIR & INSTALLATION | 2019-07-18 | 2019-08-31 | 2019-07-18 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 935790¦¦2020-03-31
TM | C | Yes | 935863 |  | TRIPLE S FARMS | SCHERM, LOGAN M | 100% | 36429 | 0 | 36429 | 57810.5 | 57810.5 | 59279.12 | 0 | 0 | 57810.5 | 30000 | 0 | 30000 | [7 empty] | 56455.68 | 12319.44 | 9810.86 |  | 34155.38 | 170 |  | 1354.82 | 0 | 188.2% |  | 0 | 56455.68 | 6429 | 17.65% | 0 | 6429 | 17.65% | 0 |  | 1354.82 | 2.344% | 1354.82 | 2.344% | -21381.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 899140 - TRIPLE S FARMS | WATER | WATER SUPPLY | 2019-07-17 | 2019-07-30 | 2019-07-17 | 2019-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 935863¦¦2020-03-31
TM | C | Yes | 935864 |  | KCPL LAKE ROAD WELL 3 REHAB | WARTICK, LOGAN M | 100% | 11475 | 19870.92 | 31345.92 | 39953.02 | 39953.02 | 39953.02 | 0 | 0 | 39953.02 | 9750 | 16997.33 | 26747.33 | 6447.58 | 2869.68 | 2680.88 |  | 897.02 |  |  | 50720.58 | 17443.78 | 11319.27 |  | 21957.53 |  |  | 0 | 10767.56 | 189.6% |  | 0 | 50720.58 | 1725 | 15.03% | 2873.59 | 4598.59 | 14.67% | 0 |  | -10767.56 | -26.95% | -10767.56 | -26.95% | -8607.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 893032 - EVERGY | WATER | WATER REPAIR & INSTALLATION | 2019-07-22 | 2019-10-29 | 2019-07-22 | 2019-10-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 935864¦¦2020-03-31
FP | C | Yes | 936046 |  | EDWARDSVILLE 8 PUMP | MIGUEL, SEAN J. | 100% | 9900 | 37491 | 47391 | 47391 | 47391 | 47391 | 0 | 0 | 47391 | 7425 | 28741 | 36166 | -36 |  |  |  | -36 |  |  | 39957.2 | 12713.09 | 4997.51 |  | 19039.9 | 3206.7 |  | 7433.8 | 0 | 110.5% |  | 0 | 39957.2 | 2475 | 25% | 8750 | 11225 | 23.69% | 0 |  | 7433.8 | 15.69% | 7433.8 | 15.69% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878800 - EDWARDSVILLE, CITY OF | WATER | WATER SUPPLY | 2019-07-19 | 2019-08-31 | 2019-07-19 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 936046¦¦2020-03-31
FP | C | Yes | 936049 |  | PIXELLE 14 MOTOR | BARNES, MATTHEW D | 100% | 6530 | 30053 | 36583 | 40063 | 40063 | 40063 | 3480 | 0 | 40063 | 4570 | 22540 | 27110 | -723.03 | 123.86 | 31.64 |  | -878.53 |  |  | 33421 | 9089.71 | 3541.46 |  | 20789.83 |  |  | 6642 | 0 | 123.3% |  | 0 | 33421 | 1960 | 30.02% | 7513 | 9473 | 25.89% | 0 |  | 6642 | 16.58% | 6642 | 16.58% | -3480 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878886 - PIXELLE SPECIALTY SOLUTIONS | WATER | WATER SUPPLY | 2019-07-19 | 2019-08-31 | 2019-07-19 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 936049¦¦2020-03-31
TM | CJ | Yes | 937070 |  | BOARDWALK 501B | GNAU, CASEY T | 100% | 27500 | 14850 | 42350 | 35475 | 35475 | 35475 | 0 | 0 | 35475 | 16467 | 7424 | 23891 | [7 empty] | 17683.05 | 8639.75 | 4403.45 |  | 4639.85 |  |  | 17791.95 | 0 | 74.02% |  | 0 | 17683.05 | 11033 | 40.12% | 7426 | 18459 | 43.59% | 0 |  | 17791.95 | 50.15% | 17791.95 | 50.15% | 6875 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 936154 - CAVERN SOLUTIONS INC | WATER | WATER REPAIR & INSTALLATION | 2019-07-19 | 2019-08-31 | 2019-07-19 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 937070¦¦2020-03-31
TM | C | Yes | 937071 |  | FRANKFORT NY WELL 3 REHAB | CROOK, CHARLES M | 100% | 25535 | 24050 | 49585 | 50155 | 50155 | 50155 | 0 | 0 | 50155 | 17535 | 14950 | 32485 | [7 empty] | 36240.6 | 12881 | 4487.54 |  | 18872.06 |  |  | 13914.4 | 0 | 111.6% |  | 0 | 36240.6 | 8000 | 31.33% | 9100 | 17100 | 34.49% | 0 |  | 13914.4 | 27.74% | 13914.4 | 27.74% | -570 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 890860 - FRANKFORT, NY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-19 | 2019-09-16 | 2019-07-19 | 2019-09-16 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 937071¦¦2020-03-31
TM | C | Yes | 937493 |  | NORMANS NURSEY PIRU WELL | SEIDEN, ANDREW L. | 100% | 9601.45 | 36785.21 | 46386.66 | 46386.56 | 46386.56 | 46844.73 | 0 | 0 | 46386.56 | 7396 | 31119.03 | 38515.03 | [7 empty] | 46390.56 | 10793.51 | 6715.69 |  | 28881.36 |  |  | 0 | 4 | 120.4% |  | 0 | 46390.56 | 2205.45 | 22.97% | 5666.18 | 7871.63 | 16.97% | 0 |  | -4 | -0.008623% | -4 | -0.008623% | 0.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 895437 - NORMAN S NURSERY | WATER | WATER REPAIR & INSTALLATION | 2019-07-22 | 2019-08-22 | 2019-07-22 | 2019-08-22 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 937493¦¦2020-03-31
UP | CJ | Yes | 937615 |  | STANTEC CLEANINGS | SIMPSON, CARL L. | 100% | 50850 | 5276 | 56126 | 87506 | 87506 | 87506 | 20828 | 0 | 87506 | 35595 | 4115 | 39710 | 39.22 | 1.57 |  |  | 37.65 |  |  | 109042.06 | 44996.1 | 24731.18 |  | 39314.78 |  |  | 0 | 21536.06 | 274.6% |  | 0 | 109042.06 | 15255 | 30% | 1161 | 16416 | 29.25% | 0 |  | -21536.06 | -24.61% | -21536.06 | -24.61% | -31380 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 898238 - STANTEC | WATER | WATER SUPPLY | 2019-07-24 | 2019-09-30 | 2019-07-24 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 937615¦¦2020-03-31
FP | C | Yes | 938102 |  | OLIVE BRANCH METRO HSP | ANDERSON, STEPHEN P. | 100% | 4915 | 500 | 5415 | 5415 | 5415 | 5415 | 0 | 0 | 5415 | 3440 | 382.94 | 3822.94 | 1268.77 | 604.66 | 166.95 |  | 497.16 |  |  | 7393.24 | 2160.31 | 903.96 |  | 4328.97 |  |  | 0 | 1978.24 | 193.4% |  | 0 | 7393.24 | 1475 | 30.01% | 117.06 | 1592.06 | 29.4% | 0 |  | -1978.24 | -36.53% | -1978.24 | -36.53% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895759 - OLIVE BRANCH, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-25 | 2019-08-01 | 2019-07-25 | 2019-08-01 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 938102¦¦2020-03-31
TM | C | Yes | 938103 |  | ZONE J WELL 2 SBD COUNTY | BRASHEAR, DAVID M | 100% | 19563 | 92932.62 | 112495.62 | 112495.58 | 112495.58 | 117149.93 | 0 | 0 | 112495.58 | 11390 | 71227.7 | 82617.7 | [7 empty] | 99063.33 | 25420.73 | 6200.51 |  | 65237.09 | 2205 |  | 13432.25 | 0 | 119.9% |  | 0 | 99063.33 | 8173 | 41.78% | 21704.92 | 29877.92 | 26.56% | 0 |  | 13432.25 | 11.94% | 13432.25 | 11.94% | 0.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878787 - SAN BERNARDINO SPECIAL DISTRICT COUNTY | WATER | WATER REPAIR & INSTALLATION | 2019-07-22 | 2019-09-30 | 2019-07-22 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 938103¦¦2020-03-31
FP | CJ | Yes | 938118 |  | ZACHRY ENGINEERING VERT PUMP | LOPEZ-VASQUEZ, JUAN C. | 100% | 335256 | 0 | 335256 | 301730.4 | 301730.4 | 301730.4 | 30173.04 | 0 | 301730.4 | 241741 | 0 | 241741 | 114.43 |  |  |  | 114.43 |  |  | 169051.35 | 52487.53 | 18394.76 |  | 85074.43 | 13094.63 |  | 132679.05 | 0 | 69.93% |  | 0 | 169051.35 | 93515 | 27.89% | 0 | 93515 | 27.89% | 0 |  | 132679.05 | 43.97% | 132679.05 | 43.97% | 33525.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 900607 - ZACHRY INDUSTRIAL INC | WATER | WATER REPAIR & INSTALLATION | 2019-07-19 | 2019-12-31 | 2019-07-19 | 2019-12-31 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 938118¦¦2020-03-31
FP | CJ | Yes | 938265 |  | EXXON BRPO EXPANSION PUMP | LOPEZ-VASQUEZ, JUAN C. | 100% | 491605 | 0 | 491605 | 204128 | 204128 | 204128 | 204128 | 0 | 204128 | 326386 | 0 | 326386 | 28745.32 | 636.57 | 176.23 |  | 27932.52 |  |  | 90531.27 | 1555.35 | 176.23 |  | 88799.69 |  |  | 113596.73 | 0 | 27.74% |  | 0 | 90531.27 | 165219 | 33.61% | 0 | 165219 | 33.61% | 0 |  | 113596.73 | 55.65% | 113596.73 | 55.65% | 287477 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 938025 - JACOBS ENGINEERING GROUP INC | WATER | WATER EQUIPMENT SALES | 2019-07-25 | 2020-01-31 | 2019-07-25 | 2020-01-31 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 938265¦¦2020-03-31
UP | C | Yes | 939960 |  | HENRY CO PM | MIGUEL, SEAN J. | 100% | 3150 | 32387 | 35537 | 35537 | 35537 | 35537 | 0 | 0 | 35537 | 2750 | 24994 | 27744 | [7 empty] | 30736.89 | 8875.18 | 2721.2 |  | 15204.51 | 3936 |  | 4800.11 | 0 | 110.8% |  | 0 | 30736.89 | 400 | 12.7% | 7393 | 7793 | 21.93% | 0 |  | 4800.11 | 13.51% | 4800.11 | 13.51% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 892021 - HENRY COUNTY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-07-26 | 2019-08-31 | 2019-07-26 | 2019-08-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 939960¦¦2020-03-31
FP | C | Yes | 940336 |  | SCVWD PRESLEY BOOSTER B41 | GRACE, GARY L. | 100% | 19271 | 0 | 19271 | 19271.06 | 19271.06 | 20593.81 | 0 | 0 | 19271.06 | 14132 | 0 | 14132 | [7 empty] | 12835.43 | 158.28 | 40.46 |  | 12636.69 |  |  | 6435.63 | 0 | 90.83% |  | 0 | 12835.43 | 5139 | 26.67% | 0 | 5139 | 26.67% | 0 |  | 6435.63 | 33.4% | 6435.63 | 33.4% | -0.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878930 - SANTA CLARITA VALLEY WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2019-07-23 | 2019-08-23 | 2019-07-23 | 2020-08-23 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 940336¦¦2020-03-31
FP | C | Yes | 940338 |  | SIPC PUMP END | WHITE, CATHLEEN R | 100% | 2770 | 0 | 2770 | 2770 | 2770 | 2770 | 0 | 0 | 2770 | 1700 | 0 | 1700 | [7 empty] | 2226.3 | 186 |  |  | 2040.3 |  |  | 543.7 | 0 | 131% |  | 0 | 2226.3 | 1070 | 38.63% | 0 | 1070 | 38.63% | 0 |  | 543.7 | 19.63% | 543.7 | 19.63% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 898037 - SOUTHERN ILLINOIS POWER COOP | WATER | WATER REPAIR & INSTALLATION | 2019-07-29 | 2019-07-31 | 2019-07-29 | 2019-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 940338¦¦2020-03-31
TM | CJ | Yes | 940339 |  | TICONDEROGA NY WARRANTY | CROOK, CHARLES M | 100% | [5 empty] | 0 | 0 | 0 |  | 20000 | 0 | 20000 | 1424.67 | 1387.42 |  |  | 37.25 |  |  | 42402.96 | 23390.51 | 8032.72 |  | 10979.73 |  |  | 0 | 42402.96 | 212% |  | 0 | 42402.96 | -20000 |  | 0 | -20000 |  | 0 |  | -42402.96 |  | -42402.96 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 898945 - TICONDEROGA, NY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-29 | 2019-08-30 | 2019-07-29 | 2019-08-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 940339¦¦2020-03-31
UP | C | Yes | 940684 |  | GRAYSON CO VIBRATIONS | MIGUEL, SEAN J. | 100% | 1530 | 0 | 1530 | 1360 | 1360 | 1360 | 0 | 0 | 1360 | 530 | 0 | 530 | [7 empty] | 0.46 |  |  |  | 0.46 |  |  | 1359.54 | 0 | 0.08679% |  | 0 | 0.46 | 1000 | 65.36% | 0 | 1000 | 65.36% | 0 |  | 1359.54 | 99.97% | 1359.54 | 99.97% | 170 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879099 - GRAYSON, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-12-31 | 2019-06-17 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 940684¦¦2020-03-31
FP | C | Yes | 940685 |  | SEALY TESTING | CALLAHAN, DANIEL E. | 100% | 2100 | 0 | 2100 | 2100 | 2100 | 2100 | 0 | 0 | 2100 | 1182 | 0 | 1182 | [7 empty] | 5271.49 | 2277.89 | 407.97 |  | 2585.63 |  |  | 0 | 3171.49 | 446% |  | 0 | 5271.49 | 918 | 43.71% | 0 | 918 | 43.71% | 0 |  | -3171.49 | -151% | -3171.49 | -151% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 897652 - SEALY, TX, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-22 | 2019-07-30 | 2019-07-22 | 2019-07-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 940685¦¦2020-03-31
FP | C | Yes | 940687 |  | HUNT FOREST WELL 1 | ALBARADO, JORDAN A | 100% | 11465 | 0 | 11465 | 12965 | 12965 | 12965 | 0 | 0 | 12965 | 5733 | 0 | 5733 | [7 empty] | 8807.28 | 3760.9 | 1188.73 |  | 3857.65 |  |  | 4157.72 | 0 | 153.6% |  | 0 | 8807.28 | 5732 | 50% | 0 | 5732 | 50% | 0 |  | 4157.72 | 32.07% | 4157.72 | 32.07% | -1500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 892380 - HUNT FOREST PRODUCTS | WATER | WATER REPAIR & INSTALLATION | 2019-07-30 | 2019-08-30 | 2019-07-30 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 940687¦¦2020-03-31
FP | C | Yes | 940689 |  | JR HAYES PUMP REPAIR | ANDERSON, STEPHEN P. | 100% | 9981 | 7006 | 16987 | 16987 | 16987 | 16987 | 0 | 0 | 16987 | 6986 | 4904 | 11890 | [7 empty] | 14318.79 | 2646.1 | 976.3 |  | 10696.39 |  |  | 2668.21 | 0 | 120.4% |  | 0 | 14318.79 | 2995 | 30.01% | 2102 | 5097 | 30.01% | 0 |  | 2668.21 | 15.71% | 2668.21 | 15.71% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 892947 - J R HAYES CONSTRUCTION CO | WATER | WATER REPAIR & INSTALLATION | 2019-07-26 | 2019-08-23 | 2019-07-26 | 2019-08-23 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 940689¦¦2020-03-31
FP | LJ | Yes | 940751 |  | LEAVENWORTH CW | HARTMAN, MICHAEL | 52.35% | 2619910 | 0 | 2619910 | 1430464.8112 | 1075148 | 1075148 | 0 | 107514.8 | 2732283 | 2039214.63 | 0 | 2039214.63 | 274077.79 | 142026.41 | 38337.21 | 2003 | 69696.11 | 22015.06 |  | 1113406.75 | 448586.23 | 114568.57 | 9985.76 | 460480.53 | 79785.66 |  | 0 | 38258.75 | 54.6% |  | 1013274.25 | 2126681 | 580695.37 | 22.16% | 0 | 580695.37 | 22.16% | 0 |  | 317058.06 | 22.16% | 605602 | 22.16% | 1189445.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 879033 - LEAVENWORTH WATERWORKS | WATER | WATER SUPPLY | 2019-07-01 | 2020-05-01 | 2019-09-01 | 2020-05-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 940751¦¦2020-03-31
FP | C | Yes | 940795 |  | LUFKIN WELL 3 REHAB PUMP MOTOR | CALLAHAN, DANIEL E. | 100% | 196675 | 0 | 196675 | 196675 | 196675 | 196675 | 0 | 0 | 196675 | 143086 | 0 | 143086 | 0 |  |  |  | 0 |  |  | 156677.73 | 14414.91 | 7295.57 |  | 134287.25 | 680 |  | 39997.27 | 0 | 109.5% |  | 0 | 156677.73 | 53589 | 27.25% | 0 | 53589 | 27.25% | 0 |  | 39997.27 | 20.34% | 39997.27 | 20.34% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 878788 - LUFKIN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-01 | 2019-12-31 | 2019-07-01 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 940795¦¦2020-03-31
FP | C | Yes | 941007 |  | HARVEY CEDAR NJ ALUM FEEDER | RANFT, DONALD R | 100% | 35250 | 0 | 35250 | 35250 | 35250 | 35250 | 0 | 0 | 35250 | 18467 | 0 | 18467 | [7 empty] | 17439.66 | 4635.43 | 494.64 |  | 12309.59 |  |  | 17810.34 | 0 | 94.44% |  | 0 | 17439.66 | 16783 | 47.61% | 0 | 16783 | 47.61% | 0 |  | 17810.34 | 50.53% | 17810.34 | 50.53% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 891894 - HARVEY CEDARS, NJ, BOROUGH OF | WATER | WATER TREATMENT | 2019-07-01 | 2019-11-30 | 2019-07-01 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 941007¦¦2020-03-31
FP | C | Yes | 941009 |  | HARVEY CEDARS NJ SALEM WTP VAL | RANFT, DONALD R | 100% | 11750 | 0 | 11750 | 11750 | 11750 | 11750 | 0 | 0 | 11750 | 8358 | 0 | 8358 | [7 empty] | 7736.63 | 3183.68 | 619.62 |  | 3933.33 |  |  | 4013.37 | 0 | 92.57% |  | 0 | 7736.63 | 3392 | 28.87% | 0 | 3392 | 28.87% | 0 |  | 4013.37 | 34.16% | 4013.37 | 34.16% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 891894 - HARVEY CEDARS, NJ, BOROUGH OF | WATER | WATER TREATMENT | 2019-07-01 | 2019-11-30 | 2019-07-01 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 941009¦¦2020-03-31
UP | CJ | Yes | 941266 |  | NOVELIS PMS | MIGUEL, SEAN J. | 100% | 8000 | 65544 | 73544 | 64403.94 | 64403.94 | 48871 | 0 | 0 | 64403.94 | 6000 | 49576 | 55576 | 1757.1 | 258.93 | 31.64 |  | 1466.53 |  |  | 52031.59 | 23276.63 | 6966.65 |  | 21788.31 |  |  | 12372.35 | 0 | 93.62% |  | 0 | 52031.59 | 2000 | 25% | 15968 | 17968 | 24.43% | 11840 |  | 12372.35 | 19.21% | 12372.35 | 19.21% | 9140.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895575 - NOVELIS CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-07-30 | 2019-08-31 | 2019-07-30 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 941266¦¦2020-03-31
UP | C | Yes | 941267 |  | DUNKIRK HS PUMPS | BARNES, MATTHEW D | 100% | 18200 | 6570 | 24770 | 23920 | 23920 | 23920 | 0 | 0 | 23920 | 11900 | 4186 | 16086 | 0.53 | 0.53 | [5 empty] | 16501.03 | 2451.71 | 810.63 |  | 13238.69 |  |  | 7418.97 | 0 | 102.6% |  | 0 | 16501.03 | 6300 | 34.62% | 2384 | 8684 | 35.06% | 0 |  | 7418.97 | 31.02% | 7418.97 | 31.02% | 850 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 940111 - DUNKIRK, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-24 | 2019-12-31 | 2019-07-31 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 941267¦¦2020-03-31
TM | C | Yes | 941331 |  | PALM BEACH COUNTY WESTERN REG | MARTINEZ, MIGUEL E | 100% | 72041 | 31209 | 103250 | 102250 | 102250 | 102250 | 102249.99 | 0 | 102250 | 72041 | 7645.51 | 79686.51 | [7 empty] | 76051.2 | 25427.54 | 16770.42 |  | 30533.82 | 3319.42 |  | 26198.8 | 0 | 95.44% |  | 0 | 76051.2 | 0 | 0% | 23563.49 | 23563.49 | 22.82% | 0 |  | 26198.8 | 25.62% | 26198.8 | 25.62% | 1000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895983 - PALM BEACH COUNTY WATER UTILITIES | WATER | WATER SUPPLY | 2019-08-01 | 2019-10-15 | 2019-08-01 | 2019-10-15 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 941331¦¦2020-03-31
TM | C | Yes | 941332 |  | CAPE CORAL 13 WELL LOGS | MARTINEZ, MIGUEL E | 100% | 28240 | 0 | 28240 | 30540 | 30540 | 30540 | 0 | 0 | 30540 | 19090 | 0 | 19090 | [7 empty] | 12711.71 | 4998.1 | 5143.94 |  | 2494.67 | 75 |  | 17828.29 | 0 | 66.59% |  | 0 | 12711.71 | 9150 | 32.4% | 0 | 9150 | 32.4% | 0 |  | 17828.29 | 58.38% | 17828.29 | 58.38% | -2300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-08-18 | 2019-08-01 | 2019-08-18 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 941332¦¦2020-03-31
FP | C | Yes | 941336 |  | CELINA TN NEW PUMP | ANDERSON, STEPHEN P. | 100% | 25495 | 0 | 25495 | 25495 | 25495 | 25495 | 0 | 0 | 25495 | 19120 | 0 | 19120 | [7 empty] | 34724.44 | 10294.82 | 3768.97 |  | 18198.02 | 2462.63 |  | 0 | 9229.44 | 181.6% |  | 0 | 34724.44 | 6375 | 25% | 0 | 6375 | 25% | 0 |  | -9229.44 | -36.2% | -9229.44 | -36.2% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 941021 - CELINA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-07-31 | 2019-09-23 | 2019-07-31 | 2019-09-23 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 941336¦¦2020-03-31
FP | CJ | Yes | 941797 |  | TOWANDA PA PITLESS AND PIPE | CROOK, CHARLES M | 100% | 40000 | 0 | 40000 | 40000 | 40000 | 40000 | 40000 | 0 | 40000 | 28500 | 0 | 28500 | 5629.72 | 3582.79 | 804.38 |  | 1242.55 |  |  | 28086.8 | 5181.45 | 851.02 |  | 22054.33 |  |  | 11913.2 | 0 | 98.55% |  | 0 | 28086.8 | 11500 | 28.75% | 0 | 11500 | 28.75% | 0 |  | 11913.2 | 29.78% | 11913.2 | 29.78% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 941674 - CONTINENTAL CONSTRUCTION INC | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-09-06 | 2019-08-01 | 2019-09-06 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 941797¦¦2020-03-31
TM | CJ | Yes | 941799 |  | ALERIS OH PUMP INSP | BARNES, MATTHEW D | 100% | 4000 | 0 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 4000 | 2422 | 0 | 2422 | 0.21 | 0.21 |  |  | 0 |  |  | 4228.29 | 2572.25 | 1193.72 |  | 462.32 |  |  | 0 | 228.29 | 174.6% |  | 0 | 4228.29 | 1578 | 39.45% | 0 | 1578 | 39.45% | 0 |  | -228.29 | -5.707% | -228.29 | -5.707% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 886057 - ALERIS ROLLED PRODUCTS LLC | WATER | WATER REPAIR & INSTALLATION | 2019-08-02 | 2019-11-30 | 2019-08-02 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 941799¦¦2020-03-31
TM | C | Yes | 941801 |  | FMI BAGDAD KIMBERLY SEEPAGE | COMBS, TAYLOR E. | 100% | 120570 | 0 | 120570 | 103551.5 | 103551.5 | 103551.5 | 0 | 0 | 103551.5 | 91921 | 0 | 91921 | 0 |  |  |  | 0 |  |  | 106514.45 | 30028.94 | 24918.06 |  | 51567.45 |  |  | 0 | 2962.95 | 115.9% |  | 0 | 106514.45 | 28649 | 23.76% | 0 | 28649 | 23.76% | 0 |  | -2962.95 | -2.861% | -2962.95 | -2.861% | 17018.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 890904 - FREEPORT MCMORAN BAGDAD | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-08-30 | 2019-08-01 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 941801¦¦2020-03-31
TM | C | Yes | 941807 |  | IRG MOTOR | SIMPSON, CARL L. | 100% | 2900 | 0 | 2900 | 6062 | 6062 | 6062 | 0 | 0 | 6062 | 2000 | 0 | 2000 | 0.05 | 0.05 | [5 empty] | 3874.54 | 1277.31 | 448.8 |  | 2148.43 |  |  | 2187.46 | 0 | 193.7% |  | 0 | 3874.54 | 900 | 31.03% | 0 | 900 | 31.03% | 0 |  | 2187.46 | 36.08% | 2187.46 | 36.08% | -3162 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 941478 - IRG REALTY ADVISORS | WATER | WATER REPAIR & INSTALLATION | 2019-07-30 | 2019-08-31 | 2019-07-30 | 2019-08-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 941807¦¦2020-03-31
FP | C | Yes | 941930 |  | SWIFT CREEK CHEMICAL NORTH WEL | PARSLEY, TRISTAN S | 100% | 25703 | 38328.97 | 64031.97 | 64031.97 | 64031.97 | 64031.97 | 0 | 0 | 64031.97 | 13228 | 7622 | 20850 | [7 empty] | 22032.04 | 8511.47 | 619.25 |  | 9302.36 | 3598.96 |  | 41999.93 | 0 | 105.7% |  | 0 | 22032.04 | 12475 | 48.54% | 30706.97 | 43181.97 | 67.44% | 0 |  | 41999.93 | 65.59% | 41999.93 | 65.59% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 896144 - PCS PHOSPHATE WHITE SPRINGS | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-09-30 | 2019-08-01 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 941930¦¦2020-03-31
FP | CJ | Yes | 941941 |  | BASTROP COUNTY TX GTM PILOT | CHESLEY, ANDREW J | 100% | 8000 | 0 | 8000 | 8000 | 8000 | 8000 | 0 | 0 | 8000 | 6693.6 | 0 | 6693.6 | [7 empty] | 6911.73 | 2640.25 |  |  | 4271.48 |  |  | 1088.27 | 0 | 103.3% |  | 0 | 6911.73 | 1306.4 | 16.33% | 0 | 1306.4 | 16.33% | 0 |  | 1088.27 | 13.6% | 1088.27 | 13.6% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 944545 - BASTROP, COUNTY OF | WATER | WATER TREATMENT | 2019-08-01 | 2019-10-31 | 2019-08-01 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 941941¦¦2020-03-31
TM | C | Yes | 941990 |  | KENDLETON WELL 1 REHAB | CALLAHAN, DANIEL E. | 100% | 49686.6 | 0 | 49686.6 | 42933.3 | 42933.3 | 42933.3 | 0 | 0 | 42933.3 | 31608 | 0 | 31608 | [7 empty] | 32813.58 | 9068.97 | 4833.79 |  | 18881.58 | 29.24 |  | 10119.72 | 0 | 103.8% |  | 0 | 32813.58 | 18078.6 | 36.39% | 0 | 18078.6 | 36.39% | 0 |  | 10119.72 | 23.57% | 10119.72 | 23.57% | 6753.3 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 941771 - DL ELLIIOT ENTERPRISES INC | WATER | WATER REPAIR & INSTALLATION | 2019-08-02 | 2019-09-15 | 2019-08-02 | 2019-09-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 941990¦¦2020-03-31
FP | C | Yes | 941992 |  | EJGH R AND I | LOPEZ-VASQUEZ, JUAN C. | 100% | 6000 | 26028.9 | 32028.9 | 32028.9 | 32028.9 | 32028.9 | 0 | 0 | 32028.9 | 4334 | 18210 | 22544 | [7 empty] | 25650.86 | 9187.5 | 2195.77 |  | 12734.59 | 1533 |  | 6378.04 | 0 | 113.8% |  | 0 | 25650.86 | 1666 | 27.77% | 7818.9 | 9484.9 | 29.61% | 0 |  | 6378.04 | 19.91% | 6378.04 | 19.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 889961 - EAST JEFFERSON GENERAL HOSP | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-10-07 | 2019-08-01 | 2019-10-07 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 941992¦¦2020-03-31
FP | CJ | Yes | 941993 |  | WEST TN PRISON TANK INSPECTION | ANDERSON, STEPHEN P. | 100% | 5600 | 10610 | 16210 | 10610 | 10610 | 10610 | 0 | 0 | 10610 | 4200 | 7950 | 12150 | [7 empty] | 7957.8 |  |  |  | 4007.8 | 3950 |  | 2652.2 | 0 | 65.5% |  | 0 | 7957.8 | 1400 | 25% | 2660 | 4060 | 25.05% | 0 |  | 2652.2 | 25% | 2652.2 | 25% | 5600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 937348 - WEST TENNESSE STATE PENITENTIARY | WATER | WATER REPAIR & INSTALLATION | 2019-08-02 | 2019-08-30 | 2019-08-02 | 2019-08-30 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 941993¦¦2020-03-31
TM | CJ | Yes | 942120 |  | JURUPA WELL 15 | GRACE, GARY L. | 100% | 4585 | 6000 | 10585 | 28920 | 28920 | 28920 | 17418.25 | 0 | 28920 | 3217 | 4877.5 | 8094.5 | 52591.77 | 12269.18 | 3406.75 |  | 36373.34 | 542.5 |  | 66666.7 | 19003.92 | 5872.22 |  | 41248.06 | 542.5 |  | 0 | 37746.7 | 823.6% |  | 0 | 66666.7 | 1368 | 29.84% | 1122.5 | 2490.5 | 23.53% | 1122.5 |  | -37746.7 | -130.5% | -37746.7 | -130.5% | -18335 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892972 - JURUPA COMMUNITY SERVICES DIST | WATER | WATER REPAIR & INSTALLATION | 2019-08-02 | 2019-09-30 | 2019-08-02 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 942120¦¦2020-03-31
TM | CJ | Yes | 942122 |  | MURPHREE WATER TREATMENT | PARSLEY, TRISTAN S | 100% | 29715 | 0 | 29715 | 17275 | 17275 | 17275 | 0 | 0 | 17275 | 19485 | 0 | 19485 | [7 empty] | 11895.69 | 5165.09 | 2096.25 |  | 4634.35 |  |  | 5379.31 | 0 | 61.05% |  | 0 | 11895.69 | 10230 | 34.43% | 0 | 10230 | 34.43% | 0 |  | 5379.31 | 31.14% | 5379.31 | 31.14% | 12440 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 891007 - GAINESVILLE REGIONAL UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-08-02 | 2019-10-31 | 2019-08-02 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 942122¦¦2020-03-31
TM | C | Yes | 942123 |  | DIXON IL WELL 10 | SNELTEN, BRIAN M | 100% | 38716.9 | 101866.75 | 140583.65 | 140397.87 | 140397.87 | 140397.87 | 0 | 0 | 140397.87 | 30861 | 61513 | 92374 | 340.64 | 91.91 | 47.59 |  | 153.14 | 48 |  | 118777.48 | 57518.05 | 11459.28 |  | 49752.15 | 48 |  | 21620.39 | 0 | 128.6% |  | 0 | 118777.48 | 7855.9 | 20.29% | 40353.75 | 48209.65 | 34.29% | 0 |  | 21620.39 | 15.4% | 21620.39 | 15.4% | 185.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878628 - DIXON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-12-31 | 2019-08-05 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 942123¦¦2020-03-31
TM | C | Yes | 942416 |  | TEXAS BRINE WC J100B | LOPEZ-VASQUEZ, JUAN C. | 100% | 6200 | 21545 | 27745 | 27745 | 27745 | 27745 | 0 | 0 | 27745 | 4448 | 15045 | 19493 | 0 |  |  |  | 0 |  |  | 23036.28 | 7154.35 | 3364.31 |  | 11984.05 | 533.57 |  | 4708.72 | 0 | 118.2% |  | 0 | 23036.28 | 1752 | 28.26% | 6500 | 8252 | 29.74% | 0 |  | 4708.72 | 16.97% | 4708.72 | 16.97% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878775 - TEXAS BRINE WHITE CASTLE COMPANY LLC | WATER | WATER REPAIR & INSTALLATION | 2019-08-05 | 2019-10-06 | 2019-08-05 | 2019-10-06 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 942416¦¦2020-03-31
TM | CJ | Yes | 942417 |  | SALINA KS 2019 WELL WORK | WARTICK, LOGAN M | 100% | 90120 | 0 | 90120 | 73740.35 | 73740.35 | 73740.35 | 0 | 7333.7 | 73740.35 | 72009.44 | 0 | 72009.44 | -1959.38 |  |  |  |  | -1959.38 |  | 48814.51 | 15379.05 | 10623.53 |  | 19987.72 | 2824.21 |  | 24925.84 | 0 | 67.79% |  | 0 | 48814.51 | 18110.56 | 20.1% | 0 | 18110.56 | 20.1% | 0 |  | 24925.84 | 33.8% | 24925.84 | 33.8% | 16379.65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 888002 - CAS CONSTRUCTORS | WATER | WATER REPAIR & INSTALLATION | 2019-08-05 | 2019-12-31 | 2019-08-05 | 2019-12-31 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 942417¦¦2020-03-31
TM | C | Yes | 942709 |  | SCARLET ELM LLC | SCHERM, LOGAN M | 100% | 18000 | 0 | 18000 | 19056.9 | 19056.9 | 20486.2 | 0 | 0 | 19056.9 | 12000 | 0 | 12000 | [7 empty] | 16964.88 | 4000.05 | 1245.39 |  | 11719.44 |  |  | 2092.02 | 0 | 141.4% |  | 0 | 16964.88 | 6000 | 33.33% | 0 | 6000 | 33.33% | 0 |  | 2092.02 | 10.98% | 2092.02 | 10.98% | -1056.9 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 886729 - BAIRD & BRUNSON LAND MANAGEMENT GROUP L | WATER | WATER REPAIR & INSTALLATION | 2019-08-05 | 2019-08-06 | 2019-08-05 | 2019-08-06 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 942709¦¦2020-03-31
TM | C | Yes | 942710 |  | EXELON CB II NEW MOTOR WELL 5 | CALLAHAN, DANIEL E. | 100% | 2280 | 0 | 2280 | 2280 | 2280 | 2280 | 0 | 0 | 2280 | 1364 | 0 | 1364 | 0 |  |  |  | 0 |  |  | 3037.13 | 1279.02 | 433.73 |  | 1315.38 | 9 |  | 0 | 757.13 | 222.7% |  | 0 | 3037.13 | 916 | 40.18% | 0 | 916 | 40.18% | 0 |  | -757.13 | -33.21% | -757.13 | -33.21% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 890503 - EXELON GENERATION COLORADO BEND ENERGY | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-08-26 | 2019-08-01 | 2019-08-26 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 942710¦¦2020-03-31
FP | C | Yes | 942711 |  | INVISTA RELINE WELL 1 | CALLAHAN, DANIEL E. | 100% | 92735 | 92735 | 185470 | 181585 | 181585 | 181585 | 92735 | 0 | 181585 | 53822 | 58068.2 | 111890.2 | [7 empty] | 157396.55 | 25528.57 | 25841.87 |  | 100281.11 | 5745 |  | 24188.45 | 0 | 140.7% |  | 0 | 157396.55 | 38913 | 41.96% | 34666.8 | 73579.8 | 39.67% | 0 |  | 24188.45 | 13.32% | 24188.45 | 13.32% | 3885 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 892626 - INVISTA C O THE MUNDY COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-09-15 | 2019-08-01 | 2019-09-15 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 942711¦¦2020-03-31
TM | CJ | Yes | 942976 |  | NYAW TM 2019 | RANFT, DONALD R | 100% | 2553 | 76731 | 79284 | 86204.5 | 86204.5 | 86204.5 | 0 | 0 | 86204.5 | 1652 | 58948 | 60600 | [7 empty] | 73130.64 | 30428.73 | 13341.88 |  | 27460.03 | 1900 |  | 13073.86 | 0 | 120.7% |  | 0 | 73130.64 | 901 | 35.29% | 17783 | 18684 | 23.57% | 0 |  | 13073.86 | 15.17% | 13073.86 | 15.17% | -6920.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878446 - LONG ISLAND AMERICAN WATER | WATER | WATER REPAIR & INSTALLATION | 2019-08-06 | 2019-12-31 | 2019-08-06 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 942976¦¦2020-03-31
FP | CJ | Yes | 942980 |  | NPPD HALLAM STATION 2019 REHAB | GANSEBOM, JASON W. | 100% | 47720 | 0 | 47720 | 89195 | 89195 | 89195 | 0 | 0 | 89195 | 30560 | 0 | 30560 | 1279.19 | 0.19 |  |  | 1279 |  |  | 85931.09 | 21657.98 | 18840.25 |  | 45125.41 | 307.45 |  | 3263.91 | 0 | 281.2% |  | 0 | 85931.09 | 17160 | 35.96% | 0 | 17160 | 35.96% | 0 |  | 3263.91 | 3.659% | 3263.91 | 3.659% | -41475 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 879101 - NEBRASKA PUBLIC POWER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-08-07 | 2019-11-30 | 2019-08-07 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 942980¦¦2020-03-31
FP | C | Yes | 943213 |  | BRW STANLEY ALBIN GEAR DRIVE | GREGORY, CRYSTAL N | 100% | 1750 | 12600 | 14350 | 14350 | 14350 | 15173.37 | 0 | 0 | 14350 | 1188 | 8081 | 9269 | [7 empty] | 9737.44 | 2086.35 | 497.61 |  | 7153.48 |  |  | 4612.56 | 0 | 105.1% |  | 0 | 9737.44 | 562 | 32.11% | 4519 | 5081 | 35.41% | 0 |  | 4612.56 | 32.14% | 4612.56 | 32.14% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-08-08 | 2019-12-31 | 2019-08-08 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 943213¦¦2020-03-31
TM | C | Yes | 943216 |  | CVD EAST WELL TEST | ALBARADO, JORDAN A | 100% | 1500 | 0 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 1500 | 750 | 0 | 750 | [7 empty] | 1340.09 | 791.43 | 203.5 |  | 345.16 |  |  | 159.91 | 0 | 178.7% |  | 0 | 1340.09 | 750 | 50% | 0 | 750 | 50% | 0 |  | 159.91 | 10.66% | 159.91 | 10.66% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 889242 - CVD CERAMICS, INC | WATER | WATER REPAIR & INSTALLATION | 2019-08-08 | 2019-08-16 | 2019-08-08 | 2019-08-16 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 943216¦¦2020-03-31
FP | CJ | Yes | 943985 |  | CITY OF GONZALEZ FLOWTESTS | GREGORY, CRYSTAL N | 100% | 2645 | 0 | 2645 | 2645 | 2645 | 2645 | 0 | 0 | 2645 | 2013 | 0 | 2013 | [7 empty] | 1490.07 | 661.38 | 488.4 |  | 340.29 |  |  | 1154.93 | 0 | 74.02% |  | 0 | 1490.07 | 632 | 23.89% | 0 | 632 | 23.89% | 0 |  | 1154.93 | 43.66% | 1154.93 | 43.66% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 891406 - GONZALES, LA, CITY OF | WATER | WATER SUPPLY | 2019-08-09 | 2019-10-20 | 2019-08-09 | 2019-10-20 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 943985¦¦2020-03-31
FP | C | Yes | 943986 |  | COUNTRY CLUB OF LOUISIANA POA | GREGORY, CRYSTAL N | 100% | 2250 | 5587 | 7837 | 10087 | 10087 | 10087 | 0 | 0 | 10087 | 1687 | 3615 | 5302 | [7 empty] | 7861.49 | 2697.58 | 835.86 |  | 4328.05 |  |  | 2225.51 | 0 | 148.3% |  | 0 | 7861.49 | 563 | 25.02% | 1972 | 2535 | 32.35% | 0 |  | 2225.51 | 22.06% | 2225.51 | 22.06% | -2250 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 889046 - COUNTRY CLUB OF LOUISIANA, THE | WATER | WATER SUPPLY | 2019-08-09 | 2019-10-19 | 2019-08-09 | 2019-10-19 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 943986¦¦2020-03-31
FP | C | Yes | 943987 |  | TPWD TP2 NEW WELL | TRAMMELL, DUANE R. | 100% | 752116 | 0 | 752116 | 720475.75 | 720475.75 | 720475.75 | 0 | 0 | 720475.75 | 617524.22 | 0 | 617524.22 | [7 empty] | 670957.71 | 151531.55 | 117912.36 |  | 384798.8 | 16715 |  | 49518.04 | 0 | 108.7% |  | 0 | 670957.71 | 134591.78 | 17.9% | 0 | 134591.78 | 17.9% | 0 |  | 49518.04 | 6.873% | 49518.04 | 6.873% | 31640.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 899229 - TWENTYNINE PALMS WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-11-15 | 2019-08-01 | 2019-11-15 | PRIME CONTRACTOR | PUBLIC | CONST MANAGER/GEN CONTRACTOR | 943987¦¦2020-03-31
FP | C | Yes | 944088 |  | 250 HP VERTICAL MOTOR BARSTOW | BRASHEAR, DAVID M | 100% | 18899 | 0 | 18899 | 18898.65 | 18898.65 | 20363.3 | 0 | 0 | 18898.65 | 14018 | 0 | 14018 | [7 empty] | 15315.39 | 297.96 | 142.45 |  | 14874.98 |  |  | 3583.26 | 0 | 109.3% |  | 0 | 15315.39 | 4881 | 25.83% | 0 | 4881 | 25.83% | 0 |  | 3583.26 | 18.96% | 3583.26 | 18.96% | 0.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 231962 - GOLDEN STATE WATER COMPANY | WATER | WATER EQUIPMENT SALES | 2019-08-08 | 2019-09-30 | 2019-08-08 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 944088¦¦2020-03-31
FP | C | Yes | 944286 |  | EXCELSIOR SPRINGS MO 9 AND 10 | WARTICK, LOGAN M | 100% | 28870 | 18755.58 | 47625.58 | 68777.58 | 68777.58 | 68777.58 | 0 | 0 | 68777.58 | 23096 | 15101.53 | 38197.53 | 0 |  |  |  | 0 |  |  | 77768.63 | 23405.5 | 18022.84 |  | 36340.29 |  |  | 0 | 8991.05 | 203.6% |  | 0 | 77768.63 | 5774 | 20% | 3654.05 | 9428.05 | 19.8% | 0 |  | -8991.05 | -13.07% | -8991.05 | -13.07% | -21152 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 890495 - EXCELSIOR SPRINGS, MO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-09 | 2019-11-30 | 1900-01-01 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 944286¦¦2020-03-31
TM | C | Yes | 944287 |  | BLACK INC PR | BENNETT, MARK C. | 100% | 18000 | 0 | 18000 | 43062.28 | 43062.28 | 43144.3 | 0 | 0 | 43062.28 | 12000 | 0 | 12000 | [7 empty] | 50719.49 | 12617.91 | 7959.28 |  | 29882.3 | 260 |  | 0 | 7657.21 | 422.7% |  | 0 | 50719.49 | 6000 | 33.33% | 0 | 6000 | 33.33% | 0 |  | -7657.21 | -17.78% | -7657.21 | -17.78% | -25062.28 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887160 - BLACK INC | WATER | WATER REPAIR & INSTALLATION | 2019-08-12 | 2019-10-31 | 2019-08-12 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 944287¦¦2020-03-31
FP | CJ | Yes | 944288 |  | WEEPING WATER WELL 2 PULL | GANSEBOM, JASON W. | 100% | 5650 | 0 | 5650 | 939.57 | 939.57 | 0 | 0 | 0 | 939.57 | 3955 | 0 | 3955 | [7 empty] | 759.07 | 358.51 | 147.24 |  | 253.32 |  |  | 180.5 | 0 | 19.19% |  | 0 | 759.07 | 1695 | 30% | 0 | 1695 | 30% | 0 |  | 180.5 | 19.21% | 180.5 | 19.21% | 4710.43 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 943138 - WEEPING WATER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-08 | 2019-09-30 | 2019-08-08 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 944288¦¦2020-03-31
FP | CJ | Yes | 944289 |  | SAVANNAH MO TEST DRILLING | WARTICK, LOGAN M | 100% | 27651 | 0 | 27651 | 972.17 | 972.17 | 0 | 0 | 0 | 972.17 | 23503 | 0 | 23503 | 0 |  |  |  | 0 |  |  | 785.41 | 485.54 | 58.3 |  | 241.57 |  |  | 186.76 | 0 | 3.342% |  | 0 | 785.41 | 4148 | 15% | 0 | 4148 | 15% | 0 |  | 186.76 | 19.21% | 186.76 | 19.21% | 26678.83 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 897532 - SAVANNAH, MO, CITY OF | WATER | WATER SUPPLY | 2019-08-09 | 2019-11-20 | 2019-08-09 | 2019-11-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 944289¦¦2020-03-31
FP | C | Yes | 944428 |  | CAMERON DRILLING SERVICES | CALLAHAN, DANIEL E. | 100% | 88550 | 0 | 88550 | 90445 | 90445 | 90445 | 54795 | 0 | 90445 | 75429 | 0 | 75429 | [7 empty] | 87818.76 | 14508.09 | 7888.78 |  | 34831.6 | 30590.29 |  | 2626.24 | 0 | 116.4% |  | 0 | 87818.76 | 13121 | 14.82% | 0 | 13121 | 14.82% | 0 |  | 2626.24 | 2.904% | 2626.24 | 2.904% | -1895 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 887833 - CAMERON DRILLING SYSTEMS | WATER | WATER REPAIR & INSTALLATION | 2019-08-19 | 2019-10-01 | 2019-08-19 | 2019-10-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 944428¦¦2020-03-31
TM | C | Yes | 944702 |  | GSW STUDEBAKER WELL 2 DEMO | GRACE, GARY L. | 100% | 23135 | 0 | 23135 | 19185 | 19185 | 19185 | 0 | 0 | 19185 | 17635 | 0 | 17635 | [7 empty] | 29222.53 | 7265.95 | 7844.69 |  | 13449.89 | 662 |  | 0 | 10037.53 | 165.7% |  | 0 | 29222.53 | 5500 | 23.77% | 0 | 5500 | 23.77% | 0 |  | -10037.53 | -52.32% | -10037.53 | -52.32% | 3950 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 231962 - GOLDEN STATE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-08-13 | 2019-10-02 | 2019-08-13 | 2019-10-02 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 944702¦¦2020-03-31
FP | C | Yes | 944704 |  | VERTEX | ANDERSON, STEPHEN P. | 100% | 4460 | 0 | 4460 | 4960 | 4960 | 4960 | 0 | 0 | 4960 | 2899 | 0 | 2899 | [7 empty] | 2566.94 | 186.24 | 132.53 |  | 2248.17 |  |  | 2393.06 | 0 | 88.55% |  | 0 | 2566.94 | 1561 | 35% | 0 | 1561 | 35% | 0 |  | 2393.06 | 48.25% | 2393.06 | 48.25% | -500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 899638 - VERTEX CHEMICAL CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-08-12 | 2019-09-30 | 2019-08-12 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 944704¦¦2020-03-31
FP | C | Yes | 944705 |  | RCWD WELL 164 | SEIDEN, ANDREW L. | 100% | 9556 | 0 | 9556 | 9555.92 | 9555.92 | 10331.69 | 0 | 0 | 9555.92 | 7732 | 0 | 7732 | [7 empty] | 9743.92 | 751.16 | 425.66 |  | 8567.1 |  |  | 0 | 188 | 126% |  | 0 | 9743.92 | 1824 | 19.09% | 0 | 1824 | 19.09% | 0 |  | -188 | -1.967% | -188 | -1.967% | 0.08 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878683 - RANCHO CALIFORNIA WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-08-13 | 2019-10-31 | 2019-08-13 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 944705¦¦2020-03-31
FP | C | Yes | 944808 |  | INTAKE REVIEW SWANSEA | HUNT, HENRY C. | 100% | 6500 | 0 | 6500 | 5954.06 | 5954.06 | 5954.06 | 0 | 0 | 5954.06 | 4622 | 0 | 4622 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 5954.05 | 0 | 0.0002164% |  | 0 | 0.01 | 1878 | 28.89% | 0 | 1878 | 28.89% | 0 |  | 5954.05 | 100% | 5954.05 | 100% | 545.94 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 944678 - WATEK ENGINEERING | WATER | WATER SUPPLY | 2019-08-01 | 2019-12-01 | 2019-08-01 | 2019-12-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 944808¦¦2020-03-31
FP | C | Yes | 944810 |  | SYNGENTA WELL C | LOPEZ-VASQUEZ, JUAN C. | 100% | 12650 | 104425 | 117075 | 117075 | 117075 | 117075 | 0 | 0 | 117075 | 8855 | 41145 | 50000 | [7 empty] | 52402.74 | 21028.03 | 11662.69 |  | 13506.57 | 6205.45 |  | 64672.26 | 0 | 104.8% |  | 0 | 52402.74 | 3795 | 30% | 63280 | 67075 | 57.29% | 0 |  | 64672.26 | 55.24% | 64672.26 | 55.24% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 898608 - SYNGENTA CROP PROTECTION, LLC | WATER | WATER REPAIR & INSTALLATION | 2019-08-12 | 2019-10-01 | 2019-08-12 | 2019-10-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 944810¦¦2020-03-31
FP | C | Yes | 945038 |  | MET WATER BOOSTER PUMP | SEIDEN, ANDREW L. | 100% | 11658 | 0 | 11658 | 10957.54 | 10957.54 | 11756.25 | 0 | 0 | 10957.54 | 8514 | 0 | 8514 | [7 empty] | 8803.88 | 1777.48 | 81.4 |  | 6945 |  |  | 2153.66 | 0 | 103.4% |  | 0 | 8803.88 | 3144 | 26.97% | 0 | 3144 | 26.97% | 0 |  | 2153.66 | 19.65% | 2153.66 | 19.65% | 700.46 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 222927 - METROPOLITAN WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-08-13 | 2019-10-31 | 2019-08-13 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 945038¦¦2020-03-31
TM | CJ | Yes | 945039 |  | BUTLER NATIONAL GC 1 | HEALY, THOMAS P. | 100% | 40000 | 0 | 40000 | 31456 | 31456 | 32444.35 | 0 | 0 | 31456 | 30000 | 0 | 30000 | 2108.32 |  |  |  | 2108.32 |  |  | 25791.31 | 14871.39 | 3309.27 |  | 7610.65 |  |  | 5664.69 | 0 | 85.97% |  | 0 | 25791.31 | 10000 | 25% | 0 | 10000 | 25% | 0 |  | 5664.69 | 18.01% | 5664.69 | 18.01% | 8544 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 887672 - BUTLER NATIONAL | WATER | WATER REPAIR & INSTALLATION | 2019-08-12 | 2019-09-30 | 2019-08-12 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 945039¦¦2020-03-31
TM | C | Yes | 945040 |  | JG BOSWELL S105 DECONSTRUCTION | BRASHEAR, DAVID M | 100% | 14860 | 0 | 14860 | 14860 | 14860 | 14860 | 0 | 0 | 14860 | 11144 | 0 | 11144 | [7 empty] | 13114.28 | 4570.93 | 3966.5 |  | 4576.85 |  |  | 1745.72 | 0 | 117.7% |  | 0 | 13114.28 | 3716 | 25.01% | 0 | 3716 | 25.01% | 0 |  | 1745.72 | 11.75% | 1745.72 | 11.75% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892821 - JG BOSWELL COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-08-29 | 2019-08-01 | 2019-08-29 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 945040¦¦2020-03-31
FP | C | Yes | 945949 |  | EAST DUNDEE IL PWM TESTING | KENNEDY, CHRISTOPHER C. | 100% | 4400 | 0 | 4400 | 4400 | 4400 | 4400 | 0 | 0 | 4400 | 3500 | 0 | 3500 | [7 empty] | 5169.8 | 3367.34 | 944.18 |  | 858.28 |  |  | 0 | 769.8 | 147.7% |  | 0 | 5169.8 | 900 | 20.45% | 0 | 900 | 20.45% | 0 |  | -769.8 | -17.5% | -769.8 | -17.5% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 889951 - EAST DUNDEE, VILLAGE OF | WATER | WATER SUPPLY | 2019-08-15 | 2019-08-15 | 2019-08-15 | 2019-08-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 945949¦¦2020-03-31
FP | C | Yes | 946280 |  | REDLANDS CALIFORNIA ST WELL | GRACE, GARY L. | 100% | 32544 | 0 | 32544 | 43477 | 43477 | 45711.1 | 0 | 0 | 43477 | 25362 | 0 | 25362 | [7 empty] | 41883.28 | 9234.89 | 2161.68 |  | 30486.71 |  |  | 1593.72 | 0 | 165.1% |  | 0 | 41883.28 | 7182 | 22.07% | 0 | 7182 | 22.07% | 0 |  | 1593.72 | 3.666% | 1593.72 | 3.666% | -10933 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 896853 - REDLANDS, CA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-08 | 2019-10-04 | 2019-08-15 | 2019-10-04 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 946280¦¦2020-03-31
FP | C | Yes | 946281 |  | NEWBERN TN HSP | ANDERSON, STEPHEN P. | 100% | 7590 | 0 | 7590 | 7590 | 7590 | 7590 | 0 | 0 | 7590 | 4933 | 0 | 4933 | [7 empty] | 9631.67 | 2731.28 | 2592.3 |  | 4308.09 |  |  | 0 | 2041.67 | 195.2% |  | 0 | 9631.67 | 2657 | 35.01% | 0 | 2657 | 35.01% | 0 |  | -2041.67 | -26.9% | -2041.67 | -26.9% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 946085 - NEWBERN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-15 | 2019-08-23 | 2019-08-15 | 2019-08-23 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 946281¦¦2020-03-31
TM | C | Yes | 946282 |  | CITY OF CHANDLER RECIRCULATION | VAN ALLEN, WESLEY C. | 100% | 3700 | 10628.75 | 14328.75 | 11147.58 | 11147.58 | 11147.58 | 0 | 0 | 11147.58 | 2724 | 8898.95 | 11622.95 | [7 empty] | 9027.07 | 1675.65 | 484.83 |  | 6122.59 | 744 |  | 2120.51 | 0 | 77.67% |  | 0 | 9027.07 | 976 | 26.38% | 1729.8 | 2705.8 | 18.88% | 0 |  | 2120.51 | 19.02% | 2120.51 | 19.02% | 3181.17 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-15 | 2019-09-06 | 2019-08-15 | 2019-09-06 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 946282¦¦2020-03-31
FP | CJ | Yes | 946286 |  | NIPCO LE MARS IA VFD PIPING | GANSEBOM, JASON W. | 100% | 15930 | 27428 | 43358 | 44344.65 | 44344.65 | 44344.65 | 0 | 0 | 44344.65 | 8258 | 20646.89 | 28904.89 | 20304.23 | 8441.03 | 4676.25 |  | 6514.95 | 672 |  | 34286.73 | 10949.27 | 5563.92 |  | 17101.54 | 672 |  | 10057.92 | 0 | 118.6% |  | 0 | 34286.73 | 7672 | 48.16% | 6781.11 | 14453.11 | 33.33% | 0 |  | 10057.92 | 22.68% | 10057.92 | 22.68% | -986.65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 944514 - NORTHWEST IOWA POWER COOPERATIVE | WATER | WATER REPAIR & INSTALLATION | 2019-08-15 | 2019-10-30 | 2019-08-15 | 2019-10-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 946286¦¦2020-03-31
FP | CJ | Yes | 946287 |  | DIXON IL WELL 6 | SNELTEN, BRIAN M | 100% | 30840 | 0 | 30840 | 20785.86 | 20785.86 | 20785.86 | 0 | 0 | 20785.86 | 23562 | 0 | 23562 | 3576.93 | 2572.28 | 55.21 |  | 949.44 |  |  | 20714.88 | 13283.3 | 2161.59 |  | 5269.99 |  |  | 70.98 | 0 | 87.92% |  | 0 | 20714.88 | 7278 | 23.6% | 0 | 7278 | 23.6% | 0 |  | 70.98 | 0.3415% | 70.98 | 0.3415% | 10054.14 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878628 - DIXON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-15 | 2019-12-31 | 2019-08-15 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 946287¦¦2020-03-31
TM | C | Yes | 946288 |  | POTLATCH CORP WARREN AR | BURGE, EVERETT E. | 100% | 5000 | 0 | 5000 | 9184.7 | 9184.7 | 9184.7 | 0 | 0 | 9184.7 | 3750 | 0 | 3750 | [7 empty] | 4301.88 | 634.53 | 188.01 |  | 3479.34 |  |  | 4882.82 | 0 | 114.7% |  | 0 | 4301.88 | 1250 | 25% | 0 | 1250 | 25% | 0 |  | 4882.82 | 53.16% | 4882.82 | 53.16% | -4184.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 896506 - POTLATCH CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-08-14 | 2019-10-14 | 2019-08-14 | 2019-10-14 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 946288¦¦2020-03-31
TM | CJ | Yes | 946289 |  | SO CAL GAS BLYTHE SAMPLE PORTS | BRASHEAR, DAVID M | 100% | 1940 | 0 | 1940 | 1287.28 | 1287.28 | 0 | 0 | 0 | 1287.28 | 1140 | 0 | 1140 | [7 empty] | 1039.99 | 434.7 | 252.16 |  | 353.13 |  |  | 247.29 | 0 | 91.23% |  | 0 | 1039.99 | 800 | 41.24% | 0 | 800 | 41.24% | 0 |  | 247.29 | 19.21% | 247.29 | 19.21% | 652.72 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 898034 - SOUTHERN CALIFORNIA GAS CO | WATER | WATER REPAIR & INSTALLATION | 2019-08-09 | 2019-08-30 | 2019-08-09 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | CONST MANAGER/GEN CONTRACTOR | 946289¦¦2020-03-31
TM | LJ | Yes | 946638 |  | LACDPW WEST COAST BARRIER MSA | SEIDEN, ANDREW L. | 56.3% | 909091 | 0 | 909091 | 511818.202 | 299664.41 | 299664.41 | 0 | 0 | 909091 | 704858.08 | 0 | 704858.08 | 34564.83 | 19635.07 | 6016.9 |  | 8637.86 | 275 |  | 396835.03 | 195322.13 | 53348.26 |  | 138908.64 | 9256 |  | 0 | 97170.62 | 56.3% |  | 308022.97 | 704858 | 204232.92 | 22.47% | 0 | 204232.92 | 22.47% | 0 |  | 114983.17 | 22.47% | 204233 | 22.47% | 397272.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 319388 - L A COUNTY DEPARTMENT OF PUBLIC WORKS | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2020-02-14 | 2019-08-01 | 2020-02-14 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 946638¦¦2020-03-31
FP | C | Yes | 946639 |  | GREEN PLAINS PWM TESTING | ANDERSON, STEPHEN P. | 100% | 5100 | 0 | 5100 | 3900 | 3900 | 3900 | 0 | 0 | 3900 | 3315 | 0 | 3315 | 0 |  |  |  | 0 |  |  | 4901.1 | 1961.24 | 1340.14 |  | 1599.72 |  |  | 0 | 1001.1 | 147.8% |  | 0 | 4901.1 | 1785 | 35% | 0 | 1785 | 35% | 0 |  | -1001.1 | -25.67% | -1001.1 | -25.67% | 1200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879091 - GREEN PLAINS OBION LLC | WATER | WATER REPAIR & INSTALLATION | 2019-08-16 | 2019-10-01 | 2019-08-16 | 2019-10-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 946639¦¦2020-03-31
FP | C | Yes | 946641 |  | DOW IL MW REHAB | SNELTEN, BRIAN M | 100% | 36925 | 0 | 36925 | 30708 | 30708 | 31460.81 | 0 | 0 | 30708 | 28642 | 0 | 28642 | [7 empty] | 23556.18 | 11467.61 | 2339.3 |  | 9749.27 |  |  | 7151.82 | 0 | 82.24% |  | 0 | 23556.18 | 8283 | 22.43% | 0 | 8283 | 22.43% | 0 |  | 7151.82 | 23.29% | 7151.82 | 23.29% | 6217 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 321763 - ARCADIS US INC | WATER | WATER REPAIR & INSTALLATION | 2019-08-16 | 2019-09-30 | 2019-08-16 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 946641¦¦2020-03-31
FP | CJ | Yes | 946643 |  | 2019 NORTH CAMPUS WELL FIELD | SCHANAMAN, MIKE L. | 100% | 411790 | 0 | 411790 | 355534.4 | 355534.4 | 355534.4 | 0 | 17776.72 | 355534.4 | 350022 | 0 | 350022 | 60797.8 | 21998.05 | 17493.5 |  | 21306.25 |  |  | 294065.59 | 56508.75 | 43133.43 |  | 194423.41 |  |  | 61468.81 | 0 | 84.01% |  | 0 | 294065.59 | 61768 | 15% | 0 | 61768 | 15% | 0 |  | 61468.81 | 17.29% | 61468.81 | 17.29% | 56255.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 413723 - AURORA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-31 | 2020-04-24 | 2019-09-30 | 2020-04-24 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 946643¦¦2020-03-31
TM | C | Yes | 946644 |  | FMI SIERRITA IW8 SWAP DISCHARG | VAN ALLEN, WESLEY C. | 100% | 4939 | 0 | 4939 | 4939.19 | 4939.19 | 4939.19 | 0 | 0 | 4939.19 | 3787 | 0 | 3787 | [7 empty] | 3269.97 | 776.2 | 591.03 |  | 1902.74 |  |  | 1669.22 | 0 | 86.35% |  | 0 | 3269.97 | 1152 | 23.32% | 0 | 1152 | 23.32% | 0 |  | 1669.22 | 33.8% | 1669.22 | 33.8% | -0.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 890921 - FREEPORT MCMORAN SIERRITA | WATER | WATER REPAIR & INSTALLATION | 2019-08-16 | 2019-09-15 | 2019-08-16 | 2019-09-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 946644¦¦2020-03-31
FP | C | Yes | 946645 |  | REDLANDS 1783 BOOSTER | GRACE, GARY L. | 100% | 10127 | 0 | 10127 | 8052.48 | 8052.48 | 8523.87 | 0 | 0 | 8052.48 | 7981 | 0 | 7981 | [7 empty] | 8385.15 | 1835.28 | 283.63 |  | 6266.24 |  |  | 0 | 332.67 | 105.1% |  | 0 | 8385.15 | 2146 | 21.19% | 0 | 2146 | 21.19% | 0 |  | -332.67 | -4.131% | -332.67 | -4.131% | 2074.52 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 896853 - REDLANDS, CA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-16 | 2019-10-02 | 2019-08-16 | 2019-10-02 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 946645¦¦2020-03-31
FP | C | Yes | 947090 |  | SOUTHERN IONICS FLOWTEST | GREGORY, CRYSTAL N | 100% | 1050 | 0 | 1050 | 1050 | 1050 | 1050 | 0 | 0 | 1050 | 785 | 0 | 785 | 0 |  |  |  | 0 |  |  | 1477.64 | 805.39 | 241.15 |  | 431.1 |  |  | 0 | 427.64 | 188.2% |  | 0 | 1477.64 | 265 | 25.24% | 0 | 265 | 25.24% | 0 |  | -427.64 | -40.73% | -427.64 | -40.73% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 898039 - SOUTHERN IONICS INC | WATER | WATER REPAIR & INSTALLATION | 2019-08-19 | 2019-11-01 | 2019-08-19 | 2019-11-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947090¦¦2020-03-31
FP | C | Yes | 947091 |  | CITGO TEST WELL 142 | GNAU, CASEY T | 100% | 2700 | 0 | 2700 | 3130 | 3130 | 3130 | 0 | 0 | 3130 | 1350 | 0 | 1350 | 0 |  |  |  | 0 |  |  | 2246.03 | 1158.53 | 488.4 |  | 599.1 |  |  | 883.97 | 0 | 166.4% |  | 0 | 2246.03 | 1350 | 50% | 0 | 1350 | 50% | 0 |  | 883.97 | 28.24% | 883.97 | 28.24% | -430 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878864 - CITGO PETROLEUM CORP | WATER | WATER REPAIR & INSTALLATION | 2019-08-19 | 2019-08-30 | 2019-08-19 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947091¦¦2020-03-31
TM | C | Yes | 947092 |  | GRACE TEST 3 WELLS | GNAU, CASEY T | 100% | 4500 | 1500 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 6000 | 2250 | 1500 | 3750 | [7 empty] | 4771.33 | 2793.45 | 732.6 |  | 1245.28 |  |  | 1228.67 | 0 | 127.2% |  | 0 | 4771.33 | 2250 | 50% | 0 | 2250 | 37.5% | 0 |  | 1228.67 | 20.48% | 1228.67 | 20.48% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879019 - W R GRACE & CO CONN | WATER | WATER REPAIR & INSTALLATION | 2019-08-19 | 2019-08-30 | 2019-08-19 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947092¦¦2020-03-31
TM | C | Yes | 947115 |  | WESTERN FLEMING RWP1 | MIGUEL, SEAN J. | 100% | 5000 | 0 | 5000 | 7430 | 7430 | 7430 | 0 | 0 | 7430 | 4000 | 0 | 4000 | [7 empty] | 5522.29 | 1024.57 | 243.6 |  | 3264.12 | 990 |  | 1907.71 | 0 | 138.1% |  | 0 | 5522.29 | 1000 | 20% | 0 | 1000 | 20% | 0 |  | 1907.71 | 25.68% | 1907.71 | 25.68% | -2430 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 900098 - WESTERN FLEMING COUNTY WATER | WATER | WATER REPAIR & INSTALLATION | 2019-08-16 | 2019-09-30 | 2019-08-16 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 947115¦¦2020-03-31
TM | CJ | Yes | 947116 |  | POLLOCK WELL 2 TOWN | GNAU, CASEY T | 100% | 13500 | 0 | 13500 | 13500 | 13500 | 13500 | 0 | 0 | 13500 | 7984 | 0 | 7984 | [7 empty] | 6195.09 | 1112.45 | 1082.44 |  | 4000.2 |  |  | 7304.91 | 0 | 77.59% |  | 0 | 6195.09 | 5516 | 40.86% | 0 | 5516 | 40.86% | 0 |  | 7304.91 | 54.11% | 7304.91 | 54.11% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 896447 - POLLOCK, LA, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-19 | 2019-08-30 | 2019-08-19 | 2019-08-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 947116¦¦2020-03-31
FP | C | Yes | 947416 |  | GRAND TOWER WELL 3 SERVICE | WHITE, CATHLEEN R | 100% | 50570 | 14590 | 65160 | 65160 | 65160 | 65160 | 0 | 0 | 65160 | 50570 | 14590 | 65160 | -0.01 |  |  |  | -0.01 |  |  | 45485.53 | 22173.87 | 7422.06 |  | 15889.6 |  |  | 19674.47 | 0 | 69.81% |  | 0 | 45485.53 | 0 | 0% | 0 | 0 | 0% | 0 |  | 19674.47 | 30.19% | 19674.47 | 30.19% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 947126 - GRAND TOWER ENERGY CENTER | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-09-30 | 2019-08-01 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 947416¦¦2020-03-31
FP | C | Yes | 947419 |  | JG BOSWELL KL16 NEW WELL | TRAMMELL, DUANE R. | 100% | 587824.1 | -0.1 | 587824 | 532912 | 532912 | 532912 | 0 | 0 | 532912 | 475270.48 | 0 | 475270.48 | 0 |  | 0 |  |  |  |  | 478478.95 | 116954.59 | 117287.46 |  | 231630.22 | 12606.68 |  | 54433.05 | 0 | 100.7% |  | 0 | 478478.95 | 112553.62 | 19.15% | -0.1 | 112553.52 | 19.15% | 0 |  | 54433.05 | 10.21% | 54433.05 | 10.21% | 54912 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892822 - JG BOSWELL COMPANY | WATER | WATER SUPPLY | 2019-08-09 | 2019-11-08 | 2019-08-15 | 2019-11-08 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 947419¦¦2020-03-31
TM | C | Yes | 947420 |  | ALLSTATE NORTH PLAZA WELL 1 | KENNEDY, CHRISTOPHER C. | 100% | 76300 | 0 | 76300 | 137779.7 | 137779.7 | 139148.1 | 0 | 0 | 137779.7 | 61000 | 0 | 61000 | 0 |  |  |  | 0 |  |  | 107043.67 | 62949.37 | 12264.72 |  | 31829.58 |  |  | 30736.03 | 0 | 175.5% |  | 0 | 107043.67 | 15300 | 20.05% | 0 | 15300 | 20.05% | 0 |  | 30736.03 | 22.31% | 30736.03 | 22.31% | -61479.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 886118 - ALLSTATE INSURANCE COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-08-20 | 2019-09-30 | 2019-08-20 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947420¦¦2020-03-31
FP | C | Yes | 947504 |  | DARAMIC FLOW TESTS | MIGUEL, SEAN J. | 100% | 2000 | 34605 | 36605 | 37061 | 37061 | 37061 | 0 | 0 | 37061 | 1400 | 25105 | 26505 | 69.96 |  |  |  | 69.96 |  |  | 25369.59 | 9032.28 | 4455.2 |  | 11882.11 |  |  | 11691.41 | 0 | 95.72% |  | 0 | 25369.59 | 600 | 30% | 9500 | 10100 | 27.59% | 0 |  | 11691.41 | 31.55% | 11691.41 | 31.55% | -456 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889327 - DARAMIC, LLC | WATER | WATER REPAIR & INSTALLATION | 2019-08-21 | 2019-09-30 | 2019-08-21 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947504¦¦2020-03-31
FP | LJ | Yes | 947513 |  | NORTH AURORA WELL 8 AND 9 | KENNEDY, CHRISTOPHER C. | 68.76% | 593317.13 | 0 | 593317.13 | 407958.159 | 368950 | 368950 | 0 | 36895 | 593317.13 | 480655.85 | 0 | 480655.85 | 145545.61 | 16934.11 | 3538.4 |  | 125073.1 |  |  | 356043.19 | 45243.78 | 5700.41 |  | 297579.8 | 7519.2 |  | 12906.81 | 0 | 74.07% |  | 161771 | 517814.19 | 112661.28 | 18.99% | 0 | 112661.28 | 18.99% | 0 |  | 51914.97 | 12.73% | 75502.94 | 12.73% | 185358.97 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878592 - NORTH AURORA, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-13 | 2020-01-30 | 2019-08-13 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 947513¦¦2020-03-31
TM | CJ | Yes | 947516 |  | INDEPENDENCE WSD A1 INSTALL | SCHANAMAN, MIKE L. | 100% | 219100 | 0 | 219100 | 218567.5 | 218567.5 | 218567.5 | 0 | 0 | 218567.5 | 179996 | 0 | 179996 | 410.44 | 290.67 |  |  | 119.77 |  |  | 194652.96 | 9284.48 | 4528.98 |  | 180839.5 |  |  | 23914.54 | 0 | 108.1% |  | 0 | 194652.96 | 39104 | 17.85% | 0 | 39104 | 17.85% | 0 |  | 23914.54 | 10.94% | 23914.54 | 10.94% | 532.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 947441 - INDEPENDENCE WATER & SANITATION DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-08-21 | 2019-10-31 | 2019-08-21 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 947516¦¦2020-03-31
TM | CJ | Yes | 947517 |  | WEST COOLEY RESERVOIR | DECKER, JASEN | 100% | 194705 | 0 | 194705 | 194705 | 194705 | 194705 | 194705 | 0 | 194705 | 144477 | 0 | 144477 | 69554.63 | 25492.69 | 29065.45 |  | 13861.49 | 1135 |  | 159818.44 | 55647.55 | 55155.01 |  | 47880.88 | 1135 |  | 34886.56 | 0 | 110.6% |  | 0 | 159818.44 | 50228 | 25.8% | 0 | 50228 | 25.8% | 0 |  | 34886.56 | 17.92% | 34886.56 | 17.92% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 947436 - AMERICAN WEST CONSTRUCTION LLC | WATER | WATER SUPPLY | 2019-08-21 | 2019-10-31 | 2019-08-21 | 2019-10-31 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 947517¦¦2020-03-31
TM | CJ | Yes | 947518 |  | ESSITY WELL 9 PUMP | BARNES, MATTHEW D | 100% | 6387 | 195083 | 201470 | 202350.3 | 202350.3 | 202350.3 | 0 | 0 | 202350.3 | 4804 | 133445 | 138249 | 24.7 | 5.28 |  |  | 19.42 |  |  | 131223.63 | 41712.21 | 22630.45 |  | 66880.97 |  |  | 71126.67 | 0 | 94.92% |  | 0 | 131223.63 | 1583 | 24.78% | 61638 | 63221 | 31.38% | 12966 |  | 71126.67 | 35.15% | 71126.67 | 35.15% | -880.3 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 947189 - ESSITY OPERATIONS WAUSAU LLC | WATER | WATER REPAIR & INSTALLATION | 2019-08-21 | 2019-09-30 | 2019-08-21 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947518¦¦2020-03-31
TM | C | Yes | 947714 |  | WESTROCK 23 | GNAU, CASEY T | 100% | 23100 | 0 | 23100 | 23100 | 23100 | 23100 | 0 | 0 | 23100 | 11546 | 0 | 11546 | [7 empty] | 12171.82 | 6277.91 | 3588.84 |  | 2305.07 |  |  | 10928.18 | 0 | 105.4% |  | 0 | 12171.82 | 11554 | 50.02% | 0 | 11554 | 50.02% | 0 |  | 10928.18 | 47.31% | 10928.18 | 47.31% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2019-08-21 | 2019-08-30 | 2019-08-21 | 2019-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947714¦¦2020-03-31
FP | C | Yes | 947716 |  | BRW MONTESANO PUMP | LOPEZ-VASQUEZ, JUAN C. | 100% | 81410.95 | 0 | 81410.95 | 80625.95 | 80625.95 | 87354.74 | 0 | 0 | 80625.95 | 61150 | 0 | 61150 | 0 |  |  |  | 0 |  |  | 56767.07 | 7958.99 | 2065.85 |  | 46742.23 |  |  | 23858.88 | 0 | 92.83% |  | 0 | 56767.07 | 20260.95 | 24.89% | 0 | 20260.95 | 24.89% | 0 |  | 23858.88 | 29.59% | 23858.88 | 29.59% | 785 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-08-21 | 2019-11-26 | 2019-08-21 | 2019-11-26 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947716¦¦2020-03-31
TM | CJ | Yes | 947961 |  | EXXON 78 PUMP REPAIR | LOPEZ-VASQUEZ, JUAN C. | 100% | 12760 | 0 | 12760 | 12760 | 12760 | 12760 | 0 | 0 | 12760 | 6780 | 0 | 6780 | [7 empty] | 1916.64 | 1318.45 | 27 |  | 571.19 |  |  | 10843.36 | 0 | 28.27% |  | 0 | 1916.64 | 5980 | 46.87% | 0 | 5980 | 46.87% | 0 |  | 10843.36 | 84.98% | 10843.36 | 84.98% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878581 - EXXON MOBIL REFINERY | WATER | WATER REPAIR & INSTALLATION | 2019-08-22 | 2019-12-31 | 2019-08-22 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947961¦¦2020-03-31
TM | CJ | Yes | 947964 |  | LIMA FOXTROT LLC | SCHERM, LOGAN M | 100% | 26500 | 0 | 26500 | 8571.6 | 8571.6 | 0 | 0 | 0 | 8571.6 | 23850 | 0 | 23850 | [7 empty] | 6924.95 | 238.73 |  |  | 6686.22 |  |  | 1646.65 | 0 | 29.04% |  | 0 | 6924.95 | 2650 | 10% | 0 | 2650 | 10% | 0 |  | 1646.65 | 19.21% | 1646.65 | 19.21% | 17928.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 947779 - LIMA FOXTROT LLC | WATER | WATER SUPPLY | 2019-08-22 | 2020-08-22 | 2019-08-22 | 2020-08-22 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 947964¦¦2020-03-31
TM | C | Yes | 947965 |  | WATCO NEW PUMP | LOPEZ-VASQUEZ, JUAN C. | 100% | 39195 | 0 | 39195 | 39195 | 39195 | 39195 | 0 | 0 | 39195 | 25531 | 0 | 25531 | [7 empty] | 26612.47 | 4548.19 | 1132.27 |  | 20202.16 | 729.85 |  | 12582.53 | 0 | 104.2% |  | 0 | 26612.47 | 13664 | 34.86% | 0 | 13664 | 34.86% | 0 |  | 12582.53 | 32.1% | 12582.53 | 32.1% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 899894 - WATCO COMPANIES | WATER | WATER REPAIR & INSTALLATION | 2019-08-22 | 2019-10-31 | 2019-08-22 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 947965¦¦2020-03-31
FP | C | Yes | 948755 |  | TOWN OF DAVIE FL WELL | TORMOEHLEN, DAVID A. | 100% | 94100 | 0 | 94100 | 94100 | 94100 | 94100 | 0 | 0 | 94100 | 61209 | 0 | 61209 | [7 empty] | 61568.26 |  | 117.15 |  | 61451.11 |  |  | 32531.74 | 0 | 100.6% |  | 0 | 61568.26 | 32891 | 34.95% | 0 | 32891 | 34.95% | 0 |  | 32531.74 | 34.57% | 32531.74 | 34.57% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878976 - DAVIE, TOWN OF | WATER | WATER SUPPLY | 2019-08-23 | 2019-11-30 | 2019-08-23 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 948755¦¦2020-03-31
TM | C | Yes | 948756 |  | TOWN OF DAVIE WELL 3 SERVICE | TORMOEHLEN, DAVID A. | 100% | 19317 | 0 | 19317 | 21267 | 21267 | 21267 | 0 | 0 | 21267 | 13270 | 0 | 13270 | [7 empty] | 7871.97 | 4117.59 | 1710.66 |  | 2043.72 |  |  | 13395.03 | 0 | 59.32% |  | 0 | 7871.97 | 6047 | 31.3% | 0 | 6047 | 31.3% | 0 |  | 13395.03 | 62.99% | 13395.03 | 62.99% | -1950 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 889355 - DAVIE, FL, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-23 | 2019-09-30 | 2019-08-23 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 948756¦¦2020-03-31
FP | C | Yes | 949016 |  | LINWOOD KS WELL 6 REHAB | WARTICK, LOGAN M | 100% | 13525 | 5419 | 18944 | 18944 | 18944 | 18944 | 0 | 0 | 18944 | 11496 | 4634.18 | 16130.18 | 105.94 | 105.94 |  |  | 0 |  |  | 22052.31 | 7860.53 | 6665.4 |  | 7526.38 |  |  | 0 | 3108.31 | 136.7% |  | 0 | 22052.31 | 2029 | 15% | 784.82 | 2813.82 | 14.85% | 0 |  | -3108.31 | -16.41% | -3108.31 | -16.41% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 893795 - LINWOOD | WATER | WATER REPAIR & INSTALLATION | 2019-08-23 | 2019-11-30 | 2019-08-23 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 949016¦¦2020-03-31
FP | C | Yes | 949017 |  | TOWN OF DAVIE FL WELL 5 PUMP | TORMOEHLEN, DAVID A. | 100% | 8405 | 0 | 8405 | 8405 | 8405 | 8405 | 0 | 0 | 8405 | 5227 | 0 | 5227 | [7 empty] | 3046.2 | 602.68 | 172.53 |  | 2270.99 |  |  | 5358.8 | 0 | 58.28% |  | 0 | 3046.2 | 3178 | 37.81% | 0 | 3178 | 37.81% | 0 |  | 5358.8 | 63.76% | 5358.8 | 63.76% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878976 - DAVIE, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-23 | 2019-09-30 | 2019-08-23 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 949017¦¦2020-03-31
FP | C | Yes | 949018 |  | ORANGE COGEN WELL AND PUMP2019 | TORMOEHLEN, DAVID A. | 100% | 13325 | 0 | 13325 | 51203 | 51203 | 51203 | 0 | 0 | 51203 | 9486 | 0 | 9486 | [7 empty] | 34917.5 | 9937.32 | 2609.78 |  | 22370.4 |  |  | 16285.5 | 0 | 368.1% |  | 0 | 34917.5 | 3839 | 28.81% | 0 | 3839 | 28.81% | 0 |  | 16285.5 | 31.81% | 16285.5 | 31.81% | -37878 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895827 - ORANGE COGENERATION LIMITED PARTNERSHIP | WATER | WATER REPAIR & INSTALLATION | 2019-08-23 | 2019-11-01 | 2019-08-23 | 2019-11-01 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 949018¦¦2020-03-31
TM | C | Yes | 949019 |  | BULL GALLOWAY FARMS | BENNETT, MARK C. | 100% | 54140 | 0 | 54140 | 96993.57 | 96993.57 | 96993.57 | 3200 | 0 | 96993.57 | 44140 | 0 | 44140 | 808.7 |  |  |  | 808.7 |  |  | 108816.79 | 25654.34 | 16456.43 |  | 66706.02 |  |  | 0 | 11823.22 | 246.5% |  | 0 | 108816.79 | 10000 | 18.47% | 0 | 10000 | 18.47% | 0 |  | -11823.22 | -12.19% | -11823.22 | -12.19% | -42853.57 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887594 - BULL GALLOWAY FARMS | WATER | WATER EQUIPMENT SALES | 2019-08-23 | 2019-12-31 | 2019-08-23 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 949019¦¦2020-03-31
TM | C | Yes | 949020 |  | RUMMEL CONSTRUCTION EASTMARK | COMBS, TAYLOR E. | 100% | 245769 | 0 | 245769 | 261006.16 | 261006.16 | 261006.16 | 0 | 0 | 261006.16 | 184004 | 0 | 184004 | [7 empty] | 270241.23 | 66160.59 | 96092.9 |  | 106171.5 | 1816.24 |  | 0 | 9235.07 | 146.9% |  | 0 | 270241.23 | 61765 | 25.13% | 0 | 61765 | 25.13% | 0 |  | -9235.07 | -3.538% | -9235.07 | -3.538% | -15237.16 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878971 - RUMMEL CONSTRUCTION | WATER | WATER SPECIALTY DRILLING | 2019-08-19 | 2019-11-30 | 2019-08-19 | 2019-11-30 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 949020¦¦2020-03-31
FP | C | Yes | 949021 |  | BRW GOVERNMENT PUMP | LOPEZ-VASQUEZ, JUAN C. | 100% | 70800 | -785 | 70015 | 70014.95 | 70014.95 | 75459.1 | 0 | 0 | 70014.95 | 50741 | -500 | 50241 | [7 empty] | 43316.97 | 4632.4 | 1363.02 |  | 37321.55 |  |  | 26697.98 | 0 | 86.22% |  | 0 | 43316.97 | 20059 | 28.33% | -285 | 19774 | 28.24% | 0 |  | 26697.98 | 38.13% | 26697.98 | 38.13% | 0.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-08-23 | 2019-11-30 | 2019-08-23 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 949021¦¦2020-03-31
FP | C | Yes | 949022 |  | MUNFORD TN PM TESTING | ANDERSON, STEPHEN P. | 100% | 2840 | 0 | 2840 | 7725 | 7725 | 7725 | 0 | 0 | 7725 | 1988 | 0 | 1988 | 0 |  |  |  | 0 |  |  | 6507.37 | 2332.31 | 1276.11 |  | 2898.95 |  |  | 1217.63 | 0 | 327.3% |  | 0 | 6507.37 | 852 | 30% | 0 | 852 | 30% | 0 |  | 1217.63 | 15.76% | 1217.63 | 15.76% | -4885 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895103 - MUNFORD, TN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-23 | 2019-09-13 | 2019-08-23 | 2019-09-13 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 949022¦¦2020-03-31
FP | CJ | Yes | 949023 |  | MT CARMEL WELL NO 2 REHAB | CROOK, CHARLES M | 100% | 39810 | 18747.5 | 58557.5 | 57852.5 | 57852.5 | 57852.5 | 0 | 883.25 | 57852.5 | 27610 | 16000 | 43610 | 354.24 | 201.05 |  |  | 153.19 |  |  | 43812.23 | 16611.88 | 8444.38 |  | 18755.97 |  |  | 14040.27 | 0 | 100.5% |  | 0 | 43812.23 | 12200 | 30.65% | 2747.5 | 14947.5 | 25.53% | 2895 |  | 14040.27 | 24.27% | 14040.27 | 24.27% | 705 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 879082 - SOUTH CENTRAL CT REGIONAL WATER AUTH | WATER | WATER SUPPLY | 2019-08-01 | 2019-09-27 | 2019-08-01 | 2019-09-27 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 949023¦¦2020-03-31
FP | C | Yes | 949043 |  | CHARLOTTE COUNTY EASTPORT IW 1 | MARTINEZ, MIGUEL E | 100% | 84200 | 0 | 84200 | 84200 | 84200 | 84200 | 0 | 0 | 84200 | 57350 | 0 | 57350 | [7 empty] | 36326.94 | 11856.9 | 7352.16 |  | 15185.96 | 1931.92 |  | 47873.06 | 0 | 63.34% |  | 0 | 36326.94 | 26850 | 31.89% | 0 | 26850 | 31.89% | 0 |  | 47873.06 | 56.86% | 47873.06 | 56.86% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 888250 - CHARLOTTE COUNTY UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-08-01 | 2019-09-18 | 2019-08-01 | 2019-09-18 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 949043¦¦2020-03-31
TM | C | Yes | 949709 |  | VALMONT EMERGENCY FIRE WELL | GANSEBOM, JASON W. | 100% | 9930 | 0 | 9930 | 46878 | 46878 | 48697.23 | 0 | 0 | 46878 | 5873 | 0 | 5873 | 0 |  |  |  | 0 |  |  | 37257.54 | 11270.93 | 3940.29 |  | 21180.93 | 865.39 |  | 9620.46 | 0 | 634.4% |  | 0 | 37257.54 | 4057 | 40.86% | 0 | 4057 | 40.86% | 0 |  | 9620.46 | 20.52% | 9620.46 | 20.52% | -36948 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 899554 - VALMONT INDUSTRIES | WATER | WATER REPAIR & INSTALLATION | 2019-08-27 | 2019-09-30 | 2019-08-27 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 949709¦¦2020-03-31
FP | C | Yes | 949710 |  | PERC WATER ADELANTO BOOSTER | BRASHEAR, DAVID M | 100% | 2570 | 0 | 2570 | 3809.69 | 3809.69 | 4001.84 | 0 | 0 | 3809.69 | 1524 | 0 | 1524 | [7 empty] | 3308.33 | 1379.58 | 168.1 |  | 1760.65 |  |  | 501.36 | 0 | 217.1% |  | 0 | 3308.33 | 1046 | 40.7% | 0 | 1046 | 40.7% | 0 |  | 501.36 | 13.16% | 501.36 | 13.16% | -1239.69 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878644 - ADELANTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-27 | 2019-09-06 | 2019-08-27 | 2019-09-06 | PRIME CONTRACTOR | PRIVATE | CONSTRUCTION MANAGEMENT | 949710¦¦2020-03-31
FP | C | Yes | 949711 |  | GRAND LAKE PWA WELL 2 | EVANS, TRAVIS L | 100% | 14510 | 0 | 14510 | 14510 | 14510 | 14510 | 0 | 0 | 14510 | 12464 | 0 | 12464 | [7 empty] | 8459.32 | 2481.8 | 829.15 |  | 5148.37 |  |  | 6050.68 | 0 | 67.87% |  | 0 | 8459.32 | 2046 | 14.1% | 0 | 2046 | 14.1% | 0 |  | 6050.68 | 41.7% | 6050.68 | 41.7% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 891480 - GRAND LAKE PWA | WATER | WATER REPAIR & INSTALLATION | 2019-08-19 | 2019-09-11 | 2019-08-19 | 2019-09-11 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 949711¦¦2020-03-31
TM | C | Yes | 949718 |  | EAST LAKE VILLAGE | GRACE, GARY L. | 100% | 6530 | 0 | 6530 | 64618.5 | 64618.5 | 66045.16 | 0 | 0 | 64618.5 | 4213 | 0 | 4213 | [7 empty] | 61493.86 | 15303.16 | 5679.59 |  | 29811.11 | 10700 |  | 3124.64 | 0 | 1460% |  | 0 | 61493.86 | 2317 | 35.48% | 0 | 2317 | 35.48% | 0 |  | 3124.64 | 4.836% | 3124.64 | 4.836% | -58088.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 949517 - EAST LAKE VILLAGE COMMUNITY ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2019-08-23 | 2019-09-30 | 2019-08-26 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 949718¦¦2020-03-31
FP | CJ | Yes | 949720 |  | SIRE WELL 2 AND 3 REHABS | GANSEBOM, JASON W. | 100% | 31090 | 0 | 31090 | 23463 | 23463 | 23463 | 23463 | 0 | 23463 | 18592 | 0 | 18592 | 16152.88 | 3744.68 | 1794.39 |  | 10293.81 | 320 |  | 19920.16 | 3744.68 | 1794.39 |  | 14061.09 | 320 |  | 3542.84 | 0 | 107.1% |  | 0 | 19920.16 | 12498 | 40.2% | 0 | 12498 | 40.2% | 0 |  | 3542.84 | 15.1% | 3542.84 | 15.1% | 7627 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 898104 - SOUTHWEST IOWA RENEWABLE ENERGY | WATER | WATER REPAIR & INSTALLATION | 2019-08-27 | 2019-10-30 | 2019-08-27 | 2019-10-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 949720¦¦2020-03-31
FP | C | Yes | 949947 |  | EA ENG OW 18 A REPLACEMENT | COMBS, TAYLOR E. | 100% | 31803 | 0 | 31803 | 32937 | 32937 | 32937 | 0 | 0 | 32937 | 23574 | 0 | 23574 | [7 empty] | 15075.27 | 4367.07 | 6712.48 |  | 3995.72 |  |  | 17861.73 | 0 | 63.95% |  | 0 | 15075.27 | 8229 | 25.87% | 0 | 8229 | 25.87% | 0 |  | 17861.73 | 54.23% | 17861.73 | 54.23% | -1134 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 906312 - EA ENGINEERING SCIENCE AND TECHNOLOGY | WATER | WATER REPAIR & INSTALLATION | 2019-08-28 | 2019-09-06 | 2019-08-28 | 2019-09-06 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 949947¦¦2020-03-31
FP | CJ | Yes | 949948 |  | WESTERN MUNI NEW CLAY WELL | BRASHEAR, DAVID M | 100% | 59516 | 0 | 59516 | 61016.35 | 61016.35 | 65264.63 | 0 | 0 | 61016.35 | 46156 | 0 | 46156 | [7 empty] | 46592.98 | 680.88 | 148.4 |  | 45763.7 |  |  | 14423.37 | 0 | 100.9% |  | 0 | 46592.98 | 13360 | 22.45% | 0 | 13360 | 22.45% | 0 |  | 14423.37 | 23.64% | 14423.37 | 23.64% | -1500.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 900107 - WESTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-08-28 | 2019-10-15 | 2019-08-28 | 2019-10-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 949948¦¦2020-03-31
FP | CJ | Yes | 950152 |  | MOON TOWNSHIP WELLFIELD STUDY | GAMBLE, BRAD F. | 100% | 24245 | 0 | 24245 | 23378.95 | 23378.95 | 23378.95 | 0 | 0 | 23378.95 | 18704 | 0 | 18704 | 0.1 | 0.1 |  |  | 0 |  |  | 10646.42 | 10402.7 |  |  | 243.72 |  |  | 12732.53 | 0 | 56.92% |  | 0 | 10646.42 | 5541 | 22.85% | 0 | 5541 | 22.85% | 0 |  | 12732.53 | 54.46% | 12732.53 | 54.46% | 866.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 593 - WRD COLLECTOR WELLS | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 894951 - MOON TOWNSHIP MUNICIPAL AUTHORITY | WATER | WATER SUPPLY | 2019-08-26 | 2020-01-15 | 2019-08-26 | 2020-01-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 950152¦¦2020-03-31
FP | CJ | Yes | 950154 |  | BASF WELL 2 | PARSLEY, TRISTAN S | 100% | 72495 | 0 | 72495 | 66120 | 66120 | 66120 | 0 | 0 | 66120 | 41906 | 0 | 41906 | [7 empty] | 57963.56 | 11098.16 | 2281.19 |  | 44584.21 |  |  | 8156.44 | 0 | 138.3% |  | 0 | 57963.56 | 30589 | 42.19% | 0 | 30589 | 42.19% | 0 |  | 8156.44 | 12.34% | 8156.44 | 12.34% | 6375 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 878980 - BASF MCINTOSH PLANT | WATER | WATER REPAIR & INSTALLATION | 2019-08-19 | 2019-09-30 | 2019-08-29 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 950154¦¦2020-03-31
FP | CJ | Yes | 950240 |  | PENNAKEM PUMP | ANDERSON, STEPHEN P. | 100% | 20000 | 0 | 20000 | 24000 | 24000 | 24000 | 2000 | 0 | 24000 | 12000 | 0 | 12000 | 0.98 |  |  |  | 0.98 |  |  | 2946.1 | 122.37 |  |  | 561.59 | 2262.14 |  | 21053.9 | 0 | 24.55% |  | 0 | 2946.1 | 8000 | 40% | 0 | 8000 | 40% | 0 |  | 21053.9 | 87.72% | 21053.9 | 87.72% | -4000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 896183 - PENNAKEM | WATER | WATER REPAIR & INSTALLATION | 2019-08-29 | 2020-01-31 | 2019-08-29 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 950240¦¦2020-03-31
FP | LJ | Yes | 950260 |  | MARATHON NEW DRILL | MCMAHON, PERRY J | 98.06% | 834400 | 802705 | 1637105 | 1556649.6229 | 1548755.75 | 1548755.75 | 33575 | 0 | 1587487 | 683246.43 | 656266.21 | 1339512.64 | 75714.79 | 30781.03 | 14605.2 |  | 25508.08 | 4820.48 |  | 1300573.26 | 327621.02 | 274588.87 |  | 655376.41 | 42986.96 |  | 248182.49 | 0 | 97.09% |  | 25764.48 | 1326337.74 | 151153.57 | 18.12% | 146438.79 | 297592.36 | 18.18% | 84242.3 |  | 256076.36 | 16.45% | 261149.26 | 16.45% | 80455.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 894198 - MARATHON PETROLEUM CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-08-29 | 2019-11-17 | 2019-08-29 | 2019-11-17 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 950260¦¦2020-03-31
TM | C | Yes | 950402 |  | ALLSTATE WEST PLAZA 2 REPAIRS | KENNEDY, CHRISTOPHER C. | 100% | 118263 | 0 | 118263 | 86459 | 86459 | 91199.95 | 0 | 0 | 86459 | 94600 | 0 | 94600 | 0 |  |  |  | 0 |  |  | 70166.3 | 23838.85 | 4295.68 |  | 42031.77 |  |  | 16292.7 | 0 | 74.17% |  | 0 | 70166.3 | 23663 | 20.01% | 0 | 23663 | 20.01% | 0 |  | 16292.7 | 18.84% | 16292.7 | 18.84% | 31804 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 950156 - NBINV AP3 LLC | WATER | WATER REPAIR & INSTALLATION | 2019-08-29 | 2019-09-30 | 2019-08-29 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 950402¦¦2020-03-31
TM | C | Yes | 950419 |  | RANCHERO BOOSTER A ZONE J | BRASHEAR, DAVID M | 100% | 4536 | 12172.9 | 16708.9 | 16708.9 | 16708.9 | 16860.02 | 0 | 0 | 16708.9 | 2939 | 7543.77 | 10482.77 | [7 empty] | 13797.12 | 6912.87 | 1044.81 |  | 5839.44 |  |  | 2911.78 | 0 | 131.6% |  | 0 | 13797.12 | 1597 | 35.21% | 4629.13 | 6226.13 | 37.26% | 0 |  | 2911.78 | 17.43% | 2911.78 | 17.43% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 965066 - SAN BERNARDINO, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-08-28 | 2019-10-31 | 2019-08-28 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 950419¦¦2020-03-31
TM | C | Yes | 950420 |  | WELL 8 HI DESERT WD | BRASHEAR, DAVID M | 100% | 16299 | 0 | 16299 | 16299.43 | 16299.43 | 16773.49 | 0 | 0 | 16299.43 | 12224 | 0 | 12224 | [7 empty] | 16664.76 | 5608.43 | 1816.58 |  | 9239.75 |  |  | 0 | 365.33 | 136.3% |  | 0 | 16664.76 | 4075 | 25% | 0 | 4075 | 25% | 0 |  | -365.33 | -2.241% | -365.33 | -2.241% | -0.43 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892080 - HI DESERT WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-08-29 | 2019-09-30 | 2019-08-29 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 950420¦¦2020-03-31
FP | C | Yes | 950422 |  | RIVERSIDE CEMENT 60 1 WELL | SEIDEN, ANDREW L. | 100% | 49605 | 8828.75 | 58433.75 | 56095.6 | 56095.6 | 58691.06 | 0 | 0 | 56095.6 | 36781 | 6912.41 | 43693.41 | [7 empty] | 60666.87 | 15321.74 | 6090.32 |  | 38504.81 | 750 |  | 0 | 4571.27 | 138.8% |  | 0 | 60666.87 | 12824 | 25.85% | 1916.34 | 14740.34 | 25.23% | 0 |  | -4571.27 | -8.149% | -4571.27 | -8.149% | 2338.15 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 950174 - RIVERSIDE CEMENT | WATER | WATER REPAIR & INSTALLATION | 2019-08-15 | 2019-12-31 | 2019-08-21 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 950422¦¦2020-03-31
FP | C | Yes | 950748 |  | LWC FT KNOX WELL 9 | MIGUEL, SEAN J. | 100% | 5950 | 26811 | 32761 | 33656 | 33656 | 33656 | 0 | 0 | 33656 | 3910 | 19682 | 23592 | 0 |  |  |  | 0 |  |  | 28790.2 | 7199.79 | 2003.67 |  | 5464.74 | 14122 |  | 4865.8 | 0 | 122% |  | 0 | 28790.2 | 2040 | 34.29% | 7129 | 9169 | 27.99% | 0 |  | 4865.8 | 14.46% | 4865.8 | 14.46% | -895 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878555 - LOUISVILLE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-08-23 | 2019-09-30 | 2019-08-23 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 950748¦¦2020-03-31
TM | CJ | Yes | 950750 |  | NESTLE TEST WELL DRILLING | CROOK, CHARLES M | 100% | 51415 | 11443 | 62858 | 116175.5 | 116175.5 | 104304.24 | 17447.4 | 0 | 116175.5 | 38615 | 7065 | 45680 | 16999.9 | 11406.14 | 2021.53 |  | 3572.23 |  |  | 89954.05 | 47261.52 | 20591.27 |  | 22101.26 |  |  | 26221.45 | 0 | 196.9% |  | 0 | 89954.05 | 12800 | 24.9% | 4378 | 17178 | 27.33% | 0 |  | 26221.45 | 22.57% | 26221.45 | 22.57% | -53317.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 950623 - NESTLE WATERS NORTH AMERICA INC | WATER | WATER SUPPLY | 2019-08-30 | 2019-09-20 | 2019-08-30 | 2019-09-27 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 950750¦¦2020-03-31
FP | CJ | Yes | 950779 |  | COAL GROVE WTP RENO | BARNES, MATTHEW D |  | 2400 | 0 | 2400 |  |  | 0 | 0 | 0 |  | 2066 | 0 | 2066 | [20 empty] | 334 | 13.92% | 0 | 334 | 13.92% | 0 | [5 empty] | 2400 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 950644 - COAL GROVE, THE VILLAGE OF | WATER | WATER SUPPLY | 2019-08-30 | 2019-09-30 | 2019-08-30 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 950779¦¦2020-03-31
TM | C | Yes | 950780 |  | FOOTHILL ELECTRIC BOOSTER | SEIDEN, ANDREW L. | 100% | 5789 | 0 | 5789 | 5789.16 | 5789.16 | 5789.16 | 0 | 0 | 5789.16 | 4622 | 0 | 4622 | [7 empty] | 2647.45 | 1112.37 | 85.43 |  | 1449.65 |  |  | 3141.71 | 0 | 57.28% |  | 0 | 2647.45 | 1167 | 20.16% | 0 | 1167 | 20.16% | 0 |  | 3141.71 | 54.27% | 3141.71 | 54.27% | -0.16 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 890750 - FOOTHILL ELECTRIC COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-09-03 | 2019-09-15 | 2019-09-03 | 2019-09-15 | PRIME CONTRACTOR | PRIVATE | PRIVATE PUBLIC PARTNERSHIP | 950780¦¦2020-03-31
FP | CJ | Yes | 950805 |  | OSCHNER KENNER W2 | GREGORY, CRYSTAL N | 100% | 8150 | 24555 | 32705 | 8150 | 8150 | 8150 | 0 | 0 | 8150 | 5440 | 17436 | 22876 | 1064.09 | 624.67 | 10 |  | 429.42 |  |  | 6123.74 | 3421.11 | 731.31 |  | 1971.32 |  |  | 2026.26 | 0 | 26.77% |  | 0 | 6123.74 | 2710 | 33.25% | 7119 | 9829 | 30.05% | 7119 | 7119 | 2026.26 | 24.86% | 2026.26 | 24.86% | 24555 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 949534 - AHG SERVICES LLC | WATER | WATER REPAIR & INSTALLATION | 2019-09-03 | 2019-11-16 | 2019-09-03 | 2019-11-16 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 950805¦¦2020-03-31
FP | C | Yes | 950836 |  | VOORHEESVILLE NY PWM | CROOK, CHARLES M | 100% | 2100 | 0 | 2100 | 2100 | 2100 | 2100 | 0 | 0 | 2100 | 1600 | 0 | 1600 | [7 empty] | 1129.74 | 713.61 | 147.93 |  | 268.2 |  |  | 970.26 | 0 | 70.61% |  | 0 | 1129.74 | 500 | 23.81% | 0 | 500 | 23.81% | 0 |  | 970.26 | 46.2% | 970.26 | 46.2% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 899745 - VOORHEESVILLE PUBLIC WORKS DEPT | WATER | WATER REPAIR & INSTALLATION | 2019-09-02 | 2019-10-07 | 2019-09-02 | 2019-10-07 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 950836¦¦2020-03-31
FP | C | Yes | 951108 |  | HENDERSON WELL 9 | ANDERSON, STEPHEN P. | 100% | 5300 | 61081 | 66381 | 66381 | 66381 | 66381 | 0 | 0 | 66381 | 4248 | 45371.42 | 49619.42 | 156.83 |  |  |  | 156.83 |  |  | 71262.84 | 29829.71 | 11187.46 |  | 30245.67 |  |  | 0 | 4881.84 | 143.6% |  | 0 | 71262.84 | 1052 | 19.85% | 15709.58 | 16761.58 | 25.25% | 0 |  | -4881.84 | -7.354% | -4881.84 | -7.354% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 892018 - HENDERSON, TN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-03 | 2019-11-29 | 2019-09-09 | 2019-11-29 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 951108¦¦2020-03-31
TM | C | Yes | 951121 |  | MONROVIA WELL 2 | SEIDEN, ANDREW L. | 100% | 6634 | 697.5 | 7331.5 | 7127.5 | 7127.5 | 7331.28 | 0 | 0 | 7127.5 | 3794 | 608.86 | 4402.86 | [7 empty] | 5046.22 | 2373.37 | 302.59 |  | 2370.26 |  |  | 2081.28 | 0 | 114.6% |  | 0 | 5046.22 | 2840 | 42.81% | 88.64 | 2928.64 | 39.95% | 0 |  | 2081.28 | 29.2% | 2081.28 | 29.2% | 204 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879074 - MONROVIA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-03 | 2019-12-31 | 2019-09-03 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 951121¦¦2020-03-31
FP | LJ | Yes | 951122 |  | WEST POINT NE LAYNEOX | MCCARTNEY, JEFFREY C | 80.77% | 583850 | 0 | 583850 | 471569.9401 | 452483.75 | 452483.75 | 0 | 0 | 583850 | 406556.53 | 0 | 406556.53 | 17881.99 | 2176.88 |  |  | 497.19 | 15207.92 |  | 404352.36 | 15486.31 |  |  | 177972.38 | 210893.67 |  | 48131.39 | 0 | 99.46% |  | 96275.66 | 500628.02 | 177293.47 | 30.37% | 0 | 177293.47 | 30.37% | 0 |  | 67217.58 | 14.25% | 83221.98 | 14.25% | 112280.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 900179 - WEST POINT, CITY OF | WATER | WATER TREATMENT | 2019-09-01 | 2020-04-30 | 2019-09-01 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 951122¦¦2020-03-31
FP | C | Yes | 951123 |  | WESTROCK WELL 4A SAMPLING | CALLAHAN, DANIEL E. | 100% | 2060 | 0 | 2060 | 2060 | 2060 | 2060 | 0 | 0 | 2060 | 1442 | 0 | 1442 | [7 empty] | 422.94 |  |  |  | 32.94 | 390 |  | 1637.06 | 0 | 29.33% |  | 0 | 422.94 | 618 | 30% | 0 | 618 | 30% | 0 |  | 1637.06 | 79.47% | 1637.06 | 79.47% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 879097 - WESTROCK | WATER | WATER REPAIR & INSTALLATION | 2019-09-04 | 2019-09-04 | 2019-09-04 | 2019-09-04 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 951123¦¦2020-03-31
FP | CJ | Yes | 951494 |  | PCA WELL 14 | GNAU, CASEY T | 100% | 40000 | 0 | 40000 | 35984.4 | 35984.4 | 35984.4 | 0 | 0 | 35984.4 | 20000 | 0 | 20000 | [7 empty] | 16695.82 | 9074.02 | 3205.71 |  | 4416.09 |  |  | 19288.58 | 0 | 83.48% |  | 0 | 16695.82 | 20000 | 50% | 0 | 20000 | 50% | 0 |  | 19288.58 | 53.6% | 19288.58 | 53.6% | 4015.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895966 - PACKAGING CORPORATION OF AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-09-04 | 2019-09-30 | 2019-09-04 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 951494¦¦2020-03-31
TM | CJ | Yes | 951495 |  | THOMAS PUMP REPAIR | MIGUEL, SEAN J. | 100% | 4592 | 53604 | 58196 | 58196 | 58196 | 58196 | 31266 | 0 | 58196 | 3214 | 37784 | 40998 | 15136.12 | 6497.08 | 456.04 |  | 8183 |  |  | 35596.62 | 16322.54 | 1224.09 |  | 18049.99 |  |  | 22599.38 | 0 | 86.83% |  | 0 | 35596.62 | 1378 | 30.01% | 15820 | 17198 | 29.55% | 15820 | 2269 | 22599.38 | 38.83% | 22599.38 | 38.83% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 898909 - THOMAS PUMP & CONTROLS | WATER | WATER REPAIR & INSTALLATION | 2019-09-03 | 2019-12-31 | 2019-09-03 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 951495¦¦2020-03-31
FP | C | Yes | 951641 |  | IP PRATTVILLE RIVER PUMP | PARSLEY, TRISTAN S | 100% | 26250 | 42700 | 68950 | 71512.21 | 71512.21 | 71512.21 | 0 | 0 | 71512.21 | 16074 | 25574 | 41648 | [7 empty] | 68826.32 | 24706.09 | 2381.22 |  | 41739.01 |  |  | 2685.89 | 0 | 165.3% |  | 0 | 68826.32 | 10176 | 38.77% | 17126 | 27302 | 39.6% | 0 |  | 2685.89 | 3.756% | 2685.89 | 3.756% | -2562.21 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 892606 - INTERNATIONAL PAPER PRATTVILLE MILL | WATER | WATER REPAIR & INSTALLATION | 2019-09-05 | 2019-09-30 | 2019-09-05 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 951641¦¦2020-03-31
TM | C | Yes | 952093 |  | DYNEGY RIVER PUMP | BARNES, MATTHEW D | 100% | 1740 | 0 | 1740 | 8400 | 8400 | 8400 | 0 | 0 | 8400 | 1425 | 0 | 1425 | 0.01 | 0.01 |  |  | 0 |  |  | 2393.69 | 1289.94 | 596.88 |  | 506.87 |  |  | 6006.31 | 0 | 168% |  | 0 | 2393.69 | 315 | 18.1% | 0 | 315 | 18.1% | 0 |  | 6006.31 | 71.5% | 6006.31 | 71.5% | -6660 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 906320 - DYNEGY | WATER | WATER REPAIR & INSTALLATION | 2019-09-03 | 2019-09-30 | 2019-09-03 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 952093¦¦2020-03-31
FP | C | Yes | 952095 |  | CHARLESTON MS WELL INSPECTION | ANDERSON, STEPHEN P. | 100% | 420 | 0 | 420 | 420 | 420 | 420 | 0 | 0 | 420 | 230 | 0 | 230 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 419.99 | 0 | 0.004348% |  | 0 | 0.01 | 190 | 45.24% | 0 | 190 | 45.24% | 0 |  | 419.99 | 100% | 419.99 | 100% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 906328 - CHARLESTON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-06 | 2019-09-18 | 2019-09-06 | 2019-09-18 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 952095¦¦2020-03-31
FP | C | Yes | 952096 |  | TERRANEXT 43RD AND BUCKEYE | COMBS, TAYLOR E. | 100% | 355017 | 0 | 355017 | 226469.5 | 226469.5 | 226469.5 | 0 | 0 | 226469.5 | 285114 | 0 | 285114 | [7 empty] | 200513.67 | 58450.83 | 57230.99 |  | 80858.62 | 3973.23 |  | 25955.83 | 0 | 70.33% |  | 0 | 200513.67 | 69903 | 19.69% | 0 | 69903 | 19.69% | 0 |  | 25955.83 | 11.46% | 25955.83 | 11.46% | 128547.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 898748 - TERRANEXT | WATER | WATER REPAIR & INSTALLATION | 2019-09-06 | 2019-11-27 | 2019-09-06 | 2019-11-27 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 952096¦¦2020-03-31
TM | CJ | Yes | 952235 |  | OTP PARTS | BARNES, MATTHEW D | 100% | 475 | 6716 | 7191 | 7191 | 7191 | 7191 | 0 | 0 | 7191 | 285 | 4649 | 4934 | 0.37 |  |  |  | 0.37 |  |  | 3571.38 |  |  |  | 3571.38 |  |  | 3619.62 | 0 | 72.38% |  | 0 | 3571.38 | 190 | 40% | 2067 | 2257 | 31.39% | 574 |  | 3619.62 | 50.34% | 3619.62 | 50.34% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 879061 - OHIO TRANSMISSION CORPORATION | WATER | WATER EQUIPMENT SALES | 2019-09-06 | 2019-12-31 | 2019-09-06 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 952235¦¦2020-03-31
FP | C | Yes | 952236 |  | ROCKFORD IL UW42 | SNELTEN, BRIAN M | 100% | 41485 | 269477 | 310962 | 309899.5 | 309899.5 | 309899.5 | 0 | 0 | 309899.5 | 30937 | 151248.09 | 182185.09 | -45 |  | -45 |  |  |  |  | 218545.17 | 85068.35 | 24331.21 |  | 109145.61 |  |  | 91354.33 | 0 | 120% |  | 0 | 218545.17 | 10548 | 25.43% | 118228.91 | 128776.91 | 41.41% | 0 |  | 91354.33 | 29.48% | 91354.33 | 29.48% | 1062.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878821 - ROCKFORD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-06 | 2019-12-31 | 2019-09-06 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 952236¦¦2020-03-31
TM | CJ | Yes | 952508 |  | MID AM ENERGY SGT BLF IA | GANSEBOM, JASON W. | 100% | 9864.84 | 0 | 9864.84 | 4604.45 | 4604.45 | 0 | 0 | 0 | 4604.45 | 5823 | 0 | 5823 | [7 empty] | 3719.91 | 1217.79 | 514.52 |  | 1222.1 | 765.5 |  | 884.54 | 0 | 63.88% |  | 0 | 3719.91 | 4041.84 | 40.97% | 0 | 4041.84 | 40.97% | 0 |  | 884.54 | 19.21% | 884.54 | 19.21% | 5260.39 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 894625 - MIDAMERICAN ENERGY SALIX | WATER | WATER REPAIR & INSTALLATION | 2019-09-06 | 2019-10-31 | 2019-09-06 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 952508¦¦2020-03-31
FP | C | Yes | 952511 |  | SYNGENTA FLOWER LLC | MCCULLERS, BLAKE E. | 100% | 2900 | 0 | 2900 | 26914.13 | 26914.13 | 26914.13 | 0 | 0 | 26914.13 | 1861 | 0 | 1861 | [7 empty] | 22003.24 | 3020.76 | 282.36 |  | 12206.19 | 6493.93 |  | 4910.89 | 0 | 1182% |  | 0 | 22003.24 | 1039 | 35.83% | 0 | 1039 | 35.83% | 0 |  | 4910.89 | 18.25% | 4910.89 | 18.25% | -24014.13 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 952292 - SYNGENTA FLOWERS LLC | WATER | WATER REPAIR & INSTALLATION | 2019-09-06 | 2019-09-30 | 2019-09-06 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 952511¦¦2020-03-31
FP | C | Yes | 952863 |  | TEXAS BRINE WESTLAKE 3 R AND I | GREGORY, CRYSTAL N | 100% | 20010 | 21840 | 41850 | 41850 | 41850 | 41850 | 0 | 0 | 41850 | 12567 | 12162 | 24729 | 0 |  |  |  | 0 |  |  | 28223.05 | 7752.62 | 2526.9 |  | 17122.65 | 820.88 |  | 13626.95 | 0 | 114.1% |  | 0 | 28223.05 | 7443 | 37.2% | 9678 | 17121 | 40.91% | 0 |  | 13626.95 | 32.56% | 13626.95 | 32.56% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 898798 - TEXAS BRINE CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-09-09 | 2019-12-16 | 2019-09-09 | 2019-12-16 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 952863¦¦2020-03-31
TM | C | Yes | 952864 |  | SCVMA S6 SUB PUMP | SEIDEN, ANDREW L. | 100% | 22202.66 | 0 | 22202.66 | 21466.74 | 21466.74 | 23237.74 | 0 | 0 | 21466.74 | 16931 | 0 | 16931 | [7 empty] | 18988.4 | 393.19 | 35.1 |  | 18560.11 |  |  | 2478.34 | 0 | 112.2% |  | 0 | 18988.4 | 5271.66 | 23.74% | 0 | 5271.66 | 23.74% | 0 |  | 2478.34 | 11.55% | 2478.34 | 11.55% | 735.92 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 897478 - SANTA CLARITA VALLEY WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2019-09-03 | 2019-09-15 | 2019-09-03 | 2019-09-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 952864¦¦2020-03-31
FP | C | Yes | 952866 |  | PICKAWAY REHAB | BARNES, MATTHEW D | 100% | 25940 | 0 | 25940 | 14351 | 14351 | 14351 | 0 | 0 | 14351 | 21053 | 0 | 21053 | 419.74 | 191.38 | 103.08 |  | 125.28 |  |  | 14098.89 | 3243.07 | 1407.82 |  | 9448 |  |  | 252.11 | 0 | 66.97% |  | 0 | 14098.89 | 4887 | 18.84% | 0 | 4887 | 18.84% | 0 |  | 252.11 | 1.757% | 252.11 | 1.757% | 11589 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 952686 - PICKAWAY CORRECTIONAL INSTITUTION | WATER | WATER REPAIR & INSTALLATION | 2019-08-06 | 2019-11-30 | 2019-09-06 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 952866¦¦2020-03-31
FP | C | Yes | 952897 |  | EVERGREEN PACKAGING STOCKMOTOR | BURGE, EVERETT E. | 100% | 14000 | 0 | 14000 | 14084 | 14084 | 14084 | 0 | 0 | 14084 | 10200 | 0 | 10200 | 0 |  |  |  | 0 |  |  | 11121.7 | 359.7 | 47.46 |  | 10714.54 |  |  | 2962.3 | 0 | 109% |  | 0 | 11121.7 | 3800 | 27.14% | 0 | 3800 | 27.14% | 0 |  | 2962.3 | 21.03% | 2962.3 | 21.03% | -84 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878972 - EVERGREEN PACKAGING INC | WATER | WATER EQUIPMENT SALES | 2019-09-09 | 2019-12-15 | 2019-09-09 | 2019-12-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 952897¦¦2020-03-31
FP | C | Yes | 952898 |  | ARAUCO FLAKEBOARD MALVERN | BURGE, EVERETT E. | 100% | 6600 | 0 | 6600 | 6499.39 | 6499.39 | 6499.39 | 0 | 0 | 6499.39 | 5500 | 0 | 5500 | [7 empty] | 4596.76 | 1500.45 | 678.88 |  | 2417.43 |  |  | 1902.63 | 0 | 83.58% |  | 0 | 4596.76 | 1100 | 16.67% | 0 | 1100 | 16.67% | 0 |  | 1902.63 | 29.27% | 1902.63 | 29.27% | 100.61 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 886405 - ARAUCO NORTH AMERICAN INC | WATER | WATER REPAIR & INSTALLATION | 2019-09-09 | 2019-12-15 | 2019-09-09 | 2019-12-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 952898¦¦2020-03-31
FP | CJ | Yes | 952899 |  | MS POWER PLANT WATSON 2019 | GREGORY, CRYSTAL N | 100% | 3180 | 0 | 3180 | 5250 | 5250 | 5250 | 0 | 0 | 5250 | 2390 | 0 | 2390 | [7 empty] | 4633.47 | 2712.12 | 636.29 |  | 1285.06 |  |  | 616.53 | 0 | 193.9% |  | 0 | 4633.47 | 790 | 24.84% | 0 | 790 | 24.84% | 0 |  | 616.53 | 11.74% | 616.53 | 11.74% | -2070 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 894805 - MISSISSIPPI POWER CO PLANT WATSON | WATER | WATER REPAIR & INSTALLATION | 2019-09-09 | 2019-10-31 | 2019-09-09 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 952899¦¦2020-03-31
FP | C | Yes | 953089 |  | JOLIET IL SPARE BRONZE BOWL | EISHA, JOSEPH J. | 100% | 61939 | 0 | 61939 | 61939 | 61939 | 61939 | 0 | 0 | 61939 | 32000 | 0 | 32000 | 1045.54 | 844.1 |  |  | 201.44 |  |  | 19044.23 | 10569.92 | 58.5 |  | 8415.81 |  |  | 42894.77 | 0 | 59.51% |  | 0 | 19044.23 | 29939 | 48.34% | 0 | 29939 | 48.34% | 0 |  | 42894.77 | 69.25% | 42894.77 | 69.25% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878985 - JOLIET, CITY OF | WATER | WATER EQUIPMENT SALES | 2019-09-11 | 2019-10-20 | 2019-09-11 | 2019-10-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 953089¦¦2020-03-31
TM | CJ | Yes | 953127 |  | AMERICAN WATER FT LEAVENWORTH | WARTICK, LOGAN M | 100% | 95690 | 282913.16 | 378603.16 | 364768.16 | 364768.16 | 364768.16 | 0 | 0 | 364768.16 | 81935.32 | 231438.29 | 313373.61 | 620.05 | 380.53 | 46.64 |  | 192.88 |  |  | 319349.79 | 72215.25 | 35779.49 |  | 113734.25 | 97620.8 |  | 45418.37 | 0 | 101.9% |  | 0 | 319349.79 | 13754.68 | 14.37% | 51474.87 | 65229.55 | 17.23% | 0 |  | 45418.37 | 12.45% | 45418.37 | 12.45% | 13835 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 879053 - AMERICAN WATER ENTERPRISES | WATER | WATER REPAIR & INSTALLATION | 2019-09-09 | 2019-12-01 | 2019-09-09 | 2019-12-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 953127¦¦2020-03-31
FP | C | Yes | 953137 |  | SOUTHERN COMPANY WELL 3 | ANDERSON, STEPHEN P. | 100% | 37730 | 18085 | 55815 | 55815 | 55815 | 55815 | 0 | 0 | 55815 | 29094 | 13312.5 | 42406.5 | [7 empty] | 36594.56 | 6884.19 | 13129.8 |  | 10354.37 | 6226.2 |  | 19220.44 | 0 | 86.29% |  | 0 | 36594.56 | 8636 | 22.89% | 4772.5 | 13408.5 | 24.02% | 0 |  | 19220.44 | 34.44% | 19220.44 | 34.44% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879060 - SOUTHERN COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-09-10 | 2019-10-18 | 2019-09-10 | 2019-10-18 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 953137¦¦2020-03-31
FP | LJ | Yes | 953138 |  | HANFORD 200 W AREA AST | MCCARTNEY, JEFFREY C | 74.29% | 755390 | 30000 | 785390 | 583490.6409 | 483234 | 483234 | 0 | 24161.7 | 785390 | 520963.52 | 22575 | 543538.52 | 125526.69 | 5388.65 |  | 7200 | 107938.04 | 5000 |  | 465863.99 | 24594 |  | 7200 | 411052.99 | 23017 |  | 17370.01 | 0 | 85.71% |  | 161198.2 | 627062.19 | 234426.48 | 31.03% | 7425 | 241851.48 | 30.79% | 0 |  | 117626.65 | 20.16% | 158327.81 | 20.16% | 201899.36 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 888200 - CH2M HILL PLATEAU REMEDIATION COMPANY | WATER | WATER TREATMENT | 2019-09-01 | 2020-08-01 | 2019-09-01 | 2020-08-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 953138¦¦2020-03-31
FP | C | Yes | 953139 |  | FMI SIERRITA IW19 REHAB | VAN ALLEN, WESLEY C. | 100% | 66284 | 3980 | 70264 | 70714.33 | 70714.33 | 70714.33 | 0 | 0 | 70714.33 | 50939 | 3321.23 | 54260.23 | 319.28 |  | 325.8 |  | -6.52 |  |  | 54465.52 | 9794.45 | 6104.07 |  | 38567 |  |  | 16248.81 | 0 | 100.4% |  | 0 | 54465.52 | 15345 | 23.15% | 658.77 | 16003.77 | 22.78% | 0 |  | 16248.81 | 22.98% | 16248.81 | 22.98% | -450.33 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 879059 - FMI SIERRITA | WATER | WATER REPAIR & INSTALLATION | 2019-09-05 | 2019-10-31 | 2019-09-05 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 953139¦¦2020-03-31
FP | C | Yes | 953156 |  | HENDERSON WELL 8 | ANDERSON, STEPHEN P. | 100% | 5300 | 20864 | 26164 | 26164 | 26164 | 26164 | 0 | 0 | 26164 | 4248 | 15876.2 | 20124.2 | [7 empty] | 11766.63 | 1069.31 | 697.45 |  | 9999.87 |  |  | 14397.37 | 0 | 58.47% |  | 0 | 11766.63 | 1052 | 19.85% | 4987.8 | 6039.8 | 23.08% | 0 |  | 14397.37 | 55.03% | 14397.37 | 55.03% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 892018 - HENDERSON, TN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-10 | 2019-11-29 | 2019-09-11 | 2019-11-29 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 953156¦¦2020-03-31
TM | C | Yes | 953500 |  | WALDEN NY MOTOR WORK | CROOK, CHARLES M | 100% | 6545 | 25765 | 32310 | 31010 | 31010 | 31010 | 0 | 0 | 31010 | 4545 | 17415 | 21960 | 433.57 | 242.29 |  |  | 191.28 |  |  | 19532.6 | 9139.51 | 1943.79 |  | 8449.3 |  |  | 11477.4 | 0 | 88.95% |  | 0 | 19532.6 | 2000 | 30.56% | 8350 | 10350 | 32.03% | 7595 |  | 11477.4 | 37.01% | 11477.4 | 37.01% | 1300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 953470 - WALDEN, THE VILLAGE OF | WATER | WATER SUPPLY | 2019-09-10 | 2019-11-11 | 2019-09-10 | 2019-11-11 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 953500¦¦2020-03-31
TM | C | Yes | 953673 |  | SHEEP CREEK WC WELL 3 | BRASHEAR, DAVID M | 100% | 19601 | 86478.39 | 106079.39 | 106078.52 | 106078.52 | 109192.59 | 0 | 0 | 106078.52 | 14730 | 64774.59 | 79504.59 | 0.43 |  |  |  | 0.43 |  |  | 86007.26 | 22196.36 | 11479.86 |  | 52331.04 |  |  | 20071.26 | 0 | 108.2% |  | 0 | 86007.26 | 4871 | 24.85% | 21703.8 | 26574.8 | 25.05% | 0 |  | 20071.26 | 18.92% | 20071.26 | 18.92% | 0.87 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 897766 - SHEEP CREEK WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-09-03 | 2019-11-30 | 2019-09-03 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 953673¦¦2020-03-31
TM | C | Yes | 953934 |  | LEE COUNTY PINEWOODS | MARTINEZ, MIGUEL E | 100% | 22696 | 0 | 22696 | 22696 | 22696 | 22696 | 0 | 0 | 22696 | 12821 | 0 | 12821 | [7 empty] | 8644.9 | 3246.19 | 2630.88 |  | 2767.83 |  |  | 14051.1 | 0 | 67.43% |  | 0 | 8644.9 | 9875 | 43.51% | 0 | 9875 | 43.51% | 0 |  | 14051.1 | 61.91% | 14051.1 | 61.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 955325 - WSP USA INC | WATER | WATER REPAIR & INSTALLATION | 2019-09-12 | 2019-09-19 | 2019-09-16 | 2019-09-19 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 953934¦¦2020-03-31
TM | CJ | Yes | 953943 |  | NAS PUMP 3 | MIGUEL, SEAN J. | 100% | 5502 | 30166 | 35668 | 35668 | 35668 | 6380 | 0 | 0 | 35668 | 4280 | 22266 | 26546 | 0 |  |  |  | 0 |  |  | 31888.29 | 9308.93 | 1292.93 |  | 20086.43 | 1200 |  | 3779.71 | 0 | 120.1% |  | 0 | 31888.29 | 1222 | 22.21% | 7900 | 9122 | 25.57% | 0 |  | 3779.71 | 10.6% | 3779.71 | 10.6% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895446 - NORTH AMERICAN STAINLESS | WATER | WATER REPAIR & INSTALLATION | 2019-09-12 | 2019-10-31 | 2019-09-12 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 953943¦¦2020-03-31
FP | CJ | Yes | 953945 |  | ALEXANDRIA 920 | GNAU, CASEY T | 100% | 28379 | 0 | 28379 | 26775.3 | 26775.3 | 26775.3 | 0 | 0 | 26775.3 | 19865 | 0 | 19865 | 820.88 |  |  |  |  | 820.88 |  | 13465.13 | 3579.43 | 999.82 |  | 8065 | 820.88 |  | 13310.17 | 0 | 67.78% |  | 0 | 13465.13 | 8514 | 30% | 0 | 8514 | 30% | 0 |  | 13310.17 | 49.71% | 13310.17 | 49.71% | 1603.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 953758 - ALEXANDRIA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-11 | 2019-10-11 | 2019-09-11 | 2019-10-11 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 953945¦¦2020-03-31
TM | C | Yes | 953946 |  | CALLEGUAS WATER BACKWASH | GRACE, GARY L. | 100% | 2941.04 | 0 | 2941.04 | 2491.04 | 2491.04 | 2491.04 | 0 | 0 | 2491.04 | 1735 | 0 | 1735 | [7 empty] | 2186.18 | 1308.8 | 209.06 |  | 668.32 |  |  | 304.86 | 0 | 126% |  | 0 | 2186.18 | 1206.04 | 41.01% | 0 | 1206.04 | 41.01% | 0 |  | 304.86 | 12.24% | 304.86 | 12.24% | 450 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887781 - CALLEGUAS MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-09-05 | 2019-11-01 | 2019-09-05 | 2019-11-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 953946¦¦2020-03-31
FP | C | Yes | 954070 |  | ETHOS ENERGY 26A REHAB | LOPEZ-VASQUEZ, JUAN C. | 100% | 229795 | 0 | 229795 | 141560 | 141560 | 147839.94 | 0 | 0 | 141560 | 170361 | 0 | 170361 | 4612.57 | 2506.6 | 32 |  | 2073.97 |  |  | 69655.18 | 19742.75 | 3388.83 |  | 14496.84 | 32026.76 |  | 71904.82 | 0 | 40.89% |  | 0 | 69655.18 | 59434 | 25.86% | 0 | 59434 | 25.86% | 0 |  | 71904.82 | 50.79% | 71904.82 | 50.79% | 88235 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 968521 - ETHOSENERGY LA STATION | WATER | WATER REPAIR & INSTALLATION | 2019-09-12 | 2019-12-31 | 2019-09-12 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 954070¦¦2020-03-31
FP | C | Yes | 954124 |  | CLECO BALDWIN TEST 3 WELLS | GNAU, CASEY T | 100% | 2550 | 0 | 2550 | 2550 | 2550 | 2550 | 0 | 0 | 2550 | 1275 | 0 | 1275 | [7 empty] | 1187.05 | 680.9 | 185.5 |  | 320.65 |  |  | 1362.95 | 0 | 93.1% |  | 0 | 1187.05 | 1275 | 50% | 0 | 1275 | 50% | 0 |  | 1362.95 | 53.45% | 1362.95 | 53.45% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878973 - CLECO POWER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-09-13 | 2019-10-31 | 2019-09-13 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 954124¦¦2020-03-31
TM | C | Yes | 954340 |  | DOUBLE D FARM MOTOR | EISHA, JOSEPH J. | 100% | 3072 | 0 | 3072 | 3072 | 3072 | 3072 | 0 | 0 | 3072 | 1750 | 0 | 1750 | 0 |  |  |  | 0 |  |  | 2664.57 | 1997.33 | 111.08 |  | 556.16 |  |  | 407.43 | 0 | 152.3% |  | 0 | 2664.57 | 1322 | 43.03% | 0 | 1322 | 43.03% | 0 |  | 407.43 | 13.26% | 407.43 | 13.26% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 954213 - DOUBLE D FARMS | WATER | WATER REPAIR & INSTALLATION | 2019-09-12 | 2019-10-09 | 2019-09-12 | 2019-10-09 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 954340¦¦2020-03-31
FP | C | Yes | 954495 |  | NUTRIEN SWIFT CREEK CHAMICAL | PARSLEY, TRISTAN S | 100% | 171285 | 37359 | 208644 | 208644 | 208644 | 208644 | 0 | 0 | 208644 | 94207 | 18217.13 | 112424.13 | 328.44 |  |  |  | 328.44 |  |  | 147762.67 | 60169.41 | 9655.56 |  | 77051.74 | 885.96 |  | 60881.33 | 0 | 131.4% |  | 0 | 147762.67 | 77078 | 45% | 19141.87 | 96219.87 | 46.12% | 6828.87 |  | 60881.33 | 29.18% | 60881.33 | 29.18% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 896144 - PCS PHOSPHATE WHITE SPRINGS | WATER | WATER REPAIR & INSTALLATION | 2019-09-13 | 2019-11-30 | 2019-09-13 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 954495¦¦2020-03-31
FP | C | Yes | 954496 |  | MISSION SPRINGS TERRACE BOOSTE | BRASHEAR, DAVID M | 100% | 4997 | 35320.64 | 40317.64 | 40317.06 | 40317.06 | 42118.42 | 0 | 0 | 40317.06 | 3798 | 26515.28 | 30313.28 | [7 empty] | 29817.72 | 8890.78 | 1403.91 |  | 19523.03 |  |  | 10499.34 | 0 | 98.37% |  | 0 | 29817.72 | 1199 | 23.99% | 8805.36 | 10004.36 | 24.81% | 0 |  | 10499.34 | 26.04% | 10499.34 | 26.04% | 0.58 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879011 - MISSION SPRINGS WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-09-12 | 2019-10-31 | 2019-09-12 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 954496¦¦2020-03-31
TM | C | Yes | 954673 |  | US WATER SERVICES LEHIGH ACRES | TORMOEHLEN, DAVID A. | 100% | 3500 | 7970 | 11470 | 11470 | 11470 | 11470 | 0 | 0 | 11470 | 2260 | 2409 | 4669 | [7 empty] | 4436.68 | 1020.04 | 177.4 |  | 3239.24 |  |  | 7033.32 | 0 | 95.02% |  | 0 | 4436.68 | 1240 | 35.43% | 5561 | 6801 | 59.29% | 0 |  | 7033.32 | 61.32% | 7033.32 | 61.32% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 899491 - US WATER SERVICES CORP | WATER | WATER REPAIR & INSTALLATION | 2019-09-13 | 2019-09-30 | 2019-09-13 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 954673¦¦2020-03-31
UP | C | Yes | 954674 |  | GEORGETOWN PMS | MIGUEL, SEAN J. | 100% | 1225 | 11294 | 12519 | 12519 | 12519 | 12519 | 0 | 0 | 12519 | 1025 | 8054 | 9079 | [7 empty] | 10451.05 | 3866.4 | 1293.17 |  | 4686.48 | 605 |  | 2067.95 | 0 | 115.1% |  | 0 | 10451.05 | 200 | 16.33% | 3240 | 3440 | 27.48% | 0 |  | 2067.95 | 16.52% | 2067.95 | 16.52% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 891147 - GEORGETOWN MUNICIPAL WATER | WATER | WATER REPAIR & INSTALLATION | 2019-09-13 | 2019-10-31 | 2019-09-13 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 954674¦¦2020-03-31
TM | C | Yes | 954948 |  | AUTAUGA COUNTY WELL 2 | PARSLEY, TRISTAN S | 100% | 20550 | 40525 | 61075 | 61075 | 61075 | 61075 | 0 | 0 | 61075 | 14543 | 28180 | 42723 | [7 empty] | 43510.64 | 13960.92 | 3544.68 |  | 26005.04 |  |  | 17564.36 | 0 | 101.8% |  | 0 | 43510.64 | 6007 | 29.23% | 12345 | 18352 | 30.05% | 0 |  | 17564.36 | 28.76% | 17564.36 | 28.76% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 886672 - AUTAUGA, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-15 | 2019-09-30 | 2019-09-15 | 2019-09-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 954948¦¦2020-03-31
FP | C | Yes | 955142 |  | BURLINGTON NJ WELL 8 AST | RANFT, DONALD R | 100% | 3245 | 0 | 3245 | 3245 | 3245 | 3245 | 0 | 0 | 3245 | 2150 | 0 | 2150 | 0 |  |  |  | 0 |  |  | 575.9 | 565.15 |  |  | 10.75 |  |  | 2669.1 | 0 | 26.79% |  | 0 | 575.9 | 1095 | 33.74% | 0 | 1095 | 33.74% | 0 |  | 2669.1 | 82.25% | 2669.1 | 82.25% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 887637 - BURLINGTON TOWNSHIP | WATER | WATER TREATMENT | 2019-09-12 | 2019-10-31 | 2019-09-12 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 955142¦¦2020-03-31
TM | C | Yes | 955143 |  | NORMAL IL WELLS 19 AND 103 | HEALY, THOMAS P. | 100% | 34000 | 68880 | 102880 | 104204.15 | 104204.15 | 104204.15 | 0 | 0 | 104204.15 | 25500 | 53000 | 78500 | 0 |  |  |  | 0 |  |  | 103856.3 | 63965.18 | 9769.77 |  | 30121.35 |  |  | 347.85 | 0 | 132.3% |  | 0 | 103856.3 | 8500 | 25% | 15880 | 24380 | 23.7% | 0 |  | 347.85 | 0.3338% | 347.85 | 0.3338% | -1324.15 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 895434 - NORMAL, IL, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-11 | 2019-12-31 | 2019-09-11 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 955143¦¦2020-03-31
FP | C | Yes | 955149 |  | OBG EW3D REHAB | BARNES, MATTHEW D | 100% | 16690 | 0 | 16690 | 16690 | 16690 | 16690 | 16690 | 0 | 16690 | 12604 | 0 | 12604 | 0.22 | 0.22 | [5 empty] | 15259.25 | 4221.1 | 5821.54 |  | 5216.61 |  |  | 1430.75 | 0 | 121.1% |  | 0 | 15259.25 | 4086 | 24.48% | 0 | 4086 | 24.48% | 0 |  | 1430.75 | 8.572% | 1430.75 | 8.572% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 895659 - RAMBOLL | WATER | WATER REPAIR & INSTALLATION | 2019-08-09 | 2019-12-31 | 2019-09-09 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 955149¦¦2020-03-31
UP | C | Yes | 955152 |  | ELANCO CBRE REHABS | MIGUEL, SEAN J. | 100% | 36000 | 0 | 36000 | 36000 | 36000 | 36000 | 0 | 0 | 36000 | 25200 | 0 | 25200 | [7 empty] | 37065.37 | 17025.89 | 5145.3 |  | 14894.18 |  |  | 0 | 1065.37 | 147.1% |  | 0 | 37065.37 | 10800 | 30% | 0 | 10800 | 30% | 0 |  | -1065.37 | -2.959% | -1065.37 | -2.959% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888069 - CBRE ELI LILLY CLINTON | WATER | WATER REPAIR & INSTALLATION | 2019-09-11 | 2019-11-30 | 2019-09-11 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 955152¦¦2020-03-31
FP | C | Yes | 955153 |  | MUNFORD TN WELL 4 | ANDERSON, STEPHEN P. | 100% | 110390 | 0 | 110390 | 110955 | 110955 | 110955 | 0 | 0 | 110955 | 80014 | 0 | 80014 | 0 |  |  |  | 0 |  |  | 93539.22 | 31289.09 | 13949.88 |  | 47464.49 | 835.76 |  | 17415.78 | 0 | 116.9% |  | 0 | 93539.22 | 30376 | 27.52% | 0 | 30376 | 27.52% | 0 |  | 17415.78 | 15.7% | 17415.78 | 15.7% | -565 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895103 - MUNFORD, TN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-17 | 2019-10-25 | 2019-09-17 | 2019-10-25 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 955153¦¦2020-03-31
FP | C | Yes | 955452 |  | CVWD WELL 23 | GRACE, GARY L. | 100% | 38775 | 0 | 38775 | 24774 | 24774 | 24774 | 0 | 0 | 24774 | 31780 | 0 | 31780 | [7 empty] | 12766.49 | 5207.07 | 4106.67 |  | 3452.75 |  |  | 12007.51 | 0 | 40.17% |  | 0 | 12766.49 | 6995 | 18.04% | 0 | 6995 | 18.04% | 0 |  | 12007.51 | 48.47% | 12007.51 | 48.47% | 14001 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878809 - CUCAMONGA VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-09-18 | 2019-10-15 | 2019-09-18 | 2019-10-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 955452¦¦2020-03-31
FP | C | Yes | 955462 |  | FOUNTAIN WELL 1 REDRILL | SCHANAMAN, MIKE L. | 100% | 93983 | 0 | 93983 | 93259 | 93259 | 93259 | 0 | 0 | 93259 | 66071 | 0 | 66071 | [7 empty] | 79594.13 | 23166.99 | 12718.32 |  | 39508.82 | 4200 |  | 13664.87 | 0 | 120.5% |  | 0 | 79594.13 | 27912 | 29.7% | 0 | 27912 | 29.7% | 0 |  | 13664.87 | 14.65% | 13664.87 | 14.65% | 724 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 890822 - FOUNTAIN, CO, CITY OF | WATER | WATER SUPPLY | 2019-09-10 | 2019-11-01 | 2019-09-10 | 2019-11-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 955462¦¦2020-03-31
TM | CJ | Yes | 955529 |  | AK FLUME FLUSH DR 612 | SIMPSON, CARL L. | 100% | 153040 | 0 | 153040 | 4226.21 | 4226.21 | 0 | 0 | 0 | 4226.21 | 105000 | 0 | 105000 | 0.88 | 0 |  |  | 0.88 |  |  | 3414.33 | 1871.05 | 598.8 |  | 764.48 | 180 |  | 811.88 | 0 | 3.252% |  | 0 | 3414.33 | 48040 | 31.39% | 0 | 48040 | 31.39% | 0 |  | 811.88 | 19.21% | 811.88 | 19.21% | 148813.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER SUPPLY | 2019-09-01 | 2019-12-31 | 2019-09-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 955529¦¦2020-03-31
TM | C | Yes | 955530 |  | AK DOOR 614 | SIMPSON, CARL L. | 100% | 40152 | 0 | 40152 | 40152 | 40152 | 40152 | 0 | 0 | 40152 | 28000 | 0 | 28000 | 0.01 | 0.01 |  |  | 0 |  |  | 26782.55 | 5513.66 | 6465.1 |  | 14803.79 |  |  | 13369.45 | 0 | 95.65% |  | 0 | 26782.55 | 12152 | 30.26% | 0 | 12152 | 30.26% | 0 |  | 13369.45 | 33.3% | 13369.45 | 33.3% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER SUPPLY | 2019-09-01 | 2019-12-31 | 2019-09-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 955530¦¦2020-03-31
FP | LJ | Yes | 955548 |  | CADIZ 3 NEW IRRIGATION WELLS | TRAMMELL, DUANE R. | 99.95% | 1976045 | 0 | 1976045 | 2291170.3477 | 2292290.73 | 2292290.73 | 0 | 0 | 2292290.73 | 1578869.75 | 0 | 1578869.75 | 83891.19 | 31221.49 | 23508.66 |  | 25998.04 | 3163 |  | 2044989.72 | 378957.26 | 451679.56 |  | 1167541.25 | 46811.65 |  | 247301.01 | 0 | 129.5% |  | 1000 | 2045989.72 | 397175.25 | 20.1% | 0 | 397175.25 | 20.1% | 0 |  | 246180.63 | 10.74% | 246301.01 | 10.74% | -315125.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887709 - CADIZ INC | WATER | WATER SUPPLY | 2019-09-10 | 2020-01-31 | 2019-09-10 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 955548¦¦2020-03-31
TM | C | Yes | 955821 |  | WOOD AE 7 | GRACE, GARY L. | 100% | 16795 | 2790 | 19585 | 18640 | 18640 | 18640 | 0 | 0 | 18640 | 10186 | 2012.45 | 12198.45 | 0 |  |  |  | 0 |  |  | 14090.11 | 4862.98 | 1763.33 |  | 4178.8 | 3285 |  | 4549.89 | 0 | 115.5% |  | 0 | 14090.11 | 6609 | 39.35% | 777.55 | 7386.55 | 37.72% | 777.55 | 777.55 | 4549.89 | 24.41% | 4549.89 | 24.41% | 945 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 955539 - WOOD GROUP | WATER | WATER REPAIR & INSTALLATION | 2019-09-16 | 2019-11-15 | 2019-09-16 | 2019-11-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 955821¦¦2020-03-31
FP | CJ | Yes | 956336 |  | PCA DERIDDER DISCHARGE HEAD | GNAU, CASEY T | 100% | 13800 | 0 | 13800 | 13800 | 13800 | 13800 | 0 | 0 | 13800 | 6900 | 0 | 6900 | [7 empty] | 4619.18 |  |  |  | 4619.18 |  |  | 9180.82 | 0 | 66.94% |  | 0 | 4619.18 | 6900 | 50% | 0 | 6900 | 50% | 0 |  | 9180.82 | 66.53% | 9180.82 | 66.53% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895966 - PACKAGING CORPORATION OF AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-09-20 | 2019-10-31 | 2019-09-20 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 956336¦¦2020-03-31
TM | C | Yes | 956344 |  | OMEGA TEST 2 WELLS | GNAU, CASEY T | 100% | 2000 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 2000 | 1000 | 0 | 1000 | [7 empty] | 1249.87 | 741.49 | 203.5 |  | 304.88 |  |  | 750.13 | 0 | 125% |  | 0 | 1249.87 | 1000 | 50% | 0 | 1000 | 50% | 0 |  | 750.13 | 37.51% | 750.13 | 37.51% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895786 - OMEGA PROTEIN ABBEVILLE | WATER | WATER REPAIR & INSTALLATION | 2019-09-20 | 2019-09-27 | 2019-09-20 | 2019-09-27 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 956344¦¦2020-03-31
FP | C | Yes | 956345 |  | WC LAKE CHARLES TEST 6 WELLS | GNAU, CASEY T | 100% | 4275 | 0 | 4275 | 4275 | 4275 | 4275 | 0 | 0 | 4275 | 2137 | 0 | 2137 | [7 empty] | 1767.69 | 966.55 | 447.7 |  | 353.44 |  |  | 2507.31 | 0 | 82.72% |  | 0 | 1767.69 | 2138 | 50.01% | 0 | 2138 | 50.01% | 0 |  | 2507.31 | 58.65% | 2507.31 | 58.65% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878710 - AXIALL CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-09-20 | 2019-10-31 | 2019-09-20 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 956345¦¦2020-03-31
FP | C | Yes | 956346 |  | ALCOA TEST 2 WELLS | GNAU, CASEY T | 100% | 2000 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 2000 | 1000 | 0 | 1000 | [7 empty] | 2658.16 | 1570.66 | 427.35 |  | 660.15 |  |  | 0 | 658.16 | 265.8% |  | 0 | 2658.16 | 1000 | 50% | 0 | 1000 | 50% | 0 |  | -658.16 | -32.91% | -658.16 | -32.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879002 - ALCOA AGC WARRICK STATION | WATER | WATER REPAIR & INSTALLATION | 2019-09-20 | 2019-10-31 | 2019-09-20 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 956346¦¦2020-03-31
TM | C | Yes | 956349 |  | BLOOMINGTON TP2 | MIGUEL, SEAN J. | 100% | 1742 | 4849 | 6591 | 6591 | 6591 | 6591 | 0 | 0 | 6591 | 1430 | 3507 | 4937 | [7 empty] | 5027.69 | 1399.98 | 617.14 |  | 2020.57 | 990 |  | 1563.31 | 0 | 101.8% |  | 0 | 5027.69 | 312 | 17.91% | 1342 | 1654 | 25.09% | 0 |  | 1563.31 | 23.72% | 1563.31 | 23.72% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888449 - CITY OF BLOOMINGTON UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-09-04 | 2019-11-30 | 2019-09-04 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 956349¦¦2020-03-31
TM | C | Yes | 956367 |  | ROCKFORD IL UW26 | SNELTEN, BRIAN M | 100% | 60621 | 186775 | 247396 | 233581.5 | 233581.5 | 233581.5 | 5788.5 | 0 | 233581.5 | 49679 | 125565.9 | 175244.9 | 16768.73 | 11432.6 | 1924.39 |  | 3411.74 |  |  | 205203.31 | 120882 | 22991.59 |  | 61329.72 |  |  | 28378.19 | 0 | 117.1% |  | 0 | 205203.31 | 10942 | 18.05% | 61209.1 | 72151.1 | 29.16% | 0 |  | 28378.19 | 12.15% | 28378.19 | 12.15% | 13814.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878821 - ROCKFORD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-19 | 2019-12-31 | 2019-09-19 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 956367¦¦2020-03-31
FP | CJ | Yes | 956368 |  | FT SCOTT KS 2019 RIVER INTAKE | WARTICK, LOGAN M | 100% | 112540 | 0 | 112540 | 116910 | 116910 | 116910 | 52200 | 11691 | 116910 | 90652.7 | 0 | 90652.7 | 41030.1 | 9349.67 | 2374.65 |  | 29305.78 |  |  | 81011.81 | 15845.07 | 3827.85 |  | 61338.89 |  |  | 35898.19 | 0 | 89.37% |  | 0 | 81011.81 | 21887.3 | 19.45% | 0 | 21887.3 | 19.45% | 0 |  | 35898.19 | 30.71% | 35898.19 | 30.71% | -4370 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 955540 - CROSSLAND HEAVY CONTRACTORS INC | WATER | WATER REPAIR & INSTALLATION | 2019-09-01 | 2019-10-30 | 2019-09-01 | 2019-10-30 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 956368¦¦2020-03-31
TM | C | Yes | 956737 |  | MT VON HOEVENBERG TESTING | CROOK, CHARLES M | 100% | 31970 | 0 | 31970 | 12085 | 12085 | 12085 | 604.25 | 0 | 12085 | 24970 | 0 | 24970 | 123.5 | 121.74 |  |  | 1.76 |  |  | 4725.61 | 3110.83 | 93.28 |  | 1521.5 |  |  | 7359.39 | 0 | 18.93% |  | 0 | 4725.61 | 7000 | 21.9% | 0 | 7000 | 21.9% | 0 |  | 7359.39 | 60.9% | 7359.39 | 60.9% | 19885 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 956215 - CREIGHTON MANNING | WATER | WATER REPAIR & INSTALLATION | 2019-09-16 | 2019-10-20 | 2019-09-16 | 2019-10-20 | SUBCONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 956737¦¦2020-03-31
FP | C | Yes | 956738 |  | AMERICAN YEAST WARRANTY | ANDERSON, STEPHEN P. | 100% | [5 empty] | 0 | 0 | 0 |  | 38713 | 0 | 38713 | 0 |  |  |  | 0 |  |  | 23587.69 | 10136.56 | 3831.57 |  | 9619.56 |  |  | 0 | 23587.69 | 60.93% |  | 0 | 23587.69 | -38713 |  | 0 | -38713 |  | 0 |  | -23587.69 |  | -23587.69 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 886250 - AMERICAN YEAST | WATER | WATER REPAIR & INSTALLATION | 2019-09-20 | 2019-10-31 | 2019-09-20 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 956738¦¦2020-03-31
FP | C | Yes | 956890 |  | BP WHITING IN J159 REPAIR | EISHA, JOSEPH J. | 100% | 211018 | 204107.41 | 415125.41 | 415125.41 | 415125.41 | 415125.41 | 0 | 0 | 415125.41 | 150000 | 135142.88 | 285142.88 | 0 |  |  |  | 0 |  |  | 296960.73 | 139962.85 | 28496.33 |  | 128501.55 |  |  | 118164.68 | 0 | 104.1% |  | 0 | 296960.73 | 61018 | 28.92% | 68964.53 | 129982.53 | 31.31% | 0 |  | 118164.68 | 28.46% | 118164.68 | 28.46% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 887352 - BP PRODUCTS NORTH AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-09-20 | 2019-10-31 | 2019-09-20 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 956890¦¦2020-03-31
FP | C | Yes | 957993 |  | DESERT VIEW MEMORIAL PARK IRR | BRASHEAR, DAVID M | 100% | [5 empty] | 0 | 0 | 0 |  | 11214 | 0 | 11214 | [7 empty] | 20435.07 | 4423.87 | 2912.78 |  | 13098.42 |  |  | 0 | 20435.07 | 182.2% |  | 0 | 20435.07 | -11214 |  | 0 | -11214 |  | 0 |  | -20435.07 |  | -20435.07 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 889556 - DESERT VIEW MEMORIAL PARK | WATER | WATER REPAIR & INSTALLATION | 2019-09-20 | 2019-10-31 | 2019-09-20 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | EXPENSE JOB | 957993¦¦2020-03-31
FP | C | Yes | 957996 |  | NORTH SLEEPING GIANT WARRANTY | CROOK, CHARLES M | 100% | 0 | 45670 | 45670 | 45670 | 45670 | 45670 | 0 | 0 | 45670 | 10000 | 25000 | 35000 | 0 |  |  |  | 0 |  |  | 30892.05 | 9466.28 | 2850.95 |  | 6470.82 | 12104 |  | 14777.95 | 0 | 88.26% |  | 0 | 30892.05 | -10000 |  | 20670 | 10670 | 23.36% | 0 |  | 14777.95 | 32.36% | 14777.95 | 32.36% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 879082 - SOUTH CENTRAL CT REGIONAL WATER AUTH | WATER | WATER SUPPLY | 2019-09-24 | 2019-10-04 | 2019-09-24 | 2019-10-04 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 957996¦¦2020-03-31
TM | C | Yes | 957997 |  | GEORGIA POWER PLANT MCINTOSH | PARSLEY, TRISTAN S | 100% | 3800 | 0 | 3800 | 3313.09 | 3313.09 | 3313.09 | 0 | 0 | 3313.09 | 2415 | 0 | 2415 | [7 empty] | 1955.34 | 1149.54 | 176.51 |  | 629.29 |  |  | 1357.75 | 0 | 80.97% |  | 0 | 1955.34 | 1385 | 36.45% | 0 | 1385 | 36.45% | 0 |  | 1357.75 | 40.98% | 1357.75 | 40.98% | 486.91 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 891173 - GEORGIA POWER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-09-23 | 2019-09-30 | 2019-09-23 | 2019-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 957997¦¦2020-03-31
FP | CJ | Yes | 958189 |  | OMEGA WELL 5 | GNAU, CASEY T | 100% | 22250 | 14500 | 36750 | 36750 | 36750 | 36750 | 0 | 0 | 36750 | 11110 | 7250 | 18360 | [7 empty] | 16786.7 | 6935 | 2563.81 |  | 7287.89 |  |  | 19963.3 | 0 | 91.43% |  | 0 | 16786.7 | 11140 | 50.07% | 7250 | 18390 | 50.04% | 0 |  | 19963.3 | 54.32% | 19963.3 | 54.32% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895786 - OMEGA PROTEIN ABBEVILLE | WATER | WATER REPAIR & INSTALLATION | 2019-09-24 | 2019-10-31 | 2019-09-24 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 958189¦¦2020-03-31
FP | C | Yes | 958196 |  | CVD EAST WELL | ALBARADO, JORDAN A | 100% | 28300 | 0 | 28300 | 28300 | 28300 | 28300 | 0 | 0 | 28300 | 14125 | 0 | 14125 | [7 empty] | 16927.66 | 2311.47 | 443.2 |  | 14172.99 |  |  | 11372.34 | 0 | 119.8% |  | 0 | 16927.66 | 14175 | 50.09% | 0 | 14175 | 50.09% | 0 |  | 11372.34 | 40.18% | 11372.34 | 40.18% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 889242 - CVD CERAMICS, INC | WATER | WATER REPAIR & INSTALLATION | 2019-09-24 | 2019-10-31 | 2019-09-24 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 958196¦¦2020-03-31
FP | C | Yes | 958197 |  | CVD PANEL | ALBARADO, JORDAN A | 100% | 2800 | 0 | 2800 | 2800 | 2800 | 2800 | 0 | 0 | 2800 | 940 | 0 | 940 | [7 empty] | 1228.02 |  |  |  | 1228.02 |  |  | 1571.98 | 0 | 130.6% |  | 0 | 1228.02 | 1860 | 66.43% | 0 | 1860 | 66.43% | 0 |  | 1571.98 | 56.14% | 1571.98 | 56.14% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 889242 - CVD CERAMICS, INC | WATER | WATER REPAIR & INSTALLATION | 2019-09-24 | 2019-10-31 | 2019-09-24 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 958197¦¦2020-03-31
TM | C | Yes | 958198 |  | SBD COUNTY PRADO LAKE BOOSTER | BRASHEAR, DAVID M | 100% | 2738 | 6225.73 | 8963.73 | 8964.13 | 8964.13 | 9228.58 | 0 | 0 | 8964.13 | 1765 | 4527.9 | 6292.9 | [7 empty] | 5624.41 | 1281.45 | 416.49 |  | 3926.47 |  |  | 3339.72 | 0 | 89.38% |  | 0 | 5624.41 | 973 | 35.54% | 1697.83 | 2670.83 | 29.8% | 0 |  | 3339.72 | 37.26% | 3339.72 | 37.26% | -0.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 965066 - SAN BERNARDINO, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-18 | 2019-10-15 | 2019-09-18 | 2019-10-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 958198¦¦2020-03-31
FP | C | Yes | 958207 |  | GULF POWER CRIST PLANT | PARSLEY, TRISTAN S | 100% | 7100 | 0 | 7100 | 7100 | 7100 | 7100 | 0 | 0 | 7100 | 4245 | 0 | 4245 | [7 empty] | 5158.71 | 2174.31 | 401.22 |  | 2583.18 |  |  | 1941.29 | 0 | 121.5% |  | 0 | 5158.71 | 2855 | 40.21% | 0 | 2855 | 40.21% | 0 |  | 1941.29 | 27.34% | 1941.29 | 27.34% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 891691 - GULF POWER COMPANY | WATER | WATER SUPPLY | 2019-09-20 | 2019-10-01 | 2019-09-23 | 2019-10-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 958207¦¦2020-03-31
FP | C | Yes | 958372 |  | GALESBURG HC 5 INSPECTION | WHITE, CATHLEEN R | 100% | 14650 | 33614 | 48264 | 48264 | 48264 | 48264 | 0 | 0 | 48264 | 11250 | 24863.71 | 36113.71 | 0 |  |  |  | 0 |  |  | 68305.81 | 33076.34 | 4203.25 |  | 31026.22 |  |  | 0 | 20041.81 | 189.1% |  | 0 | 68305.81 | 3400 | 23.21% | 8750.29 | 12150.29 | 25.17% | 861.29 |  | -20041.81 | -41.53% | -20041.81 | -41.53% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 879050 - GALESBURG, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-25 | 2019-11-30 | 2019-09-25 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 958372¦¦2020-03-31
FP | C | Yes | 958373 |  | PARISH WATER HOOPER RD P AND A | LOPEZ-VASQUEZ, JUAN C. | 100% | 91350 | 0 | 91350 | 77550 | 77550 | 77550 | 0 | 0 | 77550 | 64190 | 0 | 64190 | [7 empty] | 35961.32 | 7163.05 | 2776.42 |  | 9965.24 | 16056.61 |  | 41588.68 | 0 | 56.02% |  | 0 | 35961.32 | 27160 | 29.73% | 0 | 27160 | 29.73% | 0 |  | 41588.68 | 53.63% | 41588.68 | 53.63% | 13800 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 879024 - PARISH WATER COMPANY | WATER | WATER SUPPLY | 2019-09-19 | 2019-12-31 | 2019-09-19 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 958373¦¦2020-03-31
FP | C | Yes | 958414 |  | SEALY PULL AND INSPECT WELL 6 | PRICE, AUDREY | 100% | 12000 | 87680 | 99680 | 98510 | 98510 | 98510 | 0 | 0 | 98510 | 8545 | 67980.38 | 76525.38 | [7 empty] | 102234.08 | 25171.72 | 24118.08 |  | 48379.29 | 4564.99 |  | 0 | 3724.08 | 133.6% |  | 0 | 102234.08 | 3455 | 28.79% | 19699.62 | 23154.62 | 23.23% | 0 |  | -3724.08 | -3.78% | -3724.08 | -3.78% | 1170 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 897652 - SEALY, TX, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-25 | 2019-10-12 | 2019-09-25 | 2019-10-12 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 958414¦¦2020-03-31
FP | C | Yes | 958417 |  | PARISH WATER JOOR RD P AND A | LOPEZ-VASQUEZ, JUAN C. | 100% | 152450 | 0 | 152450 | 126150 | 126150 | 126150 | 0 | 0 | 126150 | 107032 | 0 | 107032 | [7 empty] | 54765.43 | 10463.28 | 4793.87 |  | 5190.95 | 34317.33 |  | 71384.57 | 0 | 51.17% |  | 0 | 54765.43 | 45418 | 29.79% | 0 | 45418 | 29.79% | 0 |  | 71384.57 | 56.59% | 71384.57 | 56.59% | 26300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 879024 - PARISH WATER COMPANY | WATER | WATER SUPPLY | 2019-09-19 | 2019-12-31 | 2019-09-19 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 958417¦¦2020-03-31
FP | CJ | Yes | 959019 |  | LAKE ARTHUR WELL 2 MOTOR | GNAU, CASEY T | 100% | 5745 | 0 | 5745 | 3780 | 3780 | 3780 | 0 | 0 | 3780 | 3370 | 0 | 3370 | [7 empty] | 344.88 | 217.71 | 29.32 |  | 97.85 |  |  | 3435.12 | 0 | 10.23% |  | 0 | 344.88 | 2375 | 41.34% | 0 | 2375 | 41.34% | 0 |  | 3435.12 | 90.88% | 3435.12 | 90.88% | 1965 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879047 - LAKE ARTHUR, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-25 | 2019-10-31 | 2019-09-25 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 959019¦¦2020-03-31
FP | C | Yes | 959020 |  | BALI CONSTRUCTION DISNEYLAND | GRACE, GARY L. | 100% | 6390 | 0 | 6390 | 6515 | 6515 | 6622.73 | 0 | 0 | 6515 | 3985 | 0 | 3985 | [7 empty] | 4981.97 | 2421.54 | 268.43 |  | 2292 |  |  | 1533.03 | 0 | 125% |  | 0 | 4981.97 | 2405 | 37.64% | 0 | 2405 | 37.64% | 0 |  | 1533.03 | 23.53% | 1533.03 | 23.53% | -125 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 373048 - BALI CONSTRUCTION INC | WATER | WATER REPAIR & INSTALLATION | 2019-09-12 | 2019-10-31 | 2019-09-24 | 2019-10-31 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 959020¦¦2020-03-31
FP | C | Yes | 959021 |  | AURORA GENERATION 2019 PWM | KENNEDY, CHRISTOPHER C. | 100% | 5450 | 0 | 5450 | 5670 | 5670 | 5670 | 0 | 0 | 5670 | 4360 | 0 | 4360 | [7 empty] | 6618.49 | 4949.22 | 345.95 |  | 1323.32 |  |  | 0 | 948.49 | 151.8% |  | 0 | 6618.49 | 1090 | 20% | 0 | 1090 | 20% | 0 |  | -948.49 | -16.73% | -948.49 | -16.73% | -220 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 886662 - AURORA GENERATION LLC | WATER | WATER REPAIR & INSTALLATION | 2019-09-26 | 2019-10-15 | 2019-09-26 | 2019-10-15 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 959021¦¦2020-03-31
TM | C | Yes | 959022 |  | ALMA PC21 EMERGENCY FISHING | LOPEZ-VASQUEZ, JUAN C. | 100% | 9040 | 86340 | 95380 | 102570 | 102570 | 102570 | 0 | 0 | 102570 | 6482 | 58106 | 64588 | [7 empty] | 67528.28 | 13166.66 | 4664.24 |  | 49697.38 |  |  | 35041.72 | 0 | 104.6% |  | 0 | 67528.28 | 2558 | 28.3% | 28234 | 30792 | 32.28% | 0 |  | 35041.72 | 34.16% | 35041.72 | 34.16% | -7190 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878942 - DO NOT USE ALMA PLANTATION LTD | WATER | WATER REPAIR & INSTALLATION | 2019-09-26 | 2019-10-31 | 2019-09-26 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 959022¦¦2020-03-31
FP | C | Yes | 959024 |  | SCOTTSDALE 126 WARRANTY | VAN ALLEN, WESLEY C. | 100% | 3550 | 0 | 3550 | 0 | 0 | 0 | 0 | 0 | 0 | 2856 | 0 | 2856 | [7 empty] | 5890.94 | 2603.18 | 663.21 |  | 2295.55 | 329 |  | 0 | 5890.94 | 206.3% |  | 0 | 5890.94 | 694 | 19.55% | 0 | 694 | 19.55% | 0 |  | -5890.94 |  | -5890.94 |  | 3550 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878867 - SCOTTSDALE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-25 | 2019-11-08 | 2019-09-25 | 2019-11-08 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 959024¦¦2020-03-31
FP | CJ | Yes | 959387 |  | ADM CLINTON IA WELL 6 | HEALY, THOMAS P. | 100% | 167937 | 200895 | 368832 | 352066.78 | 352066.78 | 352066.78 | 0 | 0 | 352066.78 | 124300 | 96140.63 | 220440.63 | 83474.55 | 209 |  |  | 83265.55 |  |  | 216152.31 | 52039.07 | 15118.7 |  | 139994.54 | 9000 |  | 135914.47 | 0 | 98.05% |  | 0 | 216152.31 | 43637 | 25.98% | 104754.37 | 148391.37 | 40.23% | 88602.91 | 88602.91 | 135914.47 | 38.6% | 135914.47 | 38.6% | 16765.22 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878664 - ADM PROCESSING | WATER | WATER REPAIR & INSTALLATION | 2019-09-23 | 2019-11-30 | 2019-09-23 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 959387¦¦2020-03-31
UP | CJ | Yes | 959389 |  | RAMSEY PWM | MIGUEL, SEAN J. | 100% | 2875 | 35050 | 37925 | 40746 | 40746 | 40746 | 0 | 0 | 40746 | 2560 | 26528 | 29088 | 14858 |  |  |  | 14858 |  |  | 31938.54 | 6080.28 | 1590.16 |  | 24169.1 | 99 |  | 8807.46 | 0 | 109.8% |  | 0 | 31938.54 | 315 | 10.96% | 8522 | 8837 | 23.3% | 0 |  | 8807.46 | 21.62% | 8807.46 | 21.62% | -2821 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 896750 - RAMSEY WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-09-26 | 2019-10-31 | 2019-09-26 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 959389¦¦2020-03-31
UP | C | Yes | 959390 |  | ALCOA ACID TREATMENTS | MIGUEL, SEAN J. | 100% | 22996 | 125893 | 148889 | 150239 | 150239 | 150239 | 60984 | 0 | 150239 | 20006 | 98408 | 118414 | 35.08 | 0.08 |  |  | 35 |  |  | 128991.46 | 40270.48 | 18590.24 |  | 65705.74 | 4425 |  | 21247.54 | 0 | 108.9% |  | 0 | 128991.46 | 2990 | 13% | 27485 | 30475 | 20.47% | 2835 |  | 21247.54 | 14.14% | 21247.54 | 14.14% | -1350 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879002 - ALCOA AGC WARRICK STATION | WATER | WATER REPAIR & INSTALLATION | 2019-09-27 | 2019-12-31 | 2019-09-27 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 959390¦¦2020-03-31
FP | C | Yes | 959391 |  | SARASOTA CENTRAL COUNTY MIT | MARTINEZ, MIGUEL E | 100% | 35950 | 0 | 35950 | 35950 | 35950 | 35950 | 0 | 0 | 35950 | 25295 | 0 | 25295 | [7 empty] | 17955.07 | 6658.8 | 4535.45 |  | 6282.36 | 478.46 |  | 17994.93 | 0 | 70.98% |  | 0 | 17955.07 | 10655 | 29.64% | 0 | 10655 | 29.64% | 0 |  | 17994.93 | 50.06% | 17994.93 | 50.06% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 955325 - WSP USA INC | WATER | WATER REPAIR & INSTALLATION | 2019-09-12 | 2019-10-11 | 2019-09-12 | 2019-10-11 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 959391¦¦2020-03-31
FP | C | Yes | 959393 |  | LORENA PULL AND INSPECT WELL 2 | PRICE, AUDREY | 100% | 16610 | 8538 | 25148 | 8538 | 8538 | 8538 | 0 | 0 | 8538 | 13288 | 6196.98 | 19484.98 | [7 empty] | 30897.57 | 7646.95 | 10002.85 |  | 11738.53 | 1509.24 |  | 0 | 22359.57 | 158.6% |  | 0 | 30897.57 | 3322 | 20% | 2341.02 | 5663.02 | 22.52% | 0 |  | -22359.57 | -261.9% | -22359.57 | -261.9% | 16610 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 879064 - LORENA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-30 | 2019-10-31 | 2019-09-30 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 959393¦¦2020-03-31
FP | LJ | Yes | 959395 |  | SCWA CARLETON AVE NO 2 | RANFT, DONALD R | 93.61% | 537734 | 0 | 537734 | 482476.2066 | 489929.75 | 489929.75 | 0 | 24496.49 | 515421 | 416328.19 | 0 | 416328.19 | 41542.72 | 13975.04 | 18.43 |  | 2186.95 | 25362.3 |  | 366539.67 | 134707.95 | 71384.47 |  | 129657.52 | 30789.73 |  | 123390.08 | 0 | 88.04% |  | 25028.33 | 391568 | 121405.81 | 22.58% | 0 | 121405.81 | 22.58% | 0 |  | 115936.54 | 24.03% | 123853 | 24.03% | 55257.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878736 - SUFFOLK, COUNTY OF | WATER | WATER SUPPLY | 2019-09-27 | 2020-04-01 | 2019-09-27 | 2020-04-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 959395¦¦2020-03-31
TM | C | Yes | 959647 |  | SOUTH ISLAND PSD LIGHTHOUSE | PARSLEY, TRISTAN S | 100% | 19000 | 26780 | 45780 | 46349.7 | 46349.7 | 46349.7 | 0 | 0 | 46349.7 | 13256 | 21060.16 | 34316.16 | 1171.08 |  |  |  | 1171.08 |  |  | 43543.64 | 17085.12 | 4517.91 |  | 21940.61 |  |  | 2806.06 | 0 | 126.9% |  | 0 | 43543.64 | 5744 | 30.23% | 5719.84 | 11463.84 | 25.04% | 5896.84 |  | 2806.06 | 6.054% | 2806.06 | 6.054% | -569.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 892139 - HILTON HEAD ISLAND PSD 1 | WATER | WATER REPAIR & INSTALLATION | 2019-09-25 | 2019-11-30 | 2019-09-25 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 959647¦¦2020-03-31
TM | C | Yes | 959648 |  | SOUTH ISLAND PSD BRIARWOOD | PARSLEY, TRISTAN S | 100% | 31500 | 37300 | 68800 | 68800 | 68800 | 68800 | 0 | 0 | 68800 | 21629 | 24153 | 45782 | [7 empty] | 46474.12 | 19450.8 | 8058.57 |  | 18964.75 |  |  | 22325.88 | 0 | 101.5% |  | 0 | 46474.12 | 9871 | 31.34% | 13147 | 23018 | 33.46% | 0 |  | 22325.88 | 32.45% | 22325.88 | 32.45% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 892139 - HILTON HEAD ISLAND PSD 1 | WATER | WATER REPAIR & INSTALLATION | 2019-09-25 | 2019-11-30 | 2019-09-25 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 959648¦¦2020-03-31
TM | C | Yes | 959649 |  | GOYA FOOD PULL AND INSPECT | PRICE, AUDREY | 100% | 9000 | 7800 | 16800 | 16800 | 16800 | 16800 | 0 | 0 | 16800 | 6231 | 5472 | 11703 | [7 empty] | 12783.13 | 3792.07 | 3413.31 |  | 5577.75 |  |  | 4016.87 | 0 | 109.2% |  | 0 | 12783.13 | 2769 | 30.77% | 2328 | 5097 | 30.34% | 0 |  | 4016.87 | 23.91% | 4016.87 | 23.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 959560 - GOYA FOODS OF TEXAS | WATER | WATER REPAIR & INSTALLATION | 2019-09-26 | 2019-10-30 | 2019-09-26 | 2019-10-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 959649¦¦2020-03-31
FP | C | Yes | 959650 |  | OMEGA WELL 3 | GNAU, CASEY T | 100% | 14500 | 1000 | 15500 | 15500 | 15500 | 15500 | 0 | 0 | 15500 | 7250 | 1000 | 8250 | [7 empty] | 9387.9 | 2520.71 | 896.03 |  | 5971.16 |  |  | 6112.1 | 0 | 113.8% |  | 0 | 9387.9 | 7250 | 50% | 0 | 7250 | 46.77% | 0 |  | 6112.1 | 39.43% | 6112.1 | 39.43% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895786 - OMEGA PROTEIN ABBEVILLE | WATER | WATER REPAIR & INSTALLATION | 2019-09-30 | 2019-10-31 | 2019-09-30 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 959650¦¦2020-03-31
FP | CJ | Yes | 959651 |  | WESTROCK 23 | GNAU, CASEY T | 100% | 28500 | 0 | 28500 | 30000 | 30000 | 30000 | 0 | 0 | 30000 | 14250 | 0 | 14250 | [7 empty] | 12002.27 | 3622.83 | 371 |  | 2015.68 | 5992.76 |  | 17997.73 | 0 | 84.23% |  | 0 | 12002.27 | 14250 | 50% | 0 | 14250 | 50% | 0 |  | 17997.73 | 59.99% | 17997.73 | 59.99% | -1500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2019-09-30 | 2019-10-31 | 2019-09-30 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 959651¦¦2020-03-31
FP | C | Yes | 959733 |  | TEXAS BRINE CHACAHOULA R AND I | GREGORY, CRYSTAL N | 100% | 15515 | 41758 | 57273 | 57273 | 57273 | 57273 | 0 | 0 | 57273 | 11204 | 29399 | 40603 | 71.1 |  |  |  | 71.1 |  |  | 36678.54 | 8688.47 | 2793.61 |  | 23960.65 | 1235.81 |  | 20594.46 | 0 | 90.33% |  | 0 | 36678.54 | 4311 | 27.79% | 12359 | 16670 | 29.11% | 1166 |  | 20594.46 | 35.96% | 20594.46 | 35.96% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 898677 - TBC GRAND BAYOU LLC | WATER | WATER REPAIR & INSTALLATION | 2019-09-30 | 2019-12-14 | 2019-09-30 | 2019-12-14 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 959733¦¦2020-03-31
FP | C | Yes | 960090 |  | CAT PROVING GROUNDS PUMP | VAN ALLEN, WESLEY C. | 100% | 20783 | 0 | 20783 | 20783.03 | 20783.03 | 20783.03 | 0 | 0 | 20783.03 | 15210 | 0 | 15210 | [7 empty] | 15792.93 | 4309.77 | 1912.65 |  | 9570.51 |  |  | 4990.1 | 0 | 103.8% |  | 0 | 15792.93 | 5573 | 26.82% | 0 | 5573 | 26.82% | 0 |  | 4990.1 | 24.01% | 4990.1 | 24.01% | -0.03 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 299159 - CATERPILLAR INC | WATER | WATER REPAIR & INSTALLATION | 2019-09-17 | 2019-11-04 | 2019-09-17 | 2019-11-04 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 960090¦¦2020-03-31
FP | C | Yes | 960091 |  | MONTE VISTA WELL 27 | GRACE, GARY L. | 100% | 151792 | 0 | 151792 | 156158.6 | 156158.6 | 163547.56 | 0 | 0 | 156158.6 | 116354 | 0 | 116354 | 23.39 |  |  |  | 23.39 |  |  | 137274.64 | 29141.53 | 9570.46 |  | 96452.18 | 2110.47 |  | 18883.96 | 0 | 118% |  | 0 | 137274.64 | 35438 | 23.35% | 0 | 35438 | 23.35% | 0 |  | 18883.96 | 12.09% | 18883.96 | 12.09% | -4366.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 894920 - MONTE VISTA WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-09-26 | 2019-11-25 | 2019-09-26 | 2019-11-25 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 960091¦¦2020-03-31
TM | C | Yes | 960093 |  | CITY OF CHANDLER CRANE WORK | VAN ALLEN, WESLEY C. | 100% | 2200 | 2932.5 | 5132.5 | 5132.5 | 5132.5 | 5132.5 | 0 | 0 | 5132.5 | 1274 | 2971.05 | 4245.05 | 0 |  |  |  | 0 |  |  | 3835.49 | 1629.69 | 571.74 |  | 1634.06 |  |  | 1297.01 | 0 | 90.35% |  | 0 | 3835.49 | 926 | 42.09% | -38.55 | 887.45 | 17.29% | 0 |  | 1297.01 | 25.27% | 1297.01 | 25.27% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-09-26 | 2019-10-09 | 2019-09-26 | 2019-10-09 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 960093¦¦2020-03-31
FP | CJ | Yes | 960256 |  | WC LAKE CHARLES PORTER HALL | GNAU, CASEY T | 100% | 15340 | 0 | 15340 | 19940 | 19940 | 19940 | 0 | 0 | 19940 | 7653 | 0 | 7653 | 40.99 |  |  |  | 40.99 |  |  | 10489.8 | 4510.14 | 1040.07 |  | 4939.59 |  |  | 9450.2 | 0 | 137.1% |  | 0 | 10489.8 | 7687 | 50.11% | 0 | 7687 | 50.11% | 0 |  | 9450.2 | 47.39% | 9450.2 | 47.39% | -4600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878710 - AXIALL CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-10-01 | 2019-10-31 | 2019-10-01 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 960256¦¦2020-03-31
FP | C | Yes | 960260 |  | CORNING SULLIVAN PARK PUMP | CROOK, CHARLES M | 100% | 3780 | 16930 | 20710 | 17030 | 17030 | 17030 | 0 | 0 | 17030 | 2780 | 10550 | 13330 | 5874.54 | 2371.16 | 550.38 |  | 2953 |  |  | 8229.62 | 3576.08 | 960.66 |  | 3692.88 |  |  | 8800.38 | 0 | 61.74% |  | 0 | 8229.62 | 1000 | 26.46% | 6380 | 7380 | 35.63% | 6380 | 6380 | 8800.38 | 51.68% | 8800.38 | 51.68% | 3680 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 889001 - CSS CORNING INCORPORATED | WATER | WATER REPAIR & INSTALLATION | 2019-10-01 | 2019-11-01 | 2019-10-01 | 2019-11-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 960260¦¦2020-03-31
FP | C | Yes | 960261 |  | WESTLAKE NEW PUMP | ANDERSON, STEPHEN P. | 100% | 149150 | 0 | 149150 | 149150 | 149150 | 149150 | 0 | 0 | 149150 | 96947 | 0 | 96947 | 48709.96 |  |  |  | 48709.96 |  |  | 85729.84 | 551.84 | 130.2 |  | 85047.8 |  |  | 63420.16 | 0 | 88.43% |  | 0 | 85729.84 | 52203 | 35% | 0 | 52203 | 35% | 0 |  | 63420.16 | 42.52% | 63420.16 | 42.52% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879090 - AXIALL CORPORATION | WATER | WATER EQUIPMENT SALES | 2019-10-01 | 2019-12-30 | 2019-10-01 | 2019-12-30 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 960261¦¦2020-03-31
FP | C | Yes | 960508 |  | HOA FT LEAVENWORTH PUMP | WARTICK, LOGAN M | 100% | 32806.04 | 0 | 32806.04 | 30447 | 30447 | 32806.07 | 0 | 0 | 30447 | 26244 | 0 | 26244 | [7 empty] | 16727.04 | 2170.29 | 110.52 |  | 14446.23 |  |  | 13719.96 | 0 | 63.74% |  | 0 | 16727.04 | 6562.04 | 20% | 0 | 6562.04 | 20% | 0 |  | 13719.96 | 45.06% | 13719.96 | 45.06% | 2359.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 960148 - HYDRO OPTIMIZATION AND AUTOMATION | WATER | WATER REPAIR & INSTALLATION | 2019-09-30 | 2019-11-30 | 2019-09-30 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 960508¦¦2020-03-31
TM | C | Yes | 960513 |  | TOPA TOPA WEST WARRANTY | GRACE, GARY L. | 100% | [5 empty] | 0 | 0 | 0 |  | 22877 | 0 | 22877 | [7 empty] | 18345.25 | 8904.67 | 270.54 |  | 9170.04 |  |  | 0 | 18345.25 | 80.19% |  | 0 | 18345.25 | -22877 |  | 0 | -22877 |  | 0 |  | -18345.25 |  | -18345.25 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878563 - TOPA TOPA RANCH & NURSERY LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-02 | 2019-10-03 | 2019-10-02 | 2019-10-03 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 960513¦¦2020-03-31
FP | C | Yes | 960646 |  | ENTERGY GRAND GULF WELL INSPEC | ANDERSON, STEPHEN P. | 100% | 990 | 0 | 990 | 3100 | 3100 | 3100 | 0 | 0 | 3100 | 900 | 0 | 900 | 0 |  |  |  | 0 |  |  | 1579.96 | 883.46 | 208.08 |  | 488.42 |  |  | 1520.04 | 0 | 175.6% |  | 0 | 1579.96 | 90 | 9.091% | 0 | 90 | 9.091% | 0 |  | 1520.04 | 49.03% | 1520.04 | 49.03% | -2110 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 890293 - ENTERGY OPERATIONS GRAND GULF | WATER | WATER REPAIR & INSTALLATION | 2019-10-02 | 2019-10-26 | 2019-10-02 | 2019-10-26 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 960646¦¦2020-03-31
TM | CJ | Yes | 961191 |  | MADISON WELL 2 VALVE | MIGUEL, SEAN J. | 100% | 2283 | 11940 | 14223 | 14571 | 14571 | 14571 | 0 | 0 | 14571 | 1800 | 9353 | 11153 | 0.8 |  |  |  | 0.8 |  |  | 12014.18 | 2858.77 | 710.31 |  | 8445.1 |  |  | 2556.82 | 0 | 107.7% |  | 0 | 12014.18 | 483 | 21.16% | 2587 | 3070 | 21.58% | 0 |  | 2556.82 | 17.55% | 2556.82 | 17.55% | -348 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 894073 - MADISON, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-02 | 2019-11-30 | 2019-10-02 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 961191¦¦2020-03-31
TM | C | Yes | 961194 |  | WC POLY SAND TEST | GNAU, CASEY T | 100% | 800 | 0 | 800 | 840 | 840 | 840 | 0 | 0 | 840 | 400 | 0 | 400 | [7 empty] | 370.63 | 274.4 |  |  | 96.23 |  |  | 469.37 | 0 | 92.66% |  | 0 | 370.63 | 400 | 50% | 0 | 400 | 50% | 0 |  | 469.37 | 55.88% | 469.37 | 55.88% | -40 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 900147 - WESTLAKE POLYMERS LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-03 | 2019-10-31 | 2019-10-03 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 961194¦¦2020-03-31
TM | C | Yes | 961195 |  | GRAND GULF NEW SERVICE WATER | STOWE, SAMUEL M. | 100% | 125000 | 0 | 125000 | 163380.5 | 163380.5 | 163380.5 | 0 | 0 | 163380.5 | 90460 | 0 | 90460 | 7227.23 | 7141.87 |  |  | 85.36 |  |  | 140743.64 | 40162.4 | 102.03 |  | 14547.21 | 85932 |  | 22636.86 | 0 | 155.6% |  | 0 | 140743.64 | 34540 | 27.63% | 0 | 34540 | 27.63% | 0 |  | 22636.86 | 13.86% | 22636.86 | 13.86% | -38380.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 890293 - ENTERGY OPERATIONS GRAND GULF | WATER | WATER SUPPLY | 2019-10-01 | 2019-12-31 | 2019-10-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 961195¦¦2020-03-31
TM | C | Yes | 961196 |  | PORT ANGELES 2019 MONITORING | STOWE, SAMUEL M. | 100% | 8500 | 0 | 8500 | 8500 | 8500 | 8500 | 0 | 0 | 8500 | 6000 | 0 | 6000 | 0.06 | 0.06 | [5 empty] | 2681.68 | 2628.09 |  |  | 53.59 |  |  | 5818.32 | 0 | 44.69% |  | 0 | 2681.68 | 2500 | 29.41% | 0 | 2500 | 29.41% | 0 |  | 5818.32 | 68.45% | 5818.32 | 68.45% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 896476 - PORT ANGELES, WA, CITY OF | WATER | WATER SUPPLY | 2019-10-03 | 2020-03-01 | 2019-10-03 | 2020-03-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 961196¦¦2020-03-31
TM | C | Yes | 961197 |  | BRW ROBIN 3 WELL R AND I | LOPEZ-VASQUEZ, JUAN C. | 100% | 3450 | 30368.5 | 33818.5 | 37418.5 | 37418.5 | 37418.5 | 0 | 0 | 37418.5 | 3218 | 21789 | 25007 | [7 empty] | 32140.53 | 7162.17 | 2093.7 |  | 22484.66 | 400 |  | 5277.97 | 0 | 128.5% |  | 0 | 32140.53 | 232 | 6.725% | 8579.5 | 8811.5 | 26.06% | 0 |  | 5277.97 | 14.11% | 5277.97 | 14.11% | -3600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-10-02 | 2019-12-31 | 2019-10-02 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 961197¦¦2020-03-31
TM | CJ | Yes | 961199 |  | PINEVILLE TEST 9 WELLS | GNAU, CASEY T | 100% | 7200 | 0 | 7200 | 6000 | 6000 | 6000 | 0 | 0 | 6000 | 4320 | 0 | 4320 | [7 empty] | 2559.54 | 1455.98 | 610.5 |  | 493.06 |  |  | 3440.46 | 0 | 59.25% |  | 0 | 2559.54 | 2880 | 40% | 0 | 2880 | 40% | 0 |  | 3440.46 | 57.34% | 3440.46 | 57.34% | 1200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 960905 - PAN AMERICAN ENGINEERS LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-01 | 2019-10-31 | 2019-10-01 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 961199¦¦2020-03-31
FP | C | Yes | 961200 |  | GENEVA NY PRODUCTION WELL | CROOK, CHARLES M | 100% | 99540 | 0 | 99540 | 88402.5 | 88402.5 | 88402.5 | 42762.5 | 0 | 88402.5 | 79540 | 0 | 79540 | [7 empty] | 87783.72 | 34838.52 | 27518.35 |  | 25335.05 | 91.8 |  | 618.78 | 0 | 110.4% |  | 0 | 87783.72 | 20000 | 20.09% | 0 | 20000 | 20.09% | 0 |  | 618.78 | 0.7% | 618.78 | 0.7% | 11137.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 960580 - BEM SYSTEMS INC | WATER | WATER SUPPLY | 2019-10-03 | 2019-12-06 | 2019-10-03 | 2019-12-06 | SUBCONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 961200¦¦2020-03-31
FP | C | Yes | 962817 |  | ARCADIS DN 13 | BARNES, MATTHEW D | 100% | 22950 | 17040 | 39990 | 39990 | 39990 | 39990 | 0 | 0 | 39990 | 16065 | 12325 | 28390 | 563.54 | 1.94 |  |  | 561.6 |  |  | 27332.99 | 7642.34 | 5541.42 |  | 12824.23 | 1325 |  | 12657.01 | 0 | 96.28% |  | 0 | 27332.99 | 6885 | 30% | 4715 | 11600 | 29.01% | 0 |  | 12657.01 | 31.65% | 12657.01 | 31.65% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 886413 - ARCADIS | WATER | WATER SUPPLY | 2019-10-04 | 2019-12-31 | 2019-10-04 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 962817¦¦2020-03-31
FP | C | Yes | 962818 |  | MOSAIC NEW WALES PB4 VIBRATION | TORMOEHLEN, DAVID A. | 100% | 18120 | 0 | 18120 | 47936.7 | 47936.7 | 47936.7 | 0 | 0 | 47936.7 | 12782 | 0 | 12782 | [7 empty] | 39059.04 | 20739.34 | 7120.6 |  | 11199.1 |  |  | 8877.66 | 0 | 305.6% |  | 0 | 39059.04 | 5338 | 29.46% | 0 | 5338 | 29.46% | 0 |  | 8877.66 | 18.52% | 8877.66 | 18.52% | -29816.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895011 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-04 | 2019-10-31 | 2019-10-04 | 2019-10-31 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 962818¦¦2020-03-31
FP | C | Yes | 962819 |  | DENVER WATER GARLAND PARK | SCHANAMAN, MIKE L. | 100% | 9495 | 0 | 9495 | 9495 | 9495 | 9495 | 0 | 0 | 9495 | 5584 | 0 | 5584 | [7 empty] | 2684.31 | 1214.11 | 406.31 |  | 1063.89 |  |  | 6810.69 | 0 | 48.07% |  | 0 | 2684.31 | 3911 | 41.19% | 0 | 3911 | 41.19% | 0 |  | 6810.69 | 71.73% | 6810.69 | 71.73% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 889513 - DENVER WATER | WATER | WATER REPAIR & INSTALLATION | 2019-10-01 | 2019-10-31 | 2019-10-01 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 962819¦¦2020-03-31
FP | C | Yes | 962907 |  | MEADE KS WELL 6 WARRANTY | WARTICK, LOGAN M | 100% | 0 | 44464 | 44464 | 44464 | 44464 | 44464 | 0 | 0 | 44464 | 10000 | 32505.33 | 42505.33 | 13954.11 | 6852.64 | 1783.39 |  | 5318.08 |  |  | 74586.68 | 21760.39 | 4248.82 |  | 41912.91 | 6664.56 |  | 0 | 30122.68 | 175.5% |  | 0 | 74586.68 | -10000 |  | 11958.67 | 1958.67 | 4.405% | 0 |  | -30122.68 | -67.75% | -30122.68 | -67.75% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 894454 - MEADE, KS CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-07 | 2019-12-31 | 2019-10-07 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 962907¦¦2020-03-31
FP | C | Yes | 962908 |  | LYONS KS 2019 WELL WORK | WARTICK, LOGAN M | 100% | 8357 | 0 | 8357 | 22951 | 22951 | 22951 | 0 | 0 | 22951 | 6519 | 0 | 6519 | [7 empty] | 17254.77 | 5372.77 | 1434.38 |  | 10447.62 |  |  | 5696.23 | 0 | 264.7% |  | 0 | 17254.77 | 1838 | 21.99% | 0 | 1838 | 21.99% | 0 |  | 5696.23 | 24.82% | 5696.23 | 24.82% | -14594 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 894033 - LYONS, KS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-07 | 2019-12-31 | 2019-10-07 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 962908¦¦2020-03-31
UP | C | Yes | 963242 |  | LUBECK REHAB A AND E | BARNES, MATTHEW D | 100% | 31200 | 20945 | 52145 | 52145 | 52145 | 52145 | 0 | 0 | 52145 | 21840 | 17316 | 39156 | 490.62 | 4.36 |  |  | 486.26 |  |  | 58670.93 | 25068.89 | 12002.06 |  | 21599.98 |  |  | 0 | 6525.93 | 149.8% |  | 0 | 58670.93 | 9360 | 30% | 3629 | 12989 | 24.91% | 0 |  | -6525.93 | -12.51% | -6525.93 | -12.51% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 893983 - LUBECK PUBLIC SERVICES | WATER | WATER REPAIR & INSTALLATION | 2019-10-07 | 2019-12-31 | 2019-10-07 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 963242¦¦2020-03-31
FP | C | Yes | 963249 |  | CITY OF GONZALES CABELAS TOWER | GREGORY, CRYSTAL N | 100% | 860 | 0 | 860 | 860 | 860 | 860 | 0 | 0 | 860 | 533 | 0 | 533 | [7 empty] | 215.78 | 79.72 | 37.1 |  | 98.96 |  |  | 644.22 | 0 | 40.48% |  | 0 | 215.78 | 327 | 38.02% | 0 | 327 | 38.02% | 0 |  | 644.22 | 74.91% | 644.22 | 74.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 891405 - GONZALES, LA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-07 | 2019-10-31 | 2019-10-07 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 963249¦¦2020-03-31
FP | C | Yes | 963250 |  | ALTMED FLORIDA | BRUGGER, CRAIG J. | 100% | 22363 | 0 | 22363 | 25863 | 25863 | 25863 | 0 | 0 | 25863 | 12376 | 0 | 12376 | [7 empty] | 12673.98 | 3005.96 | 848.08 |  | 8819.94 |  |  | 13189.02 | 0 | 102.4% |  | 0 | 12673.98 | 9987 | 44.66% | 0 | 9987 | 44.66% | 0 |  | 13189.02 | 51% | 13189.02 | 51% | -3500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 962964 - ALTMED FLORIDA | WATER | WATER REPAIR & INSTALLATION | 2019-10-01 | 2019-11-30 | 2019-10-01 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 963250¦¦2020-03-31
TM | C | Yes | 963251 |  | EMBREEVILLE PA ROCK WELL BAIL | CROOK, CHARLES M | 100% | 51530 | 0 | 51530 | 49355 | 49355 | 49355 | 0 | 0 | 49355 | 39530 | 0 | 39530 | [7 empty] | 28991.49 | 12423.28 | 8618.96 |  | 7949.25 |  |  | 20363.51 | 0 | 73.34% |  | 0 | 28991.49 | 12000 | 23.29% | 0 | 12000 | 23.29% | 0 |  | 20363.51 | 41.26% | 20363.51 | 41.26% | 2175 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 878918 - AQUA AMERICA PENNSYLVANIA | WATER | WATER REPAIR & INSTALLATION | 2019-10-07 | 2019-11-22 | 2019-10-07 | 2019-11-22 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 963251¦¦2020-03-31
TM | C | Yes | 963534 |  | OSCEOLA AR CITY OF PUMPING | BURGE, EVERETT E. | 100% | 7808 | 0 | 7808 | 4733.94 | 4733.94 | 5207.33 | 0 | 0 | 4733.94 | 5708 | 0 | 5708 | 262.2 |  |  |  | 262.2 |  |  | 3495.32 | 1563.53 |  |  | 1931.79 |  |  | 1238.62 | 0 | 61.24% |  | 0 | 3495.32 | 2100 | 26.9% | 0 | 2100 | 26.9% | 0 |  | 1238.62 | 26.16% | 1238.62 | 26.16% | 3074.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 895875 - OSCEOLA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-08 | 2019-12-20 | 2019-10-08 | 2019-12-20 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 963534¦¦2020-03-31
FP | LJ | Yes | 963581 |  | TUCSON WATER F001B WELL REPLAC | COMBS, TAYLOR E. | 99.14% | 589420 | 0 | 589420 | 599060.1566 | 604230 | 604230 | 0 | 0 | 604230 | 500981.58 | 0 | 500981.58 | 11838.37 |  | 1459.09 | 39790 | 4264.33 | -31682.06 | -1992.99 | 877161.87 | 235131.79 | 203756.72 | 39790 | 299296.14 | 95673.08 | 3514.14 | 0 | 272931.87 | 175.1% |  | 7569.84 | 884731.71 | 88438.42 | 15% | 0 | 88438.42 | 15% | 0 |  | -280501.71 | -47.01% | -280501.71 | -46.42% | -7240.16 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 899186 - TUCSON, CITY OF | WATER | WATER SUPPLY | 2019-10-07 | 2019-12-13 | 2019-10-07 | 2019-12-13 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 963581¦¦2020-03-31
FP | C | Yes | 963658 |  | NALCO BOOSTERS 1 AND 3 | BALLUFF, WILLIAM O. | 100% | 50000 | 0 | 50000 | 40252.8 | 40252.8 | 41217.16 | 0 | 0 | 40252.8 | 37500 | 0 | 37500 | [7 empty] | 27100.78 | 14885.78 | 1109.27 |  | 11105.73 |  |  | 13152.02 | 0 | 72.27% |  | 0 | 27100.78 | 12500 | 25% | 0 | 12500 | 25% | 0 |  | 13152.02 | 32.67% | 13152.02 | 32.67% | 9747.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 895146 - NALCO COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-10-08 | 2019-12-31 | 2019-10-08 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | FACILITIES MANAGEMENT | 963658¦¦2020-03-31
TM | CJ | Yes | 963659 |  | ROTH PLANTING CO | SCHERM, LOGAN M | 100% | 10000 | 0 | 10000 | 3061.7 | 3061.7 | 0 | 0 | 0 | 3061.7 | 6972 | 0 | 6972 | [7 empty] | 2473.53 | 1377.1 | 133.74 |  | 962.69 |  |  | 588.17 | 0 | 35.48% |  | 0 | 2473.53 | 3028 | 30.28% | 0 | 3028 | 30.28% | 0 |  | 588.17 | 19.21% | 588.17 | 19.21% | 6938.3 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879067 - ROTH PLANTING COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-10-08 | 2020-10-08 | 2019-10-08 | 2020-10-08 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 963659¦¦2020-03-31
FP | C | Yes | 963660 |  | GREEN PLAINS HSP 2 | ANDERSON, STEPHEN P. | 100% | 10499 | 0 | 10499 | 10499 | 10499 | 10499 | 0 | 0 | 10499 | 7349 | 0 | 7349 | 7336.84 | 3380.49 | 1436.11 |  | 2520.24 |  |  | 10472.35 | 3380.49 | 2201.07 |  | 4890.79 |  |  | 26.65 | 0 | 142.5% |  | 0 | 10472.35 | 3150 | 30% | 0 | 3150 | 30% | 0 |  | 26.65 | 0.2538% | 26.65 | 0.2538% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879091 - GREEN PLAINS OBION LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-08 | 2019-11-08 | 2019-10-08 | 2019-11-08 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 963660¦¦2020-03-31
TM | C | Yes | 963661 |  | DOW WELL 6 ABANDONMENT | KENNEDY, CHRISTOPHER C. | 100% | 15000 | 0 | 15000 | 10921 | 10921 | 11057.13 | 0 | 0 | 10921 | 11500 | 0 | 11500 | [7 empty] | 5688.11 | 3325.34 | 794.8 |  | 1567.97 |  |  | 5232.89 | 0 | 49.46% |  | 0 | 5688.11 | 3500 | 23.33% | 0 | 3500 | 23.33% | 0 |  | 5232.89 | 47.92% | 5232.89 | 47.92% | 4079 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878970 - ROHM AND HAAS | WATER | WATER REPAIR & INSTALLATION | 2019-10-04 | 2019-11-20 | 2019-10-04 | 2019-11-20 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 963661¦¦2020-03-31
FP | C | Yes | 963663 |  | CLEARWATER PAPER CO | BURGE, EVERETT E. | 100% | 15000 | 25457.18 | 40457.18 | 40457.18 | 40457.18 | 40457.18 | 0 | 0 | 40457.18 | 13200 | 7874.38 | 21074.38 | [7 empty] | 21882.23 | 8262.28 | 2307.14 |  | 11312.81 |  |  | 18574.95 | 0 | 103.8% |  | 0 | 21882.23 | 1800 | 12% | 17582.8 | 19382.8 | 47.91% | 0 |  | 18574.95 | 45.91% | 18574.95 | 45.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 888664 - CLEARWATER PAPER CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-10-07 | 2020-01-27 | 2019-10-07 | 2020-01-27 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 963663¦¦2020-03-31
FP | C | Yes | 963872 |  | OLIVE BRANCH NEW MOTOR | ANDERSON, STEPHEN P. | 100% | 7865 | 0 | 7865 | 7865 | 7865 | 7865 | 0 | 0 | 7865 | 5823 | 0 | 5823 | [7 empty] | 5694.43 | 267.42 | 100.86 |  | 5326.15 |  |  | 2170.57 | 0 | 97.79% |  | 0 | 5694.43 | 2042 | 25.96% | 0 | 2042 | 25.96% | 0 |  | 2170.57 | 27.6% | 2170.57 | 27.6% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895759 - OLIVE BRANCH, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-09 | 2019-11-09 | 2019-10-09 | 2019-11-09 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 963872¦¦2020-03-31
FP | C | Yes | 963873 |  | MANHATTAN IL WELL NO 8 MOTOR | EISHA, JOSEPH J. | 100% | 141946 | 0 | 141946 | 141946 | 141946 | 141946 | 0 | 0 | 141946 | 90000 | 0 | 90000 | 0 |  |  |  | 0 |  |  | 78383.29 | 1467.56 |  |  | 76915.73 |  |  | 63562.71 | 0 | 87.09% |  | 0 | 78383.29 | 51946 | 36.6% | 0 | 51946 | 36.6% | 0 |  | 63562.71 | 44.78% | 63562.71 | 44.78% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 894145 - MANHATTAN, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-09 | 2019-12-01 | 2019-10-09 | 2019-12-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 963873¦¦2020-03-31
FP | C | Yes | 963874 |  | DUPONT INDUSTRIAL BIOSCIENCES | EISHA, JOSEPH J. | 100% | 4330 | 0 | 4330 | 4330 | 4330 | 4330 | 0 | 0 | 4330 | 3000 | 0 | 3000 | [7 empty] | 2921.47 | 2291 | 115.04 |  | 515.43 |  |  | 1408.53 | 0 | 97.38% |  | 0 | 2921.47 | 1330 | 30.72% | 0 | 1330 | 30.72% | 0 |  | 1408.53 | 32.53% | 1408.53 | 32.53% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 889312 - DANISCO US INC BELOIT, WI | WATER | WATER REPAIR & INSTALLATION | 2019-10-09 | 2019-10-22 | 2019-10-09 | 2019-10-22 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 963874¦¦2020-03-31
FP | LJ | Yes | 963879 |  | NICHOLS HILLS OK 2019 WELL 10 | EVANS, TRAVIS L | 85.13% | 719527 | 0 | 719527 | 612556.4559 | 578233.92 | 578233.92 | 0 | 28911.7 | 719527 | 597245.47 | 0 | 597245.47 | 137180.01 | 47.82 |  |  | 703.59 | 136428.6 |  | 515515.66 | 54658.81 | 58641.44 |  | 85937.93 | 316277.48 |  | 62718.26 | 0 | 86.32% |  | 90024.34 | 605540 | 122281.53 | 16.99% | 0 | 122281.53 | 16.99% | 0 |  | 97040.8 | 15.84% | 113987 | 15.84% | 106970.54 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 878678 - NICHOLS HILLS, CITY OF | WATER | WATER SUPPLY | 2019-10-09 | 2020-10-10 | 2019-10-09 | 2020-10-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 963879¦¦2020-03-31
TM | C | Yes | 964255 |  | EMERALD PERFORMANCE WELL 8 | BALLUFF, WILLIAM O. | 100% | 56610 | 0 | 56610 | 57030 | 57030 | 57030 | 0 | 0 | 57030 | 42500 | 0 | 42500 | [7 empty] | 34410.02 | 16269.36 | 4575.42 |  | 13565.24 |  |  | 22619.98 | 0 | 80.96% |  | 0 | 34410.02 | 14110 | 24.92% | 0 | 14110 | 24.92% | 0 |  | 22619.98 | 39.66% | 22619.98 | 39.66% | -420 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 890216 - EMERALD PERFORMANCE MATERIALS | WATER | WATER REPAIR & INSTALLATION | 2019-10-10 | 2019-12-31 | 2019-10-10 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 964255¦¦2020-03-31
FP | C | Yes | 964256 |  | PHILLIPS 66 WELL 2 PULL INSPEC | SEIDEN, ANDREW L. | 100% | 17073 | 36126.29 | 53199.29 | 54127.73 | 54127.73 | 54928.34 | 0 | 0 | 54127.73 | 11951 | 29538.16 | 41489.16 | [7 empty] | 55671.96 | 21112.23 | 6404.56 |  | 28155.17 |  |  | 0 | 1544.23 | 134.2% |  | 0 | 55671.96 | 5122 | 30% | 6588.13 | 11710.13 | 22.01% | 0 |  | -1544.23 | -2.853% | -1544.23 | -2.853% | -928.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878724 - PHILLIPS 66 | WATER | WATER REPAIR & INSTALLATION | 2019-10-10 | 2019-11-30 | 2019-10-14 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 964256¦¦2020-03-31
FP | C | Yes | 964299 |  | HONEYWELL UOP FALL FLOW TEST | GREGORY, CRYSTAL N | 100% | 3200 | 0 | 3200 | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 2094 | 0 | 2094 | [7 empty] | 593.36 | 358.57 | 83.48 |  | 151.31 |  |  | 2606.64 | 0 | 28.34% |  | 0 | 593.36 | 1106 | 34.56% | 0 | 1106 | 34.56% | 0 |  | 2606.64 | 81.46% | 2606.64 | 81.46% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 899383 - U O P LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-11 | 2019-11-30 | 2019-10-11 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 964299¦¦2020-03-31
FP | C | Yes | 964300 |  | HONEYWELL UOP MOTOR SWAP | GREGORY, CRYSTAL N | 100% | 3190 | 0 | 3190 | 2120 | 2120 | 2120 | 0 | 0 | 2120 | 2115 | 0 | 2115 | [7 empty] | 754.48 | 398.65 | 185.5 |  | 170.33 |  |  | 1365.52 | 0 | 35.67% |  | 0 | 754.48 | 1075 | 33.7% | 0 | 1075 | 33.7% | 0 |  | 1365.52 | 64.41% | 1365.52 | 64.41% | 1070 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 899383 - U O P LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-11 | 2019-11-30 | 2019-10-11 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 964300¦¦2020-03-31
FP | C | Yes | 964301 |  | INEOS JOLIET WELL NO 1 | BALLUFF, WILLIAM O. | 100% | 50124 | 100810 | 150934 | 321871.1 | 321871.1 | 321871.1 | 0 | 0 | 321871.1 | 38000 | 74070.57 | 112070.57 | 0 |  |  |  | 0 |  |  | 246524.11 | 131837.45 | 40078.73 |  | 74531.13 | 76.8 |  | 75346.99 | 0 | 220% |  | 0 | 246524.11 | 12124 | 24.19% | 26739.43 | 38863.43 | 25.75% | 0 |  | 75346.99 | 23.41% | 75346.99 | 23.41% | -170937.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 879000 - INEOS JOLIET LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-08 | 2019-12-31 | 2019-10-08 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | FACILITIES MANAGEMENT | 964301¦¦2020-03-31
TM | C | Yes | 964342 |  | AK BACKFLOW TESTING | BARNES, MATTHEW D | 100% | 14875 | 7886 | 22761 | 22761 | 22761 | 22761 | 0 | 0 | 22761 | 10410 | 5207 | 15617 | 1.07 | 1.07 |  |  | 0 |  |  | 16935.25 | 5384.14 | 1793.79 |  | 2255.32 | 7502 |  | 5825.75 | 0 | 108.4% |  | 0 | 16935.25 | 4465 | 30.02% | 2679 | 7144 | 31.39% | 2679 |  | 5825.75 | 25.6% | 5825.75 | 25.6% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-10-07 | 2019-11-30 | 2019-10-07 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 964342¦¦2020-03-31
FP | C | Yes | 964344 |  | BRW MONTESANO 1 | LOPEZ-VASQUEZ, JUAN C. | 100% | 3450 | 17449 | 20899 | 28224 | 28224 | 29477.61 | 0 | 0 | 28224 | 6344 | 14741 | 21085 | 9482.93 | 4888.89 | 1760.87 |  | 2833.17 |  |  | 24818.55 | 10028.04 | 2316.54 |  | 12073.97 | 400 |  | 3405.45 | 0 | 117.7% |  | 0 | 24818.55 | -2894 | -83.88% | 2708 | -186 | -0.89% | 500 |  | 3405.45 | 12.07% | 3405.45 | 12.07% | -7325 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-10-11 | 2019-12-21 | 2019-10-11 | 2019-12-21 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 964344¦¦2020-03-31
FP | C | Yes | 964719 |  | OSWEGO IL WELL 9 | BALLUFF, WILLIAM O. | 100% | 165000 | 0 | 165000 | 238012.02 | 238012.02 | 238012.02 | 0 | 0 | 238012.02 | 123750 | 0 | 123750 | 0 |  |  |  | 0 |  |  | 135985.18 | 65688.22 | 12868.93 |  | 56699.23 | 728.8 |  | 102026.84 | 0 | 109.9% | 161.47 | 0 | 135985.18 | 41250 | 25% | 0 | 41250 | 25% | 0 |  | 102026.84 | 42.87% | 102026.84 | 42.87% | -73012.02 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878689 - OSWEGO, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-11 | 2019-12-31 | 2019-10-11 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 964719¦¦2020-03-31
TM | C | Yes | 964720 |  | CAT TINAJA HILLS WELL 2 PUMP | VAN ALLEN, WESLEY C. | 100% | 30413 | 5305 | 35718 | 35718 | 35718 | 35718 | 0 | 0 | 35718 | 22432 | 4558.3 | 26990.3 | [7 empty] | 26951.07 | 6240.77 | 4141.88 |  | 16568.42 |  |  | 8766.93 | 0 | 99.85% |  | 0 | 26951.07 | 7981 | 26.24% | 746.7 | 8727.7 | 24.44% | 0 |  | 8766.93 | 24.54% | 8766.93 | 24.54% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 299159 - CATERPILLAR INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-01 | 2019-11-22 | 2019-10-01 | 2019-11-22 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 964720¦¦2020-03-31
TM | C | Yes | 964729 |  | WASHINGTON FLOW TESTS | WILLIAMS, DONALD G. | 100% | 6438 | 0 | 6438 | 13855 | 13855 | 13855 | 0 | 0 | 13855 | 4980 | 0 | 4980 | [7 empty] | 12231.86 | 3346.09 | 689.37 |  | 8196.4 |  |  | 1623.14 | 0 | 245.6% |  | 0 | 12231.86 | 1458 | 22.65% | 0 | 1458 | 22.65% | 0 |  | 1623.14 | 11.72% | 1623.14 | 11.72% | -7417 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878957 - WASHINGTON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-11 | 2019-11-30 | 2019-10-11 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 964729¦¦2020-03-31
UP | C | Yes | 964731 |  | SEELYVILLE TESTS | MIGUEL, SEAN J. | 100% | 1500 | 6290 | 7790 | 7790 | 7790 | 7790 | 0 | 0 | 7790 | 1300 | 4843 | 6143 | [7 empty] | 5215.56 | 2422.56 | 582.21 |  | 1938.54 | 272.25 |  | 2574.44 | 0 | 84.9% |  | 0 | 5215.56 | 200 | 13.33% | 1447 | 1647 | 21.14% | 0 |  | 2574.44 | 33.05% | 2574.44 | 33.05% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 897676 - SEELYVILLE, IN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-14 | 2019-11-30 | 2019-10-14 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 964731¦¦2020-03-31
FP | C | Yes | 965156 |  | ENTERPRISE BOLING PWM TESTING | CALLAHAN, DANIEL E. | 100% | 2400 | 0 | 2400 | 2280 | 2280 | 2280 | 0 | 0 | 2280 | 1917 | 0 | 1917 | [7 empty] | 1810.35 | 607.67 | 204.05 |  | 998.63 |  |  | 469.65 | 0 | 94.44% |  | 0 | 1810.35 | 483 | 20.12% | 0 | 483 | 20.12% | 0 |  | 469.65 | 20.6% | 469.65 | 20.6% | 120 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 981187 - ENTERPRISE TEXAS PIPELINE LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-14 | 2019-10-16 | 2019-10-14 | 2019-10-16 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 965156¦¦2020-03-31
FP | C | Yes | 965163 |  | LYONDELLBASELL LA PORTE START | CALLAHAN, DANIEL E. | 100% | 2200 | 0 | 2200 | 2200 | 2200 | 2200 | 0 | 0 | 2200 | 1630 | 0 | 1630 | [7 empty] | 4540.19 | 1253.17 | 226.97 |  | 3060.05 |  |  | 0 | 2340.19 | 278.5% |  | 0 | 4540.19 | 570 | 25.91% | 0 | 570 | 25.91% | 0 |  | -2340.19 | -106.4% | -2340.19 | -106.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 894026 - LYONDELL CHEMICALS COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 965163¦¦2020-03-31
TM | C | Yes | 965164 |  | OAKWOOD HOMES GVRE WELL | SCHANAMAN, MIKE L. | 100% | 35995 | 0 | 35995 | 35666.5 | 35666.5 | 35666.5 | 0 | 0 | 35666.5 | 22549 | 0 | 22549 | [7 empty] | 33346.29 | 12046.29 | 6868.05 |  | 14431.95 |  |  | 2320.21 | 0 | 147.9% |  | 0 | 33346.29 | 13446 | 37.36% | 0 | 13446 | 37.36% | 0 |  | 2320.21 | 6.505% | 2320.21 | 6.505% | 328.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 576841 - OAKWOOD HOMES | WATER | WATER SUPPLY | 2019-10-14 | 2019-11-30 | 2019-10-14 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 965164¦¦2020-03-31
FP | C | Yes | 965583 |  | INVISTA RELINE WELL 2 | CALLAHAN, DANIEL E. | 100% | 92735 | 0 | 92735 |  |  | 0 | 0 | 0 |  | 53822 | 0 | 53822 | [7 empty] | -96.68 |  |  |  | -96.68 |  |  | 96.68 | 0 | -0.1796% |  | 0 | -96.68 | 38913 | 41.96% | 0 | 38913 | 41.96% | 0 |  | 96.68 |  | 96.68 |  | 92735 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 892625 - INVISTA | WATER | WATER REPAIR & INSTALLATION | 2019-10-15 | 2019-11-30 | 2019-10-15 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 965583¦¦2020-03-31
TM | C | Yes | 965584 |  | ELBURN IL WELL 5 | BALLUFF, WILLIAM O. | 100% | 50000 | 87800 | 137800 | 119624.05 | 119624.05 | 119624.05 | 0 | 0 | 119624.05 | 37500 | 65556.39 | 103056.39 | 972.79 | 771.35 |  |  | 201.44 |  |  | 93662.38 | 59096.84 | 9675.9 |  | 24889.64 |  |  | 25961.67 | 0 | 90.88% | 0 | 0 | 93662.38 | 12500 | 25% | 22243.61 | 34743.61 | 25.21% | 0 |  | 25961.67 | 21.7% | 25961.67 | 21.7% | 18175.95 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 890087 - ELBURN, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-15 | 2019-12-31 | 2019-10-15 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 965584¦¦2020-03-31
TM | CJ | Yes | 965585 |  | OXBOW FIRE PUMP TROUBLESHOOT | LOPEZ-VASQUEZ, JUAN C. |  | 450 | 0 | 450 |  |  | 0 | 0 | 0 |  | 331 | 0 | 331 | [20 empty] | 119 | 26.44% | 0 | 119 | 26.44% | 0 | [5 empty] | 450 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 879058 - OXBOW CALCINING LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-14 | 2019-12-31 | 2019-10-14 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 965585¦¦2020-03-31
TM | C | Yes | 965587 |  | CHENANGO NY MAPLEWOOD PITLESS | CROOK, CHARLES M | 100% | 15575 | 0 | 15575 | 14100 | 14100 | 14100 | 0 | 0 | 14100 | 11575 | 0 | 11575 | [7 empty] | 9887.65 | 3439.76 | 886.43 |  | 5561.46 |  |  | 4212.35 | 0 | 85.42% |  | 0 | 9887.65 | 4000 | 25.68% | 0 | 4000 | 25.68% | 0 |  | 4212.35 | 29.87% | 4212.35 | 29.87% | 1475 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 888290 - CHENANGO, NY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-11 | 2019-10-31 | 2019-10-11 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 965587¦¦2020-03-31
FP | C | Yes | 965652 |  | NUTRIEN SPARE PUMP | GREGORY, CRYSTAL N | 100% | 11975 | 0 | 11975 | 11056.72 | 11056.72 | 11975 | 0 | 0 | 11056.72 | 7148 | 0 | 7148 | [7 empty] | 6783.65 | 392.73 | 166.95 |  | 6223.97 |  |  | 4273.07 | 0 | 94.9% |  | 0 | 6783.65 | 4827 | 40.31% | 0 | 4827 | 40.31% | 0 |  | 4273.07 | 38.65% | 4273.07 | 38.65% | 918.28 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878934 - NUTRIENT | WATER | WATER EQUIPMENT SALES | 2019-10-16 | 2019-11-30 | 2019-10-16 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 965652¦¦2020-03-31
FP | C | Yes | 965653 |  | GULF SHORES WELL 9 | PARSLEY, TRISTAN S | 100% | 57125 | 43000 | 100125 | 100125 | 100125 | 100125 | 0 | 0 | 100125 | 40287 | 28746 | 69033 | [7 empty] | 87287.24 | 23950 | 7999.23 |  | 55338.01 |  |  | 12837.76 | 0 | 126.4% |  | 0 | 87287.24 | 16838 | 29.48% | 14254 | 31092 | 31.05% | 0 |  | 12837.76 | 12.82% | 12837.76 | 12.82% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 900952 - GULF SHORES UTILITIES BOARD | WATER | WATER REPAIR & INSTALLATION | 2019-10-16 | 2019-12-20 | 2019-10-07 | 2019-12-20 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 965653¦¦2020-03-31
FP | CJ | Yes | 965654 |  | CG ROXANE TEST WELL | CROOK, CHARLES M | 100% | 49330 | 0 | 49330 | 53355 | 53355 | 53355 | 0 | 0 | 53355 | 36000 | 0 | 36000 | 184.26 | 154.63 |  |  | 29.63 |  |  | 32190.56 | 12589.45 | 13094.06 |  | 6507.05 |  |  | 21164.44 | 0 | 89.42% |  | 0 | 32190.56 | 13330 | 27.02% | 0 | 13330 | 27.02% | 0 |  | 21164.44 | 39.67% | 21164.44 | 39.67% | -4025 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 888188 - CG ROXANE | WATER | WATER SUPPLY | 2019-10-01 | 2019-12-30 | 2019-10-01 | 2019-12-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 965654¦¦2020-03-31
FP | C | Yes | 965894 |  | OTEGO NY WELL 1 REHAB | CROOK, CHARLES M | 100% | 9780 | 0 | 9780 | 24325 | 24325 | 24325 | 0 | 0 | 24325 | 6780 | 0 | 6780 | 0 |  |  |  | 0 |  |  | 16900.74 | 10833.2 | 3268.86 |  | 2798.68 |  |  | 7424.26 | 0 | 249.3% |  | 0 | 16900.74 | 3000 | 30.67% | 0 | 3000 | 30.67% | 0 |  | 7424.26 | 30.52% | 7424.26 | 30.52% | -14545 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 895893 - OTEGO, NY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-01 | 2019-10-31 | 2019-10-01 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 965894¦¦2020-03-31
TM | C | Yes | 965895 |  | SELLERSBURG VALVE | MIGUEL, SEAN J. | 100% | 11169 | 0 | 11169 | 12423 | 12423 | 12423 | 0 | 0 | 12423 | 8182 | 0 | 8182 | [7 empty] | 8876.85 | 1240.4 | 316.72 |  | 7319.73 |  |  | 3546.15 | 0 | 108.5% |  | 0 | 8876.85 | 2987 | 26.74% | 0 | 2987 | 26.74% | 0 |  | 3546.15 | 28.55% | 3546.15 | 28.55% | -1254 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 965311 - SELLERSBURG, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-16 | 2019-12-30 | 2019-10-16 | 2019-12-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 965895¦¦2020-03-31
TM | C | Yes | 965896 |  | BEVERLY HILLS GREYSTONE SPLIT | GRACE, GARY L. | 100% | 14907 | 0 | 14907 | 14907.08 | 14907.08 | 15729.66 | 0 | 0 | 14907.08 | 11444 | 0 | 11444 | 4453.99 | 3488.93 | 174.9 |  | 790.16 |  |  | 11839.56 | 3488.93 | 174.9 |  | 8175.73 |  |  | 3067.52 | 0 | 103.5% |  | 0 | 11839.56 | 3463 | 23.23% | 0 | 3463 | 23.23% | 0 |  | 3067.52 | 20.58% | 3067.52 | 20.58% | -0.08 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878627 - BEVERLY HILLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-07 | 2019-10-15 | 2019-10-07 | 2019-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 965896¦¦2020-03-31
TM | C | Yes | 965897 |  | DIAZ AND YOURMAN HIGHLAND | COMBS, TAYLOR E. | 100% | 51610 | 0 | 51610 | 53331 | 53331 | 53331 | 0 | 0 | 53331 | 41349 | 0 | 41349 | [7 empty] | 36117.58 | 17599.78 | 7272.38 |  | 11245.42 |  |  | 17213.42 | 0 | 87.35% |  | 0 | 36117.58 | 10261 | 19.88% | 0 | 10261 | 19.88% | 0 |  | 17213.42 | 32.28% | 17213.42 | 32.28% | -1721 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 965737 - DIAZ YOURMAN AND ASSOCIATES | WATER | WATER REPAIR & INSTALLATION | 2019-10-14 | 2019-11-18 | 2019-10-14 | 2019-11-18 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 965897¦¦2020-03-31
CR | CJ | Yes | 966073 |  | SOUTH SHORE PILOT STUDY | MIGUEL, SEAN J. | 100% | [5 empty] | 0 | 0 | 0 |  | 10000 | 0 | 10000 | [7 empty] | 9041.41 | 4079.01 | 842.74 |  | 3012.66 | 1107 |  | 0 | 9041.41 | 90.41% |  | 0 | 9041.41 | -10000 |  | 0 | -10000 |  | 0 |  | -9041.41 |  | -9041.41 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 893590 - LAYNE HEAVY CIVIL INC | WATER | WATER TREATMENT | 2019-10-17 | 2019-12-31 | 2019-10-17 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 966073¦¦2020-03-31
TM | C | Yes | 966079 |  | ALVIN WELL 8 MOTOR REPAIR | CALLAHAN, DANIEL E. | 100% | 2710 | 0 | 2710 | 19790 | 19790 | 19790 | 0 | 0 | 19790 | 2032 | 0 | 2032 | [7 empty] | 15209.86 | 2058.33 | 1315.31 |  | 10673.73 | 1162.49 |  | 4580.14 | 0 | 748.5% |  | 0 | 15209.86 | 678 | 25.02% | 0 | 678 | 25.02% | 0 |  | 4580.14 | 23.14% | 4580.14 | 23.14% | -17080 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 886175 - ALVIN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-17 | 2019-12-14 | 2019-10-17 | 2019-12-14 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 966079¦¦2020-03-31
FP | C | Yes | 967014 |  | LEE COUNTY NLC RO PW7 REPAIR | TORMOEHLEN, DAVID A. | 100% | 9500 | 0 | 9500 | 9500 | 9500 | 9500 | 0 | 0 | 9500 | 6656 | 0 | 6656 | [7 empty] | 4854.33 | 2443.47 | 992.18 |  | 1418.68 |  |  | 4645.67 | 0 | 72.93% |  | 0 | 4854.33 | 2844 | 29.94% | 0 | 2844 | 29.94% | 0 |  | 4645.67 | 48.9% | 4645.67 | 48.9% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878637 - LEE, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-16 | 2019-11-30 | 2019-10-16 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 967014¦¦2020-03-31
TM | C | Yes | 967015 |  | MONUMENT I7 | MIGUEL, SEAN J. | 100% | 4230 | 26125 | 30355 | 30355 | 30355 | 30355 | 0 | 0 | 30355 | 3445 | 18561 | 22006 | [7 empty] | 17453.95 | 2770.72 | 767.79 |  | 12415.44 | 1500 |  | 12901.05 | 0 | 79.31% |  | 0 | 17453.95 | 785 | 18.56% | 7564 | 8349 | 27.5% | 0 |  | 12901.05 | 42.5% | 12901.05 | 42.5% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 894946 - MONUMENT CHEMICAL | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-11-30 | 2019-10-18 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967015¦¦2020-03-31
FP | CJ | Yes | 967016 |  | CAL MAINE VALVE INSTALL | LOPEZ-VASQUEZ, JUAN C. | 100% | 2785 | 0 | 2785 | 2785 | 2785 | 2785 | 0 | 0 | 2785 | 1950 | 0 | 1950 | [7 empty] | 1354.59 | 475.04 | 166.95 |  | 712.6 |  |  | 1430.41 | 0 | 69.47% |  | 0 | 1354.59 | 835 | 29.98% | 0 | 835 | 29.98% | 0 |  | 1430.41 | 51.36% | 1430.41 | 51.36% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 887794 - CAL MAINE FOODS INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-11-22 | 2019-10-18 | 2019-11-22 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 967016¦¦2020-03-31
FP | C | Yes | 967017 |  | CAL MAINE FOODS FLOW TEST | LOPEZ-VASQUEZ, JUAN C. | 100% | 1650 | 4955 | 6605 | 6605 | 6605 | 6605 | 0 | 0 | 6605 | 1186 | 2156 | 3342 | [7 empty] | 3630.54 | 780.02 | 315.35 |  | 305.22 | 2229.95 |  | 2974.46 | 0 | 108.6% |  | 0 | 3630.54 | 464 | 28.12% | 2799 | 3263 | 49.4% | 2799 |  | 2974.46 | 45.03% | 2974.46 | 45.03% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 887794 - CAL MAINE FOODS INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-12-30 | 2019-10-18 | 2019-12-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 967017¦¦2020-03-31
FP | CJ | Yes | 967018 |  | BOARDWALK 501B RELINE REHAB | GNAU, CASEY T | 100% | 199200 | 0 | 199200 | 102150 | 102150 | 102150 | 0 | 0 | 102150 | 99600 | 0 | 99600 | [7 empty] | 40537.34 | 12904.86 | 6900.36 |  | 19996.89 | 735.23 |  | 61612.66 | 0 | 40.7% |  | 0 | 40537.34 | 99600 | 50% | 0 | 99600 | 50% | 0 |  | 61612.66 | 60.32% | 61612.66 | 60.32% | 97050 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 936154 - CAVERN SOLUTIONS INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-11-30 | 2019-10-18 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967018¦¦2020-03-31
TM | CJ | Yes | 967019 |  | LOUDON BACKWASH PUMP | ANDERSON, STEPHEN P. | 100% | 11750 | 75427 | 87177 | 29685.73 | 29685.73 | 11750 | 0 | 0 | 29685.73 | 8810 | 55998.78 | 64808.78 | 4.97 |  |  |  | 4.97 |  |  | 23982.94 | 8063.28 | 1557.09 |  | 14362.57 |  |  | 5702.79 | 0 | 37.01% |  | 0 | 23982.94 | 2940 | 25.02% | 19428.22 | 22368.22 | 25.66% | 0 |  | 5702.79 | 19.21% | 5702.79 | 19.21% | 57491.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 893923 - LOUDON UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-11-21 | 2019-10-18 | 2019-11-21 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 967019¦¦2020-03-31
FP | CJ | Yes | 967021 |  | P66 | EVANS, TRAVIS L | 100% | 261240 | 0 | 261240 | 244140 | 244140 | 244140 | 0 | 0 | 244140 | 61893 | 43630 | 105523 | 0 |  |  |  | 0 |  |  | 148392.99 | 51502.48 | 27651.49 |  | 64177.77 | 5061.25 |  | 95747.01 | 0 | 140.6% |  | 0 | 148392.99 | 199347 | 76.31% | -43630 | 155717 | 59.61% | 0 |  | 95747.01 | 39.22% | 95747.01 | 39.22% | 17100 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 896285 - PHILLIPS 66 PONCA CITY REFINERY | WATER | WATER SUPPLY | 2019-10-18 | 2019-12-13 | 2019-10-18 | 2019-12-13 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 967021¦¦2020-03-31
FP | CJ | Yes | 967022 |  | WESTROCK SPARE 12 PUMP | GNAU, CASEY T | 100% | 15800 | 0 | 15800 | 15800 | 15800 | 15800 | 0 | 0 | 15800 | 8337 | 0 | 8337 | [7 empty] | 7493.03 |  |  |  | 7493.03 |  |  | 8306.97 | 0 | 89.88% |  | 0 | 7493.03 | 7463 | 47.23% | 0 | 7463 | 47.23% | 0 |  | 8306.97 | 52.58% | 8306.97 | 52.58% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-11-30 | 2019-10-18 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967022¦¦2020-03-31
TM | CJ | Yes | 967023 |  | EAST CENTRAL VERNON WELL 3 | GNAU, CASEY T | 100% | 22450 | 152685 | 175135 | 171135 | 171135 | 171135 | 0 | 0 | 171135 | 15715 | 97122 | 112837 | 1587.71 |  |  |  | 100 | 1487.71 |  | 93011.77 | 29603.89 | 21883.01 |  | 36895.27 | 4629.6 |  | 78123.23 | 0 | 82.43% |  | 0 | 93011.77 | 6735 | 30% | 55563 | 62298 | 35.57% | 0 |  | 78123.23 | 45.65% | 78123.23 | 45.65% | 4000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 889943 - EAST CENTRAL VERNON WATER SYSTEM | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-11-30 | 2019-10-18 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 967023¦¦2020-03-31
TM | C | Yes | 967024 |  | HOPE WATER AND LIGHT WELL 11 | BURGE, EVERETT E. | 100% | 47000 | 0 | 47000 | 47000 | 47000 | 47842.43 | 0 | 0 | 47000 | 42000 | 0 | 42000 | 2340.51 |  |  |  | 2340.51 |  |  | 48378.97 | 17890.29 | 4861.27 |  | 25627.41 |  |  | 0 | 1378.97 | 115.2% |  | 0 | 48378.97 | 5000 | 10.64% | 0 | 5000 | 10.64% | 0 |  | -1378.97 | -2.934% | -1378.97 | -2.934% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892243 - HOPE WATER & LIGHT | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2020-01-02 | 2019-10-18 | 2020-01-02 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 967024¦¦2020-03-31
TM | C | Yes | 967025 |  | JONESBORO CWL HIGH SERVICE PR | BURGE, EVERETT E. | 100% | 9400 | 0 | 9400 | 22776.23 | 22776.23 | 24712.2 | 0 | 0 | 22776.23 | 8400 | 0 | 8400 | 13719.9 | 2639.73 | 1227.7 |  | 9852.47 |  |  | 19696.37 | 5429.65 | 1263.7 |  | 13003.02 |  |  | 3079.86 | 0 | 234.5% |  | 0 | 19696.37 | 1000 | 10.64% | 0 | 1000 | 10.64% | 0 |  | 3079.86 | 13.52% | 3079.86 | 13.52% | -13376.23 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892917 - JONESBORO, CITY WATER & LIGHT | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-12-20 | 2019-10-18 | 2019-12-20 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 967025¦¦2020-03-31
UP | C | Yes | 967507 |  | FRENCH LICK MOTOR | MIGUEL, SEAN J. | 100% | 7105 | 0 | 7105 | 7955 | 7955 | 7955 | 0 | 0 | 7955 | 4889 | 0 | 4889 | [7 empty] | 5105.45 | 128.45 | 62.67 |  | 4914.33 |  |  | 2849.55 | 0 | 104.4% |  | 0 | 5105.45 | 2216 | 31.19% | 0 | 2216 | 31.19% | 0 |  | 2849.55 | 35.82% | 2849.55 | 35.82% | -850 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 890934 - FRENCH LICK SPRINGS RESORT & CASINO | WATER | WATER REPAIR & INSTALLATION | 2019-10-21 | 2019-11-30 | 2019-10-21 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967507¦¦2020-03-31
FP | C | Yes | 967508 |  | TOKAI CARBON SOUTH WELL REHAB | LOPEZ-VASQUEZ, JUAN C. | 100% | 60800 | 15170 | 75970 | 75970 | 75970 | 75970 | 0 | 0 | 75970 | 47421 | 8353 | 55774 | 27.11 |  |  |  | 27.11 |  |  | 43584.92 | 21054.82 | 7886.67 |  | 14243.43 | 400 |  | 32385.08 | 0 | 78.15% |  | 0 | 43584.92 | 13379 | 22% | 6817 | 20196 | 26.58% | 0 |  | 32385.08 | 42.63% | 32385.08 | 42.63% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878484 - TOKAI CARBON CB LTD | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-12-31 | 2019-10-18 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967508¦¦2020-03-31
FP | C | Yes | 967510 |  | RESTHAVEN WICHITA KS SOUTH | WARTICK, LOGAN M | 100% | 6213 | 0 | 6213 | 28351 | 28351 | 30034.6 | 0 | 0 | 28351 | 4970 | 0 | 4970 | [7 empty] | 23568.3 | 6596.26 | 2606.49 |  | 14365.55 |  |  | 4782.7 | 0 | 474.2% |  | 0 | 23568.3 | 1243 | 20.01% | 0 | 1243 | 20.01% | 0 |  | 4782.7 | 16.87% | 4782.7 | 16.87% | -22138 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 896952 - RESTHAVEN MORTUARY & CEMETERY | WATER | WATER REPAIR & INSTALLATION | 2019-10-21 | 2019-11-30 | 2019-10-21 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967510¦¦2020-03-31
TM | C | Yes | 967511 |  | DAN ELDRIDGE PR | BENNETT, MARK C. | 100% | 60000 | 0 | 60000 | 50825.22 | 50825.22 | 54637.14 | 0 | 0 | 50825.22 | 53995 | 0 | 53995 | 516.93 |  |  |  | 516.93 |  |  | 47032.84 | 19566.27 | 4021.14 |  | 23445.43 |  |  | 3792.38 | 0 | 87.11% |  | 0 | 47032.84 | 6005 | 10.01% | 0 | 6005 | 10.01% | 0 |  | 3792.38 | 7.462% | 3792.38 | 7.462% | 9174.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 889309 - DAN ELDRIDGE FARMS, INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-21 | 2020-10-21 | 2019-10-21 | 2020-10-21 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967511¦¦2020-03-31
TM | C | Yes | 967512 |  | CITY OF SCOTTSDALE 83A PUMP 7 | VAN ALLEN, WESLEY C. | 100% | 3030 | 7163.31 | 10193.31 | 10767.76 | 10767.76 | 10767.76 | 0 | 0 | 10767.76 | 1831 | 6252.79 | 8083.79 | 0 |  |  |  | 0 |  |  | 7528.17 | 2504.54 | 315.87 |  | 4707.76 |  |  | 3239.59 | 0 | 93.13% |  | 0 | 7528.17 | 1199 | 39.57% | 910.52 | 2109.52 | 20.7% | 0 |  | 3239.59 | 30.09% | 3239.59 | 30.09% | -574.45 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 897620 - SCOTTSDALE, AZ, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-12-06 | 2019-10-18 | 2019-12-06 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 967512¦¦2020-03-31
TM | C | Yes | 967513 |  | ARKANSAS INDUSTRIAL MACHINERY | BENNETT, MARK C. | 100% | 8200 | 0 | 8200 | 18830.87 | 18830.87 | 18830.87 | 0 | 0 | 18830.87 | 5676 | 0 | 5676 | 8077.5 | 648.91 | 8 |  | 7420.59 |  |  | 14559.21 | 3038.4 | 40 |  | 11415.81 | 65 |  | 4271.66 | 0 | 256.5% |  | 0 | 14559.21 | 2524 | 30.78% | 0 | 2524 | 30.78% | 0 |  | 4271.66 | 22.68% | 4271.66 | 22.68% | -10630.87 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 886483 - ARKANSAS INDUSTRIAL MACHINERY INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-21 | 2020-10-21 | 2019-10-21 | 2020-10-21 | PRIME CONTRACTOR | PRIVATE | EXPENSE JOB | 967513¦¦2020-03-31
FP | C | Yes | 967514 |  | CPNMD A4 | SCHANAMAN, MIKE L. | 100% | 83880 | 0 | 83880 | 83880 | 83880 | 83880 | 0 | 0 | 83880 | 58627 | 0 | 58627 | 4336.17 | 2029.21 | 1015.64 |  | 1291.32 |  |  | 109268.07 | 23428.67 | 9532.88 |  | 73078.52 | 3228 |  | 0 | 25388.07 | 186.4% |  | 0 | 109268.07 | 25253 | 30.11% | 0 | 25253 | 30.11% | 0 |  | -25388.07 | -30.27% | -25388.07 | -30.27% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878896 - CASTLE PINES NORTH METROPOLITAN DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-10-15 | 2020-01-31 | 2019-10-15 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 967514¦¦2020-03-31
FP | C | Yes | 967669 |  | WMWD ADS PUMP 3 | GRACE, GARY L. | 100% | 20853.75 | 0 | 20853.75 | 31182.5 | 31182.5 | 32220.03 | 0 | 0 | 31182.5 | 14901 | 0 | 14901 | [7 empty] | 28972.5 | 7456.71 | 1305.06 |  | 17369.73 | 2841 |  | 2210 | 0 | 194.4% |  | 0 | 28972.5 | 5952.75 | 28.55% | 0 | 5952.75 | 28.55% | 0 |  | 2210 | 7.087% | 2210 | 7.087% | -10328.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 900107 - WESTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-10-16 | 2019-12-25 | 2019-10-21 | 2019-12-25 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 967669¦¦2020-03-31
FP | C | Yes | 967670 |  | CBRE IBM FLOW TEST | BARNES, MATTHEW D | 100% | 2070 | 0 | 2070 | 2070 | 2070 | 2070 | 0 | 0 | 2070 | 1452 | 0 | 1452 | 0.15 | 0.15 | [5 empty] | 1991.57 | 1057.86 | 476.64 |  | 457.07 |  |  | 78.43 | 0 | 137.2% |  | 0 | 1991.57 | 618 | 29.86% | 0 | 618 | 29.86% | 0 |  | 78.43 | 3.789% | 78.43 | 3.789% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 966390 - CBRE IBM NORTH AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-10-10 | 2019-11-30 | 2019-10-10 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967670¦¦2020-03-31
TM | CJ | Yes | 967679 |  | FLOWER HILL CEMETERY PUMP PULL | GANSEBOM, JASON W. | 100% | 8940 | 0 | 8940 | 4894.62 | 4894.62 | 0 | 0 | 0 | 4894.62 | 5376 | 0 | 5376 | 0.28 |  |  |  | 0.28 |  |  | 3954.34 | 1951.13 | 411.83 |  | 1591.38 |  |  | 940.28 | 0 | 73.56% |  | 0 | 3954.34 | 3564 | 39.87% | 0 | 3564 | 39.87% | 0 |  | 940.28 | 19.21% | 940.28 | 19.21% | 4045.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 967608 - NEUHAUS, LOWELL | WATER | WATER REPAIR & INSTALLATION | 2019-10-21 | 2019-11-30 | 2019-10-21 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 967679¦¦2020-03-31
FP | C | Yes | 967795 |  | CITY OF GONZALES DHH CHECKLIST | LOPEZ-VASQUEZ, JUAN C. | 100% | 2741.57 | 2290 | 5031.57 | 5455 | 5455 | 5455 | 0 | 0 | 5455 | 1920 | 1103 | 3023 | 0.46 |  |  |  | 0.46 |  |  | 3355.63 | 1352.53 | 501.39 |  | 1501.71 |  |  | 2099.37 | 0 | 111% |  | 0 | 3355.63 | 821.57 | 29.97% | 1187 | 2008.57 | 39.92% | 1187 |  | 2099.37 | 38.49% | 2099.37 | 38.49% | -423.43 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 891406 - GONZALES, LA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-21 | 2019-12-01 | 2019-10-21 | 2019-12-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 967795¦¦2020-03-31
TM | C | Yes | 967998 |  | ROGER ESSICK NICHOLS PULL | SEIDEN, ANDREW L. | 100% | 6976 | 23397 | 30373 | 30373.45 | 30373.45 | 30622.57 | 0 | 0 | 30373.45 | 5590 | 18512.21 | 24102.21 | [7 empty] | 23662.03 | 6017.13 | 2654.26 |  | 14124.38 | 866.26 |  | 6711.42 | 0 | 98.17% |  | 0 | 23662.03 | 1386 | 19.87% | 4884.79 | 6270.79 | 20.65% | 0 |  | 6711.42 | 22.1% | 6711.42 | 22.1% | -0.45 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 890432 - ESSICK FARM MANAGEMENT | WATER | WATER REPAIR & INSTALLATION | 2019-10-14 | 2019-11-01 | 2019-10-14 | 2019-11-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 967998¦¦2020-03-31
TM | C | Yes | 968054 |  | GHD PRISTINE PUMP | BARNES, MATTHEW D | 100% | 3690 | 6911 | 10601 | 10601 | 10601 | 10601 | 0 | 0 | 10601 | 2325 | 4724 | 7049 | 0.94 | 0.94 | [5 empty] | 8230.53 | 4407.2 | 1138.79 |  | 2684.54 |  |  | 2370.47 | 0 | 116.8% |  | 0 | 8230.53 | 1365 | 36.99% | 2187 | 3552 | 33.51% | 0 |  | 2370.47 | 22.36% | 2370.47 | 22.36% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 891236 - GHD | WATER | WATER REPAIR & INSTALLATION | 2019-10-23 | 2019-11-30 | 2019-10-23 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 968054¦¦2020-03-31
TM | CJ | Yes | 968055 |  | OKALOOSA ANTIOCH WELL | PARSLEY, TRISTAN S | 100% | 17705 | 0 | 17705 | 17705 | 17705 | 8275 | 0 | 0 | 17705 | 12700 | 0 | 12700 | [7 empty] | 18409.73 | 6582.81 | 2179.82 |  | 9647.1 |  |  | 0 | 704.73 | 145% |  | 0 | 18409.73 | 5005 | 28.27% | 0 | 5005 | 28.27% | 0 |  | -704.73 | -3.98% | -704.73 | -3.98% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 895709 - OKALOOSA COUNTY WATER & SEWER SYSTEM | WATER | WATER SUPPLY | 2019-10-18 | 2019-11-30 | 2019-10-18 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 968055¦¦2020-03-31
TM | CJ | Yes | 968197 |  | GLENVILLE NY HIGH LIFT 2 INSP | CROOK, CHARLES M | 100% | 560 | 24850 | 25410 | 13928.65 | 13928.65 | 9475 | 0 | 0 | 13928.65 | 400 | 16200 | 16600 | 2163.24 | 1327.16 | 293.2 |  | 542.88 |  |  | 11252.88 | 5881.96 | 1195.12 |  | 4175.8 |  |  | 2675.77 | 0 | 67.79% |  | 0 | 11252.88 | 160 | 28.57% | 8650 | 8810 | 34.67% | 4135 |  | 2675.77 | 19.21% | 2675.77 | 19.21% | 11481.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 891312 - GLENVILLE, NY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-23 | 2019-10-24 | 2019-10-23 | 2019-10-24 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 968197¦¦2020-03-31
FP | CJ | Yes | 968295 |  | GRAND TOWER DW-4 PUMP SERVICE | WHITE, CATHLEEN R | 100% | 10523 | 0 | 10523 | 10523 | 10523 | 10523 | 0 | 0 | 10523 | 7502 | 0 | 7502 | [7 empty] | 17146.99 | 9536.44 | 2511.36 |  | 5099.19 |  |  | 0 | 6623.99 | 228.6% |  | 0 | 17146.99 | 3021 | 28.71% | 0 | 3021 | 28.71% | 0 |  | -6623.99 | -62.95% | -6623.99 | -62.95% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 947126 - GRAND TOWER ENERGY CENTER | WATER | WATER REPAIR & INSTALLATION | 2019-10-21 | 2019-12-31 | 2019-10-21 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 968295¦¦2020-03-31
TM | CJ | Yes | 968308 |  | PEACE RIVER WELL HEAD IMPROVE | MARTINEZ, MIGUEL E | 100% | 61427 | 0 | 61427 | 51018 | 51018 | 51018 | 0 | 0 | 51018 | 44470 | 0 | 44470 | 0 |  | 0 |  | 0 |  |  | 20784.36 | 5727.38 | 3071.19 |  | 6673.29 | 5312.5 |  | 30233.64 | 0 | 46.74% |  | 0 | 20784.36 | 16957 | 27.61% | 0 | 16957 | 27.61% | 0 |  | 30233.64 | 59.26% | 30233.64 | 59.26% | 10409 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 896610 - PROGRESSIVE WATER RESOURCES LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-23 | 2019-12-31 | 2019-10-23 | 2019-12-31 | SUBCONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 968308¦¦2020-03-31
TM | C | Yes | 968494 |  | ENVIRONMENTAL SERVICE PUMP | MIGUEL, SEAN J. | 100% | 4570 | -814 | 3756 | 3756 | 3756 | 3756 | 0 | 0 | 3756 | 3200 | -571 | 2629 | [7 empty] | 2760.23 | 490.94 |  |  | 2269.29 |  |  | 995.77 | 0 | 105% |  | 0 | 2760.23 | 1370 | 29.98% | -243 | 1127 | 30.01% | 0 |  | 995.77 | 26.51% | 995.77 | 26.51% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 968229 - ENVIRONMENTAL SERVICE & SUPPLY INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-24 | 2019-12-30 | 2019-10-24 | 2019-12-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 968494¦¦2020-03-31
TM | C | Yes | 968495 |  | CAL PAR 4 JACK STAND | GNAU, CASEY T | 100% | 1315 | 0 | 1315 | 1780 | 1780 | 1780 | 0 | 0 | 1780 | 665 | 0 | 665 | [7 empty] | 757.32 | 187.45 | 55.65 |  | 96.69 | 417.53 |  | 1022.68 | 0 | 113.9% |  | 0 | 757.32 | 650 | 49.43% | 0 | 650 | 49.43% | 0 |  | 1022.68 | 57.45% | 1022.68 | 57.45% | -465 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 887729 - CALCASIEU PARISH WWD 4 | WATER | WATER REPAIR & INSTALLATION | 2019-10-25 | 2019-11-30 | 2019-10-25 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 968495¦¦2020-03-31
FP | CJ | Yes | 968496 |  | WESTROCK 22 | GNAU, CASEY T | 100% | 50160 | 0 | 50160 | 50160 | 50160 | 50160 | 0 | 0 | 50160 | 25080 | 0 | 25080 | [7 empty] | 13344.61 | 5064.88 | 1287.74 |  | 2920.45 | 4071.54 |  | 36815.39 | 0 | 53.21% |  | 0 | 13344.61 | 25080 | 50% | 0 | 25080 | 50% | 0 |  | 36815.39 | 73.4% | 36815.39 | 73.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2019-10-18 | 2019-11-30 | 2019-10-18 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 968496¦¦2020-03-31
FP | C | Yes | 968680 |  | BRAUMS OUTSIDE TWW | EVANS, TRAVIS L | 100% | 15557 | 43607.2 | 59164.2 | 49132.2 | 49132.2 | 49132.2 | 0 | 0 | 49132.2 | 10010 | 30027.68 | 40037.68 | 8723.85 | 3821.46 | 2059.7 |  | 2842.69 |  |  | 39794.7 | 11721.83 | 5362.7 |  | 21860.17 | 850 |  | 9337.5 | 0 | 99.39% |  | 0 | 39794.7 | 5547 | 35.66% | 13579.52 | 19126.52 | 32.33% | 0 |  | 9337.5 | 19% | 9337.5 | 19% | 10032 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 887396 - BRAUM S DAIRY FARMS | WATER | WATER SUPPLY | 2019-10-24 | 2019-11-01 | 2019-10-24 | 2019-11-01 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 968680¦¦2020-03-31
FP | C | Yes | 968681 |  | CUMBERLAND MACHINE PUMP PARTS | ANDERSON, STEPHEN P. | 100% | 1117 | 0 | 1117 | 1117 | 1117 | 1117 | 0 | 0 | 1117 | 579 | 0 | 579 | [7 empty] | 20.48 |  |  |  | 20.48 |  |  | 1096.52 | 0 | 3.537% |  | 0 | 20.48 | 538 | 48.16% | 0 | 538 | 48.16% | 0 |  | 1096.52 | 98.17% | 1096.52 | 98.17% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 968428 - CUMBERLAND MACHINE CO | WATER | WATER REPAIR & INSTALLATION | 2019-10-23 | 2019-11-01 | 2019-10-23 | 2019-11-01 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 968681¦¦2020-03-31
FP | C | Yes | 968789 |  | BEEF PRODUCTS RESSURECT DEWATE | GANSEBOM, JASON W. | 100% | 9540 | 0 | 9540 | 27714.7 | 27714.7 | 27714.7 | 0 | 0 | 27714.7 | 5270 | 0 | 5270 | 0.28 | 0.28 | [5 empty] | 18272.19 | 7285.46 | 2149.21 |  | 8599.95 | 237.57 |  | 9442.51 | 0 | 346.7% |  | 0 | 18272.19 | 4270 | 44.76% | 0 | 4270 | 44.76% | 0 |  | 9442.51 | 34.07% | 9442.51 | 34.07% | -18174.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878799 - EMPIRICAL FOODS INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-25 | 2019-11-30 | 2019-10-25 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 968789¦¦2020-03-31
FP | C | Yes | 968790 |  | WSWC BOOSTER 2 | SNELTEN, BRIAN M | 100% | 25105 | 0 | 25105 | 18953 | 18953 | 18953 | 0 | 0 | 18953 | 16438 | 0 | 16438 | 0 |  |  |  | 0 |  |  | 16225.64 | 9484.67 | 958.16 |  | 5782.81 |  |  | 2727.36 | 0 | 98.71% |  | 0 | 16225.64 | 8667 | 34.52% | 0 | 8667 | 34.52% | 0 |  | 2727.36 | 14.39% | 2727.36 | 14.39% | 6152 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 900193 - WEST SUBURBAN WATER COMMISSION | WATER | WATER REPAIR & INSTALLATION | 2019-10-25 | 2019-12-31 | 2019-10-25 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 968790¦¦2020-03-31
FP | C | Yes | 968901 |  | WYNSTONE PWM TESTING | KENNEDY, CHRISTOPHER C. | 100% | 2800 | 0 | 2800 | 2800 | 2800 | 2800 | 0 | 0 | 2800 | 2100 | 0 | 2100 | [7 empty] | 3194.95 | 2265.86 | 298.22 |  | 630.87 |  |  | 0 | 394.95 | 152.1% |  | 0 | 3194.95 | 700 | 25% | 0 | 700 | 25% | 0 |  | -394.95 | -14.11% | -394.95 | -14.11% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878897 - WYNSTONE PROPERTY OWNERS ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2019-10-25 | 2019-11-08 | 2019-10-25 | 2019-11-08 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 968901¦¦2020-03-31
FP | C | Yes | 968903 |  | PRAXAIR TEST | GNAU, CASEY T | 100% | 800 | 0 | 800 | 800 | 800 | 800 | 0 | 0 | 800 | 400 | 0 | 400 | [7 empty] | 822.66 | 482.6 | 155.95 |  | 184.11 |  |  | 0 | 22.66 | 205.7% |  | 0 | 822.66 | 400 | 50% | 0 | 400 | 50% | 0 |  | -22.66 | -2.833% | -22.66 | -2.833% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 896548 - PRAXAIR INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-22 | 2019-10-23 | 2019-10-22 | 2019-10-23 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 968903¦¦2020-03-31
FP | C | Yes | 968904 |  | AGP SGT BLUFF IA EMERGENCY WEL | GANSEBOM, JASON W. | 100% | 2976 | 0 | 2976 | 2976.27 | 2976.27 | 2976.27 | 0 | 0 | 2976.27 | 1861 | 0 | 1861 | 55.93 |  |  |  | 55.93 |  |  | 14888.37 | 4093.96 | 2261.7 |  | 8532.71 |  |  | 0 | 11912.1 | 800% |  | 0 | 14888.37 | 1115 | 37.47% | 0 | 1115 | 37.47% | 0 |  | -11912.1 | -400.2% | -11912.1 | -400.2% | -0.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878670 - AG PROCESSING INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-24 | 2019-11-30 | 2019-10-24 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 968904¦¦2020-03-31
FP | LJ | Yes | 968905 |  | IDOT CONTRACT 76M37 | WHITE, CATHLEEN R | 54.12% | 723853 | 0 | 723853 | 391753.6343 | 251609 | 251609 | 0 | 0 | 723853 | 497875.24 | 0 | 497875.24 | 89816.53 | 46729.04 | 11043.32 |  | 32044.17 |  |  | 269452.97 | 130522.93 | 31699.97 |  | 107230.07 |  |  | 0 | 17843.97 | 54.12% |  | 228422.03 | 497875 | 225977.76 | 31.22% | 0 | 225977.76 | 31.22% | 0 |  | 122300.66 | 31.22% | 225978 | 31.22% | 332099.37 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878498 - ILLINOIS, STATE OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-24 | 2019-12-31 | 2019-10-24 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 968905¦¦2020-03-31
FP | C | Yes | 968906 |  | COLUMBUS NE 2019 EW WELL REHAB | GANSEBOM, JASON W. | 100% | 25527 | 0 | 25527 | 23642 | 23642 | 23642 | 0 | 0 | 23642 | 17044 | 0 | 17044 | [7 empty] | 30525.79 | 12666.66 | 5207.9 |  | 12651.23 |  |  | 0 | 6883.79 | 179.1% |  | 0 | 30525.79 | 8483 | 33.23% | 0 | 8483 | 33.23% | 0 |  | -6883.79 | -29.12% | -6883.79 | -29.12% | 1885 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 888829 - COLUMBUS, NE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-21 | 2019-11-30 | 2019-10-21 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 968906¦¦2020-03-31
FP | C | Yes | 968907 |  | MORRIS IL WELL 5 | BALLUFF, WILLIAM O. | 100% | 109797 | 29982 | 139779 | 139260.2 | 139260.2 | 139260.2 | 0 | 0 | 139260.2 | 80000 | 28996.16 | 108996.16 | 825.77 | 574.82 | 99.87 |  | 151.08 |  |  | 107634.21 | 59081.5 | 10786.5 |  | 37766.21 |  |  | 31625.99 | 0 | 98.75% |  | 0 | 107634.21 | 29797 | 27.14% | 985.84 | 30782.84 | 22.02% | 985.84 |  | 31625.99 | 22.71% | 31625.99 | 22.71% | 518.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 894991 - MORRIS, IL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-25 | 2020-01-31 | 2019-10-25 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 968907¦¦2020-03-31
FP | C | Yes | 968953 |  | DUNLAP IA NEW VFD INSTALL | GANSEBOM, JASON W. | 100% | 7802.49 | 0 | 7802.49 | 7802.49 | 7802.49 | 7802.49 | 0 | 0 | 7802.49 | 4100 | 0 | 4100 | [7 empty] | 5348.71 | 527.93 | 185.5 |  | 4635.28 |  |  | 2453.78 | 0 | 130.5% |  | 0 | 5348.71 | 3702.49 | 47.45% | 0 | 3702.49 | 47.45% | 0 |  | 2453.78 | 31.45% | 2453.78 | 31.45% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 889847 - DUNLAP, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-25 | 2019-11-30 | 2019-10-25 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 968953¦¦2020-03-31
TM | C | Yes | 968954 |  | GREAT LAKES JOLIET 300HP | EISHA, JOSEPH J. | 100% | 21488 | 0 | 21488 | 21488 | 21488 | 21488 | 0 | 0 | 21488 | 14000 | 0 | 14000 | 2891.47 | 2260.21 | 33.14 |  | 598.12 |  |  | 9789.72 | 4875.05 | 140.44 |  | 4774.23 |  |  | 11698.28 | 0 | 69.93% |  | 0 | 9789.72 | 7488 | 34.85% | 0 | 7488 | 34.85% | 0 |  | 11698.28 | 54.44% | 11698.28 | 54.44% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 891551 - GREAT LAKES WATER RESOURCES GROUP, INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-27 | 2019-11-01 | 2019-10-27 | 2019-11-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 968954¦¦2020-03-31
TM | CJ | Yes | 969264 |  | JOSH WATERS PULL AND INSPECT | SEIDEN, ANDREW L. | 100% | 7167 | 113067.77 | 120234.77 | 52423.62 | 52423.62 | 52423.62 | 0 | 0 | 52423.62 | 5590 | 93727.09 | 99317.09 | 212.89 |  |  |  | 212.89 |  |  | 45379.34 | 10836.63 | 5217.14 |  | 26670.57 | 2655 |  | 7044.28 | 0 | 45.69% |  | 0 | 45379.34 | 1577 | 22% | 19340.68 | 20917.68 | 17.4% | 18599.97 |  | 7044.28 | 13.44% | 7044.28 | 13.44% | 67811.15 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 968987 - JOSH WATER | WATER | WATER REPAIR & INSTALLATION | 2019-10-24 | 2019-12-31 | 2019-10-24 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 969264¦¦2020-03-31
TM | C | Yes | 969265 |  | MIDDLEBURGH NY CAISSON PUMP1 | CROOK, CHARLES M | 100% | 4240 | 0 | 4240 | 11120 | 11120 | 11120 | 0 | 0 | 11120 | 3040 | 0 | 3040 | 87.46 |  |  |  | 87.46 |  |  | 7358.84 | 4376.94 | 507.81 |  | 2204.09 | 270 |  | 3761.16 | 0 | 242.1% |  | 0 | 7358.84 | 1200 | 28.3% | 0 | 1200 | 28.3% | 0 |  | 3761.16 | 33.82% | 3761.16 | 33.82% | -6880 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 894629 - MIDDLEBURGH, NY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-23 | 2019-10-25 | 2019-10-23 | 2019-10-25 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 969265¦¦2020-03-31
TM | CJ | Yes | 969269 |  | WELL #10 IWVWD | BRASHEAR, DAVID M | 100% | 72558 | 116717.65 | 189275.65 | 170720.08 | 170720.08 | 174045.51 | 0 | 0 | 170720.08 | 61721 | 88051.57 | 149772.57 | 54384.33 | 13140.66 | 4468.02 |  | 31581.67 | 5193.98 |  | 168426.94 | 64536.09 | 30006.77 |  | 68147.6 | 5736.48 |  | 2293.14 | 0 | 112.5% |  | 0 | 168426.94 | 10837 | 14.94% | 28666.08 | 39503.08 | 20.87% | 14977.76 |  | 2293.14 | 1.343% | 2293.14 | 1.343% | 18555.57 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892526 - INDIAN WELLS VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-10-24 | 2019-11-29 | 2019-10-24 | 2019-11-29 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 969269¦¦2020-03-31
FP | C | Yes | 969270 |  | WOOD ROGERS CLAREMONT TEST HOL | MCMAHON, PERRY J | 100% | 68765 | 0 | 68765 | 68765 | 68765 | 67965 | 0 | 0 | 68765 | 58661 | 0 | 58661 | 1731.16 |  | 1731.16 |  |  |  |  | 138677.62 | 47495.03 | 37937.76 |  | 47149.83 | 6095 |  | 0 | 69912.62 | 236.4% |  | 0 | 138677.62 | 10104 | 14.69% | 0 | 10104 | 14.69% | 0 |  | -69912.62 | -101.7% | -69912.62 | -101.7% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 900482 - WOOD ROGERS | WATER | WATER SPECIALTY DRILLING | 2019-10-28 | 2019-11-30 | 2019-10-28 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 969270¦¦2020-03-31
TM | CJ | Yes | 969273 |  | LEHMAN FARMS | SCHERM, LOGAN M | 100% | 10000 | 0 | 10000 | 4574.74 | 4574.74 | 0 | 0 | 0 | 4574.74 | 8000 | 0 | 8000 | [7 empty] | 3695.91 | 1904.97 | 358.87 |  | 1432.07 |  |  | 878.83 | 0 | 46.2% |  | 0 | 3695.91 | 2000 | 20% | 0 | 2000 | 20% | 0 |  | 878.83 | 19.21% | 878.83 | 19.21% | 5425.26 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 893657 - LEHMAN FARMS | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2020-01-02 | 2019-10-28 | 2020-01-02 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 969273¦¦2020-03-31
FP | CJ | Yes | 969274 |  | SAN JACINTO BATH WELL | GRACE, GARY L. | 100% | 162085 | 94823 | 256908 | 255623 | 255623 | 262785.4 | 0 | 0 | 255623 | 128427 | 73864.72 | 202291.72 | 32286.51 | 14780.59 | 3112.68 |  | 14393.24 |  |  | 208725.95 | 74676.58 | 30097.68 |  | 100996.69 | 2955 |  | 46897.05 | 0 | 103.2% |  | 0 | 208725.95 | 33658 | 20.77% | 20958.28 | 54616.28 | 21.26% | 20958.28 |  | 46897.05 | 18.35% | 46897.05 | 18.35% | 1285 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 919351 - SAN JACINTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2019-12-31 | 2019-10-28 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 969274¦¦2020-03-31
FP | LJ | Yes | 969284 |  | WELL NO 34 AND 26A PROJECT | MCMAHON, PERRY J | 81.86% | 4470430 | 136970 | 4607400 | 3107190.8244 | 1970429.2 | 1970429.2 | 0 | 0 | 3795864.2 | 3630254.92 | 144602.04 | 3774856.96 | 937760.3 | 150033.3 | 109687.36 |  | 668543.5 | 9496.14 |  | 2889687.47 | 581657 | 351713.78 | 1100 | 1860575.8 | 94640.89 |  | 0 | 919258.27 | 76.55% |  | 640466.24 | 3530153.71 | 840175.08 | 18.79% | -7632.04 | 832543.04 | 18.07% | -7632.04 | -19389.68 | 217503.35 | 7% | 265710.49 | 7% | 1500209.18 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 899720 - VIRGIN VALLEY WATER DISTRICT | WATER | WATER SUPPLY | 2019-10-25 | 2020-07-01 | 2019-10-25 | 2020-07-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 969284¦¦2020-03-31
FP | LJ | Yes | 969285 |  | SCWA EMJAY BLVD 1A | RANFT, DONALD R | 54.11% | 469524 | 0 | 469524 | 247044.2723 | 167391 | 167391 | 0 | 8369.55 | 456524 | 408401.36 | 0 | 408401.36 | 93161.49 | 26983.12 | 18341.36 |  | 47837.01 |  |  | 234883.19 | 91077.27 | 59941.04 |  | 75864.88 | 8000 |  | 0 | 67492.19 | 57.51% |  | 199167.81 | 434051 | 61122.64 | 13.02% | 0 | 61122.64 | 13.02% | 0 |  | 12161.08 | 4.923% | 22473 | 4.923% | 222479.73 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878736 - SUFFOLK, COUNTY OF | WATER | WATER SUPPLY | 2019-10-28 | 2020-03-26 | 2019-10-28 | 2020-03-26 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 969285¦¦2020-03-31
FP | LJ | Yes | 969286 |  | FMI SAFFORD PO 4502286737 | VAN ALLEN, WESLEY C. | 68.22% | 580192.42 | 0 | 580192.42 | 395813.9901 | 412416.66 | 412416.66 | 412416.66 | 0 | 580192.42 | 375891.77 | 0 | 375891.77 | 170268.72 |  |  |  | 170268.72 |  |  | 256437.72 |  |  |  | 256437.72 |  |  | 155978.94 | 0 | 68.22% |  | 119454.05 | 375891.77 | 204300.65 | 35.21% | 0 | 204300.65 | 35.21% | 0 |  | 139376.27 | 35.21% | 204300.65 | 35.21% | 184378.43 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 890920 - FREEPORT MCMORAN SAFFORD OPERATIONS | WATER | WATER EQUIPMENT SALES | 2019-10-24 | 2020-06-01 | 2019-10-24 | 2020-06-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 969286¦¦2020-03-31
FP | CJ | Yes | 969287 |  | BEMIS RD MA WTP LAYNEOX | CHESLEY, ANDREW J | 100% | 462000 | 0 | 462000 | 226237.18 | 226237.18 | 46200 | 43890 | 2310 | 226237.18 | 329806.5 | 0 | 329806.5 | 8433.3 | 5969.69 |  |  | 2463.61 |  |  | 182775.78 | 18284.68 |  |  | 47210.19 | 117280.91 |  | 43461.4 | 0 | 55.42% |  | 0 | 182775.78 | 132193.5 | 28.61% | 0 | 132193.5 | 28.61% | 0 |  | 43461.4 | 19.21% | 43461.4 | 19.21% | 235762.82 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 906323 - WATERLINE INDUSTRIES CORPORATION | WATER | WATER TREATMENT | 2019-10-28 | 2020-05-31 | 2019-10-28 | 2020-05-31 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 969287¦¦2020-03-31
FP | C | Yes | 969290 |  | NJAW MILL RD AST REFURB | RANFT, DONALD R | 100% | 104850 | 0 | 104850 | 104850 | 104850 | 104850 | 0 | 0 | 104850 | 66870 | 0 | 66870 | 1316.36 |  |  |  | 1316.36 |  |  | 68045.58 | 13767.18 | 3114.48 |  | 51163.92 |  |  | 36804.42 | 0 | 101.8% |  | 0 | 68045.58 | 37980 | 36.22% | 0 | 37980 | 36.22% | 0 |  | 36804.42 | 35.1% | 36804.42 | 35.1% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 895316 - NEW JERSEY AMERICAN WATER | WATER | WATER TREATMENT | 2019-10-28 | 2019-12-31 | 2019-10-28 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 969290¦¦2020-03-31
FP | CJ | Yes | 969523 |  | INDEPENDENCE A1 REHAB | SCHANAMAN, MIKE L. | 100% | 41890 | 0 | 41890 | 41890 | 41890 | 41890 | 0 | 0 | 41890 | 28458 | 0 | 28458 | [7 empty] | 36281.99 | 14061.42 | 7250.34 |  | 14970.23 |  |  | 5608.01 | 0 | 127.5% |  | 0 | 36281.99 | 13432 | 32.06% | 0 | 13432 | 32.06% | 0 |  | 5608.01 | 13.39% | 5608.01 | 13.39% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 947441 - INDEPENDENCE WATER & SANITATION DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2019-11-30 | 2019-10-28 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 969523¦¦2020-03-31
FP | CJ | Yes | 969524 |  | WELL 11 IWVWD | BRASHEAR, DAVID M | 100% | 68391 | 55674.77 | 124065.77 | 115491.72 | 115491.72 | 118194.08 | 0 | 0 | 115491.72 | 54334 | 40475.67 | 94809.67 | -23.84 | -44.13 |  |  | 20.29 |  |  | 73148.34 | 20463.13 | 5983.56 |  | 34976.84 | 11724.81 |  | 42343.38 | 0 | 77.15% |  | 0 | 73148.34 | 14057 | 20.55% | 15199.1 | 29256.1 | 23.58% | 0 |  | 42343.38 | 36.66% | 42343.38 | 36.66% | 8574.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892526 - INDIAN WELLS VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-10-24 | 2019-11-29 | 2019-10-24 | 2019-11-29 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 969524¦¦2020-03-31
TM | C | Yes | 969530 |  | AURORA PWM | MIGUEL, SEAN J. | 100% | 3416 | 6276 | 9692 | 10040 | 10040 | 10040 | 0 | 0 | 10040 | 2660 | 5098 | 7758 | [7 empty] | 9922.71 | 3844.47 | 1071.78 |  | 4709.46 | 297 |  | 117.29 | 0 | 127.9% |  | 0 | 9922.71 | 756 | 22.13% | 1178 | 1934 | 19.95% | 0 |  | 117.29 | 1.168% | 117.29 | 1.168% | -348 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 886666 - AURORA UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2019-12-31 | 2019-10-28 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 969530¦¦2020-03-31
FP | C | Yes | 969531 |  | PETERSON ST MARYS PUMP | BARNES, MATTHEW D | 100% | 10962 | 0 | 10962 | 10962 | 10962 | 10962 | 82 | 0 | 10962 | 7250 | 0 | 7250 | 1669.34 | 1066.43 | 365.37 |  | 237.54 |  |  | 6760.56 | 3933.38 | 1490.01 |  | 1337.17 |  |  | 4201.44 | 0 | 93.25% |  | 0 | 6760.56 | 3712 | 33.86% | 0 | 3712 | 33.86% | 0 |  | 4201.44 | 38.33% | 4201.44 | 38.33% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 968438 - PETERSON CONSTRUCTION COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2019-12-31 | 2019-10-28 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 969531¦¦2020-03-31
TM | CJ | Yes | 969743 |  | ABERDEEN PATE WELL 2 | WILLIAMS, DONALD G. | 100% | 1152 | 5400 | 6552 | 6019.61 | 6019.61 | 0 | 0 | 0 | 6019.61 | 930 | 4050 | 4980 | 2182.01 | 1203.08 | 300.9 |  | 678.03 |  |  | 4863.21 | 2361.15 | 736.39 |  | 1765.67 |  |  | 1156.4 | 0 | 97.65% |  | 0 | 4863.21 | 222 | 19.27% | 1350 | 1572 | 23.99% | 1350 | 1350 | 1156.4 | 19.21% | 1156.4 | 19.21% | 532.39 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 885855 - ABERDEEN PATE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-10-30 | 2019-11-30 | 2019-10-30 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 969743¦¦2020-03-31
FP | CJ | Yes | 969751 |  | TIM HILD DEWATERING | COMBS, TAYLOR E. | 100% | 83095 | 0 | 83095 | 83095 | 83095 | 83095 | 0 | 0 | 83095 | 64570 | 0 | 64570 | 0 |  |  |  | 0 |  |  | 53155.6 | 17392.13 | 11721.41 |  | 24042.06 |  |  | 29939.4 | 0 | 82.32% |  | 0 | 53155.6 | 18525 | 22.29% | 0 | 18525 | 22.29% | 0 |  | 29939.4 | 36.03% | 29939.4 | 36.03% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 969364 - TANDEM RESOURCES | WATER | WATER SUPPLY | 2019-10-28 | 2019-11-30 | 2019-10-28 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 969751¦¦2020-03-31
TM | CJ | Yes | 969752 |  | BEVERLY HILLS STATION 8 | GRACE, GARY L. | 100% | 16375 | 0 | 16375 | 16375.1 | 16375.1 | 16386.98 | 0 | 0 | 16375.1 | 11301 | 0 | 11301 | 517.13 |  |  |  | 517.13 |  |  | 10375.13 | 5799.64 | 926.47 |  | 3649.02 |  |  | 5999.97 | 0 | 91.81% |  | 0 | 10375.13 | 5074 | 30.99% | 0 | 5074 | 30.99% | 0 |  | 5999.97 | 36.64% | 5999.97 | 36.64% | -0.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878627 - BEVERLY HILLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-30 | 2020-02-01 | 2019-10-30 | 2020-02-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 969752¦¦2020-03-31
TM | C | Yes | 969754 |  | CROSSETT WATER COMMISSION HIGH | BURGE, EVERETT E. | 100% | 18400 | 0 | 18400 | 16852.58 | 16852.58 | 18200.77 | 0 | 0 | 16852.58 | 15350 | 0 | 15350 | 0 |  |  |  | 0 |  |  | 12933.94 | 5238.3 | 1827.26 |  | 5868.38 |  |  | 3918.64 | 0 | 84.26% |  | 0 | 12933.94 | 3050 | 16.58% | 0 | 3050 | 16.58% | 0 |  | 3918.64 | 23.25% | 3918.64 | 23.25% | 1547.42 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 889155 - CROSSETT WATER COMMISSION | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2020-04-24 | 2019-10-28 | 2020-04-24 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 969754¦¦2020-03-31
FP | LJ | Yes | 969759 |  | LINCOLN NEW COLLECTOR WELL | HARTMAN, MICHAEL | 59.86% | 2278844 | 0 | 2278844 | 1364036.4543 | 1343720 | 1343720 | 199359 | 134372 | 2278844 | 1405867.81 | 0 | 1405867.81 | 157692.83 | 86293.4 | 19011.62 | 2835.56 | 48108.73 | 1443.52 |  | 841503.5 | 321454.09 | 125924.3 | 7472.57 | 377244.92 | 9407.62 |  | 502216.5 | 0 | 59.86% |  | 564364.5 | 1405868 | 872976.19 | 38.31% | 0 | 872976.19 | 38.31% | 0 |  | 522532.95 | 38.31% | 872976 | 38.31% | 914807.55 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878712 - BOWEN ENGINEERING CORPORATION | WATER | WATER SUPPLY | 2019-10-01 | 2020-06-30 | 2019-10-01 | 2020-06-30 | SUBCONTRACTOR | PRIVATE | DESIGN/BUILD | 969759¦¦2020-03-31
FP | LJ | Yes | 969767 |  | JG BOSWELL S239 NEW WELL | TRAMMELL, DUANE R. | 100% | 795005 | 0 | 795005 | 828813.5 | 820627.5 | 820627.5 | 0 | 0 | 828813.5 | 634378.5 | 0 | 634378.5 | 44465.37 | 20513.49 | 10808.33 |  | 11623.55 | 1520 |  | 718782.21 | 179020.84 | 133642.87 |  | 390362.36 | 15756.14 |  | 101845.29 | 0 | 113.3% |  | 0 | 718782.21 | 160626.5 | 20.2% | 0 | 160626.5 | 20.2% | 0 |  | 110031.29 | 13.28% | 110031.29 | 13.28% | -33808.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892822 - JG BOSWELL COMPANY | WATER | WATER SUPPLY | 2019-10-23 | 2020-03-15 | 2019-10-23 | 2020-03-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 969767¦¦2020-03-31
UP | C | Yes | 969772 |  | CORYDON PWM | MIGUEL, SEAN J. | 100% | 750 | 4162 | 4912 | 6882 | 6882 | 6882 | 0 | 0 | 6882 | 0 | 3121 | 3121 | [7 empty] | 5118.82 | 2318.28 | 477.84 |  | 2322.7 |  |  | 1763.18 | 0 | 164% |  | 0 | 5118.82 | 750 | 100% | 1041 | 1791 | 36.46% | 0 |  | 1763.18 | 25.62% | 1763.18 | 25.62% | -1970 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889020 - CORYDON, IN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2019-12-31 | 2019-10-28 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 969772¦¦2020-03-31
TM | C | Yes | 969926 |  | AK WATERLINE 2 PUMPHOUSE | BARNES, MATTHEW D | 100% | 25000 | 61090 | 86090 | 86090 | 86090 | 86090 | 0 | 0 | 86090 | 17500 | 42763 | 60263 | 1.57 | 1.57 | [5 empty] | 53288.86 | 9007.25 | 3734.24 |  | 33527.66 | 7019.71 |  | 32801.14 | 0 | 88.43% |  | 0 | 53288.86 | 7500 | 30% | 18327 | 25827 | 30% | 0 |  | 32801.14 | 38.1% | 32801.14 | 38.1% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-10-30 | 2019-12-31 | 2019-10-30 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 969926¦¦2020-03-31
TM | C | Yes | 969927 |  | NORTHAMPTON NY WELL 4 REHAB | CROOK, CHARLES M | 100% | 19370 | 0 | 19370 | 25880 | 25880 | 25880 | 0 | 0 | 25880 | 15370 | 0 | 15370 | [7 empty] | 18795.6 | 9925.99 | 2200.93 |  | 6668.68 |  |  | 7084.4 | 0 | 122.3% |  | 0 | 18795.6 | 4000 | 20.65% | 0 | 4000 | 20.65% | 0 |  | 7084.4 | 27.37% | 7084.4 | 27.37% | -6510 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 968744 - NORTHAMPTON, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-30 | 2019-11-15 | 2019-10-30 | 2019-11-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 969927¦¦2020-03-31
FP | C | Yes | 969928 |  | LOOGOOTEE WHPP | WILLIAMS, DONALD G. | 100% | 2100 | 0 | 2100 | 2150 | 2150 | 2150 | 0 | 0 | 2150 | 600 | 0 | 600 | 0 |  |  |  | 0 |  |  | 728.07 | 563.52 | 121.92 |  | 42.63 |  |  | 1421.93 | 0 | 121.3% |  | 0 | 728.07 | 1500 | 71.43% | 0 | 1500 | 71.43% | 0 |  | 1421.93 | 66.14% | 1421.93 | 66.14% | -50 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 893900 - LOOGOOTEE, IN, CITY OF | WATER | WATER SUPPLY | 2019-10-23 | 2019-12-31 | 2019-10-23 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 969928¦¦2020-03-31
FP | CJ | Yes | 969930 |  | ADM REHAB TREATMENT 9 WELLS | WHITE, CATHLEEN R | 100% | 164920 | 0 | 164920 | 128997 | 128997 | 128997 | 0 | 0 | 128997 | 86881 | 0 | 86881 | 0 |  |  |  | 0 |  |  | 98862.1 | 49168.83 | 10130.51 |  | 37672.76 | 1890 |  | 30134.9 | 0 | 113.8% |  | 0 | 98862.1 | 78039 | 47.32% | 0 | 78039 | 47.32% | 0 |  | 30134.9 | 23.36% | 30134.9 | 23.36% | 35923 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 885915 - ADM QUINCY | WATER | WATER SUPPLY | 2019-10-30 | 2019-12-31 | 2019-10-30 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 969930¦¦2020-03-31
TM | C | Yes | 969931 |  | RESERVOIR AT WELL 1 NEWD | BRASHEAR, DAVID M | 100% | 10490.95 | 0 | 10490.95 | 10490.96 | 10490.96 | 10688.52 | 0 | 0 | 10490.96 | 7949 | 0 | 7949 | [7 empty] | 7064.83 | 2266.89 | 277.37 |  | 4520.57 |  |  | 3426.13 | 0 | 88.88% |  | 0 | 7064.83 | 2541.95 | 24.23% | 0 | 2541.95 | 24.23% | 0 |  | 3426.13 | 32.66% | 3426.13 | 32.66% | -0.01 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 170779 - NORTH EDWARDS WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-10-30 | 2019-11-18 | 2019-10-30 | 2019-11-29 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 969931¦¦2020-03-31
TM | C | Yes | 969932 |  | TOPA TOPA WEST WELL | SEIDEN, ANDREW L. | 100% | 7200 | 0 | 7200 | 7200 | 7200 | 7200 | 0 | 0 | 7200 | 5400 | 0 | 5400 | [7 empty] | 4097.09 | 1629.23 | 768.18 |  | 1699.68 |  |  | 3102.91 | 0 | 75.87% |  | 0 | 4097.09 | 1800 | 25% | 0 | 1800 | 25% | 0 |  | 3102.91 | 43.1% | 3102.91 | 43.1% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878563 - TOPA TOPA RANCH & NURSERY LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-25 | 2019-12-31 | 2019-10-25 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 969932¦¦2020-03-31
FP | CJ | Yes | 969940 |  | PEMBROKE MA WTP LAYNEOX | MCCARTNEY, JEFFREY C | 100% | 162950 | 16615 | 179565 | 133755.56 | 133755.56 | 77565.25 | 73686.99 | 3878.26 | 133755.56 | 114857.17 | 10170 | 125027.17 | 90196.86 | 1511.68 |  |  | 87834.77 | 850.41 |  | 108060.39 | 8709.18 | 7.91 |  | 88866.89 | 10476.41 |  | 25695.17 | 0 | 86.43% |  | 0 | 108060.39 | 48092.83 | 29.51% | 6445 | 54537.83 | 30.37% | 6445 |  | 25695.17 | 19.21% | 25695.17 | 19.21% | 45809.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 969686 - HART ENGINEERING | WATER | WATER TREATMENT | 2019-10-29 | 2019-12-31 | 2019-10-29 | 2019-12-31 | SUBCONTRACTOR | PUBLIC | COST REIMBURSIBLE | 969940¦¦2020-03-31
TM | C | Yes | 970037 |  | PEORIA W214 MOTOR WARRANTY | VAN ALLEN, WESLEY C. | 100% |  |  |  | 9694.77 | 9694.77 | 9842.53 | 0 | 0 | 9694.77 | 1335 | 0 | 1335 | -0.02 | -0.02 |  |  | 0 |  |  | 34399.24 | 7178.71 | 4274.17 |  | 6711.76 | 16234.6 |  | 0 | 24704.47 | 2577% |  | 0 | 34399.24 | -1335 |  | 0 | -1335 |  | 0 |  | -24704.47 | -254.8% | -24704.47 | -254.8% | -9694.77 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 896199 - PEORIA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-30 | 2019-11-05 | 2019-10-30 | 2019-11-05 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 970037¦¦2020-03-31
TM | C | Yes | 970038 |  | PRESCOTT AR CITY OF HIGH | BURGE, EVERETT E. | 100% | 31500 | 0 | 31500 | 22709.46 | 22709.46 | 24866.87 | 0 | 0 | 22709.46 | 25200 | 0 | 25200 | 2822.98 |  |  |  | 2822.98 |  |  | 18924.83 | 7349.72 | 1285.27 |  | 10289.84 |  |  | 3784.63 | 0 | 75.1% |  | 0 | 18924.83 | 6300 | 20% | 0 | 6300 | 20% | 0 |  | 3784.63 | 16.67% | 3784.63 | 16.67% | 8790.54 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 896566 - PRESCOTT, AR, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2019-02-20 | 2019-10-28 | 2019-02-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 970038¦¦2020-03-31
FP | CJ | Yes | 970039 |  | HOLCIM NO 3 WATER WELL REHAB | PARSLEY, TRISTAN S | 100% | 84055 | 0 | 84055 | 88935.75 | 88935.75 | 88935.75 | 84053.75 | 0 | 88935.75 | 56880 | 0 | 56880 | 3462.23 | 866.67 | 323.67 |  | 2271.89 |  |  | 57157.22 | 27139.94 | 8466.31 |  | 21550.97 |  |  | 31778.53 | 0 | 100.5% |  | 0 | 57157.22 | 27175 | 32.33% | 0 | 27175 | 32.33% | 0 |  | 31778.53 | 35.73% | 31778.53 | 35.73% | -4880.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 892175 - HOLCIM, INC | WATER | WATER REPAIR & INSTALLATION | 2019-10-24 | 2019-12-31 | 2019-10-24 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 970039¦¦2020-03-31
TM | LJ | Yes | 970504 |  | OMU NEW WELLS | WILLIAMS, DONALD G. | 63.18% | 531172 | 0 | 531172 | 354041.0012 | 205862.42 | 205862.42 | 146229.67 | 0 | 560409 | 423347.7 | 0 | 423347.7 | 120103.18 | 23838.8 | 14444.64 |  | 81819.74 |  |  | 285556.9 | 41213.45 | 20336.07 | 58.32 | 223949.06 |  |  | 0 | 79694.48 | 67.45% |  | 166449.1 | 452006 | 107824.3 | 20.3% | 0 | 107824.3 | 20.3% | 0 |  | 68484.1 | 19.34% | 108403 | 19.34% | 177131 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895920 - OWENSBORO MUNICIPAL UTILITIES | WATER | WATER SUPPLY | 2019-10-10 | 2020-01-30 | 2019-10-20 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 970504¦¦2020-03-31
FP | C | Yes | 970681 |  | BPU NEARMAN PUMP REPAIRS | WARTICK, LOGAN M | 100% | 24387 | 57331 | 81718 | 78068 | 78068 | 78068 | 0 | 0 | 78068 | 20729 | 42921.16 | 63650.16 | -0.01 |  |  |  | -0.01 |  |  | 51860.02 | 9863.64 | 6110.14 |  | 35886.24 |  |  | 26207.98 | 0 | 81.48% |  | 0 | 51860.02 | 3658 | 15% | 14409.84 | 18067.84 | 22.11% | 0 |  | 26207.98 | 33.57% | 26207.98 | 33.57% | 3650 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 887355 - BPU | WATER | WATER REPAIR & INSTALLATION | 2019-11-01 | 2020-02-01 | 2019-11-01 | 2020-02-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 970681¦¦2020-03-31
FP | CJ | Yes | 970682 |  | PIKE WATER NEW WELL 6 | BARNES, MATTHEW D | 100% | 280500 | 0 | 280500 | 167600.66 | 167600.66 | 117352.42 | 0 | 9388.19 | 167600.66 | 232977 | 0 | 232977 | 51758.84 | 17459.55 | 15038.46 |  | 13298.33 | 5962.5 |  | 135403.66 | 41014.51 | 31061.6 |  | 57365.05 | 5962.5 |  | 32197 | 0 | 58.12% |  | 0 | 135403.66 | 47523 | 16.94% | 0 | 47523 | 16.94% | 0 |  | 32197 | 19.21% | 32197 | 19.21% | 112899.34 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 896316 - PIKE WATER, INC | WATER | WATER SUPPLY | 2019-10-17 | 2020-05-08 | 2019-10-30 | 2020-05-08 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 970682¦¦2020-03-31
TM | C | Yes | 971107 |  | BUTLER CO HSP 2 | BARNES, MATTHEW D | 100% | 1100 | 32240 | 33340 | 33340 | 33340 | 33340 | 0 | 0 | 33340 | 700 | 24180 | 24880 | 15.6 | 1.52 |  |  | 14.08 |  |  | 30954.31 | 12109.34 | 3804.93 |  | 15040.04 |  |  | 2385.69 | 0 | 124.4% |  | 0 | 30954.31 | 400 | 36.36% | 8060 | 8460 | 25.37% | 0 |  | 2385.69 | 7.156% | 2385.69 | 7.156% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 969443 - BUTLER, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2019-10-29 | 2019-11-30 | 2019-10-29 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 971107¦¦2020-03-31
UP | C | Yes | 971108 |  | NICHOLASVILLE PMS | MIGUEL, SEAN J. | 100% | 3420 | 0 | 3420 | 3420 | 3420 | 3420 | 0 | 0 | 3420 | 2620 | 0 | 2620 | 224.19 |  |  |  | 224.19 |  |  | 4413.13 | 1774.33 | 376.02 |  | 2262.78 |  |  | 0 | 993.13 | 168.4% |  | 0 | 4413.13 | 800 | 23.39% | 0 | 800 | 23.39% | 0 |  | -993.13 | -29.04% | -993.13 | -29.04% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895388 - NICHOLASVILLE, KY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-01 | 2019-12-31 | 2019-11-01 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 971108¦¦2020-03-31
FP | CJ | Yes | 971109 |  | MOSAIC FERTLIZER LLC | MARTINEZ, MIGUEL E | 100% | 27924 | 0 | 27924 | 27365.52 | 27365.52 | 27365.52 | 0 | 0 | 27365.52 | 19381 | 0 | 19381 | [7 empty] | 10060.93 | 4181.91 | 3475.69 |  | 2403.33 |  |  | 17304.59 | 0 | 51.91% |  | 0 | 10060.93 | 8543 | 30.59% | 0 | 8543 | 30.59% | 0 |  | 17304.59 | 63.24% | 17304.59 | 63.24% | 558.48 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895011 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-10-31 | 2019-11-30 | 2019-10-31 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 971109¦¦2020-03-31
FP | C | Yes | 971111 |  | CONTINENTAL TIRE FIRE PUMP | PARSLEY, TRISTAN S | 100% | 5000 | 0 | 5000 | 11201.1 | 11201.1 | 11201.1 | 0 | 0 | 11201.1 | 3325 | 0 | 3325 | [7 empty] | 6143.43 | 3094.8 | 724.89 |  | 1583.74 | 740 |  | 5057.67 | 0 | 184.8% |  | 0 | 6143.43 | 1675 | 33.5% | 0 | 1675 | 33.5% | 0 |  | 5057.67 | 45.15% | 5057.67 | 45.15% | -6201.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 888945 - CONTINENTAL TIRE | WATER | WATER REPAIR & INSTALLATION | 2019-10-28 | 2020-02-29 | 2019-10-28 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 971111¦¦2020-03-31
TM | CJ | Yes | 971742 |  | WESTERN LEWIS BP | MIGUEL, SEAN J. | 100% | 1150 | 0 | 1150 | 1462 | 1462 | 1462 | 0 | 0 | 1462 | 780 | 0 | 780 | 581.39 | 369.29 | 105.06 |  | 107.04 |  |  | 6653.31 | 2786.63 | 686.14 |  | 2767.14 | 413.4 |  | 0 | 5191.31 | 853% |  | 0 | 6653.31 | 370 | 32.17% | 0 | 370 | 32.17% | 0 |  | -5191.31 | -355.1% | -5191.31 | -355.1% | -312 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 900106 - WESTERN LEWIS RECTORVILLE | WATER | WATER REPAIR & INSTALLATION | 2019-11-04 | 2019-12-31 | 2019-11-04 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 971742¦¦2020-03-31
TM | CJ | Yes | 971745 |  | CYNTHIANA RWP 1 | MIGUEL, SEAN J. | 100% | 3000 | 32450 | 35450 | 21779.98 | 21779.98 | 5500 | 0 | 0 | 21779.98 | 2160 | 24369 | 26529 | 851.68 | 588.96 | 47.46 |  | 215.26 |  |  | 17595.93 | 7640.71 | 1816.7 |  | 8138.52 |  |  | 4184.05 | 0 | 66.33% |  | 0 | 17595.93 | 840 | 28% | 8081 | 8921 | 25.17% | 8081 |  | 4184.05 | 19.21% | 4184.05 | 19.21% | 13670.02 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889252 - CYNTHIANA, KY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-01 | 2019-12-31 | 2019-11-01 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 971745¦¦2020-03-31
TM | C | Yes | 971746 |  | DANVILLE HSP | MIGUEL, SEAN J. | 100% | 1500 | 9877 | 11377 | 13829 | 13829 | 13829 | 0 | 0 | 13829 | 1050 | 7919 | 8969 | 7685.3 | 1023.53 | 293.42 |  | 2654.47 | 3713.88 |  | 10933.67 | 2825.22 | 703.77 |  | 3305.8 | 4098.88 |  | 2895.33 | 0 | 121.9% |  | 0 | 10933.67 | 450 | 30% | 1958 | 2408 | 21.17% | 1958 |  | 2895.33 | 20.94% | 2895.33 | 20.94% | -2452 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889323 - DANVILLE WATER UTILITY | WATER | WATER REPAIR & INSTALLATION | 2019-11-04 | 2019-12-31 | 2019-11-04 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 971746¦¦2020-03-31
FP | C | Yes | 971747 |  | INGEVITY NEW PUMP BOWL | ANDERSON, STEPHEN P. | 100% | 4900 | 0 | 4900 | 4900 | 4900 | 4900 | 0 | 0 | 4900 | 2995 | 0 | 2995 | [7 empty] | 2822.4 |  |  |  | 2822.4 |  |  | 2077.6 | 0 | 94.24% |  | 0 | 2822.4 | 1905 | 38.88% | 0 | 1905 | 38.88% | 0 |  | 2077.6 | 42.4% | 2077.6 | 42.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 892547 - INGEVITY SOUTH CAROLINA, LLC | WATER | WATER EQUIPMENT SALES | 2019-11-04 | 2019-11-22 | 2019-11-04 | 2019-11-22 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 971747¦¦2020-03-31
TM | C | Yes | 971748 |  | HOBART NY HIGHLIFT PUMP | CROOK, CHARLES M | 100% | 30770 | 0 | 30770 | 30770 | 30770 | 30770 | 0 | 0 | 30770 | 24770 | 0 | 24770 | [7 empty] | 16642.51 | 6028.1 | 691.52 |  | 9922.89 |  |  | 14127.49 | 0 | 67.19% |  | 0 | 16642.51 | 6000 | 19.5% | 0 | 6000 | 19.5% | 0 |  | 14127.49 | 45.91% | 14127.49 | 45.91% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 892164 - HOBART, NY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-04 | 2019-12-12 | 2019-11-04 | 2019-12-12 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 971748¦¦2020-03-31
FP | C | Yes | 971749 |  | INGEVITY NEW MOTOR | ANDERSON, STEPHEN P. | 100% | 18525 | 0 | 18525 | 18525 | 18525 | 18525 | 0 | 0 | 18525 | 12131 | 0 | 12131 | [7 empty] | 11998.08 |  |  |  | 11998.08 |  |  | 6526.92 | 0 | 98.9% |  | 0 | 11998.08 | 6394 | 34.52% | 0 | 6394 | 34.52% | 0 |  | 6526.92 | 35.23% | 6526.92 | 35.23% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 892547 - INGEVITY SOUTH CAROLINA, LLC | WATER | WATER EQUIPMENT SALES | 2019-11-04 | 2019-11-22 | 2019-11-04 | 2019-11-22 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 971749¦¦2020-03-31
TM | C | Yes | 972044 |  | WELL 12 GOLF COURSE NEEDLES | BRASHEAR, DAVID M | 100% | 13819 | 47478.76 | 61297.76 | 61290.41 | 61290.41 | 63310.73 | 0 | 0 | 61290.41 | 10341 | 35646.53 | 45987.53 | 1.74 |  |  |  | 1.74 |  |  | 65819.84 | 17717.27 | 4150.91 |  | 39560.66 | 4391 |  | 0 | 4529.43 | 143.1% |  | 0 | 65819.84 | 3478 | 25.17% | 11832.23 | 15310.23 | 24.98% | 0 |  | -4529.43 | -7.39% | -4529.43 | -7.39% | 7.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 888536 - CITY OF NEEDLES | WATER | WATER REPAIR & INSTALLATION | 2019-11-05 | 2019-11-29 | 2019-11-05 | 2019-11-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 972044¦¦2020-03-31
FP | C | Yes | 972045 |  | AMERICAN YEAST | ANDERSON, STEPHEN P. | 100% | 13600 | 0 | 13600 | 13600 | 13600 | 13600 | 0 | 0 | 13600 | 9325 | 0 | 9325 | 815.68 | 409.83 | 102.03 |  | 303.82 |  |  | 11031.09 | 2685.84 | 797.47 |  | 7547.78 |  |  | 2568.91 | 0 | 118.3% |  | 0 | 11031.09 | 4275 | 31.43% | 0 | 4275 | 31.43% | 0 |  | 2568.91 | 18.89% | 2568.91 | 18.89% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 886250 - AMERICAN YEAST | WATER | WATER REPAIR & INSTALLATION | 2019-11-05 | 2019-12-27 | 2019-11-05 | 2019-12-27 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 972045¦¦2020-03-31
FP | CJ | Yes | 972058 |  | REWAK WELL AST UPGRADE | CHESLEY, ANDREW J | 100% | 59325 | 0 | 59325 | 24553.94 | 24553.94 | 9990 | 0 | 499.5 | 24553.94 | 40779.8 | 0 | 40779.8 | 2039.42 | 919.48 |  |  | 1119.94 |  |  | 19836.99 | 4235.27 |  |  | 10501.72 | 5100 |  | 4716.95 | 0 | 48.64% |  | 0 | 19836.99 | 18545.2 | 31.26% | 0 | 18545.2 | 31.26% | 0 |  | 4716.95 | 19.21% | 4716.95 | 19.21% | 34771.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 962933 - O & G BHD JV | WATER | WATER TREATMENT | 2019-11-05 | 2020-01-31 | 2019-11-05 | 2020-01-31 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 972058¦¦2020-03-31
FP | C | Yes | 972623 |  | MORTON WELL 7 MOTOR REPLACE | WHITE, CATHLEEN R | 100% | 24194 | 0 | 24194 | 24194 | 24194 | 24194 | 0 | 0 | 24194 | 16885 | 0 | 16885 | [7 empty] | 10478.23 | 7040.26 | 963.5 |  | 2474.47 |  |  | 13715.77 | 0 | 62.06% |  | 0 | 10478.23 | 7309 | 30.21% | 0 | 7309 | 30.21% | 0 |  | 13715.77 | 56.69% | 13715.77 | 56.69% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 895001 - MORTON, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-05 | 2019-12-31 | 2019-11-05 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 972623¦¦2020-03-31
FP | CJ | Yes | 972627 |  | EMERALD GLEN HOA | SCHANAMAN, MIKE L. | 100% | 5599 | 0 | 5599 | 18695.23 | 18695.23 | 19024 | 0 | 0 | 18695.23 | 4129 | 0 | 4129 | 3086.56 | 1815.76 | 312.85 |  | 957.95 |  |  | 11490.45 | 4610.87 | 884.92 |  | 5994.66 |  |  | 7204.78 | 0 | 278.3% |  | 0 | 11490.45 | 1470 | 26.25% | 0 | 1470 | 26.25% | 0 |  | 7204.78 | 38.54% | 7204.78 | 38.54% | -13096.23 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 972582 - EMERALD GLEN OF LOVELAND COMMUNITY ASSOC | WATER | WATER REPAIR & INSTALLATION | 2019-11-05 | 2019-12-31 | 2019-11-05 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 972627¦¦2020-03-31
FP | C | Yes | 973006 |  | WFEC MOORELAND OK | WARTICK, LOGAN M | 100% | 26424 | 0 | 26424 | 45645 | 45645 | 45645 | 0 | 0 | 45645 | 19818 | 0 | 19818 | [7 empty] | 33569.06 | 8941.85 | 4209.69 |  | 15906.28 | 4511.24 |  | 12075.94 | 0 | 169.4% |  | 0 | 33569.06 | 6606 | 25% | 0 | 6606 | 25% | 0 |  | 12075.94 | 26.46% | 12075.94 | 26.46% | -19221 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | WICHITA - WA | 900096 - WESTERN FARMERS ELECTRIC COOPERATIVE | WATER | WATER REPAIR & INSTALLATION | 2019-11-07 | 2019-12-15 | 2019-11-07 | 2019-12-15 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 973006¦¦2020-03-31
FP | C | Yes | 973165 |  | ROCKFORD IL UW31 BOOSTER | SNELTEN, BRIAN M | 100% | 10632 | 16563 | 27195 | 27067 | 27067 | 27067 | 0 | 0 | 27067 | 7232 | 11064 | 18296 | -440.5 |  |  |  | -440.5 |  |  | 29820.6 | 18480.89 | 1879.45 |  | 9460.26 |  |  | 0 | 2753.6 | 163% |  | 0 | 29820.6 | 3400 | 31.98% | 5499 | 8899 | 32.72% | 0 |  | -2753.6 | -10.17% | -2753.6 | -10.17% | 128 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878821 - ROCKFORD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-07 | 2019-12-31 | 2019-11-07 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 973165¦¦2020-03-31
FP | C | Yes | 973166 |  | LONESTAR NGL WELL 2 REHAB | LOPEZ-VASQUEZ, JUAN C. | 100% | 72720 | 5225 | 77945 | 77945 | 77945 | 77945 | 0 | 0 | 77945 | 52674 | 2677 | 55351 | 953.57 | 331.77 | 469.88 |  | 151.92 |  |  | 31366.31 | 15762.61 | 5999.27 |  | 9604.43 |  |  | 46578.69 | 0 | 56.67% |  | 0 | 31366.31 | 20046 | 27.57% | 2548 | 22594 | 28.99% | 2548 |  | 46578.69 | 59.76% | 46578.69 | 59.76% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 893879 - LONE STAR NGL REFINERY, LLC | WATER | WATER REPAIR & INSTALLATION | 2019-11-07 | 2019-11-30 | 2019-11-07 | 2019-11-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 973166¦¦2020-03-31
TM | C | Yes | 973167 |  | LOOGOOTEE WHP UPDATE | GAMBLE, BRAD F. | 100% | 9400 | 0 | 9400 | 9350 | 9350 | 9350 | 0 | 0 | 9350 | 6325 | 0 | 6325 | 0.07 | 0.07 | [5 empty] | 3853.67 | 3800.93 |  |  | 52.74 |  |  | 5496.33 | 0 | 60.93% |  | 0 | 3853.67 | 3075 | 32.71% | 0 | 3075 | 32.71% | 0 |  | 5496.33 | 58.78% | 5496.33 | 58.78% | 50 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 893900 - LOOGOOTEE, IN, CITY OF | WATER | WATER SUPPLY | 2019-11-06 | 2020-01-30 | 2019-11-06 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 973167¦¦2020-03-31
FP | CJ | Yes | 973168 |  | MOSAIC PLANT CITY DW 1 SPARE | MARTINEZ, MIGUEL E | 100% | 54331 | 0 | 54331 | 53244.38 | 53244.38 | 53244.38 | 0 | 0 | 53244.38 | 33541 | 0 | 33541 | -0.53 |  |  |  | -0.53 |  |  | 33480.91 |  |  |  | 33480.91 |  |  | 19763.47 | 0 | 99.82% |  | 0 | 33480.91 | 20790 | 38.27% | 0 | 20790 | 38.27% | 0 |  | 19763.47 | 37.12% | 19763.47 | 37.12% | 1086.62 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895011 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-11-07 | 2019-12-31 | 2019-11-07 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 973168¦¦2020-03-31
TM | C | Yes | 973209 |  | BOOSTER 1 PLANT 22 | BRASHEAR, DAVID M | 100% | 2520 | 20165.05 | 22685.05 | 22071.39 | 22071.39 | 23023.28 | 0 | 0 | 22071.39 | 1846 | 13537.63 | 15383.63 | 469.7 | 268.63 | 67.24 |  | 133.83 |  |  | 17375.96 | 3426.13 | 141.44 |  | 13089.39 | 719 |  | 4695.43 | 0 | 113% |  | 0 | 17375.96 | 674 | 26.75% | 6627.42 | 7301.42 | 32.19% | 3149.6 |  | 4695.43 | 21.27% | 4695.43 | 21.27% | 613.66 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878948 - HESPERIA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-06 | 2019-12-31 | 2019-11-06 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | MATERIALS MANAGEMENT | 973209¦¦2020-03-31
FP | C | Yes | 973753 |  | CALLEGUAS WATER WELL 13 MOTOR | SEIDEN, ANDREW L. | 100% | 9441 | 9236.68 | 18677.68 | 16968.77 | 16968.77 | 16968.77 | 0 | 0 | 16968.77 | 6751 | 7485.06 | 14236.06 | 0 |  |  |  | 0 |  |  | 12801.85 | 4704.74 | 1705.44 |  | 2824.67 | 3567 |  | 4166.92 | 0 | 89.93% |  | 0 | 12801.85 | 2690 | 28.49% | 1751.62 | 4441.62 | 23.78% | 1751.62 |  | 4166.92 | 24.56% | 4166.92 | 24.56% | 1708.91 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887781 - CALLEGUAS MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-11-08 | 2019-12-31 | 2019-11-08 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 973753¦¦2020-03-31
FP | CJ | Yes | 973754 |  | MARATHON REHABS | BARNES, MATTHEW D | 100% | 90600 | 74276 | 164876 | 123576 | 123576 | 123576 | 0 | 0 | 123576 | 54360 | 58266 | 112626 | 12100.2 | 6108.17 | 2418.21 |  | 3573.82 |  |  | 118676.52 | 46867.04 | 23562.05 |  | 48247.43 |  |  | 4899.48 | 0 | 105.4% |  | 0 | 118676.52 | 36240 | 40% | 16010 | 52250 | 31.69% | 12988 | 9729 | 4899.48 | 3.965% | 4899.48 | 3.965% | 41300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 894199 - MARATHON PETROLEUM CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-11-08 | 2019-12-31 | 2019-10-29 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 973754¦¦2020-03-31
FP | CJ | Yes | 973755 |  | MOSAIC PLANT CITY RECOVERY | MARTINEZ, MIGUEL E | 100% | 80598 | 0 | 80598 | 78986.04 | 78986.04 | 78986.04 | 0 | 0 | 78986.04 | 54075 | 0 | 54075 | [7 empty] | 52467.62 | 18039.74 | 9553.01 |  | 24874.87 |  |  | 26518.42 | 0 | 97.03% |  | 0 | 52467.62 | 26523 | 32.91% | 0 | 26523 | 32.91% | 0 |  | 26518.42 | 33.57% | 26518.42 | 33.57% | 1611.96 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895011 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-11-09 | 2019-12-31 | 2019-11-09 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 973755¦¦2020-03-31
FP | C | Yes | 973756 |  | SUEZ NICHOLS KIRBY PARK WELL 3 | CROOK, CHARLES M | 100% | 11445 | 0 | 11445 | 16225 | 16225 | 16225 | 0 | 0 | 16225 | 7945 | 0 | 7945 | [7 empty] | 8453.28 | 2458.18 | 1046.76 |  | 4948.34 |  |  | 7771.72 | 0 | 106.4% |  | 0 | 8453.28 | 3500 | 30.58% | 0 | 3500 | 30.58% | 0 |  | 7771.72 | 47.9% | 7771.72 | 47.9% | -4780 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 898467 - SUEZ | WATER | WATER REPAIR & INSTALLATION | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-11-08 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 973756¦¦2020-03-31
FP | C | Yes | 973757 |  | DOW EW3 RINGWOOD IL | SNELTEN, BRIAN M | 100% | 8508 | 0 | 8508 | 8508 | 8508 | 8535.8 | 0 | 0 | 8508 | 6152 | 0 | 6152 | [7 empty] | 5300.58 | 3614.36 | 734.42 |  | 951.8 |  |  | 3207.42 | 0 | 86.16% |  | 0 | 5300.58 | 2356 | 27.69% | 0 | 2356 | 27.69% | 0 |  | 3207.42 | 37.7% | 3207.42 | 37.7% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 321763 - ARCADIS US INC | WATER | WATER REPAIR & INSTALLATION | 2019-11-08 | 2019-11-28 | 2019-11-08 | 2019-11-28 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 973757¦¦2020-03-31
TM | C | Yes | 973758 |  | SCVWD CARNEGIE B19 | SEIDEN, ANDREW L. | 100% | 2651 | 0 | 2651 | 2650.73 | 2650.73 | 2790.09 | 0 | 0 | 2650.73 | 1972 | 0 | 1972 | [7 empty] | 542.47 | 256.83 | 11.7 |  | 273.94 |  |  | 2108.26 | 0 | 27.51% |  | 0 | 542.47 | 679 | 25.61% | 0 | 679 | 25.61% | 0 |  | 2108.26 | 79.54% | 2108.26 | 79.54% | 0.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878930 - SANTA CLARITA VALLEY WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2019-11-06 | 2019-11-09 | 2019-11-06 | 2019-11-09 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 973758¦¦2020-03-31
TM | CJ | Yes | 973759 |  | PAPAGO WELL GSWC APPLE VALLEY | BRASHEAR, DAVID M | 100% | 22461 | 37204.04 | 59665.04 | 59665.29 | 59665.29 | 60985.68 | 0 | 0 | 59665.29 | 17296 | 27970.99 | 45266.99 | 0 |  |  |  | 0 |  |  | 34929.23 | 9683.69 | 2463.68 |  | 21827.02 | 954.84 |  | 24736.06 | 0 | 77.16% |  | 0 | 34929.23 | 5165 | 23% | 9233.05 | 14398.05 | 24.13% | 0 |  | 24736.06 | 41.46% | 24736.06 | 41.46% | -0.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 891367 - GOLDEN STATE WATER CO APPLE VALLEY, CA | WATER | WATER REPAIR & INSTALLATION | 2019-11-08 | 2019-12-31 | 2019-11-08 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 973759¦¦2020-03-31
TM | C | Yes | 974262 |  | PIKE WATER FILTER MNT | BARNES, MATTHEW D | 100% | 39000 | 0 | 39000 | 10056 | 10056 | 10056 | 0 | 0 | 10056 | 23400 | 0 | 23400 | 811.49 | 0.01 |  |  | 811.48 |  |  | 11213.64 | 5958.7 | 1804.39 |  | 3450.55 |  |  | 0 | 1157.64 | 47.92% |  | 0 | 11213.64 | 15600 | 40% | 0 | 15600 | 40% | 0 |  | -1157.64 | -11.51% | -1157.64 | -11.51% | 28944 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 896316 - PIKE WATER, INC | WATER | WATER REPAIR & INSTALLATION | 2019-11-11 | 2019-12-31 | 2019-11-01 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 974262¦¦2020-03-31
FP | CJ | Yes | 974263 |  | FEDERAL EXPRESS | ANDERSON, STEPHEN P. | 100% | 600 | 0 | 600 | 600 | 600 | 0 | 0 | 0 | 600 | 172 | 0 | 172 | [7 empty] | 568.41 | 278.6 | 117.67 |  | 172.14 |  |  | 31.59 | 0 | 330.5% |  | 0 | 568.41 | 428 | 71.33% | 0 | 428 | 71.33% | 0 |  | 31.59 | 5.265% | 31.59 | 5.265% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 301778 - DO NOT USE FEDERAL EXPRESS PROPERTIES | WATER | WATER REPAIR & INSTALLATION | 2019-11-11 | 2020-01-24 | 2019-11-11 | 2020-01-24 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 974263¦¦2020-03-31
FP | CJ | Yes | 974264 |  | WARD 2 WATER WELL TESTS 2019 | LOPEZ-VASQUEZ, JUAN C. | 100% | 7267.5 | 1400 | 8667.5 | 9050 | 9050 | 9050 | 0 | 0 | 9050 | 4417 | 583 | 5000 | 4242.81 | 2280.34 | 927.51 |  | 1034.96 |  |  | 5849.33 | 3124.12 | 1307.8 |  | 1417.41 |  |  | 3200.67 | 0 | 117% |  | 0 | 5849.33 | 2850.5 | 39.22% | 817 | 3667.5 | 42.31% | 817 | 817 | 3200.67 | 35.37% | 3200.67 | 35.37% | -382.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 899839 - WARD 2 WATER WORKS | WATER | WATER REPAIR & INSTALLATION | 2019-11-11 | 2020-01-20 | 2019-11-11 | 2020-01-20 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 974264¦¦2020-03-31
TM | C | Yes | 974265 |  | GEORGIA POWER PLANT HATCH 2019 | PARSLEY, TRISTAN S | 100% | 12013 | 0 | 12013 | 14651.2 | 14651.2 | 14651.2 | 0 | 0 | 14651.2 | 8313 | 0 | 8313 | [7 empty] | 8145.16 | 4626.06 | 655.59 |  | 2863.51 |  |  | 6506.04 | 0 | 97.98% |  | 0 | 8145.16 | 3700 | 30.8% | 0 | 3700 | 30.8% | 0 |  | 6506.04 | 44.41% | 6506.04 | 44.41% | -2638.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 891173 - GEORGIA POWER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-11-02 | 2019-12-31 | 2019-11-04 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 974265¦¦2020-03-31
TM | LJ | Yes | 974315 |  | KINROSS ROUND MOUNTAIN 2019 | COMBS, TAYLOR E. | 100% | 998400 | 0 | 998400 | 915738.5366 | 915738.55 | 915738.55 | 0 | 0 | 915738.55 | 798113.53 | 0 | 798113.53 | 41772.34 | -0.03 |  |  | 617.37 | 41155 |  | 684978.76 | 197227.45 | 153846.38 |  | 292749.93 | 41155 |  | 230759.79 | 0 | 85.82% |  | 0.01 | 684978.77 | 200286.47 | 20.06% | 0 | 200286.47 | 20.06% | 0 |  | 230759.78 | 25.2% | 230759.78 | 25.2% | 82661.46 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 893187 - KINROSS ROUND MOUNTAIN GOLD CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-11-07 | 2019-12-31 | 2019-11-07 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 974315¦¦2020-03-31
TM | C | Yes | 974582 |  | BROOKS AND MATTHEW DAVIS MOTOR | BENNETT, MARK C. | 100% | 11150 | 0 | 11150 | 10400 | 10400 | 11180.02 | 0 | 0 | 10400 | 3500 | 0 | 3500 | [7 empty] | 2004.38 | 748.46 | 158.59 |  | 1097.33 |  |  | 8395.62 | 0 | 57.27% |  | 0 | 2004.38 | 7650 | 68.61% | 0 | 7650 | 68.61% | 0 |  | 8395.62 | 80.73% | 8395.62 | 80.73% | 750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887502 - BROOKS DAVIS | WATER | WATER EQUIPMENT SALES | 2019-11-11 | 2019-11-12 | 2019-11-11 | 2019-11-12 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 974582¦¦2020-03-31
FP | C | Yes | 974583 |  | IP RIVERDALE MISCELLANEOUS | PARSLEY, TRISTAN S | 100% | 29244 | 0 | 29244 | 29243.89 | 29243.89 | 29243.89 | 0 | 0 | 29243.89 | 16428 | 0 | 16428 | [7 empty] | 16654.43 | 1477.71 |  |  | 15176.72 |  |  | 12589.46 | 0 | 101.4% |  | 0 | 16654.43 | 12816 | 43.82% | 0 | 12816 | 43.82% | 0 |  | 12589.46 | 43.05% | 12589.46 | 43.05% | 0.11 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 878768 - INTERNATIONAL PAPER RIVERDALE | WATER | WATER REPAIR & INSTALLATION | 2019-11-12 | 2020-01-31 | 2019-11-12 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 974583¦¦2020-03-31
UP | C | Yes | 974584 |  | IAWC RICHMOND PWM | MIGUEL, SEAN J. | 100% | 1800 | 0 | 1800 | 1800 | 1800 | 1800 | 0 | 0 | 1800 | 1525 | 0 | 1525 | [7 empty] | 1576.22 | 605.09 | 211.62 |  | 759.51 |  |  | 223.78 | 0 | 103.4% |  | 0 | 1576.22 | 275 | 15.28% | 0 | 275 | 15.28% | 0 |  | 223.78 | 12.43% | 223.78 | 12.43% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878797 - INDIANA AMERICAN WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-11-12 | 2019-12-31 | 2019-11-12 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 974584¦¦2020-03-31
FP | C | Yes | 974586 |  | CARGILL WELL ABANDONMENTS | CROOK, CHARLES M | 100% | 45710 | 8585 | 54295 | 41350 | 41350 | 43831 | 43831 | 0 | 41350 | 37710 | 6500 | 44210 | 19755.36 | 10480.61 | 3391.94 |  | 5882.81 |  |  | 27066.07 | 12876.76 | 3826.98 |  | 10362.33 |  |  | 14283.93 | 0 | 61.22% |  | 0 | 27066.07 | 8000 | 17.5% | 2085 | 10085 | 18.57% | 2085 |  | 14283.93 | 34.54% | 14283.93 | 34.54% | 12945 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 973973 - MOODY AND ASSOCIATES INC | WATER | WATER REPAIR & INSTALLATION | 2019-11-12 | 2019-12-31 | 2019-11-12 | 2020-01-24 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 974586¦¦2020-03-31
FP | C | Yes | 974587 |  | IAWC WINCHESTER PWM | MIGUEL, SEAN J. | 100% | 2400 | 0 | 2400 | 2400 | 2400 | 2400 | 0 | 0 | 2400 | 1920 | 0 | 1920 | [7 empty] | 1911.12 | 801.8 | 256.13 |  | 853.19 |  |  | 488.88 | 0 | 99.54% |  | 0 | 1911.12 | 480 | 20% | 0 | 480 | 20% | 0 |  | 488.88 | 20.37% | 488.88 | 20.37% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878797 - INDIANA AMERICAN WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-11-12 | 2019-12-31 | 2019-11-12 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 974587¦¦2020-03-31
FP | C | Yes | 974590 |  | WHARTON NJ AST DEMISTER | RANFT, DONALD R | 100% | 6328.19 | 0 | 6328.19 | 5935 | 5935 | 6328.2 | 0 | 0 | 5935 | 3795 | 0 | 3795 | [7 empty] | 5055.4 | 493.5 |  |  | 4561.9 |  |  | 879.6 | 0 | 133.2% |  | 0 | 5055.4 | 2533.19 | 40.03% | 0 | 2533.19 | 40.03% | 0 |  | 879.6 | 14.82% | 879.6 | 14.82% | 393.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 973977 - GROUND WATER TREATMENT & TECHNOLOGY LLC | WATER | WATER TREATMENT | 2019-11-08 | 2019-12-31 | 2019-11-08 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 974590¦¦2020-03-31
FP | CJ | Yes | 974771 |  | MOSAIC PLANT CITY TEST PUMPING | MCCULLERS, BLAKE E. | 100% | 55380 | 0 | 55380 | 54272.4 | 54272.4 | 54272.4 | 0 | 0 | 54272.4 | 42004 | 0 | 42004 | -0.54 |  |  |  | -0.54 |  |  | 21329.88 | 11264.06 | 4482.35 |  | 5583.47 |  |  | 32942.52 | 0 | 50.78% |  | 0 | 21329.88 | 13376 | 24.15% | 0 | 13376 | 24.15% | 0 |  | 32942.52 | 60.7% | 32942.52 | 60.7% | 1107.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895011 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-11-13 | 2020-01-31 | 2019-11-13 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 974771¦¦2020-03-31
TM | C | Yes | 974964 |  | DUKE CAYUGA PUMP | MIGUEL, SEAN J. | 100% | 20225 | 9760 | 29985 | 29985 | 29985 | 29985 | 0 | 0 | 29985 | 16180 | 6832 | 23012 | [7 empty] | 28910.54 | 13271.32 | 2793.52 |  | 12845.7 |  |  | 1074.46 | 0 | 125.6% |  | 0 | 28910.54 | 4045 | 20% | 2928 | 6973 | 23.25% | 0 |  | 1074.46 | 3.583% | 1074.46 | 3.583% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879103 - DUKE ENERGY CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-11-13 | 2020-01-30 | 2019-11-13 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 974964¦¦2020-03-31
FP | CJ | Yes | 974965 |  | MSD NEW WELL 10 | WILLIAMS, DONALD G. | 100% | 178889.34 | 0 | 178889.34 | 178353 | 178353 | 178353 | 0 | 0 | 178353 | 143272.46 | 0 | 143272.46 | 25824.56 | 14788.59 | 5921.98 |  | 2008.99 | 3105 |  | 112934.96 | 42756.73 | 18926.97 |  | 40962.35 | 10288.91 |  | 65418.04 | 0 | 78.83% |  | 0 | 112934.96 | 35616.88 | 19.91% | 0 | 35616.88 | 19.91% | 0 |  | 65418.04 | 36.68% | 65418.04 | 36.68% | 536.34 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 893944 - METROPOLITAN SEWER DISTRICT | WATER | WATER SUPPLY | 2019-11-07 | 2020-01-30 | 2019-11-08 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 974965¦¦2020-03-31
TM | C | Yes | 975295 |  | ESSICK FARM MGMT LAGO MESSINA | SEIDEN, ANDREW L. | 100% | 7012 | 29579.18 | 36591.18 | 36555.18 | 36555.18 | 36955.31 | 0 | 0 | 36555.18 | 4997 | 23141.84 | 28138.84 | [7 empty] | 33641.71 | 7477.38 | 3114.91 |  | 21896.23 | 1153.19 |  | 2913.47 | 0 | 119.6% |  | 0 | 33641.71 | 2015 | 28.74% | 6437.34 | 8452.34 | 23.1% | 0 |  | 2913.47 | 7.97% | 2913.47 | 7.97% | 36 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 890432 - ESSICK FARM MANAGEMENT | WATER | WATER REPAIR & INSTALLATION | 2019-11-14 | 2019-12-31 | 2019-11-14 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 975295¦¦2020-03-31
FP | C | Yes | 975388 |  | BUNGE PWM | MIGUEL, SEAN J. | 100% | 2000 | 6875 | 8875 | 9475 | 9475 | 9475 | 0 | 0 | 9475 | 1400 | 5385 | 6785 | [7 empty] | 7476.3 | 3198.64 | 741.52 |  | 2917.34 | 618.8 |  | 1998.7 | 0 | 110.2% |  | 0 | 7476.3 | 600 | 30% | 1490 | 2090 | 23.55% | 0 |  | 1998.7 | 21.09% | 1998.7 | 21.09% | -600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 975084 - BUNGE NORTH AMERICA INC | WATER | WATER REPAIR & INSTALLATION | 2019-11-01 | 2019-12-31 | 2019-11-01 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 975388¦¦2020-03-31
TM | CJ | Yes | 975765 |  | COLLIER COUNTY LIVINGSTON ROAD | MARTINEZ, MIGUEL E | 100% | 84500 | 0 | 84500 | 29500 | 29500 | 29500 | 0 | 0 | 29500 | 64614 | 0 | 64614 | [7 empty] | 6275.5 | 3417.31 | 1672.08 |  | 1186.11 |  |  | 23224.5 | 0 | 9.712% |  | 0 | 6275.5 | 19886 | 23.53% | 0 | 19886 | 23.53% | 0 |  | 23224.5 | 78.73% | 23224.5 | 78.73% | 55000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878718 - CDM SMITH | WATER | WATER REPAIR & INSTALLATION | 2019-11-14 | 2020-01-31 | 2019-11-14 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 975765¦¦2020-03-31
TM | C | Yes | 976127 |  | GLASGOW BEAVER CREEK RWP 1 | MIGUEL, SEAN J. | 100% | 13375 | 8931 | 22306 | 22686 | 22686 | 22686 | 0 | 0 | 22686 | 9720 | 6620 | 16340 | 0.42 |  |  |  | 0.42 |  |  | 21250.24 | 7546.67 | 2419.26 |  | 10634.31 | 650 |  | 1435.76 | 0 | 130.1% |  | 0 | 21250.24 | 3655 | 27.33% | 2311 | 5966 | 26.75% | 0 |  | 1435.76 | 6.329% | 1435.76 | 6.329% | -380 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 891285 - GLASGOW WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-11-14 | 2019-12-31 | 2019-11-14 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 976127¦¦2020-03-31
FP | C | Yes | 976203 |  | EXMOOR CC WELL 2 PWM TESTING | KENNEDY, CHRISTOPHER C. | 100% | 1776 | 0 | 1776 | 1776 | 1776 | 1776 | 0 | 0 | 1776 | 1200 | 0 | 1200 | [7 empty] | 1314.61 | 920.16 | 166.95 |  | 227.5 |  |  | 461.39 | 0 | 109.6% |  | 0 | 1314.61 | 576 | 32.43% | 0 | 576 | 32.43% | 0 |  | 461.39 | 25.98% | 461.39 | 25.98% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 890509 - EXMOOR COUNTRY CLUB | WATER | WATER REPAIR & INSTALLATION | 2019-11-15 | 2019-12-06 | 2019-11-15 | 2019-12-06 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 976203¦¦2020-03-31
TM | CJ | Yes | 976204 |  | ALLSTATE WILLOW ROAD WELL 1 | KENNEDY, CHRISTOPHER C. | 100% | 80100 | 104665 | 184765 | 182663.5 | 182663.5 | 188421.1 | 0 | 0 | 182663.5 | 56000 | 77000 | 133000 | 31.09 |  |  |  | 31.09 |  |  | 138260.36 | 62379.8 | 12315.49 |  | 63565.07 |  |  | 44403.14 | 0 | 104% | 186.7 | 0 | 138260.36 | 24100 | 30.09% | 27665 | 51765 | 28.02% | 0 |  | 44403.14 | 24.31% | 44403.14 | 24.31% | 2101.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 886118 - ALLSTATE INSURANCE COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-11-20 | 2020-01-31 | 2019-11-20 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 976204¦¦2020-03-31
TM | C | Yes | 977006 |  | CENTRAL CITY RWP 3 | MIGUEL, SEAN J. | 100% | 28700 | 6789 | 35489 | 35489 | 35489 | 35489 | 0 | 0 | 35489 | 20986 | 5091 | 26077 | 0 |  |  |  | 0 |  |  | 33903.55 | 10849.04 | 1705.92 |  | 13790.49 | 7558.1 |  | 1585.45 | 0 | 130% |  | 0 | 33903.55 | 7714 | 26.88% | 1698 | 9412 | 26.52% | 0 |  | 1585.45 | 4.467% | 1585.45 | 4.467% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888144 - CENTRAL CITY WATER | WATER | WATER REPAIR & INSTALLATION | 2019-11-08 | 2019-12-31 | 2019-11-08 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 977006¦¦2020-03-31
FP | CJ | Yes | 977007 |  | DYNEGY BARTH PUMP | BARNES, MATTHEW D | 100% | 34450 | 0 | 34450 | 13250 | 13250 | 13250 | 0 | 0 | 13250 | 25838 | 0 | 25838 | 364.33 | 264.13 | 94.92 |  | 5.28 |  |  | 6431.04 | 3686.22 | 1139.14 |  | 1605.68 |  |  | 6818.96 | 0 | 24.89% |  | 0 | 6431.04 | 8612 | 25% | 0 | 8612 | 25% | 0 |  | 6818.96 | 51.46% | 6818.96 | 51.46% | 21200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 906320 - DYNEGY | WATER | WATER REPAIR & INSTALLATION | 2019-11-15 | 2020-01-30 | 2019-11-15 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 977007¦¦2020-03-31
FP | CJ | Yes | 977583 |  | KTG KRUGER | ANDERSON, STEPHEN P. | 100% | 23750 | 12950 | 36700 | 44930 | 44930 | 44930 | 0 | 0 | 44930 | 18230 | 9134.48 | 27364.48 | 0 |  |  |  | 0 |  |  | 55018.17 | 26969.85 | 7974.27 |  | 20074.05 |  |  | 0 | 10088.17 | 201.1% |  | 0 | 55018.17 | 5520 | 23.24% | 3815.52 | 9335.52 | 25.44% | 0 |  | -10088.17 | -22.45% | -10088.17 | -22.45% | -8230 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 977270 - KTG USA INC | WATER | WATER REPAIR & INSTALLATION | 2019-11-15 | 2020-03-16 | 2019-11-15 | 2020-03-16 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 977583¦¦2020-03-31
FP | C | Yes | 977584 |  | SILVER CITY PWM TESTING | ANDERSON, STEPHEN P. | 100% | 800 | 0 | 800 | 800 | 800 | 800 | 0 | 0 | 800 | 763 | 0 | 763 | [7 empty] | 150.12 |  |  |  | 150.12 |  |  | 649.88 | 0 | 19.67% |  | 0 | 150.12 | 37 | 4.625% | 0 | 37 | 4.625% | 0 |  | 649.88 | 81.23% | 649.88 | 81.23% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 977103 - SILVER CITY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-15 | 2019-11-23 | 2019-11-15 | 2019-11-23 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 977584¦¦2020-03-31
FP | C | Yes | 977673 |  | MARSHALL COUNTY PWM TESTING | ANDERSON, STEPHEN P. | 100% | 900 | 0 | 900 | 900 | 900 | 900 | 0 | 0 | 900 | 703 | 0 | 703 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 899.99 | 0 | 0.001422% |  | 0 | 0.01 | 197 | 21.89% | 0 | 197 | 21.89% | 0 |  | 899.99 | 100% | 899.99 | 100% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 894273 - MARSHALL COUNTY WATER ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2019-11-18 | 2019-11-27 | 2019-11-18 | 2019-11-27 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 977673¦¦2020-03-31
TM | C | Yes | 977674 |  | BURGESS NIPLE LAKE PUMP | BARNES, MATTHEW D | 100% | 13850 | 0 | 13850 | 13850 | 13850 | 13850 | 0 | 0 | 13850 | 9556 | 0 | 9556 | 0.5 | 0.5 | [5 empty] | 8603.27 | 2922.4 | 3066.16 |  | 2221.59 | 393.12 |  | 5246.73 | 0 | 90.03% |  | 0 | 8603.27 | 4294 | 31% | 0 | 4294 | 31% | 0 |  | 5246.73 | 37.88% | 5246.73 | 37.88% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 887618 - BURGESS & NIPLE | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-12-31 | 2019-11-19 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 977674¦¦2020-03-31
FP | C | Yes | 977675 |  | PCA WELL 24 | GNAU, CASEY T | 100% | 13000 | 40100 | 53100 | 52700 | 52700 | 52700 | 0 | 0 | 52700 | 6476 | 20084 | 26560 | -0.01 | -0.01 |  |  | 0 |  |  | 26434.27 | 7097.72 | 1733.82 |  | 17602.73 |  |  | 26265.73 | 0 | 99.53% |  | 0 | 26434.27 | 6524 | 50.18% | 20016 | 26540 | 49.98% | 7090 |  | 26265.73 | 49.84% | 26265.73 | 49.84% | 400 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895966 - PACKAGING CORPORATION OF AMERICA | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-12-31 | 2019-11-19 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 977675¦¦2020-03-31
FP | C | Yes | 977676 |  | KCP AND L ST JOE MO WELLS 5 6 | WARTICK, LOGAN M | 100% | 22950 | 0 | 22950 | 42433 | 42433 | 42433 | 0 | 0 | 42433 | 19508 | 0 | 19508 | 538.42 |  |  |  | 538.42 |  |  | 43513.28 | 15077.96 | 10584.15 |  | 17851.17 |  |  | 0 | 1080.28 | 223.1% |  | 0 | 43513.28 | 3442 | 15% | 0 | 3442 | 15% | 0 |  | -1080.28 | -2.546% | -1080.28 | -2.546% | -19483 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 893032 - EVERGY | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-12-31 | 2019-11-19 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 977676¦¦2020-03-31
FP | CJ | Yes | 977677 |  | CITY OF CHANDLER RWP 5 | VAN ALLEN, WESLEY C. | 100% | 4495 | 68662.5 | 73157.5 | 4495 | 4495 | 4495 | 0 | 0 | 4495 | 4185 | 56109.8 | 60294.8 | [7 empty] | 3460.31 | 1477.05 | 387.65 |  | 1595.61 |  |  | 1034.69 | 0 | 5.739% |  | 0 | 3460.31 | 310 | 6.897% | 12552.7 | 12862.7 | 17.58% | 12552.7 |  | 1034.69 | 23.02% | 1034.69 | 23.02% | 68662.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER SUPPLY | 2019-11-18 | 2020-01-15 | 2019-11-18 | 2020-01-15 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 977677¦¦2020-03-31
TM | CJ | Yes | 977678 |  | CAMROSA GERRY RD BOOSTER | SEIDEN, ANDREW L. | 100% | 5895 | 14489.42 | 20384.42 | 20384.2 | 20384.2 | 20962.27 | 0 | 0 | 20384.2 | 4576 | 11042.91 | 15618.91 | 3.68 |  |  |  | 3.68 |  |  | 13931.17 | 5607.01 | 722.08 |  | 7602.08 |  |  | 6453.03 | 0 | 89.19% |  | 0 | 13931.17 | 1319 | 22.37% | 3446.51 | 4765.51 | 23.38% | 0 |  | 6453.03 | 31.66% | 6453.03 | 31.66% | 0.22 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 537213 - CAMROSA WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-12-31 | 2019-11-19 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 977678¦¦2020-03-31
TM | CJ | Yes | 978238 |  | GENA JENNINGS PR | SCHERM, LOGAN M | 100% | 18000 | 13400 | 31400 | 31400 | 31400 | 0 | 0 | 0 | 31400 | 13200 | 18156.58 | 31356.58 | 14639.19 | 3909.04 | 3628.51 |  | 7101.64 |  |  | 29373.04 | 9043.02 | 4264.15 |  | 16065.87 |  |  | 2026.96 | 0 | 93.67% |  | 0 | 29373.04 | 4800 | 26.67% | -4756.58 | 43.42 | 0.1383% | 0 |  | 2026.96 | 6.455% | 2026.96 | 6.455% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 977709 - JENNINGS, GENA | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-11-19 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 978238¦¦2020-03-31
FP | C | Yes | 978239 |  | OLIVE BRANCH METRO MOTOR | ANDERSON, STEPHEN P. | 100% | 7865 | 0 | 7865 | 7865 | 7865 | 7865 | 0 | 0 | 7865 | 5895 | 0 | 5895 | [7 empty] | 5241.88 |  |  |  | 5241.88 |  |  | 2623.12 | 0 | 88.92% |  | 0 | 5241.88 | 1970 | 25.05% | 0 | 1970 | 25.05% | 0 |  | 2623.12 | 33.35% | 2623.12 | 33.35% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895759 - OLIVE BRANCH, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-11-30 | 2019-11-19 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 978239¦¦2020-03-31
FP | LJ | Yes | 978240 |  | CHOCTAW DURANT OK WELLS | EVANS, TRAVIS L | 94.78% | 478552 | 0 | 478552 | 453563.4021 | 399884 | 399884 | 0 | 39988.4 | 478552 | 378973.15 | 0 | 378973.15 | 20025.43 | 2490.55 | 4971.67 |  | 12542.23 | 6159.14 | -6138.16 | 592591.78 | 158908.43 | 173431.64 |  | 185678.29 | 64565.94 | 10007.48 | 0 | 192707.78 | 156.4% |  | 32648.22 | 625240 | 99578.85 | 20.81% | 0 | 99578.85 | 20.81% | 0 |  | -146688 | -32.9% | -146688 | -30.65% | 32648.22 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | GUTHRIE - WA | 888370 - CHOCTAW NATION OF OKLAHOMA | WATER | WATER SUPPLY | 2019-11-20 | 2020-03-01 | 2019-11-20 | 2020-03-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 978240¦¦2020-03-31
FP | C | Yes | 978241 |  | DELTA PLASTICS | SCHERM, LOGAN M | 100% | 13560 | 34974 | 48534 | 48534.44 | 48534.44 | 48534.44 | 0 | 0 | 48534.44 | 10848 | 25862.36 | 36710.36 | 500 |  |  |  | 500 |  |  | 32694.98 | 13269.79 | 2080.26 |  | 17344.93 |  |  | 15839.46 | 0 | 89.06% |  | 0 | 32694.98 | 2712 | 20% | 9111.64 | 11823.64 | 24.36% | 0 |  | 15839.46 | 32.64% | 15839.46 | 32.64% | -0.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 889481 - DELTA PLASTICS | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-11-20 | 2019-11-19 | 2019-11-20 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 978241¦¦2020-03-31
FP | C | Yes | 978242 |  | ELECTRIC ENERGY JOPPA PUMP PUL | WHITE, CATHLEEN R | 100% | 11351 | 0 | 11351 | 11425 | 11425 | 11425 | 0 | 0 | 11425 | 8013 | 0 | 8013 | [7 empty] | 4899.53 | 2726 | 509.4 |  | 1664.13 |  |  | 6525.47 | 0 | 61.14% |  | 0 | 4899.53 | 3338 | 29.41% | 0 | 3338 | 29.41% | 0 |  | 6525.47 | 57.12% | 6525.47 | 57.12% | -74 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 890112 - ELECTRIC ENERGY INC | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-12-31 | 2019-11-19 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 978242¦¦2020-03-31
FP | C | Yes | 978243 |  | JOLIET 18D WARRANTY | EISHA, JOSEPH J. | 100% | [5 empty] | 0 | 0 | 0 |  | 16800 | 0 | 16800 | 353.44 | 261.24 | 29.25 |  | 62.95 |  |  | 32035.33 | 22014.93 | 5114.01 |  | 4906.39 |  |  | 0 | 32035.33 | 190.7% |  | 0 | 32035.33 | -16800 |  | 0 | -16800 |  | 0 |  | -32035.33 |  | -32035.33 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878985 - JOLIET, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-20 | 2020-01-21 | 2019-11-20 | 2020-01-21 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 978243¦¦2020-03-31
FP | CJ | Yes | 978244 |  | RIVERSIDE WELL PROJECT 2020 | SEIDEN, ANDREW L. | 100% | 385089 | 0 | 385089 | 385089 | 385089 | 352437.91 | 0 | 17621.9 | 385089 | 281911 | 0 | 281911 | 99800.65 | 37644.78 | 18315.34 |  | 32882.65 | 10957.88 |  | 449288.51 | 159812.41 | 59060.04 |  | 188713.17 | 41702.89 |  | 0 | 64199.51 | 159.4% |  | 0 | 449288.51 | 103178 | 26.79% | 0 | 103178 | 26.79% | 0 |  | -64199.51 | -16.67% | -64199.51 | -16.67% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 897082 - RIVERSIDE, CA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-20 | 2020-12-31 | 2019-11-20 | 2020-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 978244¦¦2020-03-31
FP | CJ | Yes | 978245 |  | GAINESVILLE WASTEWATER PUMP | PARSLEY, TRISTAN S | 100% | 39418 | 0 | 39418 | 1882.39 | 1882.39 | 0 | 0 | 0 | 1882.39 | 30309 | 0 | 30309 | 0.92 |  |  |  | 0.92 |  |  | 1520.77 | 840.05 | 309.6 |  | 371.12 |  |  | 361.62 | 0 | 5.018% |  | 0 | 1520.77 | 9109 | 23.11% | 0 | 9109 | 23.11% | 0 |  | 361.62 | 19.21% | 361.62 | 19.21% | 37535.61 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 891007 - GAINESVILLE REGIONAL UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-11-18 | 2019-12-31 | 2019-11-18 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 978245¦¦2020-03-31
FP | C | Yes | 978246 |  | DHI FMI MIAMI WELL DEVELOPMENT | VAN ALLEN, WESLEY C. | 100% | 47250 | 12675 | 59925 | 59925 | 59925 | 59925 | 0 | 0 | 59925 | 31848 | 11045.91 | 42893.91 | 62.63 |  |  |  | 62.63 |  |  | 38951.22 | 13317.43 | 7668.37 |  | 17965.42 |  |  | 20973.78 | 0 | 90.81% |  | 0 | 38951.22 | 15402 | 32.6% | 1629.09 | 17031.09 | 28.42% | 0 |  | 20973.78 | 35% | 20973.78 | 35% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 977706 - DHI | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2020-01-15 | 2019-11-19 | 2020-01-15 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 978246¦¦2020-03-31
FP | C | Yes | 978443 |  | CAMDEN HSP MOTOR | BARNES, MATTHEW D | 100% | 3400 | 0 | 3400 | 3400 | 3400 | 3400 | 0 | 0 | 3400 | 1890 | 0 | 1890 | [7 empty] | 1834.95 |  | 63.28 |  | 1771.67 |  |  | 1565.05 | 0 | 97.09% |  | 0 | 1834.95 | 1510 | 44.41% | 0 | 1510 | 44.41% | 0 |  | 1565.05 | 46.03% | 1565.05 | 46.03% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 973402 - CAMDEN, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-11-30 | 2019-11-19 | 2019-11-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 978443¦¦2020-03-31
TM | C | Yes | 978454 |  | STATION 1 E2 MECH SEAL AND RAG | BRASHEAR, DAVID M | 100% | 2184 | 2827.44 | 5011.44 | 5011.79 | 5011.79 | 5045.89 | 0 | 0 | 5011.79 | 1572 | 1931.31 | 3503.31 | 0.01 |  |  |  | 0.01 |  |  | 3964.55 | 2331.63 | 308.49 |  | 934.43 | 390 |  | 1047.24 | 0 | 113.2% |  | 0 | 3964.55 | 612 | 28.02% | 896.13 | 1508.13 | 30.09% | 0 |  | 1047.24 | 20.9% | 1047.24 | 20.9% | -0.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878584 - CRESTLINE LAKE ARROWHEAD WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2019-11-19 | 2019-11-22 | 2019-11-19 | 2019-11-22 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 978454¦¦2020-03-31
TM | C | Yes | 978455 |  | JS TARKINGTON PR | SCHERM, LOGAN M | 100% | 9800 | 0 | 9800 | 26077.36 | 26077.36 | 28033.18 | 0 | 0 | 26077.36 | 7325 | 0 | 7325 | 2221.04 | 554.97 | 356.64 |  | 1309.43 |  |  | 23524.51 | 9920.85 | 967.6 |  | 12636.06 |  |  | 2552.85 | 0 | 321.2% |  | 0 | 23524.51 | 2475 | 25.26% | 0 | 2475 | 25.26% | 0 |  | 2552.85 | 9.79% | 2552.85 | 9.79% | -16277.36 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892953 - J S TARKINGTON FARMS | WATER | WATER REPAIR & INSTALLATION | 2019-11-21 | 2019-11-21 | 2019-11-21 | 2019-11-21 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 978455¦¦2020-03-31
FP | C | Yes | 978456 |  | JOLIET 18D SEPARATION SERVICES | EISHA, JOSEPH J. | 100% | 46913 | 33842 | 80755 | 80755 | 80755 | 80755 | 0 | 0 | 80755 | 29820 | 30180 | 60000 | 8372.77 | 5554.22 | 1145.4 |  | 1385.15 | 288 |  | 70909.14 | 40895.98 | 15878.13 |  | 13847.03 | 288 |  | 9845.86 | 0 | 118.2% | 62.1 | 0 | 70909.14 | 17093 | 36.44% | 3662 | 20755 | 25.7% | 3662 |  | 9845.86 | 12.19% | 9845.86 | 12.19% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 892910 - DO NOT USE JOLIET, IL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-21 | 2020-01-21 | 2019-11-21 | 2020-01-21 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 978456¦¦2020-03-31
FP | CJ | Yes | 978783 |  | CITGO TEST 142 | GNAU, CASEY T | 100% | 3130 | 32127.5 | 35257.5 | 35257.5 | 35257.5 | 35257.5 | 0 | 0 | 35257.5 | 2128 | 15501 | 17629 | 0 |  |  |  | 0 |  |  | 17942.75 | 9593.71 | 1122.4 |  | 5991.39 | 1235.25 |  | 17314.75 | 0 | 101.8% |  | 0 | 17942.75 | 1002 | 32.01% | 16626.5 | 17628.5 | 50% | 16626.5 |  | 17314.75 | 49.11% | 17314.75 | 49.11% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878864 - CITGO PETROLEUM CORP | WATER | WATER REPAIR & INSTALLATION | 2019-11-22 | 2019-12-15 | 2019-11-22 | 2019-12-15 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 978783¦¦2020-03-31
FP | C | Yes | 978784 |  | TYSON 2019 PWM TESTING | ANDERSON, STEPHEN P. | 100% | 1000 | 0 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 1000 | 878 | 0 | 878 | 0.49 |  |  |  | 0.49 |  |  | 941.13 | 432.77 | 204.05 |  | 304.31 |  |  | 58.87 | 0 | 107.2% |  | 0 | 941.13 | 122 | 12.2% | 0 | 122 | 12.2% | 0 |  | 58.87 | 5.887% | 58.87 | 5.887% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 899267 - TYSON FRESH MEATS COLUMBUS JCT | WATER | WATER REPAIR & INSTALLATION | 2019-11-22 | 2019-12-20 | 2019-11-22 | 2019-12-20 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 978784¦¦2020-03-31
TM | C | Yes | 978785 |  | WELL 1A HELENDALE CSD | BRASHEAR, DAVID M | 100% | 7580 | 57630.68 | 65210.68 | 65209.88 | 65209.88 | 67882.4 | 0 | 0 | 65209.88 | 5685 | 43263.35 | 48948.35 | 29.17 |  |  |  | 29.17 |  |  | 57105.47 | 16228.05 | 4602.98 |  | 36274.44 |  |  | 8104.41 | 0 | 116.7% |  | 0 | 57105.47 | 1895 | 25% | 14367.33 | 16262.33 | 24.94% | 0 |  | 8104.41 | 12.43% | 8104.41 | 12.43% | 0.8 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 891999 - HELENDALE CSD | WATER | WATER REPAIR & INSTALLATION | 2019-11-21 | 2019-12-31 | 2019-11-21 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 978785¦¦2020-03-31
TM | CJ | Yes | 978786 |  | OCALA WELL 4 PULL AND INSPECT | PARSLEY, TRISTAN S | 100% | 5000 | 70050.38 | 75050.38 | 11908.38 | 11908.38 | 11908.38 | 0 | 0 | 11908.38 | 4106 | 42344.23 | 46450.23 | 1195.92 | 741.67 | 84.05 |  | 370.2 |  |  | 8039.16 | 4055.23 | 479.1 |  | 2557.88 | 946.95 |  | 3869.22 | 0 | 17.31% |  | 0 | 8039.16 | 894 | 17.88% | 27706.15 | 28600.15 | 38.11% | 27706.15 | 25910.26 | 3869.22 | 32.49% | 3869.22 | 32.49% | 63142 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 895661 - OCALA, CITY OF | WATER | WATER SUPPLY | 2019-11-08 | 2019-12-31 | 2019-11-11 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 978786¦¦2020-03-31
TM | CJ | Yes | 978787 |  | OCALA MUNICIPAL 6 INCH WELL | PARSLEY, TRISTAN S | 100% | 5000 | 0 | 5000 | 5000 | 5000 | 5000 | 0 | 0 | 5000 | 4106 | 0 | 4106 | 223.78 |  |  |  | 223.78 |  |  | 1290.85 | 673.02 | 168.1 |  | 449.73 |  |  | 3709.15 | 0 | 31.44% |  | 0 | 1290.85 | 894 | 17.88% | 0 | 894 | 17.88% | 0 |  | 3709.15 | 74.18% | 3709.15 | 74.18% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 895661 - OCALA, CITY OF | WATER | WATER SUPPLY | 2019-11-08 | 2019-12-31 | 2019-11-11 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 978787¦¦2020-03-31
FP | C | Yes | 978823 |  | OKALOOSA ANTIOCH WELL | PARSLEY, TRISTAN S | 100% | 48290 | 0 | 48290 | 47839.24 | 47839.24 | 47839.24 | 0 | 0 | 47839.24 | 38525 | 0 | 38525 | [7 empty] | 40691.53 | 13452.59 | 6790.3 |  | 19698.64 | 750 |  | 7147.71 | 0 | 105.6% |  | 0 | 40691.53 | 9765 | 20.22% | 0 | 9765 | 20.22% | 0 |  | 7147.71 | 14.94% | 7147.71 | 14.94% | 450.76 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 895709 - OKALOOSA COUNTY WATER & SEWER SYSTEM | WATER | WATER SUPPLY | 2019-11-22 | 2019-12-31 | 2019-11-22 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 978823¦¦2020-03-31
FP | CJ | Yes | 979520 |  | WC LAKE CHARLES REHAB 38 | GNAU, CASEY T | 100% | 150500 | 0 | 150500 | 151700 | 151700 | 151700 | 0 | 0 | 151700 | 85747 | 0 | 85747 | 17.51 |  |  |  | 17.51 |  |  | 89245.09 | 31391.25 | 15362.41 |  | 24110.76 | 18380.67 |  | 62454.91 | 0 | 104.1% |  | 0 | 89245.09 | 64753 | 43.03% | 0 | 64753 | 43.03% | 0 |  | 62454.91 | 41.17% | 62454.91 | 41.17% | -1200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878710 - AXIALL CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-11-26 | 2019-12-31 | 2019-11-26 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 979520¦¦2020-03-31
FP | C | Yes | 979521 |  | SCHAUMBURG IL PWM TESTING | KENNEDY, CHRISTOPHER C. | 100% | 4200 | 0 | 4200 | 3500 | 3500 | 3500 | 0 | 0 | 3500 | 3150 | 0 | 3150 | [7 empty] | 3423.76 | 2572.9 | 303.37 |  | 547.49 |  |  | 76.24 | 0 | 108.7% |  | 0 | 3423.76 | 1050 | 25% | 0 | 1050 | 25% | 0 |  | 76.24 | 2.178% | 76.24 | 2.178% | 700 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 897562 - SCHAUMBURG, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-26 | 2019-12-06 | 2019-11-26 | 2019-12-06 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 979521¦¦2020-03-31
FP | C | Yes | 979522 |  | BOONVILLE 5A REHAB | MIGUEL, SEAN J. | 100% | 16950 | 5975 | 22925 | 22925 | 22925 | 22925 | 0 | 0 | 22925 | 13285 | 4450 | 17735 | [7 empty] | 21425.67 | 7628.55 | 4985.54 |  | 8811.58 |  |  | 1499.33 | 0 | 120.8% |  | 0 | 21425.67 | 3665 | 21.62% | 1525 | 5190 | 22.64% | 0 |  | 1499.33 | 6.54% | 1499.33 | 6.54% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 887294 - BOONVILLE, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-11-26 | 2019-12-31 | 2019-11-26 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 979522¦¦2020-03-31
TM | C | Yes | 979524 |  | EASTSIDE HOMEOWNERS SUB MOTOR | SCHERM, LOGAN M | 100% | 5300 | 0 | 5300 | 5805.24 | 5805.24 | 6298.68 | 0 | 0 | 5805.24 | 4000 | 0 | 4000 | [7 empty] | 3577.76 | 894.44 | 445.8 |  | 2237.52 |  |  | 2227.48 | 0 | 89.44% |  | 0 | 3577.76 | 1300 | 24.53% | 0 | 1300 | 24.53% | 0 |  | 2227.48 | 38.37% | 2227.48 | 38.37% | -505.24 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 889987 - EASTSIDE HOMEOWNERS WATER | WATER | WATER REPAIR & INSTALLATION | 2019-11-25 | 2020-02-25 | 2019-11-25 | 2020-02-25 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 979524¦¦2020-03-31
FP | C | Yes | 979559 |  | SPRINGFIELD NJ AST INSPECTION | RANFT, DONALD R | 100% | 4620 | 0 | 4620 | 4620 | 4620 | 4620 | 0 | 0 | 4620 | 2704 | 0 | 2704 | 0 |  |  |  | 0 |  |  | 1232.02 | 901.37 |  |  | 330.65 |  |  | 3387.98 | 0 | 45.56% |  | 0 | 1232.02 | 1916 | 41.47% | 0 | 1916 | 41.47% | 0 |  | 3387.98 | 73.33% | 3387.98 | 73.33% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 979379 - MOTT MACDONALD | WATER | WATER TREATMENT | 2019-11-26 | 2020-01-31 | 2019-11-26 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 979559¦¦2020-03-31
FP | C | Yes | 979560 |  | ARCADIS QUESTA ABANDON | DECKER, JASEN | 100% | 355115 | 0 | 355115 | 197870.75 | 197870.75 | 214442.43 | 214442.43 | 0 | 197870.75 | 240539 | 0 | 240539 | 54.16 |  |  |  | 54.16 |  |  | 93031.78 | 30429.22 | 14043.17 |  | 48559.39 |  |  | 104838.97 | 0 | 38.68% |  | 0 | 93031.78 | 114576 | 32.26% | 0 | 114576 | 32.26% | 0 |  | 104838.97 | 52.98% | 104838.97 | 52.98% | 157244.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 886424 - ARCADIS U S HIGHLANDS RANCH COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-11-26 | 2020-01-30 | 2019-11-26 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 979560¦¦2020-03-31
FP | C | Yes | 979561 |  | MARSHALL COUNTY WELL 1 MOTOR | ANDERSON, STEPHEN P. | 100% | 5405 | 0 | 5405 | 5405 | 5405 | 5405 | 0 | 0 | 5405 | 3545 | 0 | 3545 | [7 empty] | 4575.48 | 901.23 | 185.5 |  | 3488.75 |  |  | 829.52 | 0 | 129.1% |  | 0 | 4575.48 | 1860 | 34.41% | 0 | 1860 | 34.41% | 0 |  | 829.52 | 15.35% | 829.52 | 15.35% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 894273 - MARSHALL COUNTY WATER ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2019-11-26 | 2019-12-07 | 2019-11-26 | 2019-12-07 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 979561¦¦2020-03-31
FP | CJ | Yes | 979562 |  | OS WETLAND PUMP STATION | BARNES, MATTHEW D | 100% | 47960 | 0 | 47960 | 37180.65 | 37180.65 | 37180.65 | 37180.65 | 0 | 37180.65 | 31174 | 0 | 31174 | 1623.25 | 1191.6 | 311.76 |  | 119.89 |  |  | 17296.58 | 8007.44 | 1383.12 |  | 7906.02 |  |  | 19884.07 | 0 | 55.48% |  | 0 | 17296.58 | 16786 | 35% | 0 | 16786 | 35% | 0 |  | 19884.07 | 53.48% | 19884.07 | 53.48% | 10779.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 979414 - OHIO STATE UNIVERSITY, THE | WATER | WATER REPAIR & INSTALLATION | 2019-11-18 | 2019-12-31 | 2019-11-18 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 979562¦¦2020-03-31
FP | C | Yes | 981016 |  | SANDERSON FARMS 2019 FLOW TEST | PARSLEY, TRISTAN S | 100% | 7957 | 0 | 7957 | 7957 | 7957 | 7957 | 0 | 0 | 7957 | 4772 | 0 | 4772 | 0 |  |  |  | 0 |  |  | 6049.83 | 3803.46 | 487.5 |  | 1758.87 |  |  | 1907.17 | 0 | 126.8% |  | 0 | 6049.83 | 3185 | 40.03% | 0 | 3185 | 40.03% | 0 |  | 1907.17 | 23.97% | 1907.17 | 23.97% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 878808 - SANDERSON FARMS MOULTRIE PLANT | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2019-12-31 | 2019-12-03 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 981016¦¦2020-03-31
FP | CJ | Yes | 981017 |  | MURPHREE WT PLANT WELL 11MOTOR | PARSLEY, TRISTAN S | 100% | 83915 | 23140 | 107055 | 107266.96 | 107266.96 | 107266.96 | 17790 | 0 | 107266.96 | 61973 | 17276.56 | 79249.56 | 12374.2 | 5373.09 | 2027.97 |  | 4973.14 |  |  | 73170.73 | 14821.42 | 5373.25 |  | 52976.06 |  |  | 34096.23 | 0 | 92.33% |  | 0 | 73170.73 | 21942 | 26.15% | 5863.44 | 27805.44 | 25.97% | 5863.44 | 4821.27 | 34096.23 | 31.79% | 34096.23 | 31.79% | -211.96 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 891007 - GAINESVILLE REGIONAL UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2020-03-31 | 2019-12-03 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 981017¦¦2020-03-31
FP | C | Yes | 981018 |  | CPNMD A4 REINSTALL | DECKER, JASEN | 100% | 144400 | 0 | 144400 | 144400 | 144400 | 144400 | 0 | 0 | 144400 | 108905 | 0 | 108905 | 1395.84 | 283.61 | 128.65 |  | 983.58 |  |  | 35826.88 | 1008.47 | 331.99 |  | 34486.42 |  |  | 108573.12 | 0 | 32.9% |  | 0 | 35826.88 | 35495 | 24.58% | 0 | 35495 | 24.58% | 0 |  | 108573.12 | 75.19% | 108573.12 | 75.19% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878896 - CASTLE PINES NORTH METROPOLITAN DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-12-02 | 2020-03-30 | 2019-12-02 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 981018¦¦2020-03-31
FP | CJ | Yes | 981533 |  | FT RILEY KS 2020 WELL WORK | WARTICK, LOGAN M | 100% | 51018 | 0 | 51018 | 52778 | 52778 | 52778 | 5277.8 | 0 | 52778 | 38264 | 0 | 38264 | 23619.56 | 1957.17 | 114.43 |  | 21505.46 | 42.5 |  | 92972.57 | 24085.3 | 6747 |  | 61463.52 | 676.75 |  | 0 | 40194.57 | 243% |  | 0 | 92972.57 | 12754 | 25% | 0 | 12754 | 25% | 0 |  | -40194.57 | -76.16% | -40194.57 | -76.16% | -1760 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 981226 - AMERICAN STATES UTILITY SERVICES INC | WATER | WATER REPAIR & INSTALLATION | 2019-12-02 | 2019-12-30 | 2019-12-02 | 2019-12-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 981533¦¦2020-03-31
FP | CJ | Yes | 981534 |  | TROPICANA MITS | MARTINEZ, MIGUEL E | 100% | 58300 | 0 | 58300 | 67086 | 67086 | 67086 | 0 | 0 | 67086 | 39809 | 0 | 39809 | [7 empty] | 30648.96 | 13018.17 | 11089.43 |  | 6316.36 | 225 |  | 36437.04 | 0 | 76.99% |  | 0 | 30648.96 | 18491 | 31.72% | 0 | 18491 | 31.72% | 0 |  | 36437.04 | 54.31% | 36437.04 | 54.31% | -8786 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 981102 - PEPSICO INC | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2019-12-31 | 2019-12-03 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 981534¦¦2020-03-31
FP | CJ | Yes | 981535 |  | MYOMA WATER CO PWM SERVICES | GRACE, GARY L. | 100% | 23230 | 0 | 23230 | 11030 | 11030 | 11030 | 0 | 0 | 11030 | 15139 | 0 | 15139 | 867.26 |  |  |  | 87.26 | 780 |  | 8951.83 | 3640.53 | 262.74 |  | 4268.56 | 780 |  | 2078.17 | 0 | 59.13% |  | 0 | 8951.83 | 8091 | 34.83% | 0 | 8091 | 34.83% | 0 |  | 2078.17 | 18.84% | 2078.17 | 18.84% | 12200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878810 - MYOMA WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2020-01-15 | 2019-12-03 | 2020-01-15 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 981535¦¦2020-03-31
UP | C | Yes | 981536 |  | PARIS PMS | MIGUEL, SEAN J. | 100% | 1200 | 0 | 1200 | 1200 | 1200 | 1200 | 0 | 0 | 1200 | 1000 | 0 | 1000 | [7 empty] | 1226.97 | 545.66 | 194.39 |  | 486.92 |  |  | 0 | 26.97 | 122.7% |  | 0 | 1226.97 | 200 | 16.67% | 0 | 200 | 16.67% | 0 |  | -26.97 | -2.248% | -26.97 | -2.248% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 896029 - PARIS, KY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2019-12-31 | 2019-12-03 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 981536¦¦2020-03-31
TM | C | Yes | 981537 |  | OLDHAM CO HSP | MIGUEL, SEAN J. | 100% | 1692 | 0 | 1692 | 985 | 985 | 985 | 0 | 0 | 985 | 1280 | 0 | 1280 | [7 empty] | 783.58 | 223.33 | 138.85 |  | 173.9 | 247.5 |  | 201.42 | 0 | 61.22% |  | 0 | 783.58 | 412 | 24.35% | 0 | 412 | 24.35% | 0 |  | 201.42 | 20.45% | 201.42 | 20.45% | 707 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895736 - OLDHAM CO WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-12-02 | 2019-12-31 | 2019-12-02 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 981537¦¦2020-03-31
FP | CJ | Yes | 981539 |  | BUNKER HILL WELL 3 REHAB | CALLAHAN, DANIEL E. | 100% | 14900 | 113860 | 128760 | 128740 | 128740 | 128740 | 0 | 0 | 128740 | 12786 | 87526.41 | 100312.41 | 13052.64 | 5772.72 | 1782.13 |  | 5497.79 |  |  | 92275.11 | 14017.7 | 9503.9 |  | 66513.51 | 2240 |  | 36464.89 | 0 | 91.99% |  | 0 | 92275.11 | 2114 | 14.19% | 26333.59 | 28447.59 | 22.09% | 26333.59 |  | 36464.89 | 28.32% | 36464.89 | 28.32% | 20 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 879046 - BUNKER HILL VILLAGE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2020-02-02 | 2019-12-03 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 981539¦¦2020-03-31
FP | C | Yes | 981540 |  | PAWNEE MEADOWS WELL 2 REHAB | GANSEBOM, JASON W. | 100% | 24853 | 0 | 24853 | 19843 | 19843 | 20103.7 | 0 | 0 | 19843 | 16050 | 0 | 16050 | 0 |  |  |  | 0 |  |  | 27310.69 | 10611.38 | 5049.44 |  | 11172.67 | 477.2 |  | 0 | 7467.69 | 170.2% |  | 0 | 27310.69 | 8803 | 35.42% | 0 | 8803 | 35.42% | 0 |  | -7467.69 | -37.63% | -7467.69 | -37.63% | 5010 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 896118 - PAWNEE MEADOWS SID 4 | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2020-01-31 | 2019-12-03 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 981540¦¦2020-03-31
FP | C | Yes | 981543 |  | BRIDGE ST MA MEDIA REPLACEMENT | JOHANSON, MELISSA J. | 100% | 12825 | 0 | 12825 | 12825 | 12825 | 12825 | 0 | 0 | 12825 | 7109 | 0 | 7109 | 0.01 | 0.01 |  |  | 0 |  |  | 8095.74 | 255.75 |  |  | 7839.99 |  |  | 4729.26 | 0 | 113.9% |  | 0 | 8095.74 | 5716 | 44.57% | 0 | 5716 | 44.57% | 0 |  | 4729.26 | 36.88% | 4729.26 | 36.88% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 900056 - WESCOR ASSOCIATES, INC | WATER | WATER TREATMENT | 2019-12-01 | 2020-01-31 | 2019-12-01 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 981543¦¦2020-03-31
FP | LJ | Yes | 981577 |  | TUCSON WATER WELL A062A REPLAC | COMBS, TAYLOR E. | 79.44% | 747455 | 0 | 747455 | 582080.5533 | 654038.75 | 654038.75 | 0 | 0 | 732768.75 | 550334.13 | 0 | 550334.13 | 71378.59 | 25910.54 | 27198.08 |  | 17369.97 | 900 |  | 454598.88 | 126107.65 | 143379.18 |  | 171857.46 | 13254.59 |  | 199439.87 | 0 | 82.6% | 0 | 117685.92 | 572284.8 | 197120.87 | 26.37% | 0 | 197120.87 | 26.37% | 0 |  | 127481.67 | 21.9% | 160483.95 | 21.9% | 165374.45 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 899189 - TUCSON WATER DISTRICT | WATER | WATER SUPPLY | 2019-12-03 | 2020-02-28 | 2019-12-03 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 981577¦¦2020-03-31
TM | C | Yes | 981880 |  | IAWC MUNCIE | MIGUEL, SEAN J. | 100% | 5430 | 2554 | 7984 | 7984 | 7984 | 7984 | 0 | 0 | 7984 | 4250 | 1915 | 6165 | [7 empty] | 4926.97 | 2044.54 | 695.8 |  | 2186.63 |  |  | 3057.03 | 0 | 79.92% |  | 0 | 4926.97 | 1180 | 21.73% | 639 | 1819 | 22.78% | 0 |  | 3057.03 | 38.29% | 3057.03 | 38.29% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878797 - INDIANA AMERICAN WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2020-01-30 | 2019-12-03 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 981880¦¦2020-03-31
UP | CJ | Yes | 981881 |  | EMT DS | BARNES, MATTHEW D | 100% | 750 | 0 | 750 | 750 | 750 | 750 | 0 | 0 | 750 | 450 | 0 | 450 | 0.02 | 0.02 |  |  | 0 |  |  | 279.23 | 80.77 | 31.64 |  | 166.82 |  |  | 470.77 | 0 | 62.05% |  | 0 | 279.23 | 300 | 40% | 0 | 300 | 40% | 0 |  | 470.77 | 62.77% | 470.77 | 62.77% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 879062 - ELECTRIC MOTOR TECHNOLOGIES | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2019-12-31 | 2019-12-03 | 2009-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 981881¦¦2020-03-31
TM | C | Yes | 981884 |  | FASIG TIPTON | MIGUEL, SEAN J. | 100% | 1500 | 0 | 1500 | 3807 | 3807 | 3807 | 0 | 0 | 3807 | 1300 | 0 | 1300 | [7 empty] | 2742.18 | 268.7 | 62.68 |  | 243.81 | 2166.99 |  | 1064.82 | 0 | 210.9% |  | 0 | 2742.18 | 200 | 13.33% | 0 | 200 | 13.33% | 0 |  | 1064.82 | 27.97% | 1064.82 | 27.97% | -2307 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 890598 - FASIG TIPTON | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2019-12-31 | 2019-12-03 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 981884¦¦2020-03-31
FP | C | Yes | 981923 |  | COMPASS MINERALS TEST FIRE | GNAU, CASEY T | 100% | 3500 | 0 | 3500 | 3500 | 3500 | 3500 | 0 | 0 | 3500 | 1750 | 0 | 1750 | [7 empty] | 1802.19 | 1249.38 | 185.5 |  | 367.31 |  |  | 1697.81 | 0 | 103% |  | 0 | 1802.19 | 1750 | 50% | 0 | 1750 | 50% | 0 |  | 1697.81 | 48.51% | 1697.81 | 48.51% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878974 - COMPASS MINERALS | WATER | WATER REPAIR & INSTALLATION | 2019-12-04 | 2019-12-31 | 2019-12-04 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 981923¦¦2020-03-31
TM | CJ | Yes | 982223 |  | ADVANCED READY MIX | MIGUEL, SEAN J. | 100% | 1320 | 4321.5 | 5641.5 | 5271.5 | 5271.5 | 5271.5 | 5271.5 | 0 | 5271.5 | 1080 | 3709 | 4789 | 1570.78 | 971.2 | 138.86 |  | 460.72 |  |  | 4904.03 | 1500.36 | 305.48 |  | 3098.19 |  |  | 367.47 | 0 | 102.4% |  | 0 | 4904.03 | 240 | 18.18% | 612.5 | 852.5 | 15.11% | 612.5 |  | 367.47 | 6.971% | 367.47 | 6.971% | 370 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 885928 - ADVANCED READY MIX CONCRETE INC | WATER | WATER REPAIR & INSTALLATION | 2019-12-05 | 2020-01-30 | 2019-12-05 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 982223¦¦2020-03-31
TM | C | Yes | 982224 |  | SILVER MESA AND ELSTNER WELLS | BRASHEAR, DAVID M | 100% | 64777 | 0 | 64777 | 64777.3 | 64777.3 | 64777.3 | 0 | 0 | 64777.3 | 48583 | 0 | 48583 | [7 empty] | 49567.27 | 25109.05 | 7932.43 |  | 16525.79 |  |  | 15210.03 | 0 | 102% |  | 0 | 49567.27 | 16194 | 25% | 0 | 16194 | 25% | 0 |  | 15210.03 | 23.48% | 15210.03 | 23.48% | -0.3 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 895492 - NORTH LAS VEGAS, NV, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-05 | 2020-02-02 | 2019-12-05 | 2020-02-02 | PRIME CONTRACTOR | PUBLIC | CONST MANAGER/GEN CONTRACTOR | 982224¦¦2020-03-31
FP | CJ | Yes | 982278 |  | AURORA IL WELL NO 28 | BALLUFF, WILLIAM O. | 100% | 25000 | 182649 | 207649 | 145118.94 | 145118.94 | 145118.94 | 120118.94 | 0 | 145118.94 | 20000 | 153052.77 | 173052.77 | 28962.65 | 12571.59 | 668.92 |  | 15722.14 |  |  | 69628.48 | 40576.3 | 6130.55 |  | 22921.63 |  |  | 75490.46 | 0 | 40.24% |  | 0 | 69628.48 | 5000 | 20% | 29596.23 | 34596.23 | 16.66% | 29596.23 |  | 75490.46 | 52.02% | 75490.46 | 52.02% | 62530.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 886663 - AURORA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-06 | 2019-12-31 | 2019-12-06 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 982278¦¦2020-03-31
FP | C | Yes | 982290 |  | CHOBANI WELL 1 REHAB | CROOK, CHARLES M | 100% | 28860 | 0 | 28860 | 24720 | 24720 | 24720 | 0 | 0 | 24720 | 21860 | 0 | 21860 | 79.26 | 78.38 |  |  | 0.88 |  |  | 15041.61 | 9572.22 | 1592.76 |  | 3876.63 |  |  | 9678.39 | 0 | 68.81% |  | 0 | 15041.61 | 7000 | 24.26% | 0 | 7000 | 24.26% | 0 |  | 9678.39 | 39.15% | 9678.39 | 39.15% | 4140 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 982031 - CHOBANI | WATER | WATER REPAIR & INSTALLATION | 2019-12-06 | 2020-01-31 | 2019-12-06 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 982290¦¦2020-03-31
FP | CJ | Yes | 982517 |  | CAPE CORAL ACID TASK 1 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 89765 | 89765 | 89765 | 0 | 8976.5 | 89765 | 71475 | 0 | 71475 | 13.84 |  |  |  | 13.84 |  |  | 52634.93 | 11871.68 | 4938.19 |  | 27925.06 | 7900 |  | 37130.07 | 0 | 73.64% |  | 0 | 52634.93 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 37130.07 | 41.36% | 37130.07 | 41.36% | -3440 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-03-15 | 2019-12-09 | 2020-03-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 982517¦¦2020-03-31
TM | C | Yes | 982518 |  | SOUTH ISLAND PSD FOREST BEACH3 | PARSLEY, TRISTAN S | 100% | 30750 | 0 | 30750 | 31222 | 31222 | 31222 | 0 | 0 | 31222 | 18840 | 0 | 18840 | 0 |  |  |  | 0 |  |  | 18794.32 | 9518.38 | 3254.28 |  | 6021.66 |  |  | 12427.68 | 0 | 99.76% |  | 0 | 18794.32 | 11910 | 38.73% | 0 | 11910 | 38.73% | 0 |  | 12427.68 | 39.8% | 12427.68 | 39.8% | -472 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 892139 - HILTON HEAD ISLAND PSD 1 | WATER | WATER REPAIR & INSTALLATION | 2019-12-02 | 2020-01-31 | 2019-12-02 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 982518¦¦2020-03-31
FP | CJ | Yes | 982882 |  | CITY OF MELBOURNE GRANT ST | MARTINEZ, MIGUEL E | 100% | 104115 | 0 | 104115 | 99000 | 99000 | 99000 | 99000 | 0 | 99000 | 62480 | 0 | 62480 | 35218.37 | 6465.41 | 3938.13 |  | 24814.83 |  |  | 49736.57 | 6465.41 | 3938.13 |  | 39333.03 |  |  | 49263.43 | 0 | 79.6% |  | 0 | 49736.57 | 41635 | 39.99% | 0 | 41635 | 39.99% | 0 |  | 49263.43 | 49.76% | 49263.43 | 49.76% | 5115 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878718 - CDM SMITH | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-02-29 | 2019-12-09 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 982882¦¦2020-03-31
TM | CJ | Yes | 982883 |  | MYOMA WATER PUMP STATION 1 | GRACE, GARY L. | 100% | 4540 | 10750 | 15290 | 8842.09 | 8842.09 | 4540 | 0 | 0 | 8842.09 | 3348 | 7881.65 | 11229.65 | 3927.51 | 1080.03 |  |  | 720.17 | 2127.31 |  | 7143.48 | 2504.89 | 374.59 |  | 2136.69 | 2127.31 |  | 1698.61 | 0 | 63.61% |  | 0 | 7143.48 | 1192 | 26.26% | 2868.35 | 4060.35 | 26.56% | 2868.35 | 2868.35 | 1698.61 | 19.21% | 1698.61 | 19.21% | 6447.91 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878774 - MYOMA WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-01-30 | 2019-12-09 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 982883¦¦2020-03-31
TM | C | Yes | 982884 |  | TRIPLE H FARMS PR | BENNETT, MARK C. | 100% | 10500 | 0 | 10500 | 10500.09 | 10500.09 | 11287.62 | 0 | 0 | 10500.09 | 7825 | 0 | 7825 | 0 |  |  |  | 0 |  |  | 10010.15 | 4507.99 | 282.9 |  | 5219.26 |  |  | 489.94 | 0 | 127.9% |  | 0 | 10010.15 | 2675 | 25.48% | 0 | 2675 | 25.48% | 0 |  | 489.94 | 4.666% | 489.94 | 4.666% | -0.09 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 899137 - TRIPLE H FARMS | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-02-09 | 2019-12-09 | 2020-02-09 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 982884¦¦2020-03-31
FP | C | Yes | 982885 |  | ARCHROMA 2019 PM FLOW TESTING1 | PARSLEY, TRISTAN S | 100% | 3675 | 0 | 3675 | 3675 | 3675 | 3675 | 0 | 0 | 3675 | 2565 | 0 | 2565 | [7 empty] | 1819.36 | 1095.16 |  |  | 724.2 |  |  | 1855.64 | 0 | 70.93% |  | 0 | 1819.36 | 1110 | 30.2% | 0 | 1110 | 30.2% | 0 |  | 1855.64 | 50.49% | 1855.64 | 50.49% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 982600 - ARCHROMA US INC | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-01-31 | 2019-12-09 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 982885¦¦2020-03-31
TM | C | Yes | 982886 |  | TRI COUNTY WATER WELLS 3 AND 4 | WARTICK, LOGAN M | 100% | 33510 | 0 | 33510 | 42550 | 42550 | 42550 | 0 | 0 | 42550 | 28276 | 0 | 28276 | 266.96 | 266.96 |  |  | 0 |  |  | 56177.73 | 23510.94 | 16388 |  | 16278.79 |  |  | 0 | 13627.73 | 198.7% |  | 0 | 56177.73 | 5234 | 15.62% | 0 | 5234 | 15.62% | 0 |  | -13627.73 | -32.03% | -13627.73 | -32.03% | -9040 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 899123 - TRI COUNTY WATER AUTHORITY | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-05-15 | 2019-12-09 | 2020-05-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 982886¦¦2020-03-31
TM | CJ | Yes | 982887 |  | EVONIK WELLS | MIGUEL, SEAN J. | 100% | 2000 | 8625 | 10625 | 16249.5 | 16249.5 | 16249.5 | 0 | 0 | 16249.5 | 1476 | 5906 | 7382 | 4134.21 | 2442.39 | 274.34 |  | 1417.48 |  |  | 13936.33 | 7667.51 | 1846.11 |  | 4422.71 |  |  | 2313.17 | 0 | 188.8% |  | 0 | 13936.33 | 524 | 26.2% | 2719 | 3243 | 30.52% | 2719 |  | 2313.17 | 14.24% | 2313.17 | 14.24% | -5624.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 890483 - EVONIK DEGUSSA CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-01-30 | 2019-12-09 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 982887¦¦2020-03-31
TM | CJ | Yes | 982888 |  | GRANITE INLINER | WILLIAMS, DONALD G. | 100% | 2202 | 0 | 2202 | 2519.08 | 2519.08 | 2519.08 | 0 | 0 | 2519.08 | 1762 | 0 | 1762 | [7 empty] | 4452.62 | 2326.41 |  |  | 2126.21 |  |  | 0 | 1933.54 | 252.7% |  | 0 | 4452.62 | 440 | 19.98% | 0 | 440 | 19.98% | 0 |  | -1933.54 | -76.76% | -1933.54 | -76.76% | -317.08 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 848974 - GRANITE INLINER LLC | WATER | WATER REPAIR & INSTALLATION | 2019-12-06 | 2020-12-31 | 2019-12-06 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 982888¦¦2020-03-31
FP | CJ | Yes | 982889 |  | ENTERGY GRAND GULF WELL 4 | ANDERSON, STEPHEN P. | 100% | 17060 | 50448 | 67508 | 67508 | 67508 | 67508 | 0 | 0 | 67508 | 12310 | 32172.05 | 44482.05 | 351.73 | 93.5 |  |  | 258.23 |  |  | 41744.05 | 10522 | 2121.26 |  | 29100.79 |  |  | 25763.95 | 0 | 93.84% |  | 0 | 41744.05 | 4750 | 27.84% | 18275.95 | 23025.95 | 34.11% | 18275.95 |  | 25763.95 | 38.16% | 25763.95 | 38.16% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 890293 - ENTERGY OPERATIONS GRAND GULF | WATER | WATER REPAIR & INSTALLATION | 2019-12-06 | 2020-01-31 | 2019-12-06 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 982889¦¦2020-03-31
FP | CJ | Yes | 982890 |  | GREEN PLAINS SST HSP 1 | ANDERSON, STEPHEN P. | 100% | 29641 | 6770 | 36411 | 31111 | 31111 | 31111 | 0 | 0 | 31111 | 19859 | 4802.84 | 24661.84 | 13488.15 |  | 432.42 |  | 13055.73 |  |  | 14833.56 | 689.49 | 619.16 |  | 13524.91 |  |  | 16277.44 | 0 | 60.15% |  | 0 | 14833.56 | 9782 | 33% | 1967.16 | 11749.16 | 32.27% | 1967.16 | 1967.16 | 16277.44 | 52.32% | 16277.44 | 52.32% | 5300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879091 - GREEN PLAINS OBION LLC | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-03-20 | 2019-12-09 | 2020-03-20 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 982890¦¦2020-03-31
UP | CJ | Yes | 982891 |  | HILLTOP PWM | MIGUEL, SEAN J. | 100% | 2100 | 0 | 2100 | 5080 | 5080 | 5080 | 0 | 0 | 5080 | 1707 | 0 | 1707 | 0.78 |  |  |  | 0.78 |  |  | 4301.6 | 1624.58 | 420.92 |  | 2256.1 |  |  | 778.4 | 0 | 252% |  | 0 | 4301.6 | 393 | 18.71% | 0 | 393 | 18.71% | 0 |  | 778.4 | 15.32% | 778.4 | 15.32% | -2980 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 892133 - HILLTOP BASIC RESOURCES | WATER | WATER REPAIR & INSTALLATION | 2019-12-06 | 2019-12-31 | 2019-12-06 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 982891¦¦2020-03-31
FP | C | Yes | 982916 |  | CLINTON ST WTP AST REPACK | RANFT, DONALD R | 100% | 113450 | 0 | 113450 | 113450 | 113450 | 113450 | 0 | 0 | 113450 | 78020 | 0 | 78020 | 0.01 | 0.01 |  |  | 0 |  |  | 83497.89 | 1388.9 |  |  | 82108.99 |  |  | 29952.11 | 0 | 107% |  | 0 | 83497.89 | 35430 | 31.23% | 0 | 35430 | 31.23% | 0 |  | 29952.11 | 26.4% | 29952.11 | 26.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 887004 - BENSIN CONTRACTING INC | WATER | WATER TREATMENT | 2019-12-09 | 2020-02-29 | 2019-12-09 | 2020-02-29 | SUBCONTRACTOR | PUBLIC | COST REIMBURSIBLE | 982916¦¦2020-03-31
FP | C | Yes | 982949 |  | ERATH CHECK VALVE | GNAU, CASEY T | 100% | 3300 | 0 | 3300 | 3300 | 3300 | 3300 | 0 | 0 | 3300 | 2438 | 0 | 2438 | [7 empty] | 1061.46 | 425.01 | 427.22 |  | 209.23 |  |  | 2238.54 | 0 | 43.54% |  | 0 | 1061.46 | 862 | 26.12% | 0 | 862 | 26.12% | 0 |  | 2238.54 | 67.83% | 2238.54 | 67.83% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 890375 - ERATH, LA, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-10 | 2019-12-31 | 2019-12-10 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 982949¦¦2020-03-31
FP | C | Yes | 983587 |  | MEMC DW 1 PUMP SERVICE | WHITE, CATHLEEN R | 100% | 24807 | 0 | 24807 | 24807 | 24807 | 24807 | 0 | 0 | 24807 | 17807 | 0 | 17807 | 0 |  |  |  | 0 |  |  | 8151.66 | 4859.13 | 982.82 |  | 2309.71 |  |  | 16655.34 | 0 | 45.78% |  | 0 | 8151.66 | 7000 | 28.22% | 0 | 7000 | 28.22% | 0 |  | 16655.34 | 67.14% | 16655.34 | 67.14% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 894508 - MEMC ELECTRONIC MATERIALS | WATER | WATER REPAIR & INSTALLATION | 2019-12-10 | 2019-12-31 | 2019-12-10 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 983587¦¦2020-03-31
FP | C | Yes | 983588 |  | RANCHO CALIFORNIA WELL 164 | SEIDEN, ANDREW L. | 100% | 12592 | 0 | 12592 | 12593.75 | 12593.75 | 13635.33 | 0 | 0 | 12593.75 | 9523 | 0 | 9523 | [7 empty] | 10925.76 |  |  |  | 10925.76 |  |  | 1667.99 | 0 | 114.7% |  | 0 | 10925.76 | 3069 | 24.37% | 0 | 3069 | 24.37% | 0 |  | 1667.99 | 13.24% | 1667.99 | 13.24% | -1.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878683 - RANCHO CALIFORNIA WATER DISTRICT | WATER | WATER EQUIPMENT SALES | 2019-12-09 | 2020-01-30 | 2019-12-09 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 983588¦¦2020-03-31
FP | C | Yes | 983589 |  | EMWD 76 WSE SAMPLES AND TEST | GRACE, GARY L. | 100% | 3504 | 0 | 3504 | 3504 | 3504 | 3504 | 0 | 0 | 3504 | 2662 | 0 | 2662 | [7 empty] | 1819.22 | 616.96 | 93.28 |  | 358.98 | 750 |  | 1684.78 | 0 | 68.34% |  | 0 | 1819.22 | 842 | 24.03% | 0 | 842 | 24.03% | 0 |  | 1684.78 | 48.08% | 1684.78 | 48.08% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878619 - EASTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2019-12-10 | 2019-12-31 | 2019-12-10 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 983589¦¦2020-03-31
TM | CJ | Yes | 983590 |  | MYOMA WATER PUMP STATION 2 | GRACE, GARY L. | 100% | 6761 | 0 | 6761 | 6761.14 | 6761.14 | 7055.34 | 0 | 0 | 6761.14 | 5187 | 0 | 5187 | 2617.72 | 957.35 | 978.08 |  | 682.29 |  |  | 13488.03 | 2854.76 | 1199.62 |  | 8478.81 | 954.84 |  | 0 | 6726.89 | 260% |  | 0 | 13488.03 | 1574 | 23.28% | 0 | 1574 | 23.28% | 0 |  | -6726.89 | -99.49% | -6726.89 | -99.49% | -0.14 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 122923 - MYOMA DUNES WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-10 | 2020-01-05 | 2019-12-10 | 2020-01-05 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 983590¦¦2020-03-31
FP | CJ | Yes | 983707 |  | CHARLOTTE BURNT STORE IW VALVE | MARTINEZ, MIGUEL E | 100% | 8463 | 0 | 8463 | 8463 | 8463 | 8463 | 0 | 0 | 8463 | 5043 | 0 | 5043 | [7 empty] | 2633.82 | 1398.22 | 595.61 |  | 639.99 |  |  | 5829.18 | 0 | 52.23% |  | 0 | 2633.82 | 3420 | 40.41% | 0 | 3420 | 40.41% | 0 |  | 5829.18 | 68.88% | 5829.18 | 68.88% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 888250 - CHARLOTTE COUNTY UTILITIES | WATER | WATER EQUIPMENT SALES | 2019-12-09 | 2020-01-16 | 2019-12-10 | 2020-01-16 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 983707¦¦2020-03-31
FP | CJ | Yes | 983727 |  | GROVE ST MA WTP LAYNEOX LITE | MCCARTNEY, JEFFREY C | 100% | 472250 | 0 | 472250 | 178196.69 | 178196.69 | 0 | 0 | 0 | 178196.69 | 346472.98 | 0 | 346472.98 | 51430.69 | 2345.41 |  |  | 2229.28 | 46856 |  | 143964.13 | 7711.99 |  |  | 19112.14 | 117140 |  | 34232.56 | 0 | 41.55% |  | 0 | 143964.13 | 125777.02 | 26.63% | 0 | 125777.02 | 26.63% | 0 |  | 34232.56 | 19.21% | 34232.56 | 19.21% | 294053.31 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 982986 - DANIEL O CONNELLS SONS INC | WATER | WATER TREATMENT | 2019-12-01 | 2020-07-31 | 2019-12-01 | 2020-07-31 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 983727¦¦2020-03-31
TM | CJ | Yes | 983983 |  | ROLLING HILLS CC PM BI ANNUAL | BRASHEAR, DAVID M |  | 2995 | 0 | 2995 |  |  | 0 | 0 | 0 |  | 1832 | 0 | 1832 | [20 empty] | 1163 | 38.83% | 0 | 1163 | 38.83% | 0 | [5 empty] | 2995 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878661 - ROLLING HILLS COUNTRY CLUB | WATER | WATER REPAIR & INSTALLATION | 2019-12-10 | 2021-01-01 | 2019-12-10 | 2021-01-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 983983¦¦2020-03-31
FP | C | Yes | 983984 |  | LINTON WELL 11 REHAB | WILLIAMS, DONALD G. | 100% | 25220 | 10907 | 36127 | 36127 | 36127 | 36127 | 0 | 0 | 36127 | 18347 | 7769 | 26116 | 3054.61 | 174.3 | 29.32 |  | 2850.99 |  |  | 27964.57 | 9592 | 5679.69 |  | 12692.88 |  |  | 8162.43 | 0 | 107.1% |  | 0 | 27964.57 | 6873 | 27.25% | 3138 | 10011 | 27.71% | 3138 |  | 8162.43 | 22.59% | 8162.43 | 22.59% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 893792 - LINTON, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-11 | 2020-01-30 | 2019-12-11 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 983984¦¦2020-03-31
TM | C | Yes | 983985 |  | AK BLAST FURNACE EXCAVATION | BARNES, MATTHEW D | 100% | 23250 | 0 | 23250 | 23250 | 23250 | 23250 | 0 | 0 | 23250 | 16275 | 0 | 16275 | 1.69 | 1.69 |  |  | 0 |  |  | 21141.92 | 11016.97 | 5845.07 |  | 3779.88 | 500 |  | 2108.08 | 0 | 129.9% |  | 0 | 21141.92 | 6975 | 30% | 0 | 6975 | 30% | 0 |  | 2108.08 | 9.067% | 2108.08 | 9.067% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2019-12-10 | 2020-01-30 | 2019-12-10 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 983985¦¦2020-03-31
FP | C | Yes | 983986 |  | OLIN WELL 2 REPAIR | WHITE, CATHLEEN R | 100% | 46828 | 0 | 46828 | 46828 | 46828 | 46828 | 0 | 0 | 46828 | 32828 | 0 | 32828 | 0 |  |  |  | 0 |  |  | 29277.46 | 15274.73 | 2156.09 |  | 11833.38 | 13.26 |  | 17550.54 | 0 | 89.18% |  | 0 | 29277.46 | 14000 | 29.9% | 0 | 14000 | 29.9% | 0 |  | 17550.54 | 37.48% | 17550.54 | 37.48% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 895753 - OLIN CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2019-12-31 | 2019-12-03 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 983986¦¦2020-03-31
FP | C | Yes | 983987 |  | JEFFERSON COUNTY PWSD 2 PUMP | WHITE, CATHLEEN R | 100% | 7075 | 11341 | 18416 | 18416 | 18416 | 18416 | 0 | 0 | 18416 | 4975 | 9159.27 | 14134.27 | 2.37 | 2.38 |  |  | -0.01 |  |  | 13915.52 | 7394.39 | 815.89 |  | 5705.24 |  |  | 4500.48 | 0 | 98.45% |  | 0 | 13915.52 | 2100 | 29.68% | 2181.73 | 4281.73 | 23.25% | 2181.73 |  | 4500.48 | 24.44% | 4500.48 | 24.44% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878887 - JEFFERSON COUNTY MO PWSD NO 2 | WATER | WATER REPAIR & INSTALLATION | 2019-12-06 | 2020-01-31 | 2019-12-06 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 983987¦¦2020-03-31
FP | C | Yes | 983988 |  | ARCHROMA 2019 PM FLOW TESTING | PARSLEY, TRISTAN S | 100% | 3675 | 0 | 3675 | 3675 | 3675 | 3675 | 0 | 0 | 3675 | 2565 | 0 | 2565 | [7 empty] | 2641.98 | 760.21 |  |  | 381.77 | 1500 |  | 1033.02 | 0 | 103% |  | 0 | 2641.98 | 1110 | 30.2% | 0 | 1110 | 30.2% | 0 |  | 1033.02 | 28.11% | 1033.02 | 28.11% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 982600 - ARCHROMA US INC | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-01-31 | 2019-12-09 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 983988¦¦2020-03-31
FP | C | Yes | 983989 |  | WAYNESVILLE WELL 6 REHAB | BARNES, MATTHEW D | 100% | 16121 | 0 | 16121 | 18985 | 18985 | 18985 | 0 | 0 | 18985 | 11345 | 0 | 11345 | 1.33 | 1.33 |  |  | 0 |  |  | 21289.49 | 8606.46 | 4073.37 |  | 8609.66 |  |  | 0 | 2304.49 | 187.7% |  | 0 | 21289.49 | 4776 | 29.63% | 0 | 4776 | 29.63% | 0 |  | -2304.49 | -12.14% | -2304.49 | -12.14% | -2864 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 912058 - WAYNESVILLE, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-11 | 2020-01-30 | 2019-12-11 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 983989¦¦2020-03-31
TM | C | Yes | 984234 |  | PLAINFIELD HSP | MIGUEL, SEAN J. | 100% | 2500 | 10800 | 13300 | 13300 | 13300 | 13300 | 0 | 0 | 13300 | 1900 | 8640 | 10540 | 0 |  |  |  | 0 |  |  | 11616.69 | 5920.78 | 1277.18 |  | 4121.73 | 297 |  | 1683.31 | 0 | 110.2% |  | 0 | 11616.69 | 600 | 24% | 2160 | 2760 | 20.75% | 2160 |  | 1683.31 | 12.66% | 1683.31 | 12.66% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 896383 - PLAINFIELD, IN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-12 | 2020-01-30 | 2019-12-12 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 984234¦¦2020-03-31
FP | C | Yes | 984503 |  | PETERESBURG BW PIPING | WILLIAMS, DONALD G. | 100% | 9200 | 0 | 9200 | 9200 | 9200 | 9200 | 0 | 0 | 9200 | 7136 | 0 | 7136 | [7 empty] | 4860.47 | 1966.59 | 737.48 |  | 2156.4 |  |  | 4339.53 | 0 | 68.11% |  | 0 | 4860.47 | 2064 | 22.43% | 0 | 2064 | 22.43% | 0 |  | 4339.53 | 47.17% | 4339.53 | 47.17% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 896240 - PETERSBURG, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-12 | 2020-01-30 | 2019-12-12 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 984503¦¦2020-03-31
FP | C | Yes | 985208 |  | IAWC RICHMOND 10 REHAB | MIGUEL, SEAN J. | 100% | 19534 | 10527 | 30061 | 30061 | 30061 | 30061 | 0 | 0 | 30061 | 13953 | 9600 | 23553 | 0 |  |  |  | 0 |  |  | 25448.9 | 11313.83 | 4666.99 |  | 9468.08 |  |  | 4612.1 | 0 | 108% |  | 0 | 25448.9 | 5581 | 28.57% | 927 | 6508 | 21.65% | 927 |  | 4612.1 | 15.34% | 4612.1 | 15.34% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878797 - INDIANA AMERICAN WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-12 | 2020-01-30 | 2019-12-12 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 985208¦¦2020-03-31
TM | C | Yes | 985209 |  | RAIN CARBON MOTOR | GNAU, CASEY T | 100% | 2790 | 0 | 2790 | 3310 | 3310 | 3310 | 0 | 0 | 3310 | 1674 | 0 | 1674 | [7 empty] | 1442.33 | 745.89 | 408.1 |  | 288.34 |  |  | 1867.67 | 0 | 86.16% |  | 0 | 1442.33 | 1116 | 40% | 0 | 1116 | 40% | 0 |  | 1867.67 | 56.43% | 1867.67 | 56.43% | -520 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879116 - RAIN CII CARBON LLC | WATER | WATER REPAIR & INSTALLATION | 2019-12-12 | 2019-12-31 | 2019-12-12 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 985209¦¦2020-03-31
FP | C | Yes | 985210 |  | TWIN RIVERS PAPER PINE BLUFF 5 | BURGE, EVERETT E. | 100% | 20000 | 0 | 20000 | 27540 | 27540 | 27540 | 0 | 0 | 27540 | 15000 | 0 | 15000 | 3.84 |  |  |  | 3.84 |  |  | 16187.92 | 7107.15 | 2805.53 |  | 6275.24 |  |  | 11352.08 | 0 | 107.9% |  | 0 | 16187.92 | 5000 | 25% | 0 | 5000 | 25% | 0 |  | 11352.08 | 41.22% | 11352.08 | 41.22% | -7540 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 899242 - TWIN RIVERS PAPER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-12 | 2020-07-24 | 2019-12-12 | 2020-07-24 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 985210¦¦2020-03-31
TM | C | Yes | 985211 |  | AQUA IL SUN RIVER TERRACE | EISHA, JOSEPH J. | 100% | 27500 | 0 | 27500 | 13800 | 13800 | 13800 | 0 | 0 | 13800 | 18000 | 0 | 18000 | 0 |  |  |  | 0 |  |  | 11649.23 | 8101.08 | 1690.04 |  | 1858.11 |  |  | 2150.77 | 0 | 64.72% |  | 0 | 11649.23 | 9500 | 34.55% | 0 | 9500 | 34.55% | 0 |  | 2150.77 | 15.59% | 2150.77 | 15.59% | 13700 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 886378 - AQUA ILLINOIS KANKAKEE | WATER | WATER REPAIR & INSTALLATION | 2019-12-13 | 2019-12-31 | 2019-12-13 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 985211¦¦2020-03-31
TM | CJ | Yes | 985212 |  | GRU MWTP WELL 15 PUMP | PARSLEY, TRISTAN S | 100% | 344385 | 0 | 344385 | 25461.15 | 25461.15 | 25461.15 | 0 | 0 | 25461.15 | 269975 | 0 | 269975 | 13537.33 | 6607 | 2281.04 |  | 4649.29 |  |  | 15715.1 | 7833.17 | 2482.77 |  | 5399.16 |  |  | 9746.05 | 0 | 5.821% |  | 0 | 15715.1 | 74410 | 21.61% | 0 | 74410 | 21.61% | 0 |  | 9746.05 | 38.28% | 9746.05 | 38.28% | 318923.85 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 891007 - GAINESVILLE REGIONAL UTILITIES | WATER | WATER SUPPLY | 2019-12-13 | 2020-06-30 | 2019-12-13 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 985212¦¦2020-03-31
FP | C | Yes | 985524 |  | BAXTER SPRINGS KS WELL 5 PULL | WARTICK, LOGAN M | 100% | 9575 | 0 | 9575 | 9575 | 9575 | 9575 | 0 | 0 | 9575 | 7851 | 0 | 7851 | 2640.46 | 16.39 |  |  | 2624.07 |  |  | 9754 | 3871.76 | 1423.88 |  | 4458.36 |  |  | 0 | 179 | 124.2% |  | 0 | 9754 | 1724 | 18.01% | 0 | 1724 | 18.01% | 0 |  | -179 | -1.869% | -179 | -1.869% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 886857 - BAXTER SPRINGS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-13 | 2020-05-05 | 2019-12-13 | 2020-05-05 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 985524¦¦2020-03-31
FP | CJ | Yes | 986017 |  | LAWCO EUNICE WELL 3 | GNAU, CASEY T | 100% | 18900 | 0 | 18900 | 19995 | 19995 | 19995 | 0 | 0 | 19995 | 11298 | 0 | 11298 | 0 |  |  |  | 0 |  |  | 10600.3 | 2916.74 | 1005.26 |  | 5816.38 | 861.92 |  | 9394.7 | 0 | 93.82% |  | 0 | 10600.3 | 7602 | 40.22% | 0 | 7602 | 40.22% | 0 |  | 9394.7 | 46.99% | 9394.7 | 46.99% | -1095 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 893536 - LAWCO | WATER | WATER REPAIR & INSTALLATION | 2019-12-16 | 2019-12-31 | 2019-12-16 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 986017¦¦2020-03-31
FP | C | Yes | 986018 |  | CHANUTE KS INTAKE PUMP PULL | WARTICK, LOGAN M | 100% | 10462 | 0 | 10462 | 34069 | 34069 | 34069 | 0 | 0 | 34069 | 7215 | 0 | 7215 | 1239.21 | 483.89 | 111.3 |  | 644.02 |  |  | 16972.53 | 6714.45 | 1560.86 |  | 8609.92 | 87.3 |  | 17096.47 | 0 | 235.2% |  | 0 | 16972.53 | 3247 | 31.04% | 0 | 3247 | 31.04% | 0 |  | 17096.47 | 50.18% | 17096.47 | 50.18% | -23607 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 985919 - RE PEDROTTI CO INC | WATER | WATER REPAIR & INSTALLATION | 2019-12-15 | 2020-05-15 | 2019-12-15 | 2020-05-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 986018¦¦2020-03-31
FP | C | Yes | 986019 |  | EDINBURG WELL 10 REPLACEMENT | WHITE, CATHLEEN R | 100% | 12129 | 0 | 12129 | 12129 | 12129 | 12129 | 0 | 0 | 12129 | 8559 | 0 | 8559 | 0 |  |  |  | 0 |  |  | 7219.58 | 4306.31 | 18.55 |  | 2894.72 |  |  | 4909.42 | 0 | 84.35% |  | 0 | 7219.58 | 3570 | 29.43% | 0 | 3570 | 29.43% | 0 |  | 4909.42 | 40.48% | 4909.42 | 40.48% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 890041 - EDINBURG, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-16 | 2020-01-31 | 2019-12-16 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 986019¦¦2020-03-31
FP | CJ | Yes | 986020 |  | ARVIN COMM DISTRICT WELL 12 | SEIDEN, ANDREW L. | 100% | 196785 | 0 | 196785 | 3033.47 | 3033.47 | 0 | 0 | 0 | 3033.47 | 160805 | 0 | 160805 | 2405.61 | 34.59 | 11.7 |  | 2359.32 |  |  | 2450.72 | 34.59 | 11.7 |  | 2404.43 |  |  | 582.75 | 0 | 1.524% |  | 0 | 2450.72 | 35980 | 18.28% | 0 | 35980 | 18.28% | 0 |  | 582.75 | 19.21% | 582.75 | 19.21% | 193751.53 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 861 - WRD HANFORD | HANFORD - WA | 984941 - UNIFIED FIELD SERVICES CORPORATION | WATER | WATER SUPPLY | 2019-12-12 | 2020-02-01 | 2019-12-12 | 2020-02-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 986020¦¦2020-03-31
FP | CJ | Yes | 986082 |  | SONORAN VISTA VESSEL REPL | MCCARTNEY, JEFFREY C | 100% | 179145 | 0 | 179145 | 179145 | 179145 | 179145 | 179145 | 0 | 179145 | 106370.5 | 0 | 106370.5 | 20054.56 | 2961.56 |  |  | -6485.97 | 23578.97 |  | 104777.12 | 4327.28 |  |  | 20486.12 | 79963.72 |  | 74367.88 | 0 | 98.5% |  | 0 | 104777.12 | 72774.5 | 40.62% | 0 | 72774.5 | 40.62% | 0 |  | 74367.88 | 41.51% | 74367.88 | 41.51% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 887556 - BUCKEYE, AZ, CITY OF | WATER | WATER TREATMENT | 2019-12-16 | 2020-03-31 | 2019-12-16 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 986082¦¦2020-03-31
FP | CJ | Yes | 986129 |  | CITGO 143 EMERGENCY | GNAU, CASEY T | 100% | 21173 | 0 | 21173 | 19515 | 19515 | 19515 | 0 | 0 | 19515 | 10586 | 0 | 10586 | [7 empty] | 8956.86 | 4510.95 | 432.47 |  | 1699.24 | 2314.2 |  | 10558.14 | 0 | 84.61% |  | 0 | 8956.86 | 10587 | 50% | 0 | 10587 | 50% | 0 |  | 10558.14 | 54.1% | 10558.14 | 54.1% | 1658 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878864 - CITGO PETROLEUM CORP | WATER | WATER REPAIR & INSTALLATION | 2019-12-17 | 2019-12-31 | 2019-12-17 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 986129¦¦2020-03-31
FP | C | Yes | 986130 |  | WEST COLUMBIA PULL AND INSPECT | CALLAHAN, DANIEL E. | 100% | 8275 | 29996 | 38271 | 37921 | 37921 | 37921 | 0 | 0 | 37921 | 5501 | 17732.84 | 23233.84 | 0 |  |  |  | 0 |  |  | 55009.82 | 21169.73 | 10285.33 |  | 23554.76 |  |  | 0 | 17088.82 | 236.8% |  | 0 | 55009.82 | 2774 | 33.52% | 12263.16 | 15037.16 | 39.29% | 12263.16 |  | -17088.82 | -45.06% | -17088.82 | -45.06% | 350 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA | 900085 - WEST COLUMBIA, TX, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-03-02 | 2019-12-09 | 2020-03-02 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 986130¦¦2020-03-31
TM | CJ | Yes | 986997 |  | ALFRED ZAUNBRECHER | GNAU, CASEY T | 100% | 15000 | 0 | 15000 | 8435 | 8435 | 8435 | 0 | 0 | 8435 | 9000 | 0 | 9000 | 0 |  |  |  | 0 |  |  | 5549.23 | 3326.92 | 808.17 |  | 1414.14 |  |  | 2885.77 | 0 | 61.66% |  | 0 | 5549.23 | 6000 | 40% | 0 | 6000 | 40% | 0 |  | 2885.77 | 34.21% | 2885.77 | 34.21% | 6565 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 986893 - ALFRED ZAUNBRECHER | WATER | WATER REPAIR & INSTALLATION | 2019-12-16 | 2019-12-31 | 2019-12-16 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 986997¦¦2020-03-31
FP | C | Yes | 986999 |  | JEFFERSON CO RWD 13 NORTH | WARTICK, LOGAN M | 100% | 5388 | 0 | 5388 | 10749 | 10749 | 10749 | 0 | 0 | 10749 | 4041 | 0 | 4041 | 0 |  |  |  | 0 |  |  | 4723.57 | 2737.6 | 739.03 |  | 1246.94 |  |  | 6025.43 | 0 | 116.9% |  | 0 | 4723.57 | 1347 | 25% | 0 | 1347 | 25% | 0 |  | 6025.43 | 56.06% | 6025.43 | 56.06% | -5361 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 892767 - JEFFERSON CO RWD NO 13 | WATER | WATER REPAIR & INSTALLATION | 2019-12-18 | 2020-04-05 | 2019-12-18 | 2020-04-05 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 986999¦¦2020-03-31
TM | CJ | Yes | 987000 |  | SJC 2 BOOSTER R AND I | SEIDEN, ANDREW L. | 100% | 13918 | 14459 | 28377 | 28377 | 28377 | 6028 | 0 | 0 | 28377 | 10359 | 11627.49 | 21986.49 | 14530.54 | 6748.11 | 1322.75 |  | 3517 | 2942.68 |  | 28267.05 | 8217.1 | 1322.75 |  | 12205.21 | 6521.99 |  | 109.95 | 0 | 128.6% |  | 0 | 28267.05 | 3559 | 25.57% | 2831.51 | 6390.51 | 22.52% | 2831.51 | 2831.51 | 109.95 | 0.3875% | 109.95 | 0.3875% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878779 - SAN JUAN CAPISTRANO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-11 | 2019-12-31 | 2019-12-11 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 987000¦¦2020-03-31
FP | CJ | Yes | 987001 |  | DAVIE FL WELL 3 PUMP AND MOTOR | TORMOEHLEN, DAVID A. | 100% | 24140 | 0 | 24140 | 13880 | 13880 | 13880 | 0 | 0 | 13880 | 14698 | 0 | 14698 | 515.7 | 268 | 120.58 |  | 127.12 |  |  | 7265.37 | 268 | 120.58 |  | 6876.79 |  |  | 6614.63 | 0 | 49.43% |  | 0 | 7265.37 | 9442 | 39.11% | 0 | 9442 | 39.11% | 0 |  | 6614.63 | 47.66% | 6614.63 | 47.66% | 10260 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 878976 - DAVIE, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-11 | 2020-02-29 | 2019-12-11 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 987001¦¦2020-03-31
FP | CJ | Yes | 987002 |  | DESERT CENTER SITE WORK | TRAMMELL, DUANE R. | 100% | 495000 | 0 | 495000 | 488081.64 | 488081.64 | 0 | 0 | 0 | 488081.64 | 394572 | 0 | 394572 | 135316.79 | 70306.38 | 16677.81 |  | 48332.6 |  |  | 394318.49 | 112822.1 | 30923.94 |  | 217094.72 | 33477.73 |  | 93763.15 | 0 | 99.94% |  | 0 | 394318.49 | 100428 | 20.29% | 0 | 100428 | 20.29% | 0 |  | 93763.15 | 19.21% | 93763.15 | 19.21% | 6918.36 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879013 - GRANITE CONSTRUCTION COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-02 | 2020-03-15 | 2019-12-02 | 2020-03-15 | SUBCONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 987002¦¦2020-03-31
FP | CJ | Yes | 987003 |  | KCP AND L LAKE ROAD 2019WELL14 | WARTICK, LOGAN M | 100% | 28404 | 179875 | 208279 | 179499 | 179499 | 179499 | 0 | 0 | 179499 | 18463 | 126671.24 | 145134.24 | 37910 | 14198.74 | 6585.11 |  | 14986.15 | 2140 |  | 68864.63 | 20704.7 | 10732.46 |  | 35287.47 | 2140 |  | 110634.37 | 0 | 47.45% |  | 0 | 68864.63 | 9941 | 35% | 53203.76 | 63144.76 | 30.32% | 53203.76 |  | 110634.37 | 61.64% | 110634.37 | 61.64% | 28780 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 986353 - EVERGY | WATER | WATER SUPPLY | 2019-12-18 | 2020-03-18 | 2019-12-18 | 2020-03-18 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 987003¦¦2020-03-31
FP | C | Yes | 987004 |  | CITY OF NEWPORT BEACH MSA | SEIDEN, ANDREW L. |  | 25000 | 0 | 25000 |  |  | 0 | 0 | 0 |  | 20000 | 0 | 20000 | [20 empty] | 5000 | 20% | 0 | 5000 | 20% | 0 | [5 empty] | 25000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878826 - NEWPORT BEACH, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-18 | 2019-12-31 | 2019-12-18 | 2019-12-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 987004¦¦2020-03-31
FP | LJ | Yes | 987010 |  | SRP 69E9 N WELL INSTALLATION | COMBS, TAYLOR E. | 92.59% | 712191.2 | 0 | 712191.2 | 583971.8826 | 515464 | 515464 | 0 | 0 | 630733 | 592048.76 | 0 | 592048.76 | 158654.56 | 40514.01 | 54057.83 | 23057.5 | 24825.22 | 16200 |  | 574890.72 | 133490.26 | 161877.74 | 25382.5 | 233717.94 | 20422.28 |  | 0 | 59426.72 | 97.1% |  | 46033.95 | 620924.67 | 120142.44 | 16.87% | 0 | 120142.44 | 16.87% | 0 |  | 9081.16 | 1.555% | 9808.33 | 1.555% | 128219.32 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878691 - SALT RIVER PROJECT | WATER | WATER SUPPLY | 2019-12-16 | 2020-03-01 | 2019-12-16 | 2020-03-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 987010¦¦2020-03-31
UP | CJ | Yes | 987188 |  | WELL 4 PERC WATER ADELANTO | BRASHEAR, DAVID M | 100% | 38198 | 0 | 38198 | 45547.79 | 45547.79 | 46289.79 | 0 | 0 | 45547.79 | 27467 | 0 | 27467 | 11.86 | -0.02 |  |  | 11.88 |  |  | 26966.93 | 10080.87 | 3521.97 |  | 11914.09 | 1450 |  | 18580.86 | 0 | 98.18% |  | 0 | 26966.93 | 10731 | 28.09% | 0 | 10731 | 28.09% | 0 |  | 18580.86 | 40.79% | 18580.86 | 40.79% | -7349.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878644 - ADELANTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-03 | 2020-01-31 | 2019-12-03 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 987188¦¦2020-03-31
TM | C | Yes | 987477 |  | PATOKA WELL 5 REHAB | MIGUEL, SEAN J. | 100% | 14500 | 4923 | 19423 | 19423 | 19423 | 19423 | 0 | 0 | 19423 | 11260 | 3545 | 14805 | 0 |  |  |  | 0 |  |  | 16415.89 | 7209.23 | 3494.77 |  | 5711.89 |  |  | 3007.11 | 0 | 110.9% |  | 0 | 16415.89 | 3240 | 22.34% | 1378 | 4618 | 23.78% | 1378 |  | 3007.11 | 15.48% | 3007.11 | 15.48% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 896083 - PATOKA, IN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-19 | 2020-01-30 | 2019-12-19 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 987477¦¦2020-03-31
TM | C | Yes | 987478 |  | PAMPLICO RIVER ROAD WELL | PARSLEY, TRISTAN S | 100% | 6500 | 29072 | 35572 | 36657 | 36657 | 36657 | 14934.22 | 0 | 36657 | 4513 | 23941.41 | 28454.41 | 478.4 |  |  |  | 478.4 |  |  | 31329.76 | 8894.2 | 1834.72 |  | 20600.84 |  |  | 5327.24 | 0 | 110.1% |  | 0 | 31329.76 | 1987 | 30.57% | 5130.59 | 7117.59 | 20.01% | 5130.59 |  | 5327.24 | 14.53% | 5327.24 | 14.53% | -1085 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 896004 - PAMPLICO, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-12 | 2020-01-31 | 2019-12-12 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 987478¦¦2020-03-31
FP | CJ | Yes | 987479 |  | BAILEY SIMPSON FARMS LLC PR | BENNETT, MARK C. | 100% | 28000 | 0 | 28000 | 13953.49 | 13953.49 | 15000 | 0 | 0 | 13953.49 | 22400 | 0 | 22400 | [7 empty] | 6.84 |  |  |  | 6.84 |  |  | 13946.65 | 0 | 0.03054% |  | 0 | 6.84 | 5600 | 20% | 0 | 5600 | 20% | 0 |  | 13946.65 | 99.95% | 13946.65 | 99.95% | 14046.51 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 886726 - BAILEY SIMPSON | WATER | WATER REPAIR & INSTALLATION | 2019-12-19 | 2020-08-15 | 2019-12-19 | 2020-08-15 | PRIME CONTRACTOR | PRIVATE | EXPENSE JOB | 987479¦¦2020-03-31
TM | CJ | Yes | 987480 |  | PRAXAIR SULPHUR WELL 1 | GNAU, CASEY T | 100% | 22500 | 8350 | 30850 | 30850 | 30850 | 30850 | 30850 | 0 | 30850 | 12350 | 3757 | 16107 | 0.01 |  |  |  | 0.01 |  |  | 15182.25 | 4462.28 | 932.48 |  | 9787.49 |  |  | 15667.75 | 0 | 94.26% |  | 0 | 15182.25 | 10150 | 45.11% | 4593 | 14743 | 47.79% | 4593 | 4593 | 15667.75 | 50.79% | 15667.75 | 50.79% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 896548 - PRAXAIR INC | WATER | WATER REPAIR & INSTALLATION | 2019-12-19 | 2019-12-31 | 2019-12-19 | 2019-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 987480¦¦2020-03-31
FP | CJ | Yes | 987481 |  | NILES BOLLER PUMP 1 AND 3 | EISHA, JOSEPH J. | 100% | 68680 | 0 | 68680 | 68680 | 68680 | 68680 | 68680 | 0 | 68680 | 40800 | 0 | 40800 | 31636.42 | 3363.86 | 10 |  | 28262.56 |  |  | 35616.18 | 6373.88 | 51.43 |  | 29190.87 |  |  | 33063.82 | 0 | 87.29% |  | 0 | 35616.18 | 27880 | 40.59% | 0 | 27880 | 40.59% | 0 |  | 33063.82 | 48.14% | 33063.82 | 48.14% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 887282 - BOLLER CONSTRUCTION COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-10 | 2020-02-05 | 2019-12-10 | 2020-02-05 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 987481¦¦2020-03-31
UP | C | Yes | 987482 |  | OTTAWA IL WELL 12 MOTOR REHAB | EISHA, JOSEPH J. | 100% | 9960 | 0 | 9960 | 19544 | 19544 | 19544 | 0 | 0 | 19544 | 5800 | 0 | 5800 | 2229.1 | 1758.85 | 126.56 |  | 343.69 |  |  | 13764.89 | 5394.23 | 920.68 |  | 7449.98 |  |  | 5779.11 | 0 | 237.3% |  | 0 | 13764.89 | 4160 | 41.77% | 0 | 4160 | 41.77% | 0 |  | 5779.11 | 29.57% | 5779.11 | 29.57% | -9584 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 895898 - OTTAWA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-20 | 2020-02-25 | 2019-12-20 | 2020-02-25 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 987482¦¦2020-03-31
UP | CJ | Yes | 987819 |  | TOWN OF APPLE VALLEY GC | BRASHEAR, DAVID M | 100% | 358482 | 0 | 358482 | 3450.34 | 3450.34 | 0 | 0 | 0 | 3450.34 | 174079 | 0 | 174079 | 2304.55 |  |  |  | 2304.55 |  |  | 2787.51 |  |  |  | 2787.51 |  |  | 662.83 | 0 | 1.601% |  | 0 | 2787.51 | 184403 | 51.44% | 0 | 184403 | 51.44% | 0 |  | 662.83 | 19.21% | 662.83 | 19.21% | 355031.66 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 886362 - APPLE VALLEY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-10 | 2020-04-01 | 2019-12-10 | 2020-04-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 987819¦¦2020-03-31
FP | C | Yes | 987820 |  | SARALAND WELL 1 | PARSLEY, TRISTAN S | 100% | 24014 | 28154.8 | 52168.8 | 52168.8 | 52168.8 | 52168.8 | 0 | 0 | 52168.8 | 16784 | 20069.53 | 36853.53 | 14.64 |  |  |  | 14.64 |  |  | 31718.57 | 9077.34 | 2359.39 |  | 19516.84 | 765 |  | 20450.23 | 0 | 86.07% |  | 0 | 31718.57 | 7230 | 30.11% | 8085.27 | 15315.27 | 29.36% | 8085.27 |  | 20450.23 | 39.2% | 20450.23 | 39.2% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 897504 - SARALAND WATER & SEWER BOARD | WATER | WATER SUPPLY | 2019-12-23 | 2020-02-29 | 2019-12-23 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 987820¦¦2020-03-31
FP | C | Yes | 987821 |  | BRW SOUTER 5 | LOPEZ-VASQUEZ, JUAN C. | 100% | 3450 | 48735 | 52185 | 50610 | 50610 | 54038.29 | 0 | 0 | 50610 | 3218 | 35403 | 38621 | 608.67 | 300.16 | 111.3 |  | 197.21 |  |  | 44931.59 | 12748.73 | 4211.94 |  | 27470.92 | 500 |  | 5678.41 | 0 | 116.3% |  | 0 | 44931.59 | 232 | 6.725% | 13332 | 13564 | 25.99% | 13332 |  | 5678.41 | 11.22% | 5678.41 | 11.22% | 1575 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2019-12-23 | 2020-01-30 | 2019-12-23 | 2020-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 987821¦¦2020-03-31
FP | CJ | Yes | 987822 |  | KIMBERLY CLARK WELL 3 REHAB | MIGUEL, SEAN J. | 100% | 19750 | 10186 | 29936 | 29936 | 29936 | 29936 | 29936 | 0 | 29936 | 15783 | 7639 | 23422 | 4.99 |  |  |  | 4.99 |  |  | 20891.79 | 8628.58 | 3123.68 |  | 7839.53 | 1300 |  | 9044.21 | 0 | 89.2% |  | 0 | 20891.79 | 3967 | 20.09% | 2547 | 6514 | 21.76% | 2547 |  | 9044.21 | 30.21% | 9044.21 | 30.21% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879048 - KIMBERLY CLARK CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2019-12-09 | 2020-02-28 | 2019-12-09 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 987822¦¦2020-03-31
UP | C | Yes | 987823 |  | SOUTH ELGIN IL WELL 12 | SNELTEN, BRIAN M | 100% | 10276 | 28084 | 38360 | 36284 | 36284 | 36284 | 0 | 0 | 36284 | 7056 | 16476 | 23532 | 12884.73 | 6989.33 | 1831.57 |  | 4063.83 |  |  | 22341.23 | 11353.47 | 2646.87 |  | 8340.89 |  |  | 13942.77 | 0 | 94.94% |  | 0 | 22341.23 | 3220 | 31.34% | 11608 | 14828 | 38.65% | 11608 |  | 13942.77 | 38.43% | 13942.77 | 38.43% | 2076 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 898030 - SOUTH ELGIN, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2019-12-23 | 2020-03-31 | 2019-12-23 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 987823¦¦2020-03-31
CR | C | Yes | 987877 |  | LAKE SUCCESS NY WTP MANWAY | RANFT, DONALD R | 100% | 2642.41 | 0 | 2642.41 | 2583 | 2583 | 2583 | 0 | 0 | 2583 | 1606.75 | 0 | 1606.75 | 0 |  |  |  | 0 |  |  | 1718.2 | 420.89 |  |  | 1297.31 |  |  | 864.8 | 0 | 106.9% |  | 0 | 1718.2 | 1035.66 | 39.19% | 0 | 1035.66 | 39.19% | 0 |  | 864.8 | 33.48% | 864.8 | 33.48% | 59.41 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 987381 - WOOD ENVIRONMENT AND INFRASTRUCTURE INC | WATER | WATER TREATMENT | 2019-12-18 | 2020-02-29 | 2019-12-18 | 2020-02-29 | SUBCONTRACTOR | PRIVATE | COST REIMBURSIBLE | 987877¦¦2020-03-31
FP | C | Yes | 989299 |  | ST MARY SUGAR TROUBLESHOOT | GNAU, CASEY T | 100% | 1900 | 0 | 1900 | 1900 | 1900 | 1900 | 0 | 0 | 1900 | 1054 | 0 | 1054 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 1899.99 | 0 | 0.0009488% |  | 0 | 0.01 | 846 | 44.53% | 0 | 846 | 44.53% | 0 |  | 1899.99 | 100% | 1899.99 | 100% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 898369 - ST MARY SUGAR CO OP, INC | WATER | WATER REPAIR & INSTALLATION | 2019-12-26 | 2019-12-30 | 2019-12-26 | 2019-12-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 989299¦¦2020-03-31
FP | CJ | Yes | 989382 |  | GREEN PLAINS WELL 8 | ANDERSON, STEPHEN P. | 100% | 5815 | 66355 | 72170 | 72170 | 72170 | 72170 | 0 | 0 | 72170 | 4361 | 43611.98 | 47972.98 | 16527.84 | 4121.75 | 1273.81 |  | 11132.28 |  |  | 52164.52 | 18362.75 | 7248.91 |  | 26552.86 |  |  | 20005.48 | 0 | 108.7% |  | 0 | 52164.52 | 1454 | 25% | 22743.02 | 24197.02 | 33.53% | 22743.02 |  | 20005.48 | 27.72% | 20005.48 | 27.72% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 879091 - GREEN PLAINS OBION LLC | WATER | WATER REPAIR & INSTALLATION | 2019-12-26 | 2020-01-31 | 2019-12-26 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 989382¦¦2020-03-31
UP | C | Yes | 989611 |  | COLCHESTER CT LAYNEOX REPL | MCCARTNEY, JEFFREY C | 100% | 24099.5 | 0 | 24099.5 | 24099.5 | 24099.5 | 24099.5 | 0 | 0 | 24099.5 | 20455 | 0 | 20455 | 0.01 | 0.01 |  |  | 0 |  |  | 22135.2 | 225.06 |  |  | 21910.14 |  |  | 1964.3 | 0 | 108.2% |  | 0 | 22135.2 | 3644.5 | 15.12% | 0 | 3644.5 | 15.12% | 0 |  | 1964.3 | 8.151% | 1964.3 | 8.151% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 989500 - WATER SERVICE PROFESSIONALS | WATER | WATER TREATMENT | 2020-01-01 | 2020-02-29 | 2020-01-01 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 989611¦¦2020-03-31
FP | CJ | Yes | 989853 |  | EXXON BRPP 961A | LOPEZ-VASQUEZ, JUAN C. | 100% | 42020 | 19860 | 61880 | 61880 | 61880 | 61880 | 61880 | 0 | 61880 | 25212 | 5288 | 30500 | 0 |  |  |  | 0 |  |  | 37137.7 | 15019.41 | 2875.92 |  | 19242.37 |  |  | 24742.3 | 0 | 121.8% |  | 0 | 37137.7 | 16808 | 40% | 14572 | 31380 | 50.71% | 14572 |  | 24742.3 | 39.98% | 24742.3 | 39.98% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878941 - EXXON MOBIL CHEMICAL COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-01-02 | 2020-06-30 | 2020-01-02 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 989853¦¦2020-03-31
FP | CJ | Yes | 989854 |  | MILLINGTON NAVAL PWM TESTING | ANDERSON, STEPHEN P. | 100% | 3000 | 0 | 3000 | 3000 | 3000 | 2400 | 0 | 0 | 3000 | 2098 | 0 | 2098 | 1291.86 | 626.39 | 166.95 |  | 498.52 |  |  | 3547.11 | 1713.17 | 686.35 |  | 1147.59 |  |  | 0 | 547.11 | 169.1% |  | 0 | 3547.11 | 902 | 30.07% | 0 | 902 | 30.07% | 0 |  | -547.11 | -18.24% | -547.11 | -18.24% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 893216 - KJS MP JOINT VENTURE FORMERLY CTSI CES | WATER | WATER REPAIR & INSTALLATION | 2020-01-02 | 2020-01-31 | 2020-01-02 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 989854¦¦2020-03-31
FP | C | Yes | 989855 |  | CORBIN UTILITIES DS | MIGUEL, SEAN J. | 100% | 2775 | 0 | 2775 | 2918.75 | 2918.75 | 2918.75 | 0 | 0 | 2918.75 | 1976 | 0 | 1976 | [7 empty] | 2120.32 |  |  |  | 2120.32 |  |  | 798.43 | 0 | 107.3% |  | 0 | 2120.32 | 799 | 28.79% | 0 | 799 | 28.79% | 0 |  | 798.43 | 27.36% | 798.43 | 27.36% | -143.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878574 - CORBIN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-01 | 2020-01-30 | 2020-01-01 | 2020-01-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 989855¦¦2020-03-31
TM | C | Yes | 989856 |  | HODGENVILLE RWP 3 | MIGUEL, SEAN J. | 100% | 5000 | 6511 | 11511 | 10824 | 10824 | 10824 | 0 | 0 | 10824 | 3750 | 5010 | 8760 | 0 |  |  |  | 0 |  |  | 8664.36 | 3809.64 | 1203.08 |  | 3503.14 | 148.5 |  | 2159.64 | 0 | 98.91% |  | 0 | 8664.36 | 1250 | 25% | 1501 | 2751 | 23.9% | 1501 |  | 2159.64 | 19.95% | 2159.64 | 19.95% | 687 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 892168 - HODGENVILLE, KY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-02 | 2020-02-28 | 2020-01-02 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 989856¦¦2020-03-31
TM | CJ | Yes | 989857 |  | AK IMS MAINTENANCE | BARNES, MATTHEW D | 100% | 240000 | 44867.35 | 284867.35 | 79859.45 | 79859.45 | 79859.45 | 58737.1 | 0 | 79859.45 | 184800 | 32285 | 217085 | 16933.53 | 11321.48 | 2931.36 |  | 3426.19 | -745.5 |  | 72901.59 | 30238.65 | 7283.73 |  | 30332.98 | 5046.23 |  | 6957.86 | 0 | 33.58% |  | 0 | 72901.59 | 55200 | 23% | 12582.35 | 67782.35 | 23.79% | 12582.35 |  | 6957.86 | 8.713% | 6957.86 | 8.713% | 205007.9 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2020-01-01 | 2020-12-31 | 2020-01-01 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 989857¦¦2020-03-31
FP | CJ | Yes | 989858 |  | AK EAST SIDE MAINTENANCE | BARNES, MATTHEW D | 100% | 142200 | 15749 | 157949 | 109414.08 | 109414.08 | 51299 | 11850 | 0 | 109414.08 | 106650 | 11024 | 117674 | 39045.83 | 20257.72 | 8623.32 |  | 10164.79 |  |  | 88395.04 | 35860.87 | 15507.97 |  | 37026.2 |  |  | 21019.04 | 0 | 75.12% |  | 0 | 88395.04 | 35550 | 25% | 4725 | 40275 | 25.5% | 4725 |  | 21019.04 | 19.21% | 21019.04 | 19.21% | 48534.92 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2020-01-01 | 2020-12-31 | 2020-01-01 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 989858¦¦2020-03-31
TM | C | Yes | 989859 |  | DOW WELL 2 | MIGUEL, SEAN J. | 100% | 5000 | 59540 | 64540 | 64540 | 64540 | 64540 | 64540 | 0 | 64540 | 3385 | 45410 | 48795 | 24490.59 | 5856.09 | 2261.71 |  | 16289.02 | 83.77 |  | 40271.71 | 10789.48 | 3324.97 |  | 22291.49 | 3865.77 |  | 24268.29 | 0 | 82.53% |  | 0 | 40271.71 | 1615 | 32.3% | 14130 | 15745 | 24.4% | 14130 |  | 24268.29 | 37.6% | 24268.29 | 37.6% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889765 - DOW SILICONES CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-01-02 | 2020-02-28 | 2020-01-02 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 989859¦¦2020-03-31
FP | C | Yes | 989860 |  | OXFORD MS PWM TESTING | ANDERSON, STEPHEN P. | 100% | 3000 | 0 | 3000 | 3600 | 3600 | 3600 | 0 | 0 | 3600 | 3000 | 0 | 3000 | 1.64 |  |  |  | 1.64 |  |  | 6452.83 | 2986.05 | 1307.78 |  | 2159 |  |  | 0 | 2852.83 | 215.1% |  | 0 | 6452.83 | 0 | 0% | 0 | 0 | 0% | 0 |  | -2852.83 | -79.25% | -2852.83 | -79.25% | -600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895929 - OXFORD, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-02 | 2020-01-31 | 2020-01-02 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 989860¦¦2020-03-31
UP | CJ | Yes | 989861 |  | KTG KRUGER | ANDERSON, STEPHEN P. | 100% | 28950 | 0 | 28950 | 7800 | 7800 | 7800 | 0 | 0 | 7800 | 22295 | 0 | 22295 | 35.08 |  |  |  | 35.08 |  |  | 3779.31 | 1592.24 | 844.08 |  | 1342.99 |  |  | 4020.69 | 0 | 16.95% |  | 0 | 3779.31 | 6655 | 22.99% | 0 | 6655 | 22.99% | 0 |  | 4020.69 | 51.55% | 4020.69 | 51.55% | 21150 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 977270 - KTG USA INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-02 | 2020-04-24 | 2020-01-06 | 2020-04-24 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 989861¦¦2020-03-31
UP | FJ | Yes | 989910 |  | FAYETTE MS NEW WELL | ANDERSON, STEPHEN P. | 28.12% | 489762 | 0 | 489762 | 137743.5234 | 0 | 0 | 0 | 0 | 489762 | 391809 | 0 | 391809 | 19297.21 | 7624.1 | 3767.71 |  | 7905.4 |  |  | 110194.65 | 15931.71 | 8830.89 |  | 85432.05 |  |  | 0 | 110194.65 | 28.12% |  | 281614.35 | 391809 | 97953 | 20% | 0 | 97953 | 20% | 0 |  | 27548.87 | 20% | 97953 | 20% | 352018.48 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 911567 - FAYETTE, CITY OF | WATER | WATER SUPPLY | 2020-01-02 | 2020-10-31 | 2020-01-02 | 2020-10-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 989910¦¦2020-03-31
FP | LJ | Yes | 989925 |  | NICHOLS HILLS WELL 17 | EVANS, TRAVIS L | 29.64% | 848678.9 | 0 | 848678.9 | 251580.0637 | 302067 | 302067 | 0 | 15103.35 | 848678.9 | 668067.71 | 0 | 668067.71 | 180681.34 | 45663.34 | 36336.23 |  | 76636.83 | 22044.94 |  | 198040.26 | 46410.19 | 36522.79 |  | 80572.34 | 34534.94 |  | 104026.74 | 0 | 29.64% |  | 470027.74 | 668068 | 180611.19 | 21.28% | 0 | 180611.19 | 21.28% | 0 |  | 53539.8 | 21.28% | 180610.9 | 21.28% | 597098.84 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 878678 - NICHOLS HILLS, CITY OF | WATER | WATER SUPPLY | 2020-01-01 | 2020-07-02 | 2020-01-01 | 2020-07-02 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 989925¦¦2020-03-31
FP | CJ | Yes | 990250 |  | RICHTON PARK IL WELL 4 REHAB | EISHA, JOSEPH J. | 100% | 13704 | 67854.5 | 81558.5 | 81462.5 | 81462.5 | 81462.5 | 81462.5 | 0 | 81462.5 | 9200 | 39047.5 | 48247.5 | 36991.15 | 15550.81 | 2275.06 |  | 19165.28 |  |  | 47969.32 | 22444.76 | 4079.5 |  | 21445.06 |  |  | 33493.18 | 0 | 99.42% |  | 0 | 47969.32 | 4504 | 32.87% | 28807 | 33311 | 40.84% | 28807 | 28807 | 33493.18 | 41.11% | 33493.18 | 41.11% | 96 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 897018 - RICHTON PARK, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-03 | 2020-04-06 | 2020-01-03 | 2020-04-06 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 990250¦¦2020-03-31
FP | C | Yes | 990570 |  | ROVISYS GOOGLE MONCKS CORNER | PARSLEY, TRISTAN S | 100% | 49975 | 0 | 49975 | 49975 | 49975 | 49975 | 0 | 0 | 49975 | 28036 | 0 | 28036 | 2.62 | 2.62 |  |  | 0 |  |  | 25991.67 | 12645.27 | 4322.45 |  | 9023.95 |  |  | 23983.33 | 0 | 92.71% |  | 0 | 25991.67 | 21939 | 43.9% | 0 | 21939 | 43.9% | 0 |  | 23983.33 | 47.99% | 23983.33 | 47.99% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 990264 - ROVISYS BUILDING TECHNOLOGIES | WATER | WATER REPAIR & INSTALLATION | 2020-01-01 | 2020-01-31 | 2020-01-02 | 2020-01-31 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 990570¦¦2020-03-31
TM | C | Yes | 990571 |  | AK WELL PIT 22 | BARNES, MATTHEW D | 100% | 25000 | 37745 | 62745 | 62745 | 62745 | 62745 | 0 | 0 | 62745 | 17500 | 29500 | 47000 | 1.71 | 1.71 |  |  | 0 |  |  | 40461.33 | 12748 | 12333.11 |  | 13630.22 | 1750 |  | 22283.67 | 0 | 86.09% |  | 0 | 40461.33 | 7500 | 30% | 8245 | 15745 | 25.09% | 8245 |  | 22283.67 | 35.51% | 22283.67 | 35.51% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2020-01-03 | 2020-02-28 | 2020-01-03 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 990571¦¦2020-03-31
UP | C | Yes | 990590 |  | MORRIS WELL 7 | KENNEDY, CHRISTOPHER C. | 100% | 150000 | 0 | 150000 | 137312 | 137312 | 137312 | 0 | 0 | 137312 | 112500 | 0 | 112500 | 30345.83 | 18925.94 | 5197.68 |  | 6222.21 |  |  | 96548.6 | 59472.68 | 12867.25 |  | 24208.67 |  |  | 40763.4 | 0 | 85.82% |  | 0 | 96548.6 | 37500 | 25% | 0 | 37500 | 25% | 0 |  | 40763.4 | 29.69% | 40763.4 | 29.69% | 12688 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 894991 - MORRIS, IL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-03 | 2020-05-30 | 2020-01-03 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 990590¦¦2020-03-31
UP | C | Yes | 990591 |  | TX BRINE WC WATER ANALYSIS | LOPEZ-VASQUEZ, JUAN C. | 100% | 5400 | 0 | 5400 | 5400 | 5400 | 5400 | 0 | 0 | 5400 | 3640 | 0 | 3640 | 0 |  |  |  | 0 |  |  | 2482.3 | 563.12 | 1154.29 |  | 351.89 | 413 |  | 2917.7 | 0 | 68.2% |  | 0 | 2482.3 | 1760 | 32.59% | 0 | 1760 | 32.59% | 0 |  | 2917.7 | 54.03% | 2917.7 | 54.03% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878775 - TEXAS BRINE WHITE CASTLE COMPANY LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-03 | 2020-04-30 | 2020-01-03 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 990591¦¦2020-03-31
UP | C | Yes | 990592 |  | CORINTH NY BOOSTER PUMP REPAIR | CROOK, CHARLES M | 100% | 58820 | 0 | 58820 | 47720 | 47720 | 47720 | 0 | 0 | 47720 | 43000 | 0 | 43000 | 224.75 | 156.72 |  |  | 68.03 |  |  | 20339.57 | 6521.48 | 1619.2 |  | 12198.89 |  |  | 27380.43 | 0 | 47.3% |  | 0 | 20339.57 | 15820 | 26.9% | 0 | 15820 | 26.9% | 0 |  | 27380.43 | 57.38% | 27380.43 | 57.38% | 11100 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 990353 - CORINTH, VILLAGE OF | WATER | WATER SUPPLY | 2020-01-01 | 2020-01-17 | 2020-01-01 | 2020-01-17 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 990592¦¦2020-03-31
FP | CJ | Yes | 991159 |  | PIKE RUN PUMP | BARNES, MATTHEW D | 100% | 6853 | 10384 | 17237 | 15632.05 | 15632.05 | 0 | 0 | 0 | 15632.05 | 4868 | 7061 | 11929 | 8870.14 | 1494.95 | 416.78 |  | 6958.41 |  |  | 12629.05 | 3546.54 | 1198.67 |  | 7883.84 |  |  | 3003 | 0 | 105.9% |  | 0 | 12629.05 | 1985 | 28.97% | 3323 | 5308 | 30.79% | 3323 |  | 3003 | 19.21% | 3003 | 19.21% | 1604.95 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 990216 - PIKE RUN GOLF CLUB | WATER | WATER REPAIR & INSTALLATION | 2020-01-03 | 2020-02-28 | 2020-01-03 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 991159¦¦2020-03-31
FP | C | Yes | 991160 |  | GHD WELL REHAB OU2EW N | VAN ALLEN, WESLEY C. | 100% | 30039 | 27324.92 | 57363.92 | 49339.51 | 49339.51 | 49339.51 | 0 | 0 | 49339.51 | 21997 | 21248.27 | 43245.27 | 95.34 | -0.01 |  |  | 95.35 |  |  | 35204.98 | 9900.54 | 2942.86 |  | 18562.82 | 3798.76 |  | 14134.53 | 0 | 81.41% |  | 0 | 35204.98 | 8042 | 26.77% | 6076.65 | 14118.65 | 24.61% | 6076.65 |  | 14134.53 | 28.65% | 14134.53 | 28.65% | 8024.41 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 891241 - GHD SERVICES, INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-06 | 2020-02-10 | 2020-01-06 | 2020-02-10 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 991160¦¦2020-03-31
FP | C | Yes | 991161 |  | ARKEMA WELL 1 CHEMICAL REHAB | PARSLEY, TRISTAN S | 100% | 60000 | 0 | 60000 | 60000 | 60000 | 60000 | 0 | 0 | 60000 | 44895 | 0 | 44895 | -0.01 |  |  |  | -0.01 |  |  | 45252.6 | 17553.29 | 5604.19 |  | 22095.12 |  |  | 14747.4 | 0 | 100.8% |  | 0 | 45252.6 | 15105 | 25.17% | 0 | 15105 | 25.17% | 0 |  | 14747.4 | 24.58% | 14747.4 | 24.58% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 886488 - ARKEMA INC | WATER | WATER SUPPLY | 2020-01-06 | 2020-02-29 | 2020-01-06 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 991161¦¦2020-03-31
UP | CJ | Yes | 991634 |  | CLARK EDGAR WELL 1 AND 3 PUMP | WHITE, CATHLEEN R | 100% | 39990 | 0 | 39990 | 20400 | 20400 | 20400 | 0 | 0 | 20400 | 28000 | 0 | 28000 | 134.3 |  |  |  | 134.3 |  |  | 17181.66 | 2555.5 | 70.2 |  | 14555.96 |  |  | 3218.34 | 0 | 61.36% |  | 0 | 17181.66 | 11990 | 29.98% | 0 | 11990 | 29.98% | 0 |  | 3218.34 | 15.78% | 3218.34 | 15.78% | 19590 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 888623 - CLARK EDGAR RURAL WATER | WATER | WATER REPAIR & INSTALLATION | 2020-01-06 | 2020-01-07 | 2020-01-06 | 2020-01-07 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 991634¦¦2020-03-31
UP | C | Yes | 991635 |  | CHURCHILL DOWNS TESTS | MIGUEL, SEAN J. | 100% | 1350 | 0 | 1350 | 1350 | 1350 | 1350 | 0 | 0 | 1350 | 1138 | 0 | 1138 | 0 |  |  |  | 0 |  |  | 1135.07 | 648.36 | 194.39 |  | 292.32 |  |  | 214.93 | 0 | 99.74% |  | 0 | 1135.07 | 212 | 15.7% | 0 | 212 | 15.7% | 0 |  | 214.93 | 15.92% | 214.93 | 15.92% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888386 - CHURCHILL DOWNS RACE TRACK | WATER | WATER REPAIR & INSTALLATION | 2020-01-06 | 2020-02-28 | 2020-01-06 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 991635¦¦2020-03-31
UP | CJ | Yes | 991636 |  | CITY OF LINCOLN PARTS | GANSEBOM, JASON W. | 100% | 15935 | 0 | 15935 | 20407.33 | 20407.33 | 21482.89 | 0 | 0 | 20407.33 | 5500 | 0 | 5500 | 3143.54 |  |  |  | 3143.54 |  |  | 9667.83 | 831.48 |  |  | 8500.32 | 336.03 |  | 10739.5 | 0 | 175.8% |  | 0 | 9667.83 | 10435 | 65.48% | 0 | 10435 | 65.48% | 0 |  | 10739.5 | 52.63% | 10739.5 | 52.63% | -4472.33 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878876 - LINCOLN, CITY OF | WATER | WATER EQUIPMENT SALES | 2020-01-06 | 2020-02-28 | 2020-01-06 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 991636¦¦2020-03-31
FP | CJ | Yes | 991637 |  | ST CHARLES WELL 11 BOOSTER | KENNEDY, CHRISTOPHER C. | 100% | 6269 | 33670 | 39939 | 9756.27 | 9756.27 | 6793 | 0 | 0 | 9756.27 | 4400 | 24000 | 28400 | 3290.74 | 322.91 |  |  | 2967.83 |  |  | 7882.04 | 3694.19 | 299.46 |  | 3888.39 |  |  | 1874.23 | 0 | 27.75% |  | 0 | 7882.04 | 1869 | 29.81% | 9670 | 11539 | 28.89% | 9670 | 9670 | 1874.23 | 19.21% | 1874.23 | 19.21% | 30182.73 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878882 - SAINT CHARLES, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-07 | 2020-01-31 | 2020-01-07 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 991637¦¦2020-03-31
FP | CJ | Yes | 991638 |  | PUNTA GORDA WWTP IW 1 MIT | MARTINEZ, MIGUEL E |  | 35000 | 0 | 35000 |  |  | 0 | 0 | 0 |  | 24466 | 0 | 24466 | [20 empty] | 10534 | 30.1% | 0 | 10534 | 30.1% | 0 | [5 empty] | 35000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 896652 - PUNTA GORDA, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-07 | 2020-06-01 | 2020-01-07 | 2020-06-01 | PRIME CONTRACTOR | PUBLIC | PROFESSIONAL SERVICES | 991638¦¦2020-03-31
UP | CJ | Yes | 991639 |  | LEONVILLE TEST | GNAU, CASEY T | 100% | 2400 | 0 | 2400 | 1200 | 1200 | 1200 | 0 | 0 | 1200 | 1420 | 0 | 1420 | 0.07 |  |  |  | 0.07 |  |  | 851.92 | 470.59 | 185.5 |  | 195.83 |  |  | 348.08 | 0 | 59.99% |  | 0 | 851.92 | 980 | 40.83% | 0 | 980 | 40.83% | 0 |  | 348.08 | 29.01% | 348.08 | 29.01% | 1200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 893676 - LEONVILLE, LA, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-06 | 2020-01-31 | 2020-01-06 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 991639¦¦2020-03-31
TM | CJ | Yes | 991640 |  | PPG ROUTINE SERVICES | BARNES, MATTHEW D | 100% | 18000 | 0 | 18000 | 3455.71 | 3455.71 | 3455.71 | 3455.71 | 0 | 3455.71 | 14760 | 0 | 14760 | 1141.64 |  |  |  | 0.5 | 1141.14 |  | 3181.73 |  |  |  | 26.3 | 3155.43 |  | 273.98 | 0 | 21.56% |  | 0 | 3181.73 | 3240 | 18% | 0 | 3240 | 18% | 0 |  | 273.98 | 7.928% | 273.98 | 7.928% | 14544.29 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878532 - PPG INDUSTRIES INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-07 | 2020-12-31 | 2020-01-07 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 991640¦¦2020-03-31
FP | CJ | Yes | 991653 |  | TURIN GA LAYNEOX | CHESLEY, ANDREW J | 100% | 166000 | 0 | 166000 | 57956.87 | 57956.87 | 41500 | 37350 | 4150 | 57956.87 | 104617.11 | 0 | 104617.11 | 24421.12 | 1565.41 |  |  | 9960.71 | 12895 |  | 46823.04 | 3451.07 |  |  | 17581.97 | 25790 |  | 11133.83 | 0 | 44.76% |  | 0 | 46823.04 | 61382.89 | 36.98% | 0 | 61382.89 | 36.98% | 0 |  | 11133.83 | 19.21% | 11133.83 | 19.21% | 108043.13 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 991361 - TURIN, TOWN OF | WATER | WATER TREATMENT | 2020-01-06 | 2020-06-30 | 2020-01-06 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 991653¦¦2020-03-31
TM | C | Yes | 991717 |  | DARDANELLE CITY OF TEST HOLES | SCHERM, LOGAN M | 100% | 66400 | 0 | 66400 | 66382 | 66382 | 66382 | 0 | 0 | 66382 | 51600 | 0 | 51600 | 1797.53 |  |  |  | 1797.53 |  |  | 37959.52 | 14674.87 | 7254.58 |  | 16030.07 |  |  | 28422.48 | 0 | 73.56% |  | 0 | 37959.52 | 14800 | 22.29% | 0 | 14800 | 22.29% | 0 |  | 28422.48 | 42.82% | 28422.48 | 42.82% | 18 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879083 - DARDANELLE, CITY OF | WATER | WATER SUPPLY | 2020-01-06 | 2020-05-30 | 2020-01-07 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 991717¦¦2020-03-31
FP | CJ | Yes | 991802 |  | EAST FORK ROCK HOLE | WILLIAMS, DONALD G. | 100% | 13000 | 0 | 13000 | 17068 | 17068 | 17068 | 0 | 0 | 17068 | 10027 | 0 | 10027 | 0 |  |  |  | 0 |  |  | 16564.38 | 6754.41 | 4543.11 |  | 5266.86 |  |  | 503.62 | 0 | 165.2% |  | 0 | 16564.38 | 2973 | 22.87% | 0 | 2973 | 22.87% | 0 |  | 503.62 | 2.951% | 503.62 | 2.951% | -4068 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878557 - EAST FORK WATER INC | WATER | WATER SUPPLY | 2020-01-08 | 2020-02-28 | 2020-01-08 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 991802¦¦2020-03-31
FP | C | Yes | 992014 |  | COMO MS ELECTRICAL INSPECTION | ANDERSON, STEPHEN P. | 100% | 420 | 0 | 420 | 420 | 420 | 420 | 0 | 0 | 420 | 312 | 0 | 312 | 0 |  |  |  | 0 |  |  | 200.79 | 117.72 |  |  | 83.07 |  |  | 219.21 | 0 | 64.36% |  | 0 | 200.79 | 108 | 25.71% | 0 | 108 | 25.71% | 0 |  | 219.21 | 52.19% | 219.21 | 52.19% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 888859 - COMO,TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-01-08 | 2020-01-08 | 2020-01-08 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 992014¦¦2020-03-31
FP | CJ | Yes | 992023 |  | TYSON MADISON NE HS PUMP | GANSEBOM, JASON W. | 100% | 123128 | 0 | 123128 | 143123.6 | 143123.6 | 143123.6 | 0 | 0 | 143123.6 | 69522 | 0 | 69522 | 7779.08 | 3126.19 | 1048.43 |  | 3604.46 |  |  | 81713.24 | 7108.69 | 2309.35 |  | 72295.2 |  |  | 61410.36 | 0 | 117.5% |  | 0 | 81713.24 | 53606 | 43.54% | 0 | 53606 | 43.54% | 0 |  | 61410.36 | 42.91% | 61410.36 | 42.91% | -19995.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878697 - TYSON FRESH MEATS MADISON NE | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-03-30 | 2020-01-08 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 992023¦¦2020-03-31
UP | CJ | Yes | 992579 |  | ARIZONA BEEMAN SELL SILIBEADS | COMBS, TAYLOR E. | 100% | 42560 | 0 | 42560 | 39200 | 39200 | 39200 | 39200 | 0 | 39200 | 39200 | 0 | 39200 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 39199.99 | 0 | 2.551e-05% |  | 0 | 0.01 | 3360 | 7.895% | 0 | 3360 | 7.895% | 0 |  | 39199.99 | 100% | 39199.99 | 100% | 3360 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 894969 - MOREX INVESTMENTS, DBA ARIZONA BEEMAN | WATER | WATER EQUIPMENT SALES | 2020-01-09 | 2020-02-02 | 2020-01-09 | 2020-02-02 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 992579¦¦2020-03-31
UP | CJ | Yes | 992591 |  | SAND KNOB FARM | EISHA, JOSEPH J. | 100% | 17278 | 0 | 17278 | 9094.74 | 9094.74 | 0 | 0 | 0 | 9094.74 | 11500 | 0 | 11500 | 5010.39 | 2776.6 | 406.54 |  | 1827.25 |  |  | 7347.59 | 4486.97 | 423.54 |  | 2437.08 |  |  | 1747.15 | 0 | 63.89% |  | 0 | 7347.59 | 5778 | 33.44% | 0 | 5778 | 33.44% | 0 |  | 1747.15 | 19.21% | 1747.15 | 19.21% | 8183.26 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 992204 - SAND KNOB FARM | WATER | WATER REPAIR & INSTALLATION | 2020-01-09 | 2020-02-24 | 2020-01-09 | 2020-02-24 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 992591¦¦2020-03-31
TM | C | Yes | 992594 |  | GP AND S FARMS | SCHERM, LOGAN M | 100% | 8000 | 0 | 8000 | 10725.25 | 10725.25 | 11529.65 | 29.36 | 0 | 10725.25 | 6000 | 0 | 6000 | 131.34 |  |  |  | 1.34 | 130 |  | 10651.05 | 5095.1 | 286.37 |  | 5139.58 | 130 |  | 74.2 | 0 | 177.5% |  | 0 | 10651.05 | 2000 | 25% | 0 | 2000 | 25% | 0 |  | 74.2 | 0.6918% | 74.2 | 0.6918% | -2725.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 891440 - GP&S FARMS | WATER | WATER REPAIR & INSTALLATION | 2020-01-09 | 2020-05-20 | 2020-01-09 | 2020-05-20 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 992594¦¦2020-03-31
UP | C | Yes | 992595 |  | TERRACON SOIL CORING RIOSALADO | COMBS, TAYLOR E. | 100% | 13276 | 0 | 13276 | 12764 | 12764 | 12764 | 0 | 0 | 12764 | 10744 | 0 | 10744 | 0 |  |  |  | 0 |  |  | 6316.14 | 4020.44 |  |  | 2295.7 |  |  | 6447.86 | 0 | 58.79% |  | 0 | 6316.14 | 2532 | 19.07% | 0 | 2532 | 19.07% | 0 |  | 6447.86 | 50.52% | 6447.86 | 50.52% | 512 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 898745 - TERRACON PHOENIX | WATER | WATER REPAIR & INSTALLATION | 2020-01-09 | 2020-01-17 | 2020-01-09 | 2020-01-17 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 992595¦¦2020-03-31
TM | C | Yes | 992596 |  | US WATER SERVICES CORP EQPT | SCHERM, LOGAN M | 100% | 4030 | 7406.39 | 11436.39 | 11329.1 | 11329.1 | 11329.1 | 0 | 0 | 11329.1 | 3144 | 6352.77 | 9496.77 | 2719.43 |  |  |  | 2719.43 |  |  | 6464.37 | 1870.14 | 252.15 |  | 4342.08 |  |  | 4864.73 | 0 | 68.07% |  | 0 | 6464.37 | 886 | 21.99% | 1053.62 | 1939.62 | 16.96% | 1053.62 |  | 4864.73 | 42.94% | 4864.73 | 42.94% | 107.29 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 899490 - US WATER SERVICES CORP | WATER | WATER EQUIPMENT SALES | 2020-01-08 | 2020-03-30 | 2020-01-08 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 992596¦¦2020-03-31
FP | C | Yes | 992597 |  | OWENS CORNING KS EAST CULLET | WARTICK, LOGAN M | 100% | 800 | 0 | 800 | 10745 | 10745 | 10745 | 10745 | 0 | 10745 | 640 | 0 | 640 | 16.95 | 16.95 |  |  | 0 |  |  | 7175.24 | 3519.65 | 347.19 |  | 3308.4 |  |  | 3569.76 | 0 | 1121% |  | 0 | 7175.24 | 160 | 20% | 0 | 160 | 20% | 0 |  | 3569.76 | 33.22% | 3569.76 | 33.22% | -9945 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 895921 - OWENS CORNING | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-04-15 | 2020-01-08 | 2020-04-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 992597¦¦2020-03-31
UP | CJ | Yes | 992598 |  | SUGAR GROVE IL WELL NO 10 | BALLUFF, WILLIAM O. | 100% | 175000 | 0 | 175000 | 60578.02 | 60578.02 | 60578.02 | 12642.15 | 0 | 60578.02 | 131250 | 0 | 131250 | 8471.54 | 6455 | 243.8 |  | 1772.74 |  |  | 46205.91 | 32619.12 | 4518.91 |  | 9067.88 |  |  | 14372.11 | 0 | 35.2% |  | 0 | 46205.91 | 43750 | 25% | 0 | 43750 | 25% | 0 |  | 14372.11 | 23.72% | 14372.11 | 23.72% | 114421.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 879066 - SUGAR GROVE, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-04-30 | 2020-01-08 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 992598¦¦2020-03-31
TM | CJ | Yes | 992599 |  | BARONET MOTOR | GNAU, CASEY T | 100% | 1500 | 0 | 1500 | 1930 | 1930 | 1930 | 0 | 0 | 1930 | 1000 | 0 | 1000 | 492.28 | 276.08 | 74.2 |  | 142 |  |  | 492.28 | 276.08 | 74.2 |  | 142 |  |  | 1437.72 | 0 | 49.23% |  | 0 | 492.28 | 500 | 33.33% | 0 | 500 | 33.33% | 0 |  | 1437.72 | 74.49% | 1437.72 | 74.49% | -430 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 886787 - BARONET FARMS LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-01-31 | 2020-01-08 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 992599¦¦2020-03-31
FP | C | Yes | 992600 |  | REICHHOLD WELL 1 PUMP | WHITE, CATHLEEN R | 100% | 7060 | 0 | 7060 | 7060 | 7060 | 7060 | 0 | 0 | 7060 | 4942 | 0 | 4942 | 0.01 |  |  |  | 0.01 |  |  | 4538.71 | 2651.59 | 135.54 |  | 1751.58 |  |  | 2521.29 | 0 | 91.84% |  | 0 | 4538.71 | 2118 | 30% | 0 | 2118 | 30% | 0 |  | 2521.29 | 35.71% | 2521.29 | 35.71% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896900 - REICHHOLD LLC 2 | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-01-09 | 2020-01-08 | 2020-01-09 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 992600¦¦2020-03-31
FP | CJ | Yes | 992602 |  | CITY OF LINCOLN TEST HOLE | GANSEBOM, JASON W. | 100% | 7495 | 0 | 7495 | 7495 | 7495 | 7495 | 0 | 0 | 7495 | 4855 | 0 | 4855 | 0 |  |  |  | 0 |  |  | 6780.93 | 2909.06 | 2178.01 |  | 1693.86 |  |  | 714.07 | 0 | 139.7% |  | 0 | 6780.93 | 2640 | 35.22% | 0 | 2640 | 35.22% | 0 |  | 714.07 | 9.527% | 714.07 | 9.527% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 891956 - HDR ENGINEERING INC | WATER | WATER SPECIALTY DRILLING | 2020-01-09 | 2020-03-30 | 2020-01-09 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 992602¦¦2020-03-31
FP | LJ | Yes | 992877 |  | SHINTECH 3 INDUSTRIAL WELLS | LOPEZ-VASQUEZ, JUAN C. | 24.28% | 1582300 | 0 | 1582300 | 384132.4553 | 398900 | 398900 | 0 | 19945 | 1582300 | 1121283.35 | 0 | 1121283.35 | 39683.71 | 4045.15 | 4435.28 |  | 28003.28 | 3200 |  | 274611.25 | 66559.04 | 71505.5 |  | 133346.71 | 3200 |  | 124288.75 | 0 | 24.49% | 0 | 856554.25 | 1131165.5 | 461016.65 | 29.14% | 0 | 461016.65 | 29.14% | 0 |  | 109521.21 | 28.51% | 451134.5 | 28.51% | 1198167.54 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 897810 - SHINTECH LOUISIANA, LLC | WATER | WATER SUPPLY | 2020-01-08 | 2020-05-30 | 2020-01-08 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 992877¦¦2020-03-31
FP | LJ | Yes | 992878 |  | BRW N SHARP 3 WELL | LOPEZ-VASQUEZ, JUAN C. | 67.63% | 813180 | 0 | 813180 | 607458.8055 | 259350 | 259350 | 0 | 25935 | 898180 | 674266.2 | 0 | 674266.2 | 309486.23 | 45805.51 | 47907.51 |  | 215773.21 |  |  | 501704 | 112695.37 | 113559.22 |  | 275449.41 |  |  | 0 | 242354 | 74.41% | 0 | 240108.44 | 741812.44 | 138913.8 | 17.08% | 0 | 138913.8 | 17.08% | 0 |  | 105754.81 | 17.41% | 156367.56 | 17.41% | 205721.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER SUPPLY | 2020-01-07 | 2020-04-30 | 2020-01-07 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 992878¦¦2020-03-31
UP | CJ | Yes | 994400 |  | CATALINA MONTHLY INSP | BARNES, MATTHEW D | 100% | 2880 | 0 | 2880 | 720 | 720 | 720 | 0 | 0 | 720 | 2160 | 0 | 2160 | 180.12 |  |  |  | 0.12 | 180 |  | 540.24 |  |  |  | 0.24 | 540 |  | 179.76 | 0 | 25.01% |  | 0 | 540.24 | 720 | 25% | 0 | 720 | 25% | 0 |  | 179.76 | 24.97% | 179.76 | 24.97% | 2160 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 888039 - CATALINA MANUFACTURED HOME COMMUNITY | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-12-31 | 2020-01-08 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 994400¦¦2020-03-31
TM | CJ | Yes | 994401 |  | WHEATLAND VLV PROBE | WILLIAMS, DONALD G. | 100% | 18123 | 0 | 18123 | 9389 | 9389 | 9389 | 0 | 0 | 9389 | 13592 | 0 | 13592 | 2356.46 | 1220.46 | 374.2 |  | 761.8 |  |  | 7452.31 | 1942.64 | 491.48 |  | 5018.19 |  |  | 1936.69 | 0 | 54.83% |  | 0 | 7452.31 | 4531 | 25% | 0 | 4531 | 25% | 0 |  | 1936.69 | 20.63% | 1936.69 | 20.63% | 8734 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 900241 - WHEATLAND, IN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-10 | 2020-07-31 | 2020-01-10 | 2020-07-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 994401¦¦2020-03-31
UP | CJ | Yes | 994402 |  | PLANO IL WELL 4 | HEALY, THOMAS P. | 100% | 54200 | 0 | 54200 | 44039.25 | 44039.25 | 44039.25 | 0 | 0 | 44039.25 | 37940 | 0 | 37940 | 16410.56 | 8364.84 | 25.84 |  | 8019.88 |  |  | 28024.86 | 15803.18 | 1098.03 |  | 11123.65 |  |  | 16014.39 | 0 | 73.87% |  | 0 | 28024.86 | 16260 | 30% | 0 | 16260 | 30% | 0 |  | 16014.39 | 36.36% | 16014.39 | 36.36% | 10160.75 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878516 - PLANO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-10 | 2020-02-29 | 2020-01-10 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 994402¦¦2020-03-31
UP | CJ | Yes | 994403 |  | EXMOOR CC WELL 2 | KENNEDY, CHRISTOPHER C. | 100% | 53000 | 25400 | 78400 | 24900 | 24900 | 24900 | 2632.5 | 0 | 24900 | 37100 | 17780 | 54880 | 2665.65 | 1474.01 | 11.7 |  | 1179.94 |  |  | 19881.57 | 12240.18 | 3125.05 |  | 4516.34 |  |  | 5018.43 | 0 | 36.23% |  | 0 | 19881.57 | 15900 | 30% | 7620 | 23520 | 30% | 7620 | 7620 | 5018.43 | 20.15% | 5018.43 | 20.15% | 53500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 890509 - EXMOOR COUNTRY CLUB | WATER | WATER REPAIR & INSTALLATION | 2020-01-10 | 2020-04-30 | 2020-01-10 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 994403¦¦2020-03-31
UP | C | Yes | 994561 |  | FMI SIERRITA FFS 2 | VAN ALLEN, WESLEY C. | 100% | 59226 | 2640.6 | 61866.6 | 57276.6 | 57276.6 | 57276.6 | 0 | 0 | 57276.6 | 44262 | 1969.73 | 46231.73 | 762.78 | -0.02 |  |  | 762.8 |  |  | 36416.44 | 10138.6 | 4067.59 |  | 22210.25 |  |  | 20860.16 | 0 | 78.77% |  | 0 | 36416.44 | 14964 | 25.27% | 670.87 | 15634.87 | 25.27% | 670.87 |  | 20860.16 | 36.42% | 20860.16 | 36.42% | 4590 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878891 - FREEPORT MCMORAN SIERRITA OPERATIONS | WATER | WATER REPAIR & INSTALLATION | 2020-01-03 | 2020-02-28 | 2020-01-03 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 994561¦¦2020-03-31
FP | CJ | Yes | 994562 |  | BASF P804 BORE BLAST | GREGORY, CRYSTAL N |  | 51000 | 0 | 51000 |  |  | 0 | 0 | 0 |  | 35431 | 0 | 35431 | [20 empty] | 15569 | 30.53% | 0 | 15569 | 30.53% | 0 | [5 empty] | 51000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878707 - BASF CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-04-30 | 2020-01-08 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 994562¦¦2020-03-31
UP | CJ | Yes | 994623 |  | AUTO CLUB SPEEDWAY BOOSTER 2 | GRACE, GARY L. | 100% | 4680 | 10805 | 15485 | 15485 | 15485 | 15528.4 | 10848.4 | 0 | 15485 | 0 | 7312.78 | 7312.78 | 6813.81 | 2315.33 | 416.88 |  | 1543.27 | 2538.33 |  | 9220.54 | 3289.49 | 666.81 |  | 2725.91 | 2538.33 |  | 6264.46 | 0 | 126.1% |  | 0 | 9220.54 | 4680 | 100% | 3492.22 | 8172.22 | 52.78% | 3492.22 |  | 6264.46 | 40.46% | 6264.46 | 40.46% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 886673 - AUTO CLUB SPEEDWAY | WATER | WATER REPAIR & INSTALLATION | 2020-01-09 | 2020-02-25 | 2020-01-09 | 2020-02-25 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 994623¦¦2020-03-31
TM | C | Yes | 994651 |  | MARIANNA AR CITY OF PR | SCHERM, LOGAN M | 100% | 23000 | 0 | 23000 | 23644.37 | 23644.37 | 25417.71 | 0 | 0 | 23644.37 | 18800 | 0 | 18800 | 4.84 |  |  |  | 4.84 |  |  | 11257.22 | 4911.19 | 797.44 |  | 5548.59 |  |  | 12387.15 | 0 | 59.88% |  | 0 | 11257.22 | 4200 | 18.26% | 0 | 4200 | 18.26% | 0 |  | 12387.15 | 52.39% | 12387.15 | 52.39% | -644.37 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 894212 - MARIANNA, AR, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-10 | 2020-04-20 | 2020-01-10 | 2020-04-20 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 994651¦¦2020-03-31
UP | CJ | Yes | 995673 |  | PARIS TN PWM TESTING | ANDERSON, STEPHEN P. |  | 1500 | 0 | 1500 |  |  | 0 | 0 | 0 |  | 1248 | 0 | 1248 | [20 empty] | 252 | 16.8% | 0 | 252 | 16.8% | 0 | [5 empty] | 1500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 896031 - PARIS, TN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-13 | 2020-02-20 | 2020-01-13 | 2020-02-20 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 995673¦¦2020-03-31
FP | C | Yes | 995674 |  | LONESTAR VFD | LOPEZ-VASQUEZ, JUAN C. | 100% | 3645 | 0 | 3645 | 3295 | 3295 | 3589.9 | 0 | 0 | 3295 | 2797 | 0 | 2797 | [7 empty] | 2817.94 |  |  |  | 2817.94 |  |  | 477.06 | 0 | 100.7% |  | 0 | 2817.94 | 848 | 23.26% | 0 | 848 | 23.26% | 0 |  | 477.06 | 14.48% | 477.06 | 14.48% | 350 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 893879 - LONE STAR NGL REFINERY, LLC | WATER | WATER EQUIPMENT SALES | 2020-01-13 | 2020-02-28 | 2020-01-13 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 995674¦¦2020-03-31
FP | CJ | Yes | 995675 |  | RLH RENTAL MULDER FARM TESTING | EISHA, JOSEPH J. | 100% | 1592 | 0 | 1592 | 1592 | 1592 | 1592 | 0 | 0 | 1592 | 1000 | 0 | 1000 | 0 |  |  |  | 0 |  |  | 1667.5 | 1079.78 | 333.24 |  | 254.48 |  |  | 0 | 75.5 | 166.8% |  | 0 | 1667.5 | 592 | 37.19% | 0 | 592 | 37.19% | 0 |  | -75.5 | -4.742% | -75.5 | -4.742% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 994978 - RLH RENTAL | WATER | WATER REPAIR & INSTALLATION | 2020-01-07 | 2020-01-09 | 2020-01-07 | 2020-01-09 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 995675¦¦2020-03-31
FP | C | Yes | 995676 |  | US AMINES AXIS AL SBS WELL | PARSLEY, TRISTAN S | 100% | 2250 | 0 | 2250 | 2250 | 2250 | 2250 | 0 | 0 | 2250 | 1573 | 0 | 1573 | 0 |  |  |  | 0 |  |  | 1151.97 | 464.38 | 117.67 |  | 569.92 |  |  | 1098.03 | 0 | 73.23% |  | 0 | 1151.97 | 677 | 30.09% | 0 | 677 | 30.09% | 0 |  | 1098.03 | 48.8% | 1098.03 | 48.8% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 899431 - US AMINES | WATER | WATER SUPPLY | 2020-01-12 | 2020-02-29 | 2020-01-12 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 995676¦¦2020-03-31
UP | CJ | Yes | 995677 |  | HANSEN RANCHES WELL PF5 SE | SEIDEN, ANDREW L. | 100% | 66955 | 0 | 66955 | 66955 | 66955 | 67830.94 | 0 | 0 | 66955 | 53483 | 0 | 53483 | 1065.44 |  |  |  | 1065.44 |  |  | 64985.49 | 16398.61 | 5288.8 |  | 43298.08 |  |  | 1969.51 | 0 | 121.5% |  | 0 | 64985.49 | 13472 | 20.12% | 0 | 13472 | 20.12% | 0 |  | 1969.51 | 2.942% | 1969.51 | 2.942% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | HANFORD - WA | 878723 - HANSEN RANCHES LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-09 | 2020-02-28 | 2020-01-09 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 995677¦¦2020-03-31
FP | C | Yes | 995678 |  | DAVID ADAMSON VIDEO SURVEY | SEIDEN, ANDREW L. | 100% | 1170 | 0 | 1170 | 1170 | 1170 | 1170 | 0 | 0 | 1170 | 805 | 0 | 805 | 0 |  |  |  | 0 |  |  | 1038.29 | 506.42 | 206.4 |  | 325.47 |  |  | 131.71 | 0 | 129% |  | 0 | 1038.29 | 365 | 31.2% | 0 | 365 | 31.2% | 0 |  | 131.71 | 11.26% | 131.71 | 11.26% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 994938 - ADAMSON, DAVID | WATER | WATER REPAIR & INSTALLATION | 2020-01-09 | 2020-01-10 | 2020-01-09 | 2020-01-10 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 995678¦¦2020-03-31
UP | C | Yes | 995693 |  | IMERYS DEEPSTEP WELLS 4 AND 7 | PARSLEY, TRISTAN S | 100% | 11400 | 0 | 11400 | 11400 | 11400 | 11400 | 0 | 0 | 11400 | 7801 | 0 | 7801 | 0 |  |  |  | 0 |  |  | 15249.86 | 8143.08 | 681.87 |  | 6424.91 |  |  | 0 | 3849.86 | 195.5% |  | 0 | 15249.86 | 3599 | 31.57% | 0 | 3599 | 31.57% | 0 |  | -3849.86 | -33.77% | -3849.86 | -33.77% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 995349 - IMERYS CLAYS INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-13 | 2020-02-29 | 2020-01-13 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 995693¦¦2020-03-31
FP | C | Yes | 996141 |  | AECI NEW MADRID | SCHERM, LOGAN M | 100% | 1500 | 0 | 1500 | 1380 | 1380 | 1380 | 0 | 0 | 1380 | 1100 | 0 | 1100 | 0 |  |  |  | 0 |  |  | 902.94 | 379.89 | 234.52 |  | 288.53 |  |  | 477.06 | 0 | 82.09% |  | 0 | 902.94 | 400 | 26.67% | 0 | 400 | 26.67% | 0 |  | 477.06 | 34.57% | 477.06 | 34.57% | 120 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 886579 - ASSOCIATED ELECTRIC COOPERATIVE INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-13 | 2021-01-13 | 2020-01-13 | 2021-01-13 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 996141¦¦2020-03-31
UP | CJ | Yes | 996142 |  | SUNCOR ENERGY WELL 4 | SCHANAMAN, MIKE L. | 100% | 39125 | 0 | 39125 | 26125 | 26125 | 26125 | 0 | 0 | 26125 | 26541 | 0 | 26541 | 417.43 | 155.27 | 72.24 |  | 189.92 |  |  | 9830.3 | 1312.14 | 794.16 |  | 7724 |  |  | 16294.7 | 0 | 37.04% |  | 0 | 9830.3 | 12584 | 32.16% | 0 | 12584 | 32.16% | 0 |  | 16294.7 | 62.37% | 16294.7 | 62.37% | 13000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 912353 - SUNCOR ENERGY USA INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-06 | 2020-02-25 | 2020-01-06 | 2020-02-25 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 996142¦¦2020-03-31
UP | CJ | Yes | 996143 |  | DENVER WATER GARLAND PARK | SCHANAMAN, MIKE L. | 100% | 15250 | 0 | 15250 | 15000 | 15000 | 15000 | 0 | 0 | 15000 | 10551 | 0 | 10551 | 546.05 | 408.75 |  |  | 137.3 |  |  | 9469.41 | 2360.77 | 347.63 |  | 6761.01 |  |  | 5530.59 | 0 | 89.75% |  | 0 | 9469.41 | 4699 | 30.81% | 0 | 4699 | 30.81% | 0 |  | 5530.59 | 36.87% | 5530.59 | 36.87% | 250 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 889513 - DENVER WATER | WATER | WATER REPAIR & INSTALLATION | 2020-01-13 | 2020-02-25 | 2020-01-13 | 2020-02-25 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 996143¦¦2020-03-31
UP | CJ | Yes | 996144 |  | SLAYDEN SALEM PRECONSTRUCTION | HUNT, HENRY C. | 100% | 37040 | 0 | 37040 | 7631.85 | 7631.85 | 0 | 0 | 0 | 7631.85 | 26000 | 0 | 26000 | 2206.1 | 1511.11 |  |  | 19.99 | 675 |  | 6165.73 | 4682.02 |  |  | 58.71 | 1425 |  | 1466.12 | 0 | 23.71% |  | 0 | 6165.73 | 11040 | 29.81% | 0 | 11040 | 29.81% | 0 |  | 1466.12 | 19.21% | 1466.12 | 19.21% | 29408.15 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 276489 - SLAYDEN CONSTRUCTION GROUP INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-12 | 2020-05-01 | 2020-01-12 | 2020-05-01 | SUBCONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 996144¦¦2020-03-31
UP | C | Yes | 996145 |  | MARATHON ST JAMES FLOW TEST | GREGORY, CRYSTAL N | 100% | 2043 | 0 | 2043 | 1963 | 1963 | 1963 | 0 | 0 | 1963 | 1380 | 0 | 1380 | 0 |  |  |  | 0 |  |  | 1187.98 | 688.34 | 222.6 |  | 277.04 |  |  | 775.02 | 0 | 86.09% |  | 0 | 1187.98 | 663 | 32.45% | 0 | 663 | 32.45% | 0 |  | 775.02 | 39.48% | 775.02 | 39.48% | 80 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 894198 - MARATHON PETROLEUM CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-01-06 | 2020-02-28 | 2020-01-06 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 996145¦¦2020-03-31
UP | C | Yes | 996146 |  | BOLINGBROOK WELL 12 | KENNEDY, CHRISTOPHER C. | 100% | 11200 | 55366 | 66566 | 60241.5 | 60241.5 | 62196.17 | 0 | 0 | 60241.5 | 8500 | 36300 | 44800 | 2667.41 | 736.72 | 222.16 |  | 1708.53 |  |  | 40502.74 | 17770.45 | 3400.38 |  | 19331.91 |  |  | 19738.76 | 0 | 90.41% |  | 0 | 40502.74 | 2700 | 24.11% | 19066 | 21766 | 32.7% | 19066 | 7956 | 19738.76 | 32.77% | 19738.76 | 32.77% | 6324.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 892460 - ILLINOIS AMERICAN WATER | WATER | WATER REPAIR & INSTALLATION | 2020-01-14 | 2020-02-14 | 2020-01-14 | 2020-02-14 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 996146¦¦2020-03-31
FP | C | Yes | 996147 |  | DANISCO ABANDONMENT | MIGUEL, SEAN J. | 100% | 11800 | 0 | 11800 | 11800 | 11800 | 11800 | 0 | 0 | 11800 | 8314 | 0 | 8314 | 257.72 |  |  |  | 257.72 |  |  | 4625.01 | 2311.25 | 463.98 |  | 1849.78 |  |  | 7174.99 | 0 | 55.63% |  | 0 | 4625.01 | 3486 | 29.54% | 0 | 3486 | 29.54% | 0 |  | 7174.99 | 60.8% | 7174.99 | 60.8% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889311 - DANISCO USA | WATER | WATER SUPPLY | 2020-01-14 | 2020-02-28 | 2020-01-14 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 996147¦¦2020-03-31
FP | C | Yes | 996148 |  | PIXELLE WELL 19 PINCH VALVE | HARTMAN, MICHAEL | 100% | 41400 | 0 | 41400 | 41400 | 41400 | 41400 | 41400 | 0 | 41400 | 29600 | 0 | 29600 | 1544.94 | 1527.34 |  |  | 17.6 |  |  | 16139.71 | 9073.11 | 46.8 |  | 3893.4 | 3126.4 |  | 25260.29 | 0 | 54.53% |  | 0 | 16139.71 | 11800 | 28.5% | 0 | 11800 | 28.5% | 0 |  | 25260.29 | 61.02% | 25260.29 | 61.02% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878886 - PIXELLE SPECIALTY SOLUTIONS | WATER | WATER REPAIR & INSTALLATION | 2020-01-14 | 2020-03-31 | 2020-01-14 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 996148¦¦2020-03-31
UP | CJ | Yes | 996149 |  | PRAXAIR PETE MANENA RD | GNAU, CASEY T | 100% | 20060 | 0 | 20060 | 20060 | 20060 | 20060 | 20060 | 0 | 20060 | 10030 | 0 | 10030 | 155.92 |  |  |  | 155.92 |  |  | 8743.07 | 1675.11 | 278.25 |  | 6789.71 |  |  | 11316.93 | 0 | 87.17% |  | 0 | 8743.07 | 10030 | 50% | 0 | 10030 | 50% | 0 |  | 11316.93 | 56.42% | 11316.93 | 56.42% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 896548 - PRAXAIR INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-14 | 2020-02-26 | 2020-01-14 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 996149¦¦2020-03-31
FP | CJ | Yes | 996192 |  | DENHAM SPRINGS BRIGNAC MOTOR | GREGORY, CRYSTAL N | 100% | 8590 | 0 | 8590 | 8590 | 8590 | 8590 | 0 | 0 | 8590 | 5584 | 0 | 5584 | 4.21 |  |  |  | 4.21 |  |  | 4901 | 149.17 | 55.65 |  | 61.18 | 4635 |  | 3689 | 0 | 87.77% |  | 0 | 4901 | 3006 | 34.99% | 0 | 3006 | 34.99% | 0 |  | 3689 | 42.95% | 3689 | 42.95% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 889494 - DENHAM SPRINGS, LA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-13 | 2020-03-31 | 2020-01-13 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 996192¦¦2020-03-31
FP | CJ | Yes | 996193 |  | MERCK WELL ABANDONMENTS | GANSEBOM, JASON W. | 100% | 11600 | 0 | 11600 | 11600 | 11600 | 12238 | 12238 | 0 | 11600 | 6574 | 0 | 6574 | 2554.96 | 874.71 | 1017.54 |  | 662.71 |  |  | 2705.86 | 962.3 | 1017.54 |  | 726.02 |  |  | 8894.14 | 0 | 41.16% |  | 0 | 2705.86 | 5026 | 43.33% | 0 | 5026 | 43.33% | 0 |  | 8894.14 | 76.67% | 8894.14 | 76.67% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 894523 - MERCK ANIMAL HEALTH | WATER | WATER REPAIR & INSTALLATION | 2020-01-14 | 2020-02-28 | 2020-01-14 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 996193¦¦2020-03-31
FP | C | Yes | 996194 |  | SCOTTS HILL | ANDERSON, STEPHEN P. | 100% | 1163 | 0 | 1163 | 1163 | 1163 | 1163 | 0 | 0 | 1163 | 867 | 0 | 867 | 0 |  |  |  | 0 |  |  | 1313.75 | 575.78 | 176.23 |  | 561.74 |  |  | 0 | 150.75 | 151.5% |  | 0 | 1313.75 | 296 | 25.45% | 0 | 296 | 25.45% | 0 |  | -150.75 | -12.96% | -150.75 | -12.96% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 878931 - SCOTTS HILL | WATER | WATER REPAIR & INSTALLATION | 2020-01-10 | 2020-01-31 | 2020-01-13 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 996194¦¦2020-03-31
FP | C | Yes | 996394 |  | NPPD COOPER NUCLEAR SPARE | HEILIGER, TERENCE L. | 100% | 15770 | 0 | 15770 | 15770 | 15770 | 16637.35 | 0 | 0 | 15770 | 6865 | 0 | 6865 | 0 |  |  |  | 0 |  |  | 7024.05 | 97.57 | 41.28 |  | 6885.2 |  |  | 8745.95 | 0 | 102.3% |  | 0 | 7024.05 | 8905 | 56.47% | 0 | 8905 | 56.47% | 0 |  | 8745.95 | 55.46% | 8745.95 | 55.46% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 879101 - NEBRASKA PUBLIC POWER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-01-15 | 2020-01-31 | 2020-01-15 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 996394¦¦2020-03-31
UP | LJ | Yes | 996425 |  | NYAW NEWBRIDGE RD 4A | RANFT, DONALD R | 33.41% | 693381 | 0 | 693381 | 231633.9659 | 274688 | 274688 | 127372.39 | 13734.4 | 693381 | 519355.25 | 0 | 519355.25 | 120319.56 | 44343.83 | 22308.1 |  | 53667.63 |  |  | 173498.06 | 74691.66 | 29839.03 |  | 68967.37 |  |  | 101189.94 | 0 | 33.41% |  | 345856.94 | 519355 | 174025.75 | 25.1% | 0 | 174025.75 | 25.1% | 0 |  | 58135.91 | 25.1% | 174026 | 25.1% | 461747.03 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878512 - NEW YORK AMERICAN WATER | WATER | WATER SUPPLY | 2020-01-15 | 2020-06-01 | 2020-01-15 | 2020-06-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 996425¦¦2020-03-31
UP | LJ | Yes | 996426 |  | NYAW JEFFERSON STREET 12A | RANFT, DONALD R | 30.53% | 693420 | 0 | 693420 | 211693.5757 | 268168 | 268168 | 127379.8 | 13408.4 | 693420 | 522065 | 0 | 522065 | 108312.1 | 34192.65 | 17387.65 |  | 56731.8 |  |  | 159380.76 | 58073.98 | 27744.95 |  | 73561.83 |  |  | 108787.24 | 0 | 30.53% |  | 362684.24 | 522065 | 171355 | 24.71% | 0 | 171355 | 24.71% | 0 |  | 52312.82 | 24.71% | 171355 | 24.71% | 481726.42 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA | 878512 - NEW YORK AMERICAN WATER | WATER | WATER SUPPLY | 2020-01-15 | 2020-06-01 | 2020-01-15 | 2020-06-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 996426¦¦2020-03-31
UP | CJ | Yes | 996744 |  | FMI BAGDAD KIMBERLY SEEPAGE | COMBS, TAYLOR E. | 100% | 117340 | 0 | 117340 | 97808.55 | 97808.55 | 71616.05 | 71616.05 | 0 | 97808.55 | 92044 | 0 | 92044 | 229.32 | 112.75 |  |  | 116.57 |  |  | 79018.99 | 24604.14 | 16737.8 |  | 37677.05 |  |  | 18789.56 | 0 | 85.85% |  | 0 | 79018.99 | 25296 | 21.56% | 0 | 25296 | 21.56% | 0 |  | 18789.56 | 19.21% | 18789.56 | 19.21% | 19531.45 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 890903 - FREEPORT MCMORAN | WATER | WATER SPECIALTY DRILLING | 2020-01-15 | 2020-02-28 | 2020-01-15 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 996744¦¦2020-03-31
UP | C | Yes | 996745 |  | FOREST HILL TEST 3 WELLS | GNAU, CASEY T | 100% | 2250 | 0 | 2250 | 2250 | 2250 | 2250 | 0 | 0 | 2250 | 1125 | 0 | 1125 | 0 |  |  |  | 0 |  |  | 825.43 | 425.63 | 204.05 |  | 195.75 |  |  | 1424.57 | 0 | 73.37% |  | 0 | 825.43 | 1125 | 50% | 0 | 1125 | 50% | 0 |  | 1424.57 | 63.31% | 1424.57 | 63.31% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 890770 - FOREST HILL, LA, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-15 | 2020-01-31 | 2020-01-15 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 996745¦¦2020-03-31
TM | CJ | Yes | 996746 |  | GREENSPAN WELL PUMP | BARNES, MATTHEW D | 100% | 4000 | 0 | 4000 | 3619.71 | 3619.71 | 0 | 0 | 0 | 3619.71 | 2800 | 0 | 2800 | 463.86 | 263.6 | 94.92 |  | 105.34 |  |  | 2924.34 | 1626.89 | 560.77 |  | 736.68 |  |  | 695.37 | 0 | 104.4% |  | 0 | 2924.34 | 1200 | 30% | 0 | 1200 | 30% | 0 |  | 695.37 | 19.21% | 695.37 | 19.21% | 380.29 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 995718 - GREENSPAN SOD | WATER | WATER REPAIR & INSTALLATION | 2020-01-14 | 2020-02-28 | 2020-01-14 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 996746¦¦2020-03-31
UP | CJ | Yes | 996845 |  | MARINGOUIN MOTOR REPAIR | GREGORY, CRYSTAL N | 100% | 4735 | 0 | 4735 | 4735 | 4735 | 4735 | 0 | 0 | 4735 | 3222 | 0 | 3222 | 2.32 |  |  |  | 2.32 |  |  | 2771.89 | 198.91 | 74.2 |  | 78.28 | 2420.5 |  | 1963.11 | 0 | 86.03% |  | 0 | 2771.89 | 1513 | 31.95% | 0 | 1513 | 31.95% | 0 |  | 1963.11 | 41.46% | 1963.11 | 41.46% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 894223 - MARINGOUIN, LA, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-15 | 2020-02-28 | 2020-01-15 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 996845¦¦2020-03-31
UP | CJ | Yes | 996846 |  | ROCKFORD IL UW37 | SNELTEN, BRIAN M | 100% | 32923 | 240085 | 273008 | 41354.73 | 41354.73 | 32901.5 | 0 | 0 | 41354.73 | 24600 | 148378 | 172978 | 6802.69 | 1380.14 | 102.83 |  | 5319.72 |  |  | 33410.26 | 19299.15 | 3458.83 |  | 10652.28 |  |  | 7944.47 | 0 | 19.31% |  | 0 | 33410.26 | 8323 | 25.28% | 91707 | 100030 | 36.64% | 91707 | 91707 | 7944.47 | 19.21% | 7944.47 | 19.21% | 231653.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878821 - ROCKFORD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-16 | 2020-04-20 | 2020-01-16 | 2020-04-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 996846¦¦2020-03-31
FP | C | Yes | 996849 |  | TWIN CITY OH FILTER INSPECTION | CURLEY, ROBERT E. | 100% | 3450 | 0 | 3450 | 3450 | 3450 | 3450 | 0 | 0 | 3450 | 2244.5 | 0 | 2244.5 | 48.15 | 39.59 |  |  | 8.56 |  |  | 1257.22 | 961.9 |  |  | 109.82 | 185.5 |  | 2192.78 | 0 | 56.01% |  | 0 | 1257.22 | 1205.5 | 34.94% | 0 | 1205.5 | 34.94% | 0 |  | 2192.78 | 63.56% | 2192.78 | 63.56% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 899233 - TWIN CITY WATER & SEWER | WATER | WATER TREATMENT | 2020-01-16 | 2020-02-29 | 2020-01-16 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 996849¦¦2020-03-31
TM | CJ | Yes | 996919 |  | CAMPBELLSVILLE RWP 1 | MIGUEL, SEAN J. | 100% | 1611 | 0 | 1611 | 2558 | 2558 | 2558 | 0 | 0 | 2558 | 1280 | 0 | 1280 | 0.46 |  |  |  | 0.46 |  |  | 2456.19 | 1658.78 | 338.64 |  | 458.77 |  |  | 101.81 | 0 | 191.9% |  | 0 | 2456.19 | 331 | 20.55% | 0 | 331 | 20.55% | 0 |  | 101.81 | 3.98% | 101.81 | 3.98% | -947 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 887847 - CAMPBELLSVILLE WATER & SEWER | WATER | WATER REPAIR & INSTALLATION | 2020-01-16 | 2020-02-28 | 2020-01-16 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 996919¦¦2020-03-31
UP | CJ | Yes | 997406 |  | NEBRASKA CITY NE 2020 REHABS | GANSEBOM, JASON W. | 100% | 191597 | 0 | 191597 | 251766.06 | 251766.06 | 254628.74 | 0 | 0 | 251766.06 | 149439 | 0 | 149439 | 68189.5 | 27251.47 | 13847.36 |  | 26738.67 | 352 |  | 231746.59 | 87930.29 | 44698.39 |  | 97667.75 | 1450.16 |  | 20019.47 | 0 | 155.1% |  | 0 | 231746.59 | 42158 | 22% | 0 | 42158 | 22% | 0 |  | 20019.47 | 7.952% | 20019.47 | 7.952% | -60169.06 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878611 - NEBRASKA CITY UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2020-01-16 | 2020-04-30 | 2020-01-16 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 997406¦¦2020-03-31
FP | CJ | Yes | 997407 |  | ST JOE LEVEE REHABS AND SURVEY | WARTICK, LOGAN M | 100% | 20430 | 0 | 20430 | 20430 | 20430 | 20430 | 0 | 0 | 20430 | 16344 | 0 | 16344 | 16192.81 | 6786.06 | 5260.63 |  | 4146.12 |  |  | 16409.14 | 6786.06 | 5260.63 |  | 4362.45 |  |  | 4020.86 | 0 | 100.4% |  | 0 | 16409.14 | 4086 | 20% | 0 | 4086 | 20% | 0 |  | 4020.86 | 19.68% | 4020.86 | 19.68% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 898349 - ST JOSEPH LEVEE DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-01-16 | 2020-07-20 | 2020-01-16 | 2020-07-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 997407¦¦2020-03-31
UP | CJ | Yes | 997427 |  | CAPE CORAL ACID TASK 2 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 87635 | 87635 | 87635 | 0 | 8763.5 | 87635 | 71475 | 0 | 71475 | 9014.64 | 180.04 | 144.51 |  | 8636.84 | 53.25 |  | 50602.53 | 10631.86 | 7450.08 |  | 31867.34 | 653.25 |  | 37032.47 | 0 | 70.8% |  | 0 | 50602.53 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 37032.47 | 42.26% | 37032.47 | 42.26% | -1310 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-03-15 | 2020-01-17 | 2020-03-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 997427¦¦2020-03-31
UP | C | Yes | 997428 |  | LIBERTY UTILITIES HAMPTON | SEIDEN, ANDREW L. | 100% | 7979 | 23839.24 | 31818.24 | 31818.09 | 31818.09 | 32934.02 | 32934.02 | 0 | 31818.09 | 5607 | 18045.37 | 23652.37 | 7.85 |  |  |  | 7.85 |  |  | 20013.21 | 3545.65 | 502.43 |  | 10985.6 | 4979.53 |  | 11804.88 | 0 | 84.61% |  | 0 | 20013.21 | 2372 | 29.73% | 5793.87 | 8165.87 | 25.66% | 5793.87 |  | 11804.88 | 37.1% | 11804.88 | 37.1% | 0.15 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 893732 - LIBERTY UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2020-01-16 | 2020-12-31 | 2020-01-16 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 997428¦¦2020-03-31
FP | CJ | Yes | 997429 |  | MORTON SALT WELL 11 | GNAU, CASEY T | 100% | 14000 | 0 | 14000 | 14000 | 14000 | 14000 | 0 | 0 | 14000 | 7000 | 0 | 7000 | 0 |  |  |  | 0 |  |  | 2896.56 | 1645.74 | 583.92 |  | 666.9 |  |  | 11103.44 | 0 | 41.38% |  | 0 | 2896.56 | 7000 | 50% | 0 | 7000 | 50% | 0 |  | 11103.44 | 79.31% | 11103.44 | 79.31% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895006 - MORTON SALT, INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-16 | 2020-01-31 | 2020-01-16 | 2020-01-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 997429¦¦2020-03-31
TM | C | Yes | 997626 |  | WOOD CREEK RWP 2 | MIGUEL, SEAN J. | 100% | 5000 | 10077 | 15077 | 15465 | 15465 | 15465 | 0 | 0 | 15465 | 3835 | 7789 | 11624 | 5726.49 | 1912.19 | 323.64 |  | 3317.41 | 173.25 |  | 12436.85 | 4518.24 | 977.84 |  | 4667.52 | 2273.25 |  | 3028.15 | 0 | 107% |  | 0 | 12436.85 | 1165 | 23.3% | 2288 | 3453 | 22.9% | 2288 |  | 3028.15 | 19.58% | 3028.15 | 19.58% | -388 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 900468 - WOOD CREEK WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-02-28 | 2020-01-17 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 997626¦¦2020-03-31
TM | C | Yes | 997627 |  | GEORGETOWN SP 3 | MIGUEL, SEAN J. | 100% | 5000 | 8671 | 13671 | 14579 | 14579 | 14579 | 0 | 0 | 14579 | 3750 | 6503 | 10253 | 6985.37 | 1779.28 | 545.61 |  | 4660.48 |  |  | 10853.85 | 3776.24 | 1207.55 |  | 5375.06 | 495 |  | 3725.15 | 0 | 105.9% |  | 0 | 10853.85 | 1250 | 25% | 2168 | 3418 | 25% | 2168 |  | 3725.15 | 25.55% | 3725.15 | 25.55% | -908 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 891147 - GEORGETOWN MUNICIPAL WATER | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-02-28 | 2020-01-17 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 997627¦¦2020-03-31
TM | CJ | Yes | 997630 |  | AK GROUND MAINTENANCE | BARNES, MATTHEW D | 100% | 22000 | 0 | 22000 | 12777.5 | 12777.5 | 12777.5 | 12777.5 | 0 | 12777.5 | 16500 | 0 | 16500 | 969.7 | 146.79 | 46.64 |  | 30.77 | 745.5 |  | 8280.03 | 2419.39 | 1063.04 |  | 1070.1 | 3727.5 |  | 4497.47 | 0 | 50.18% |  | 0 | 8280.03 | 5500 | 25% | 0 | 5500 | 25% | 0 |  | 4497.47 | 35.2% | 4497.47 | 35.2% | 9222.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-12-31 | 2020-01-17 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 997630¦¦2020-03-31
FP | CJ | Yes | 997637 |  | ST CHARLES CW REHAB | HARTMAN, MICHAEL | 100% | 308710 | 0 | 308710 | 308710 | 308710 | 308710 | 0 | 0 | 308710 | 207466 | 0 | 207466 | 22611.1 | 10775.28 | 648.6 |  | 10390.18 | 797.04 |  | 147640.87 | 69686.98 | 16679.94 |  | 49712.91 | 11561.04 |  | 161069.13 | 0 | 71.16% |  | 0 | 147640.87 | 101244 | 32.8% | 0 | 101244 | 32.8% | 0 |  | 161069.13 | 52.17% | 161069.13 | 52.17% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 997553 - ST CHARLES, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-08 | 2020-02-28 | 2020-01-20 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 997637¦¦2020-03-31
UP | CJ | Yes | 997938 |  | MYOMA WATER WELL 9 | GRACE, GARY L. | 100% | 13450 | 0 | 13450 | 13450 | 13450 | 13450 | 0 | 0 | 13450 | 9993 | 0 | 9993 | 1.99 |  |  |  | 1.99 |  |  | 8484.21 | 3644.03 | 2169.41 |  | 2670.77 |  |  | 4965.79 | 0 | 84.9% |  | 0 | 8484.21 | 3457 | 25.7% | 0 | 3457 | 25.7% | 0 |  | 4965.79 | 36.92% | 4965.79 | 36.92% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878774 - MYOMA WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-02-28 | 2020-01-17 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 997938¦¦2020-03-31
TM | C | Yes | 997945 |  | NORTH CROSSETT WATER SUB PR | SCHERM, LOGAN M | 100% | 37500 | 0 | 37500 | 35180.14 | 35180.14 | 38434.31 | 0 | 0 | 35180.14 | 30000 | 0 | 30000 | 1242.14 | 259.32 |  |  | 982.82 |  |  | 28258.65 | 10314.28 | 4201.94 |  | 13742.43 |  |  | 6921.49 | 0 | 94.2% |  | 0 | 28258.65 | 7500 | 20% | 0 | 7500 | 20% | 0 |  | 6921.49 | 19.67% | 6921.49 | 19.67% | 2319.86 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 895462 - NORTH CROSSETT GAS & WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-04-24 | 2020-01-17 | 2020-04-24 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 997945¦¦2020-03-31
FP | CJ | Yes | 997946 |  | SALINA KS 2020 WELL 20 | WARTICK, LOGAN M | 100% | 2610 | 0 | 2610 | 292.22 | 292.22 | 0 | 0 | 0 | 292.22 | 2088 | 0 | 2088 | 236.08 | 131.88 | 2 |  | 102.2 |  |  | 236.08 | 131.88 | 2 |  | 102.2 |  |  | 56.14 | 0 | 11.31% |  | 0 | 236.08 | 522 | 20% | 0 | 522 | 20% | 0 |  | 56.14 | 19.21% | 56.14 | 19.21% | 2317.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 897385 - SALINA, KS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-20 | 2020-02-29 | 2020-01-20 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 997946¦¦2020-03-31
UP | CJ | Yes | 997947 |  | AMERICAN YEAST | ANDERSON, STEPHEN P. | 100% | 1232 | 0 | 1232 | 705.69 | 705.69 | 0 | 0 | 0 | 705.69 | 793 | 0 | 793 | [7 empty] | 570.12 |  |  |  | 570.12 |  |  | 135.57 | 0 | 71.89% |  | 0 | 570.12 | 439 | 35.63% | 0 | 439 | 35.63% | 0 |  | 135.57 | 19.21% | 135.57 | 19.21% | 526.31 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 886250 - AMERICAN YEAST | WATER | WATER REPAIR & INSTALLATION | 2020-01-20 | 2020-02-10 | 2020-01-20 | 2020-02-10 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 997947¦¦2020-03-31
UP | C | Yes | 998012 |  | OZAWKIE KS WELLS 1 AND 2 REHAB | WARTICK, LOGAN M | 100% | 33932 | 0 | 33932 | 39866.09 | 39866.09 | 39866.09 | 0 | 0 | 39866.09 | 28482 | 0 | 28482 | 20951 | 7690.85 | 4773.87 |  | 8486.28 |  |  | 23292.33 | 7690.85 | 4773.87 |  | 10827.61 |  |  | 16573.76 | 0 | 81.78% |  | 0 | 23292.33 | 5450 | 16.06% | 0 | 5450 | 16.06% | 0 |  | 16573.76 | 41.57% | 16573.76 | 41.57% | -5934.09 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 895946 - OZAWKIE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-05-20 | 2020-01-17 | 2020-05-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 998012¦¦2020-03-31
UP | C | Yes | 998013 |  | INGREDION WELL 31 PULL AND INS | WARTICK, LOGAN M | 100% | 5982 | 0 | 5982 | 15214 | 15214 | 15214 | 9957 | 0 | 15214 | 4785 | 0 | 4785 | 1886.83 | 1087.94 | 263.59 |  | 535.3 |  |  | 17174.88 | 8122.07 | 2782.14 |  | 6270.67 |  |  | 0 | 1960.88 | 358.9% |  | 0 | 17174.88 | 1197 | 20.01% | 0 | 1197 | 20.01% | 0 |  | -1960.88 | -12.89% | -1960.88 | -12.89% | -9232 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 879079 - INGREDION INCORPORATED | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-05-20 | 2020-01-17 | 2020-05-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 998013¦¦2020-03-31
UP | C | Yes | 998036 |  | OZAWKIE KS WELL 3 REHAB | WARTICK, LOGAN M | 100% | 26883 | 0 | 26883 | 26883 | 26883 | 26883 | 0 | 0 | 26883 | 21681 | 0 | 21681 | 1661.16 | 893.46 | 284.48 |  | 483.22 |  |  | 15641.25 | 6786.7 | 3716.5 |  | 5138.05 |  |  | 11241.75 | 0 | 72.14% |  | 0 | 15641.25 | 5202 | 19.35% | 0 | 5202 | 19.35% | 0 |  | 11241.75 | 41.82% | 11241.75 | 41.82% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 895946 - OZAWKIE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-05-20 | 2020-01-17 | 2020-05-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 998036¦¦2020-03-31
FP | CJ | Yes | 998037 |  | MOSAIC NEW WALES NORTH DEEP | TORMOEHLEN, DAVID A. |  | 19905 | 0 | 19905 |  |  | 0 | 0 | 0 |  | 14726 | 0 | 14726 | [20 empty] | 5179 | 26.02% | 0 | 5179 | 26.02% | 0 | [5 empty] | 19905 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 906311 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-20 | 2020-02-29 | 2020-01-20 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 998037¦¦2020-03-31
UP | CJ | Yes | 998256 |  | SAVANNAH MO 2020 HIGH SERVICE | WARTICK, LOGAN M | 100% | 7850 | 35065 | 42915 | 27808.5 | 27808.5 | 27808.5 | 27808.5 | 0 | 27808.5 | 6280 | 26088.34 | 32368.34 | 12360.64 | 5520.41 | 1899.04 |  | 4941.19 |  |  | 20948.55 | 8199.59 | 3031.8 |  | 9717.16 |  |  | 6859.95 | 0 | 64.72% |  | 0 | 20948.55 | 1570 | 20% | 8976.66 | 10546.66 | 24.58% | 8976.66 | 8976.66 | 6859.95 | 24.67% | 6859.95 | 24.67% | 15106.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 897532 - SAVANNAH, MO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-20 | 2020-02-29 | 2020-01-20 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 998256¦¦2020-03-31
UP | CJ | Yes | 998880 |  | OLIN 2020 SPRING PWM | ANDERSON, STEPHEN P. |  | 1200 | 0 | 1200 |  |  | 0 | 0 | 0 |  | 1052 | 0 | 1052 | [20 empty] | 148 | 12.33% | 0 | 148 | 12.33% | 0 | [5 empty] | 1200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895753 - OLIN CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-01-20 | 2020-05-15 | 2020-01-20 | 2020-05-15 | PRIME CONTRACTOR | PRIVATE | MAINTENANCE ONLY CONTRACT | 998880¦¦2020-03-31
UP | CJ | Yes | 998881 |  | SCHAAFSMA SOD FARM WELL 1 | EISHA, JOSEPH J. | 100% | 31375 | 0 | 31375 | 3769.38 | 3769.38 | 0 | 0 | 0 | 3769.38 | 21000 | 0 | 21000 | 1.84 |  |  |  | 1.84 |  |  | 3045.26 | 2377.42 | 36.5 |  | 631.34 |  |  | 724.12 | 0 | 14.5% |  | 0 | 3045.26 | 10375 | 33.07% | 0 | 10375 | 33.07% | 0 |  | 724.12 | 19.21% | 724.12 | 19.21% | 27605.62 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 897557 - SCHAAFSMA SOD FARM | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-02-26 | 2020-01-17 | 2020-02-26 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 998881¦¦2020-03-31
UP | C | Yes | 998882 |  | CANTIGNY FIRE WELL | KENNEDY, CHRISTOPHER C. | 100% | 24600 | 0 | 24600 | 22291 | 22291 | 22291 | 0 | 0 | 22291 | 19700 | 0 | 19700 | 0 |  |  |  | 0 |  |  | 14862.45 | 6146.1 | 1595.36 |  | 7120.99 |  |  | 7428.55 | 0 | 75.44% |  | 0 | 14862.45 | 4900 | 19.92% | 0 | 4900 | 19.92% | 0 |  | 7428.55 | 33.33% | 7428.55 | 33.33% | 2309 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 887891 - CANTIGNY FOUNDATION | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-02-20 | 2020-01-17 | 2020-02-20 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 998882¦¦2020-03-31
UP | CJ | Yes | 998883 |  | KOCH DODGE CITY KS 2020 4 AND6 | WARTICK, LOGAN M | 100% | 62960 | 0 | 62960 | 146726 | 146726 | 146726 | 0 | 0 | 146726 | 47067.62 | 0 | 47067.62 | 35133.14 | 5305.58 | 6294.37 |  | 8410.79 | 15122.4 |  | 110692.2 | 14737.07 | 9390.77 |  | 71441.96 | 15122.4 |  | 36033.8 | 0 | 235.2% |  | 0 | 110692.2 | 15892.38 | 25.24% | 0 | 15892.38 | 25.24% | 0 |  | 36033.8 | 24.56% | 36033.8 | 24.56% | -83766 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 893265 - KOCH FERTILIZER DODGE CITY, LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-20 | 2020-03-20 | 2020-01-20 | 2020-03-20 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 998883¦¦2020-03-31
UP | CJ | Yes | 998947 |  | WELL 2 BLYTHE ENERGY | BRASHEAR, DAVID M | 100% | 105232 | 0 | 105232 | 54073.39 | 54073.39 | 54473.45 | 0 | 0 | 54073.39 | 76261 | 0 | 76261 | 16529.9 | 7449.48 | 2590.36 |  | 6490.06 |  |  | 40559.94 | 18623.61 | 5695.43 |  | 16240.9 |  |  | 13513.45 | 0 | 53.19% |  | 0 | 40559.94 | 28971 | 27.53% | 0 | 28971 | 27.53% | 0 |  | 13513.45 | 24.99% | 13513.45 | 24.99% | 51158.61 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887234 - BLYTHE ENERGY INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-21 | 2020-05-03 | 2020-01-21 | 2020-05-03 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 998947¦¦2020-03-31
TM | C | Yes | 998948 |  | DE AM RON WELL TV | MIGUEL, SEAN J. | 100% | 1656 | 0 | 1656 | 1770 | 1770 | 1770 | 0 | 0 | 1770 | 1289 | 0 | 1289 | 0 |  |  |  | 0 |  |  | 856.67 | 560.41 | 135.54 |  | 160.72 |  |  | 913.33 | 0 | 66.46% |  | 0 | 856.67 | 367 | 22.16% | 0 | 367 | 22.16% | 0 |  | 913.33 | 51.6% | 913.33 | 51.6% | -114 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 998816 - DEAM RON BUILDING SYSTEMS LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-20 | 2020-02-28 | 2020-01-20 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 998948¦¦2020-03-31
UP | CJ | Yes | 999078 |  | TEXAS BRINE WESTLAKE 1A | LOPEZ-VASQUEZ, JUAN C. | 100% | 13350 | 35400 | 48750 | 13350 | 13350 | 13350 | 0 | 0 | 13350 | 9203 | 24541 | 33744 | 670.17 | 195.63 | 420.19 |  | 54.35 |  |  | 11606.82 | 5455.73 | 3060.11 |  | 3090.98 |  |  | 1743.18 | 0 | 34.4% | 0 | 0 | 11606.82 | 4147 | 31.06% | 10859 | 15006 | 30.78% | 10859 |  | 1743.18 | 13.06% | 1743.18 | 13.06% | 35400 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878775 - TEXAS BRINE WHITE CASTLE COMPANY LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-21 | 2020-03-31 | 2020-01-21 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 999078¦¦2020-03-31
UP | CJ | Yes | 999079 |  | PORT OF LAKE CHARLES TEST3WELL | GNAU, CASEY T | 100% | 3000 | 0 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 3000 | 1500 | 0 | 1500 | 1.47 |  |  |  | 1.47 |  |  | 1211.02 | 686.8 | 185.5 |  | 338.72 |  |  | 1788.98 | 0 | 80.73% |  | 0 | 1211.02 | 1500 | 50% | 0 | 1500 | 50% | 0 |  | 1788.98 | 59.63% | 1788.98 | 59.63% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 896489 - PORT OF LAKE CHARLES | WATER | WATER REPAIR & INSTALLATION | 2020-01-22 | 2020-02-22 | 2020-01-22 | 2020-02-22 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 999079¦¦2020-03-31
UP | C | Yes | 999095 |  | COMO MS PWM TESTING | ANDERSON, STEPHEN P. | 100% | 1000 | 0 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 1000 | 701 | 0 | 701 | 0.11 |  |  |  | 0.11 |  |  | 628.7 | 352.01 |  |  | 276.69 |  |  | 371.3 | 0 | 89.69% |  | 0 | 628.7 | 299 | 29.9% | 0 | 299 | 29.9% | 0 |  | 371.3 | 37.13% | 371.3 | 37.13% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 888859 - COMO,TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-21 | 2020-01-31 | 2020-01-21 | 2020-01-31 | PRIME CONTRACTOR | PUBLIC | MAINTENANCE ONLY CONTRACT | 999095¦¦2020-03-31
UP | CJ | Yes | 999273 |  | RIVERSIDE LAKES SID HS PUMP | GANSEBOM, JASON W. | 100% | 4340 | 0 | 4340 | 6057 | 6057 | 6139.34 | 6139.34 | 0 | 6057 | 3171 | 0 | 3171 | 2112.36 | 821.2 | 303.82 |  | 586.34 | 401 |  | 4683.37 | 2046.31 | 574.17 |  | 1661.89 | 401 |  | 1373.63 | 0 | 147.7% |  | 0 | 4683.37 | 1169 | 26.94% | 0 | 1169 | 26.94% | 0 |  | 1373.63 | 22.68% | 1373.63 | 22.68% | -1717 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 897087 - RIVERSIDE LAKES SID 177 | WATER | WATER REPAIR & INSTALLATION | 2020-01-22 | 2020-03-31 | 2020-01-22 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 999273¦¦2020-03-31
UP | CJ | Yes | 999288 |  | GSK LINCOLN NE CONDENSER | GANSEBOM, JASON W. | 100% | 9520 | 0 | 9520 | 8278 | 8278 | 8278 | 8278 | 0 | 8278 | 6664 | 0 | 6664 | 1240.99 | 666.88 | 83.48 |  | 490.63 |  |  | 2349.13 | 1300.87 | 83.48 |  | 964.78 |  |  | 5928.87 | 0 | 35.25% |  | 0 | 2349.13 | 2856 | 30% | 0 | 2856 | 30% | 0 |  | 5928.87 | 71.62% | 5928.87 | 71.62% | 1242 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 891670 - GSK NORTH AMERICA | WATER | WATER EQUIPMENT SALES | 2020-01-22 | 2020-02-28 | 2020-01-22 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 999288¦¦2020-03-31
UP | C | Yes | 999447 |  | AMITE STEEL MOTOR REPAIR | LOPEZ-VASQUEZ, JUAN C. | 100% | 1300 | 4565 | 5865 | 5815 | 5815 | 5815 | 0 | 0 | 5815 | 943 | 2657 | 3600 | 889.66 | 531.16 | 176.23 |  | 182.27 | 0 |  | 4092.32 | 1621.26 | 539.96 |  | 1004.1 | 927 |  | 1722.68 | 0 | 113.7% |  | 0 | 4092.32 | 357 | 27.46% | 1908 | 2265 | 38.62% | 1908 |  | 1722.68 | 29.62% | 1722.68 | 29.62% | 50 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 886265 - AMITE, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-22 | 2020-03-30 | 2020-01-22 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 999447¦¦2020-03-31
TM | C | Yes | 999754 |  | PATRIOT FLORENCE WELL | MIGUEL, SEAN J. | 100% | 1150 | 0 | 1150 | 400 | 400 | 400 | 0 | 0 | 400 | 760 | 0 | 760 | 0 |  |  |  | 0 |  |  | 155.44 | 92.79 | 20.89 |  | 41.76 |  |  | 244.56 | 0 | 20.45% |  | 0 | 155.44 | 390 | 33.91% | 0 | 390 | 33.91% | 0 |  | 244.56 | 61.14% | 244.56 | 61.14% | 750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 896090 - PATRIOT WATER DEPARTMENT | WATER | WATER REPAIR & INSTALLATION | 2020-01-22 | 2020-02-28 | 2020-01-22 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 999754¦¦2020-03-31
FP | CJ | Yes | 999755 |  | SPRINGFIELD NE TEST WELL | GANSEBOM, JASON W. | 100% | 3495 | 0 | 3495 | 3495 | 3495 | 3495 | 0 | 0 | 3495 | 2665 | 0 | 2665 | 2641.99 | 952.23 | 626.14 |  | 679.62 | 384 |  | 2641.99 | 952.23 | 626.14 |  | 679.62 | 384 |  | 853.01 | 0 | 99.14% |  | 0 | 2641.99 | 830 | 23.75% | 0 | 830 | 23.75% | 0 |  | 853.01 | 24.41% | 853.01 | 24.41% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 898177 - SPRINGFIELD, NE, CITY OF | WATER | WATER SUPPLY | 2020-01-22 | 2020-02-28 | 2020-01-22 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 999755¦¦2020-03-31
UP | CJ | Yes | 999756 |  | WELL 2 NEWD | BRASHEAR, DAVID M | 100% | 55189 | 0 | 55189 | 38359.3 | 38359.3 | 22427.8 | 0 | 0 | 38359.3 | 40446 | 0 | 40446 | 30990.27 | 8301.26 | 4252.54 |  | 18436.47 |  |  | 30990.27 | 8301.26 | 4252.54 |  | 18436.47 |  |  | 7369.03 | 0 | 76.62% |  | 0 | 30990.27 | 14743 | 26.71% | 0 | 14743 | 26.71% | 0 |  | 7369.03 | 19.21% | 7369.03 | 19.21% | 16829.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 170779 - NORTH EDWARDS WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-01-21 | 2020-05-29 | 2020-01-21 | 2020-05-29 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 999756¦¦2020-03-31
UP | C | Yes | 999757 |  | FORT RUCKER RUNKLE WELL PUMP | PARSLEY, TRISTAN S | 100% | 9120 | 0 | 9120 | 9120 | 9120 | 9120 | 0 | 0 | 9120 | 6100 | 0 | 6100 | 55.68 |  |  |  | 55.68 |  |  | 8114.05 | 2215.66 | 1203.68 |  | 4694.71 |  |  | 1005.95 | 0 | 133% |  | 0 | 8114.05 | 3020 | 33.11% | 0 | 3020 | 33.11% | 0 |  | 1005.95 | 11.03% | 1005.95 | 11.03% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 886247 - AMERICAN WATER FORT RUCKER ALABAMA | WATER | WATER SUPPLY | 2020-01-13 | 2020-02-29 | 2020-01-20 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 999757¦¦2020-03-31
FP | C | Yes | 999758 |  | DESTIN WATER FLOW TESTS | PARSLEY, TRISTAN S | 100% | 6156 | 0 | 6156 | 6156 | 6156 | 6156 | 0 | 0 | 6156 | 5390 | 0 | 5390 | 1517.44 | 504.22 | 184.92 |  | 828.3 |  |  | 5498.47 | 2158.92 | 865.73 |  | 2473.82 |  |  | 657.53 | 0 | 102% |  | 0 | 5498.47 | 766 | 12.44% | 0 | 766 | 12.44% | 0 |  | 657.53 | 10.68% | 657.53 | 10.68% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 878869 - DESTIN WATER USERS INC | WATER | WATER SUPPLY | 2020-01-17 | 2020-03-30 | 2020-01-21 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 999758¦¦2020-03-31
FP | CJ | Yes | 999759 |  | FORMOSA FLOW TEST | GREGORY, CRYSTAL N | 100% | 2500 | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 2500 | 1690 | 0 | 1690 | 15.23 |  |  |  | 15.23 |  |  | 1149.98 | 595.19 | 259.7 |  | 295.09 |  |  | 1350.02 | 0 | 68.05% |  | 0 | 1149.98 | 810 | 32.4% | 0 | 810 | 32.4% | 0 |  | 1350.02 | 54% | 1350.02 | 54% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 890781 - FORMOSA PLASTICS CORP, LA | WATER | WATER REPAIR & INSTALLATION | 2020-01-23 | 2020-02-28 | 2020-01-23 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 999759¦¦2020-03-31
TM | CJ | Yes | 1000162 |  | PCA VALDOSTA WELL 1 | PARSLEY, TRISTAN S | 100% | 35482 | 48865 | 84347 | 83864.4 | 83864.4 | 83864.4 | 2000 | 0 | 83864.4 | 23063 | 48662.26 | 71725.26 | 1702.89 |  |  |  | 1702.89 |  |  | 56850.1 | 22545.77 | 5683.15 |  | 28621.18 |  |  | 27014.3 | 0 | 79.26% |  | 0 | 56850.1 | 12419 | 35% | 202.74 | 12621.74 | 14.96% | 202.74 | 202.74 | 27014.3 | 32.21% | 27014.3 | 32.21% | 482.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 896132 - PCA VALDOSTA | WATER | WATER REPAIR & INSTALLATION | 2020-01-23 | 2020-02-29 | 2020-01-23 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1000162¦¦2020-03-31
UP | CJ | Yes | 1000163 |  | WYNSTONE POA WELL 6 | KENNEDY, CHRISTOPHER C. | 100% | 150000 | 35000 | 185000 | 60487 | 60487 | 60487 | 0 | 0 | 60487 | 105000 | 23224.5 | 128224.5 | 4795.93 | 3510.05 | 216.24 |  | 1069.64 |  |  | 38588.83 | 25815.5 | 5255.7 |  | 7517.63 |  |  | 21898.17 | 0 | 30.09% |  | 0 | 38588.83 | 45000 | 30% | 11775.5 | 56775.5 | 30.69% | 11775.5 | 11775.5 | 21898.17 | 36.2% | 21898.17 | 36.2% | 124513 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878897 - WYNSTONE PROPERTY OWNERS ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2020-01-20 | 2020-04-30 | 2020-01-20 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1000163¦¦2020-03-31
FP | CJ | Yes | 1000164 |  | DOMTAR FLOW TESTS | MIGUEL, SEAN J. | 100% | 6250 | 25885 | 32135 | 19256 | 19256 | 19256 | 13006 | 0 | 19256 | 5000 | 17857 | 22857 | 8178.15 | 820.22 | 81.79 |  | 7276.14 |  |  | 14731.02 | 4214.67 | 886.36 |  | 9629.99 |  |  | 4524.98 | 0 | 64.45% |  | 0 | 14731.02 | 1250 | 20% | 8028 | 9278 | 28.87% | 8028 |  | 4524.98 | 23.5% | 4524.98 | 23.5% | 12879 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878859 - DOMTAR | WATER | WATER REPAIR & INSTALLATION | 2020-01-21 | 2020-02-28 | 2020-01-21 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1000164¦¦2020-03-31
UP | C | Yes | 1000165 |  | PRINCETON TESTS | WILLIAMS, DONALD G. | 100% | 4340 | 0 | 4340 | 4340 | 4340 | 4340 | 0 | 0 | 4340 | 3514 | 0 | 3514 | 0 |  |  |  | 0 |  |  | 3387.35 | 1907.73 | 417.8 |  | 1061.82 |  |  | 952.65 | 0 | 96.4% |  | 0 | 3387.35 | 826 | 19.03% | 0 | 826 | 19.03% | 0 |  | 952.65 | 21.95% | 952.65 | 21.95% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 896586 - PRINCETON, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-24 | 2020-02-28 | 2020-01-24 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1000165¦¦2020-03-31
TM | CJ | Yes | 1000168 |  | EKP 2020 MAINTENANCE | MIGUEL, SEAN J. | 100% | 225000 | 0 | 225000 | 96406.17 | 96406.17 | 73622.66 | 73622.66 | 0 | 96406.17 | 168750 | 0 | 168750 | 55857.02 | 22044.72 | 9709.15 |  | 21209.15 | 2894 |  | 77886.02 | 34515.42 | 13770.13 |  | 26706.47 | 2894 |  | 18520.15 | 0 | 46.15% |  | 0 | 77886.02 | 56250 | 25% | 0 | 56250 | 25% | 0 |  | 18520.15 | 19.21% | 18520.15 | 19.21% | 128593.83 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878840 - EAST KENTUCKY POWER CO OP | WATER | WATER REPAIR & INSTALLATION | 2020-01-01 | 2020-07-31 | 2020-01-01 | 2020-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1000168¦¦2020-03-31
FP | CJ | Yes | 1001097 |  | EMERSON NE WELL 5 REHAB | GANSEBOM, JASON W. | 100% | 16150 | 0 | 16150 | 22159.6 | 22159.6 | 22519.34 | 0 | 0 | 22159.6 | 12650 | 0 | 12650 | 214.39 | 57.62 |  |  | 156.77 |  |  | 29922.72 | 11338.62 | 5111.81 |  | 12653.92 | 818.37 |  | 0 | 7763.12 | 236.5% |  | 0 | 29922.72 | 3500 | 21.67% | 0 | 3500 | 21.67% | 0 |  | -7763.12 | -35.03% | -7763.12 | -35.03% | -6009.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 1000545 - EMERSON, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-23 | 2020-02-14 | 2020-01-23 | 2020-02-14 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1001097¦¦2020-03-31
UP | C | Yes | 1001098 |  | WICHITA KS H AND E WELLS | WARTICK, LOGAN M | 100% | 14140 | 0 | 14140 | 15394.2 | 15394.2 | 15394.2 | 0 | 0 | 15394.2 | 11595 | 0 | 11595 | 573.69 | 300.64 | 46.64 |  | 226.41 |  |  | 16759.9 | 8464.76 | 2712.92 |  | 5582.22 |  |  | 0 | 1365.7 | 144.5% |  | 0 | 16759.9 | 2545 | 18% | 0 | 2545 | 18% | 0 |  | -1365.7 | -8.872% | -1365.7 | -8.872% | -1254.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 900295 - WICHITA DEPT HEALTH & ENVIRO | WATER | WATER REPAIR & INSTALLATION | 2020-01-24 | 2020-03-20 | 2020-01-24 | 2020-03-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1001098¦¦2020-03-31
UP | CJ | Yes | 1001099 |  | WESTLAKE PLAQUEMINE 2020 FLOW | GREGORY, CRYSTAL N | 100% | 12000 | 0 | 12000 | 9010.1 | 9010.1 | 6000 | 0 | 0 | 9010.1 | 5462 | 0 | 5462 | 3203.34 | 1669.82 | 608.04 |  | 925.48 |  |  | 7279.21 | 4051.14 | 1122.65 |  | 2105.42 |  |  | 1730.89 | 0 | 133.3% |  | 0 | 7279.21 | 6538 | 54.48% | 0 | 6538 | 54.48% | 0 |  | 1730.89 | 19.21% | 1730.89 | 19.21% | 2989.9 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 886694 - AXIALL WESTLAKE PLAQUEMINE | WATER | WATER REPAIR & INSTALLATION | 2020-01-24 | 2020-03-31 | 2020-01-24 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1001099¦¦2020-03-31
FP | CJ | Yes | 1001100 |  | CHEMOURS RWP 6 | MIGUEL, SEAN J. | 100% | 176600 | 23757.45 | 200357.45 | 104845.75 | 104845.75 | 12507.45 | 12507.45 | 0 | 104845.75 | 132450 | 17818 | 150268 | 7579.65 | 3125.81 | 641.27 |  | 3812.57 |  |  | 84704.31 | 9395.43 | 2640.32 |  | 72668.56 |  |  | 20141.44 | 0 | 56.37% |  | 0 | 84704.31 | 44150 | 25% | 5939.45 | 50089.45 | 25% | 5939.45 | 5939.45 | 20141.44 | 19.21% | 20141.44 | 19.21% | 95511.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888287 - CHEMOURS LOUISVILLE WORKS | WATER | WATER REPAIR & INSTALLATION | 2020-01-24 | 2020-07-31 | 2020-01-24 | 2020-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1001100¦¦2020-03-31
UP | C | Yes | 1002092 |  | FREE STATE GROWERS LINWOOD KS3 | WARTICK, LOGAN M | 100% | 3780 | 0 | 3780 | 10124 | 10124 | 10124 | 0 | 0 | 10124 | 2948 | 0 | 2948 | 143.36 | 143.36 |  |  | 0 |  |  | 4648.45 | 1705.65 | 537.63 |  | 2405.17 |  |  | 5475.55 | 0 | 157.7% |  | 0 | 4648.45 | 832 | 22.01% | 0 | 832 | 22.01% | 0 |  | 5475.55 | 54.08% | 5475.55 | 54.08% | -6344 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 890925 - FREE STATE GROWERS INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-27 | 2020-02-29 | 2020-01-27 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1002092¦¦2020-03-31
UP | CJ | Yes | 1002093 |  | CITY OF CHANDLER FRYE RECIRC | VAN ALLEN, WESLEY C. |  | 3150 | 0 | 3150 |  |  | 0 | 0 | 0 |  | 2861 | 0 | 2861 | [20 empty] | 289 | 9.175% | 0 | 289 | 9.175% | 0 | [5 empty] | 3150 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-27 | 2020-03-27 | 2020-01-27 | 2020-03-27 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1002093¦¦2020-03-31
FP | CJ | Yes | 1002094 |  | REPUBLIC SERVICES LCS 6B 5A 5B | WHITE, CATHLEEN R | 100% | 18730 | 8480 | 27210 | 11053.89 | 11053.89 | 7846 | 7846 | 0 | 11053.89 | 13100 | 6044.1 | 19144.1 | 3862.14 | 908.35 | 279.12 |  | 2674.67 |  |  | 8930.38 | 908.35 | 279.12 |  | 7742.91 |  |  | 2123.51 | 0 | 46.65% |  | 0 | 8930.38 | 5630 | 30.06% | 2435.9 | 8065.9 | 29.64% | 2435.9 |  | 2123.51 | 19.21% | 2123.51 | 19.21% | 16156.11 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896943 - REPUBLIC SERVICES PROCUREMENT, INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-24 | 2020-03-31 | 2020-01-24 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1002094¦¦2020-03-31
UP | CJ | Yes | 1002095 |  | DARAMIC TESTS | MIGUEL, SEAN J. | 100% | 2250 | 41662 | 43912 | 43912 | 43912 | 43912 | 41662 | 0 | 43912 | 1750 | 31247 | 32997 | 14576.93 | 7146.55 | 2709.55 |  | 4720.83 |  |  | 26763.45 | 11624.71 | 4832.24 |  | 10306.5 |  |  | 17148.55 | 0 | 81.11% |  | 0 | 26763.45 | 500 | 22.22% | 10415 | 10915 | 24.86% | 10415 |  | 17148.55 | 39.05% | 17148.55 | 39.05% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889327 - DARAMIC, LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-24 | 2020-02-28 | 2020-01-24 | 2020-08-20 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1002095¦¦2020-03-31
UP | CJ | Yes | 1002404 |  | CHILTON COUNTY WATER ANALYSIS | PARSLEY, TRISTAN S | 100% | 1350 | 0 | 1350 | 1350 | 1350 | 1350 | 0 | 0 | 1350 | 800 | 0 | 800 | 780.66 |  |  |  | 0.66 | 780 |  | 780.66 |  |  |  | 0.66 | 780 |  | 569.34 | 0 | 97.58% |  | 0 | 780.66 | 550 | 40.74% | 0 | 550 | 40.74% | 0 |  | 569.34 | 42.17% | 569.34 | 42.17% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 1011807 - CHILTON WATER AUTHORITY | WATER | WATER SUPPLY | 2020-01-21 | 2020-03-30 | 2020-01-27 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1002404¦¦2020-03-31
UP | C | Yes | 1002659 |  | GREENDALE PWMS | MIGUEL, SEAN J. | 100% | 3870 | 0 | 3870 | 3870 | 3870 | 3870 | 0 | 0 | 3870 | 3138 | 0 | 3138 | 324.35 | 276.67 | 44.16 |  | 3.52 |  |  | 3949.39 | 1916.64 | 1071.65 |  | 961.1 |  |  | 0 | 79.39 | 125.9% |  | 0 | 3949.39 | 732 | 18.91% | 0 | 732 | 18.91% | 0 |  | -79.39 | -2.051% | -79.39 | -2.051% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 891562 - GREENDALE, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-27 | 2020-02-28 | 2020-01-27 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1002659¦¦2020-03-31
UP | CJ | Yes | 1002660 |  | APPLE VALLEY HORSEMANS CENTER | BRASHEAR, DAVID M | 100% | 6344 | 11360.16 | 17704.16 | 17704.16 | 17704.16 | 17940.17 | 0 | 0 | 17704.16 | 4757 | 8528.07 | 13285.07 | 5298.38 | 1916.55 | 1078.94 |  | 2302.89 |  |  | 10867.28 | 4589.82 | 1824.24 |  | 4453.22 |  |  | 6836.88 | 0 | 81.8% |  | 0 | 10867.28 | 1587 | 25.02% | 2832.09 | 4419.09 | 24.96% | 2832.09 |  | 6836.88 | 38.62% | 6836.88 | 38.62% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 886362 - APPLE VALLEY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-27 | 2020-02-14 | 2020-01-27 | 2020-02-14 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1002660¦¦2020-03-31
UP | C | Yes | 1002665 |  | GRANDVIEW NY MEDIA REPL | MCCARTNEY, JEFFREY C | 100% | 80400 | -5500 | 74900 | 74900 | 74900 | 74900 | 74900 | 0 | 74900 | 46540 | -4815 | 41725 | 10972.44 | 3193.77 | 1742.4 |  | 6036.27 |  |  | 47886.58 | 3797.53 | 1742.4 |  | 42346.65 |  |  | 27013.42 | 0 | 114.8% |  | 0 | 47886.58 | 33860 | 42.11% | -685 | 33175 | 44.29% | -685 | -685 | 27013.42 | 36.07% | 27013.42 | 36.07% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 898467 - SUEZ | WATER | WATER TREATMENT | 2020-01-22 | 2020-03-31 | 2020-01-22 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 1002665¦¦2020-03-31
FP | CJ | Yes | 1002698 |  | EVERGREEN PACKAGING WELL 16 | BURGE, EVERETT E. | 100% | 25000 | 0 | 25000 | 25000 | 25000 | 24362 | 0 | 0 | 25000 | 18500 | 0 | 18500 | 2045.69 |  | -218.89 |  | 2264.58 |  |  | 42566.57 | 20656.17 | 3800.11 |  | 18110.29 |  |  | 0 | 17566.57 | 230.1% |  | 0 | 42566.57 | 6500 | 26% | 0 | 6500 | 26% | 0 |  | -17566.57 | -70.27% | -17566.57 | -70.27% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878972 - EVERGREEN PACKAGING INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-27 | 2020-06-24 | 2020-01-27 | 2020-06-24 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1002698¦¦2020-03-31
UP | CJ | Yes | 1002699 |  | WC LAKE CHARLES REHAB 33 | GNAU, CASEY T |  | 149300 | 0 | 149300 |  |  | 0 | 0 | 0 |  | 85065 | 0 | 85065 | [20 empty] | 64235 | 43.02% | 0 | 64235 | 43.02% | 0 | [5 empty] | 149300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879005 - DO NOT USE WESTLAKE C A & O CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-01-29 | 2020-03-31 | 2020-01-29 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1002699¦¦2020-03-31
UP | CJ | Yes | 1002738 |  | FRANKFORT IL WELL 8 PUMP REHAB | EISHA, JOSEPH J. | 100% | 20000 | 0 | 20000 | 29917 | 29917 | 29917 | 0 | 0 | 29917 | 13500 | 0 | 13500 | 9755.24 | 5810.89 | 1646.68 |  | 2297.67 |  |  | 20218.62 | 13052.23 | 3093.53 |  | 4072.86 |  |  | 9698.38 | 0 | 149.8% |  | 0 | 20218.62 | 6500 | 32.5% | 0 | 6500 | 32.5% | 0 |  | 9698.38 | 32.42% | 9698.38 | 32.42% | -9917 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878861 - FRANKFORT, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-29 | 2020-02-08 | 2020-01-29 | 2020-02-08 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1002738¦¦2020-03-31
UP | C | Yes | 1002811 |  | DOW | GREGORY, CRYSTAL N | 100% | 13825 | 0 | 13825 | 13825 | 13825 | 13825 | 0 | 0 | 13825 | 10152 | 0 | 10152 | 3549.09 | 256.42 | 249.93 |  | 137.74 | 2905 |  | 11013.93 | 4397.21 | 1409.31 |  | 2302.41 | 2905 |  | 2811.07 | 0 | 108.5% |  | 0 | 11013.93 | 3673 | 26.57% | 0 | 3673 | 26.57% | 0 |  | 2811.07 | 20.33% | 2811.07 | 20.33% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 887214 - BLUE CUBE OPERATIONS LLC | WATER | WATER REPAIR & INSTALLATION | 2020-01-28 | 2020-03-31 | 2020-01-28 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1002811¦¦2020-03-31
FP | CJ | Yes | 1002812 |  | JAY NY PUMP SETTING | CROOK, CHARLES M | 100% | 165695 | 0 | 165695 | 649.53 | 649.53 | 0 | 0 | 0 | 649.53 | 120000 | 0 | 120000 | 234.8 | 231.29 |  |  | 3.51 |  |  | 524.75 | 498.6 |  |  | 26.15 |  |  | 124.78 | 0 | 0.4373% |  | 0 | 524.75 | 45695 | 27.58% | 0 | 45695 | 27.58% | 0 |  | 124.78 | 19.21% | 124.78 | 19.21% | 165045.47 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 996395 - JFP ENTERPRISES INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-03-30 | 2020-01-17 | 2020-03-30 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 1002812¦¦2020-03-31
UP | CJ | Yes | 1002813 |  | DIXON IL BOOSTER 2 | SNELTEN, BRIAN M |  | 3611 | 0 | 3611 |  |  | 0 | 0 | 0 |  | 2542 | 0 | 2542 | [20 empty] | 1069 | 29.6% | 0 | 1069 | 29.6% | 0 | [5 empty] | 3611 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878628 - DIXON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-29 | 2020-04-03 | 2020-01-29 | 2020-04-03 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1002813¦¦2020-03-31
UP | CJ | Yes | 1002961 |  | CID WELL 103 | BRASHEAR, DAVID M | 100% | 10750 | 25724.33 | 36474.33 | 36474.76 | 36474.76 | 36858.98 | 0 | 0 | 36474.76 | 9031 | 21953.24 | 30984.24 | 18031.5 | 6386.8 | 2851.1 |  | 4447.29 | 4346.31 |  | 32863.37 | 13280.99 | 5100.36 |  | 10135.71 | 4346.31 |  | 3611.39 | 0 | 106.1% |  | 0 | 32863.37 | 1719 | 15.99% | 3771.09 | 5490.09 | 15.05% | 3771.09 |  | 3611.39 | 9.901% | 3611.39 | 9.901% | -0.43 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 861 - WRD HANFORD | HANFORD - WA | 878571 - CORCORAN IRRIGATION DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-01-15 | 2020-04-30 | 2020-01-15 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1002961¦¦2020-03-31
UP | CJ | Yes | 1003088 |  | CARLOS CARTER PR | SCHERM, LOGAN M | 100% | 29165 | 0 | 29165 | 16326.51 | 16326.51 | 0 | 0 | 0 | 16326.51 | 19915 | 0 | 19915 | 8425.56 | 3192.44 | 1234.7 |  | 3998.42 |  |  | 13190.1 | 5803.54 | 1326.75 |  | 6059.81 |  |  | 3136.41 | 0 | 66.23% |  | 0 | 13190.1 | 9250 | 31.72% | 0 | 9250 | 31.72% | 0 |  | 3136.41 | 19.21% | 3136.41 | 19.21% | 12838.49 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887946 - CARLOS CARTER, INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-30 | 2020-03-30 | 2020-01-30 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1003088¦¦2020-03-31
UP | CJ | Yes | 1003090 |  | CAPE CORAL ACID TASK 3 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 88965 | 88965 | 88965 | 0 | 8896.5 | 88965 | 71475 | 0 | 71475 | 42057.36 | 13180.58 | 11290.25 |  | 17536.53 | 50 |  | 52955.38 | 14405.55 | 11927.92 |  | 26571.91 | 50 |  | 36009.62 | 0 | 74.09% |  | 0 | 52955.38 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 36009.62 | 40.48% | 36009.62 | 40.48% | -2640 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-30 | 2020-04-10 | 2020-01-30 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003090¦¦2020-03-31
FP | C | Yes | 1003092 |  | ZEN NOH GRAIN SUBMONITOR | GREGORY, CRYSTAL N | 100% | 1000 | 0 | 1000 | 1000 | 1000 | 1079.5 | 0 | 0 | 1000 | 714 | 0 | 714 | [7 empty] | 649 |  |  |  | 649 |  |  | 351 | 0 | 90.9% |  | 0 | 649 | 286 | 28.6% | 0 | 286 | 28.6% | 0 |  | 351 | 35.1% | 351 | 35.1% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 1002895 - ZEN NOH GRAIN CORP | WATER | WATER EQUIPMENT SALES | 2020-01-29 | 2020-03-31 | 2020-01-29 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1003092¦¦2020-03-31
FP | CJ | Yes | 1003093 |  | ENBRIDGE DISCHARGE HEAD REPAIR | GNAU, CASEY T | 100% | 9800 | 26200 | 36000 | 36000 | 36000 | 36000 | 36000 | 0 | 36000 | 5616 | 14927 | 20543 | 6139.13 | 3094.85 | 812.75 |  | 1681.53 | 550 |  | 17119.98 | 7233.03 | 2402.67 |  | 6934.28 | 550 |  | 18880.02 | 0 | 83.34% |  | 0 | 17119.98 | 4184 | 42.69% | 11273 | 15457 | 42.94% | 11273 | 11273 | 18880.02 | 52.44% | 18880.02 | 52.44% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 890063 - EGAN HUB STORAGE LLC SPECTRA | WATER | WATER REPAIR & INSTALLATION | 2020-01-29 | 2020-02-29 | 2020-01-29 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1003093¦¦2020-03-31
FP | C | Yes | 1003094 |  | HARTWICK NY VFD INSTALL | CROOK, CHARLES M | 100% | 7500 | 0 | 7500 | 8600 | 8600 | 8600 | 8600 | 0 | 8600 | 5500 | 0 | 5500 | 6523.83 | 60.87 |  |  | 1.09 | 6461.87 |  | 6877.39 | 410.03 |  |  | 5.49 | 6461.87 |  | 1722.61 | 0 | 125% |  | 0 | 6877.39 | 2000 | 26.67% | 0 | 2000 | 26.67% | 0 |  | 1722.61 | 20.03% | 1722.61 | 20.03% | -1100 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 891885 - HARTWICK, NY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-30 | 2020-03-13 | 2020-01-30 | 2020-03-13 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1003094¦¦2020-03-31
UP | CJ | Yes | 1003095 |  | CITY OF CHANDLER PLEASANT WELL | VAN ALLEN, WESLEY C. | 100% | 10775 | 77606.53 | 88381.53 | 82337.05 | 82337.05 | 82337.05 | 0 | 0 | 82337.05 | 9658 | 65582.85 | 75240.85 | 16535.44 | 3849 | 1992.5 |  | 2597.22 | 8096.72 |  | 63781.99 | 9306.94 | 6040.82 |  | 40337.51 | 8096.72 |  | 18555.06 | 0 | 84.77% |  | 0 | 63781.99 | 1117 | 10.37% | 12023.68 | 13140.68 | 14.87% | 12023.68 |  | 18555.06 | 22.54% | 18555.06 | 22.54% | 6044.48 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-27 | 2020-03-27 | 2020-01-27 | 2020-03-27 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1003095¦¦2020-03-31
FP | CJ | Yes | 1003102 |  | CANYON COUNTY LANDFILL | DECKER, JASEN | 100% | 277370 | 32826.5 | 310196.5 | 310196.45 | 310196.45 | 310196.45 | 0 | 0 | 310196.45 | 207732.78 | 22810.52 | 230543.3 | 107751.07 | 39153.32 | 37380.38 |  | 31217.37 |  |  | 186962.24 | 71556.46 | 55989.37 |  | 59416.41 |  |  | 123234.21 | 0 | 81.1% |  | 0 | 186962.24 | 69637.22 | 25.11% | 10015.98 | 79653.2 | 25.68% | 10015.98 | 10015.98 | 123234.21 | 39.73% | 123234.21 | 39.73% | 0.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 1002821 - PICKLES BUTTE SANITARY LANDFIL | WATER | WATER SPECIALTY DRILLING | 2020-01-10 | 2020-02-29 | 2020-01-10 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003102¦¦2020-03-31
UP | CJ | Yes | 1003419 |  | CAPE CORAL ACID TASK 4 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 90665 | 90665 | 90665 | 0 | 9066.5 | 90665 | 71475 | 0 | 71475 | 32130.83 | 10323.14 | 11761.53 |  | 5746.16 | 4300 |  | 34572 | 10323.14 | 11761.53 |  | 8187.33 | 4300 |  | 56093 | 0 | 48.37% |  | 0 | 34572 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 56093 | 61.87% | 56093 | 61.87% | -4340 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-15 | 2020-03-15 | 2020-01-15 | 2020-03-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003419¦¦2020-03-31
UP | CJ | Yes | 1003420 |  | KTG WELL 10 | ANDERSON, STEPHEN P. | 100% | 4795 | 0 | 4795 | 875.91 | 875.91 | 0 | 0 | 0 | 875.91 | 3334 | 0 | 3334 | 0.43 |  |  |  | 0.43 |  |  | 707.64 | 274.34 | 163.53 |  | 269.77 |  |  | 168.27 | 0 | 21.22% |  | 0 | 707.64 | 1461 | 30.47% | 0 | 1461 | 30.47% | 0 |  | 168.27 | 19.21% | 168.27 | 19.21% | 3919.09 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 977270 - KTG USA INC | WATER | WATER REPAIR & INSTALLATION | 2020-01-31 | 2020-03-15 | 2020-01-31 | 2020-03-15 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1003420¦¦2020-03-31
UP | CJ | Yes | 1003426 |  | CAPE CORAL ACID TASK 5 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 2164.56 | 2164.56 | 0 | 0 | 0 | 2164.56 | 71475 | 0 | 71475 | 1.06 |  |  |  | 1.06 |  |  | 2164.56 |  |  |  | 2164.56 |  |  | 0 | 0 | 3.028% |  | 0 | 2164.56 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 0 | 0% | 0 | 0% | 84160.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-31 | 2020-04-10 | 2020-01-31 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003426¦¦2020-03-31
UP | CJ | Yes | 1003429 |  | SAN CAYETANO MWC WELL 8 | SEIDEN, ANDREW L. | 100% | 6308 | 26368 | 32676 | 8028.98 | 8028.98 | 6308.18 | 0 | 0 | 8028.98 | 4554 | 20271.42 | 24825.42 | 6486.57 | 2581.44 | 934.25 |  | 2970.88 |  |  | 6486.57 | 2581.44 | 934.25 |  | 2970.88 |  |  | 1542.41 | 0 | 26.13% |  | 0 | 6486.57 | 1754 | 27.81% | 6096.58 | 7850.58 | 24.03% | 6096.58 | 6096.58 | 1542.41 | 19.21% | 1542.41 | 19.21% | 24647.02 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 897421 - SAN CAYETANO MUTUAL WATER CO | WATER | WATER REPAIR & INSTALLATION | 2020-01-28 | 2020-03-01 | 2020-01-28 | 2020-03-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1003429¦¦2020-03-31
UP | CJ | Yes | 1003436 |  | CAPE CORAL ACID TASK 6 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 3807.6 | 3807.6 | 0 | 0 | 0 | 3807.6 | 71475 | 0 | 71475 | 1644.1 | 662.33 | 639.3 |  | 342.47 |  |  | 3807.6 | 662.33 | 639.3 |  | 2505.97 |  |  | 0 | 0 | 5.327% |  | 0 | 3807.6 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 0 | 0% | 0 | 0% | 82517.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-31 | 2020-04-10 | 2020-01-31 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003436¦¦2020-03-31
UP | C | Yes | 1003569 |  | FOLLANSBEE WV LAYNEOX PILOT | CHESLEY, ANDREW J | 100% | 13900 | 0 | 13900 | 13900 | 13900 | 13900 | 13900 | 0 | 13900 | 9619.33 | 0 | 9619.33 | 5133.93 | 3558.93 | 1032.39 |  | 542.61 |  |  | 6106.65 | 4277.18 | 1274.63 |  | 554.84 |  |  | 7793.35 | 0 | 63.48% |  | 0 | 6106.65 | 4280.67 | 30.8% | 0 | 4280.67 | 30.8% | 0 |  | 7793.35 | 56.07% | 7793.35 | 56.07% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 1003330 - GHOSH ENGINEERS INC | WATER | WATER TREATMENT | 2020-01-20 | 2020-04-30 | 2020-01-20 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1003569¦¦2020-03-31
UP | CJ | Yes | 1003793 |  | GRANITE I40 NEW WELL | TRAMMELL, DUANE R. | 100% | 324730 | 0 | 324730 | 52444 | 52444 | 52444 | 52444 | 0 | 52444 | 256538 | 0 | 256538 | 28726 | 10022.48 | 6142.91 |  | 12560.61 |  |  | 28726 | 10022.48 | 6142.91 |  | 12560.61 |  |  | 23718 | 0 | 11.2% |  | 0 | 28726 | 68192 | 21% | 0 | 68192 | 21% | 0 |  | 23718 | 45.23% | 23718 | 45.23% | 272286 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 891515 - GRANITE CONSTRUCTION INDIO BRANCH | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-04-30 | 2020-01-17 | 2020-04-30 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 1003793¦¦2020-03-31
UP | CJ | Yes | 1003834 |  | CAPE CORAL ACID TASK 7 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 2164.56 | 2164.56 | 0 | 0 | 0 | 2164.56 | 71475 | 0 | 71475 | 1.06 |  |  |  | 1.06 |  |  | 2164.56 |  |  |  | 2164.56 |  |  | 0 | 0 | 3.028% |  | 0 | 2164.56 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 0 | 0% | 0 | 0% | 84160.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-31 | 2020-04-10 | 2020-01-31 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003834¦¦2020-03-31
FP | CJ | Yes | 1003835 |  | RIO TINTO WELL 30 | BRASHEAR, DAVID M | 100% | 9820 | 18211 | 28031 | 28031.81 | 28031.81 | 28664.6 | 28664.6 | 0 | 28031.81 | 7332 | 13834.14 | 21166.14 | 2733.96 | 1057.72 | 833.18 |  | 843.06 |  |  | 19714.48 | 6367.79 | 2809.13 |  | 10537.56 |  |  | 8317.33 | 0 | 93.14% |  | 0 | 19714.48 | 2488 | 25.34% | 4376.86 | 6864.86 | 24.49% | 4376.86 |  | 8317.33 | 29.67% | 8317.33 | 29.67% | -0.81 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 897054 - RIO TINTO MINERALS BORON OPERATIONS | WATER | WATER REPAIR & INSTALLATION | 2020-01-31 | 2020-02-29 | 2020-01-31 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1003835¦¦2020-03-31
UP | CJ | Yes | 1003845 |  | CAPE CORAL ACID TASK 8 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 2164.56 | 2164.56 | 0 | 0 | 0 | 2164.56 | 71475 | 0 | 71475 | 1.06 |  |  |  | 1.06 |  |  | 2164.56 |  |  |  | 2164.56 |  |  | 0 | 0 | 3.028% |  | 0 | 2164.56 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 0 | 0% | 0 | 0% | 84160.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2020-04-10 | 2020-02-03 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003845¦¦2020-03-31
FP | C | Yes | 1003846 |  | SOUTH ISLAND PSD CRETACEOUS | PARSLEY, TRISTAN S | 100% | 20515 | 10717 | 31232 | 31232 | 31232 | 31232 | 0 | 0 | 31232 | 13334 | 8294.98 | 21628.98 | 342.33 |  |  |  | 342.33 |  |  | 23044.6 | 7535.57 | 1720.26 |  | 13788.77 |  |  | 8187.4 | 0 | 106.5% |  | 0 | 23044.6 | 7181 | 35% | 2422.02 | 9603.02 | 30.75% | 2422.02 |  | 8187.4 | 26.21% | 8187.4 | 26.21% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 892139 - HILTON HEAD ISLAND PSD 1 | WATER | WATER REPAIR & INSTALLATION | 2020-01-29 | 2020-02-29 | 2020-01-29 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1003846¦¦2020-03-31
UP | CJ | Yes | 1003847 |  | EASTMAN CHEMICAL PUMP PARTS | ANDERSON, STEPHEN P. |  | 6549 | 0 | 6549 |  |  | 0 | 0 | 0 |  | 3922 | 0 | 3922 | [20 empty] | 2627 | 40.11% | 0 | 2627 | 40.11% | 0 | [5 empty] | 6549 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 889970 - EASTMAN CHEMICAL COMPANY | WATER | WATER EQUIPMENT SALES | 2020-02-03 | 2020-02-28 | 2020-02-03 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1003847¦¦2020-03-31
UP | CJ | Yes | 1003851 |  | CAPE CORAL ACID TASK 9 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 2164.56 | 2164.56 | 0 | 0 | 0 | 2164.56 | 71475 | 0 | 71475 | 1.06 |  |  |  | 1.06 |  |  | 2164.56 |  |  |  | 2164.56 |  |  | 0 | 0 | 3.028% |  | 0 | 2164.56 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 0 | 0% | 0 | 0% | 84160.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2020-04-10 | 2020-02-03 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003851¦¦2020-03-31
FP | C | Yes | 1003852 |  | PHILLIPS MAINTENANCE | WHITE, CATHLEEN R | 100% | 14860 | 0 | 14860 | 14860 | 14860 | 14860 | 0 | 0 | 14860 | 10400 | 0 | 10400 | 7.29 |  |  |  | 7.29 |  |  | 12557.64 | 6775.25 | 575.4 |  | 4681.99 | 525 |  | 2302.36 | 0 | 120.7% |  | 0 | 12557.64 | 4460 | 30.01% | 0 | 4460 | 30.01% | 0 |  | 2302.36 | 15.49% | 2302.36 | 15.49% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896286 - PHILLIPS 66 WOOD RIVER REFINERY | WATER | WATER REPAIR & INSTALLATION | 2020-01-31 | 2020-03-31 | 2020-01-31 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1003852¦¦2020-03-31
UP | CJ | Yes | 1003854 |  | EDWARDSVILLE ANNUAL MAINT | MIGUEL, SEAN J. | 100% | 20700 | 80700 | 101400 | 61050 | 61050 | 61050 | 40350 | 0 | 61050 | 16500 | 60540 | 77040 | 33251.36 | 15491.53 | 5271.53 |  | 12488.3 |  |  | 50753.45 | 24635.68 | 7358.83 |  | 18758.94 |  |  | 10296.55 | 0 | 65.88% |  | 0 | 50753.45 | 4200 | 20.29% | 20160 | 24360 | 24.02% | 20160 | 16800 | 10296.55 | 16.87% | 10296.55 | 16.87% | 40350 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878800 - EDWARDSVILLE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-24 | 2020-07-31 | 2020-01-30 | 2020-07-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1003854¦¦2020-03-31
UP | CJ | Yes | 1003865 |  | CAPE CORAL ACID TASK 10 | MCCULLERS, BLAKE E. | 100% | 86325 | 0 | 86325 | 2164.56 | 2164.56 | 0 | 0 | 0 | 2164.56 | 71475 | 0 | 71475 | 1.06 |  |  |  | 1.06 |  |  | 2164.56 |  |  |  | 2164.56 |  |  | 0 | 0 | 3.028% |  | 0 | 2164.56 | 14850 | 17.2% | 0 | 14850 | 17.2% | 0 |  | 0 | 0% | 0 | 0% | 84160.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2020-04-10 | 2020-02-03 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1003865¦¦2020-03-31
UP | C | Yes | 1004206 |  | TANGIPAHOA SHAFT AND SEAL | GREGORY, CRYSTAL N | 100% | 4495 | 0 | 4495 | 4494.81 | 4494.81 | 4494.81 | 0 | 0 | 4494.81 | 3236 | 0 | 3236 | 3984.96 | 2097.23 | 764.19 |  | 1123.54 |  |  | 3984.96 | 2097.23 | 764.19 |  | 1123.54 |  |  | 509.85 | 0 | 123.1% |  | 0 | 3984.96 | 1259 | 28.01% | 0 | 1259 | 28.01% | 0 |  | 509.85 | 11.34% | 509.85 | 11.34% | 0.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 898650 - TANGIPAHOA WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2020-03-31 | 2020-02-03 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1004206¦¦2020-03-31
TM | C | Yes | 1004207 |  | E AND D INC | SCHERM, LOGAN M | 100% | 50000 | 0 | 50000 | 53090.99 | 53090.99 | 57338.29 | 0 | 0 | 53090.99 | 40000 | 0 | 40000 | 38768.29 | 13859.23 | 2380.69 |  | 22528.37 |  |  | 38768.29 | 13859.23 | 2380.69 |  | 22528.37 |  |  | 14322.7 | 0 | 96.92% |  | 0 | 38768.29 | 10000 | 20% | 0 | 10000 | 20% | 0 |  | 14322.7 | 26.98% | 14322.7 | 26.98% | -3090.99 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 890043 - E & D INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2021-02-03 | 2020-02-03 | 2021-02-03 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1004207¦¦2020-03-31
UP | CJ | Yes | 1004208 |  | SOUTH ISLAND PSD LONG COVER 2 | PARSLEY, TRISTAN S | 100% | 30750 | 34193 | 64943 | 25000 | 25000 | 25000 | 0 | 0 | 25000 | 20067 | 24677.73 | 44744.73 | 13224.03 | 6611.73 | 2103.58 |  | 4508.72 |  |  | 13224.03 | 6611.73 | 2103.58 |  | 4508.72 |  |  | 11775.97 | 0 | 29.55% |  | 0 | 13224.03 | 10683 | 34.74% | 9515.27 | 20198.27 | 31.1% | 9515.27 | 9515.27 | 11775.97 | 47.1% | 11775.97 | 47.1% | 39943 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 892139 - HILTON HEAD ISLAND PSD 1 | WATER | WATER REPAIR & INSTALLATION | 2020-01-10 | 2020-03-31 | 2020-01-10 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1004208¦¦2020-03-31
UP | CJ | Yes | 1004209 |  | IA WATER STERLING IL 8 | HEALY, THOMAS P. | 100% | 24250 | 50160 | 74410 | 46281.71 | 46281.71 | 19882 | 0 | 0 | 46281.71 | 18250 | 40785.11 | 59035.11 | 10810.14 | 7882.08 | 200.37 |  | 2689.29 | 38.4 |  | 37390.74 | 25385.69 | 4098.85 |  | 7867.8 | 38.4 |  | 8890.97 | 0 | 63.34% |  | 0 | 37390.74 | 6000 | 24.74% | 9374.89 | 15374.89 | 20.66% | 9374.89 | 9374.89 | 8890.97 | 19.21% | 8890.97 | 19.21% | 28128.29 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 879026 - ILLINOIS AMERICAN WATER CO STERLING | WATER | WATER REPAIR & INSTALLATION | 2020-01-02 | 2020-04-30 | 2020-01-02 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1004209¦¦2020-03-31
TM | CJ | Yes | 1004210 |  | JS TARKINGTON | SCHERM, LOGAN M | 100% | 18000 | 0 | 18000 | 2795.48 | 2795.48 | 0 | 0 | 0 | 2795.48 | 14000 | 0 | 14000 | 2258.45 | 976.4 | 573.84 |  | 708.21 |  |  | 2258.45 | 976.4 | 573.84 |  | 708.21 |  |  | 537.03 | 0 | 16.13% |  | 0 | 2258.45 | 4000 | 22.22% | 0 | 4000 | 22.22% | 0 |  | 537.03 | 19.21% | 537.03 | 19.21% | 15204.52 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892953 - J S TARKINGTON FARMS | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2021-02-03 | 2020-02-03 | 2021-02-03 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1004210¦¦2020-03-31
UP | C | Yes | 1004213 |  | CHESTERFIELD WELL 4 TEST | MIGUEL, SEAN J. | 100% | 530 | 0 | 530 | 530 | 530 | 530 | 0 | 0 | 530 | 450 | 0 | 450 | 0 |  |  |  | 0 |  |  | 584.51 | 352.18 |  |  | 232.33 |  |  | 0 | 54.51 | 129.9% |  | 0 | 584.51 | 80 | 15.09% | 0 | 80 | 15.09% | 0 |  | -54.51 | -10.28% | -54.51 | -10.28% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888331 - CHESTERFIELD, IN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-31 | 2020-02-28 | 2020-01-31 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1004213¦¦2020-03-31
TM | CJ | Yes | 1004214 |  | OTWELL WELL 4 REHAB | WILLIAMS, DONALD G. | 100% | 18000 | 3371 | 21371 | 13388.65 | 13388.65 | 0 | 0 | 0 | 13388.65 | 14416 | 2528 | 16944 | 10816.62 | 4693.61 | 2087.11 |  | 4035.9 |  |  | 10816.62 | 4693.61 | 2087.11 |  | 4035.9 |  |  | 2572.03 | 0 | 63.84% |  | 0 | 10816.62 | 3584 | 19.91% | 843 | 4427 | 20.71% | 843 | 843 | 2572.03 | 19.21% | 2572.03 | 19.21% | 7982.35 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895907 - OTWELL WATER CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 1930-03-31 | 2020-02-03 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1004214¦¦2020-03-31
UP | CJ | Yes | 1004215 |  | FLORALA WELL 2 R AND I | PARSLEY, TRISTAN S | 100% | 10894 | 100901 | 111795 | 111795 | 111795 | 111795 | 0 | 0 | 111795 | 7813 | 73148.66 | 80961.66 | 55257.39 | 18616.57 | 6477.78 |  | 30163.04 |  |  | 72222.23 | 24261.7 | 7946.3 |  | 40014.23 |  |  | 39572.77 | 0 | 89.21% |  | 0 | 72222.23 | 3081 | 28.28% | 27752.34 | 30833.34 | 27.58% | 27752.34 |  | 39572.77 | 35.4% | 39572.77 | 35.4% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 890691 - FLORALA, CITY OF | WATER | WATER SUPPLY | 2020-01-29 | 2020-03-30 | 2020-01-29 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1004215¦¦2020-03-31
UP | CJ | Yes | 1004218 |  | SWUCI DESTIN FL WELL 12 | PARSLEY, TRISTAN S | 100% | 29454 | 0 | 29454 | 29239.5 | 29239.5 | 29239.5 | 0 | 0 | 29239.5 | 20596 | 0 | 20596 | 2762.82 | 633.89 | 401.22 |  | 1727.71 |  |  | 16282.89 | 6051.72 | 2563.38 |  | 7667.79 |  |  | 12956.61 | 0 | 79.06% |  | 0 | 16282.89 | 8858 | 30.07% | 0 | 8858 | 30.07% | 0 |  | 12956.61 | 44.31% | 12956.61 | 44.31% | 214.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 898087 - SOUTH WALTON UTILITY COMPANY, INC | WATER | WATER SUPPLY | 2020-01-15 | 2020-03-30 | 2020-01-20 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1004218¦¦2020-03-31
UP | CJ | Yes | 1004401 |  | BEVERLY HILLS RES 6 BOOSTER 1 | GRACE, GARY L. | 100% | 3357 | 24608.93 | 27965.93 | 27965.86 | 27965.86 | 28511.29 | 0 | 0 | 27965.86 | 2683 | 14608.04 | 17291.04 | 7362.93 | 4103.16 | 478.31 |  | 2781.46 |  |  | 20823.57 | 8229.26 | 1464.06 |  | 9467.74 | 1662.51 |  | 7142.29 | 0 | 120.4% |  | 0 | 20823.57 | 674 | 20.08% | 10000.89 | 10674.89 | 38.17% | 10000.89 |  | 7142.29 | 25.54% | 7142.29 | 25.54% | 0.07 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878627 - BEVERLY HILLS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-02-29 | 2020-02-04 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1004401¦¦2020-03-31
TM | C | Yes | 1004402 |  | DEWITT AND CO PR | SCHERM, LOGAN M | 100% | 9000 | 0 | 9000 | 6998.81 | 6998.81 | 7523.73 | 0 | 0 | 6998.81 | 6640 | 0 | 6640 | 3824.22 | 1556.92 | 341.9 |  | 1925.4 |  |  | 4172.42 | 1556.92 | 341.9 |  | 1925.4 | 348.2 |  | 2826.39 | 0 | 62.84% |  | 0 | 4172.42 | 2360 | 26.22% | 0 | 2360 | 26.22% | 0 |  | 2826.39 | 40.38% | 2826.39 | 40.38% | 2001.19 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 889585 - DEWITT AND COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-04-30 | 2020-02-04 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 1004402¦¦2020-03-31
FP | CJ | Yes | 1004403 |  | PIXELLE 2020 MONITORING | BELL, JAMES J. | 100% | 11500 | 0 | 11500 | 839.75 | 839.75 | 0 | 0 | 0 | 839.75 | 8200 | 0 | 8200 | 678.43 | 616.7 |  |  | 61.73 |  |  | 678.43 | 616.7 |  |  | 61.73 |  |  | 161.32 | 0 | 8.274% |  | 0 | 678.43 | 3300 | 28.7% | 0 | 3300 | 28.7% | 0 |  | 161.32 | 19.21% | 161.32 | 19.21% | 10660.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878886 - PIXELLE SPECIALTY SOLUTIONS | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2021-01-30 | 2020-02-03 | 2021-01-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1004403¦¦2020-03-31
TM | CJ | Yes | 1004404 |  | BILLY CLAUDE ADAMS | SCHERM, LOGAN M | 100% | 9000 | 0 | 9000 | 22873.11 | 22873.11 | 23559.89 | 0 | 0 | 22873.11 | 6040 | 0 | 6040 | 9693.46 | 4846.98 | 709.51 |  | 4136.97 |  |  | 15725.89 | 7371.5 | 718.51 |  | 7635.88 |  |  | 7147.22 | 0 | 260.4% |  | 0 | 15725.89 | 2960 | 32.89% | 0 | 2960 | 32.89% | 0 |  | 7147.22 | 31.25% | 7147.22 | 31.25% | -13873.11 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887122 - ADAMS, BILLY C | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-04-30 | 2020-02-04 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 1004404¦¦2020-03-31
UP | LJ | Yes | 1004405 |  | GRAND GULF COLLECTOR WELL 6 | HARTMAN, MICHAEL | 0.276% | 511800 | 0 | 511800 | 1412.5991 |  | 0 | 0 | 0 | 511800 | 361800 | 0 | 361800 | 998.59 |  |  |  | 998.59 |  |  | 998.59 |  |  |  | 998.59 |  |  | 0 | 998.59 | 0.276% |  | 360801.41 | 361800 | 150000 | 29.31% | 0 | 150000 | 29.31% | 0 |  | 414.01 | 29.31% | 150000 | 29.31% | 510387.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 890293 - ENTERGY OPERATIONS GRAND GULF | WATER | WATER REPAIR & INSTALLATION | 2020-01-27 | 2020-05-30 | 2020-01-27 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1004405¦¦2020-03-31
TM | C | Yes | 1004751 |  | VALLEY RURAL BOOSTER | MIGUEL, SEAN J. | 100% | 18657 | 0 | 18657 | 15103 | 15103 | 15103 | 0 | 0 | 15103 | 13900 | 0 | 13900 | 6913.67 | 3591.56 | 808.78 |  | 2018.33 | 495 |  | 11171.37 | 5486.27 | 1210.79 |  | 3484.31 | 990 |  | 3931.63 | 0 | 80.37% |  | 0 | 11171.37 | 4757 | 25.5% | 0 | 4757 | 25.5% | 0 |  | 3931.63 | 26.03% | 3931.63 | 26.03% | 3554 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 1003294 - VALLEY RURAL UTILITY COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2020-03-30 | 2020-02-03 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1004751¦¦2020-03-31
UP | CJ | Yes | 1004752 |  | AGP SGT BLUFF WELL 7 REHAB | GANSEBOM, JASON W. | 100% | 23336 | 0 | 23336 | 21136 | 21136 | 21136 | 0 | 0 | 21136 | 17475 | 0 | 17475 | 16835.08 | 5767.69 | 4899.58 |  | 4886.73 | 1281.08 |  | 19140.06 | 5767.69 | 4899.58 |  | 7191.71 | 1281.08 |  | 1995.94 | 0 | 109.5% |  | 0 | 19140.06 | 5861 | 25.12% | 0 | 5861 | 25.12% | 0 |  | 1995.94 | 9.443% | 1995.94 | 9.443% | 2200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878670 - AG PROCESSING INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-03-31 | 2020-02-04 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1004752¦¦2020-03-31
UP | CJ | Yes | 1004791 |  | JOLIET ROCK 3 PUMP AND MOTOR | EISHA, JOSEPH J. | 100% | 25000 | 0 | 25000 | 9242 | 9242 | 9242 | 0 | 0 | 9242 | 17500 | 0 | 17500 | 2220.22 | 922.53 |  |  | 1297.69 |  |  | 7205.57 | 4496.93 | 567.42 |  | 2141.22 |  |  | 2036.43 | 0 | 41.17% |  | 0 | 7205.57 | 7500 | 30% | 0 | 7500 | 30% | 0 |  | 2036.43 | 22.03% | 2036.43 | 22.03% | 15758 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878985 - JOLIET, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-05 | 2020-04-10 | 2020-02-05 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1004791¦¦2020-03-31
UP | CJ | Yes | 1004792 |  | MOSAIC FY19 MFC 09100907 | MCCULLERS, BLAKE E. | 100% | 20781 | 0 | 20781 | 8330 | 8330 | 8330 | 0 | 0 | 8330 | 15004 | 0 | 15004 | 5728.21 | 1804.97 | 1100.07 |  | 2823.17 |  |  | 5728.21 | 1804.97 | 1100.07 |  | 2823.17 |  |  | 2601.79 | 0 | 38.18% |  | 0 | 5728.21 | 5777 | 27.8% | 0 | 5777 | 27.8% | 0 |  | 2601.79 | 31.23% | 2601.79 | 31.23% | 12451 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895011 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-06 | 2020-03-22 | 2020-02-06 | 2020-03-02 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1004792¦¦2020-03-31
FP | C | Yes | 1004793 |  | P66 RW 15 TREATMENT | WHITE, CATHLEEN R | 100% | 42216 | 0 | 42216 | 42216.14 | 42216.14 | 42216.14 | 0 | 0 | 42216.14 | 29545 | 0 | 29545 | 154.52 |  |  |  | 154.52 |  |  | 31563.15 | 15072.67 | 2968.7 |  | 13521.78 |  |  | 10652.99 | 0 | 106.8% |  | 0 | 31563.15 | 12671 | 30.01% | 0 | 12671 | 30.01% | 0 |  | 10652.99 | 25.23% | 10652.99 | 25.23% | -0.14 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878946 - PHILLIPS 66 WOOD RIVER REFINERY | WATER | WATER SUPPLY | 2020-02-04 | 2020-03-31 | 2020-02-04 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1004793¦¦2020-03-31
UP | CJ | Yes | 1004794 |  | CORING INCORPORATED PWM | CROOK, CHARLES M | 100% | 13550 | 0 | 13550 | 371.92 | 371.92 | 0 | 0 | 0 | 371.92 | 11050 | 0 | 11050 | 112.26 | 91.27 |  |  | 20.99 |  |  | 300.47 | 276.84 |  |  | 23.63 |  |  | 71.45 | 0 | 2.719% |  | 0 | 300.47 | 2500 | 18.45% | 0 | 2500 | 18.45% | 0 |  | 71.45 | 19.21% | 71.45 | 19.21% | 13178.08 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 889001 - CSS CORNING INCORPORATED | WATER | WATER REPAIR & INSTALLATION | 2020-02-05 | 2020-04-13 | 2020-02-05 | 2020-04-13 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1004794¦¦2020-03-31
UP | CJ | Yes | 1004795 |  | PIMA UTILITIES WELL 31 PUMP | VAN ALLEN, WESLEY C. | 100% | 9560 | 46490 | 56050 | 54127.5 | 54127.5 | 56247.45 | 0 | 0 | 54127.5 | 7167 | 26600.89 | 33767.89 | 11571.13 | 2806.97 | 1266.75 |  | 7497.41 |  |  | 37627.59 | 6294.92 | 2613.4 |  | 28719.27 |  |  | 16499.91 | 0 | 111.4% |  | 0 | 37627.59 | 2393 | 25.03% | 19889.11 | 22282.11 | 39.75% | 19889.11 |  | 16499.91 | 30.48% | 16499.91 | 30.48% | 1922.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 896326 - PIMA UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-03-30 | 2020-02-04 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1004795¦¦2020-03-31
FP | CJ | Yes | 1004796 |  | TODD ALLEN WELL 1 | SEIDEN, ANDREW L. | 100% | 13123 | 16996.39 | 30119.39 | 30119.62 | 30119.62 | 30369.44 | 30369.44 | 0 | 30119.62 | 9720 | 18312.27 | 28032.27 | 18439.98 | 8481.29 | 3738.64 |  | 6220.05 |  |  | 18439.98 | 8481.29 | 3738.64 |  | 6220.05 |  |  | 11679.64 | 0 | 65.78% |  | 0 | 18439.98 | 3403 | 25.93% | -1315.88 | 2087.12 | 6.929% | -1315.88 |  | 11679.64 | 38.78% | 11679.64 | 38.78% | -0.23 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 898987 - TODD ALLEN FARMS | WATER | WATER REPAIR & INSTALLATION | 2020-01-31 | 2020-12-01 | 2020-01-31 | 2020-12-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1004796¦¦2020-03-31
FP | CJ | Yes | 1004797 |  | LA VERNE AMHERST WELL REHAB | SEIDEN, ANDREW L. | 100% | 78725 | 0 | 78725 | 66544.66 | 66544.66 | 0 | 0 | 0 | 66544.66 | 60341 | 0 | 60341 | 29531.08 | 9038.5 | 4126.31 |  | 4177.97 | 12188.3 |  | 53761.07 | 9403.07 | 4126.31 |  | 28043.39 | 12188.3 |  | 12783.59 | 0 | 89.1% |  | 0 | 53761.07 | 18384 | 23.35% | 0 | 18384 | 23.35% | 0 |  | 12783.59 | 19.21% | 12783.59 | 19.21% | 12180.34 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879037 - LA VERNE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-05 | 2020-12-01 | 2020-02-05 | 2020-12-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1004797¦¦2020-03-31
UP | CJ | Yes | 1004798 |  | GOODLAND KS MEDIA REPL | MCCARTNEY, JEFFREY C | 100% | 104730 | 0 | 104730 | 324.35 | 324.35 | 0 | 0 | 0 | 324.35 | 71334.8 | 0 | 71334.8 | 0 |  |  |  | 0 |  |  | 262.04 | 256.94 |  |  | 5.1 |  |  | 62.31 | 0 | 0.3673% |  | 0 | 262.04 | 33395.2 | 31.89% | 0 | 33395.2 | 31.89% | 0 |  | 62.31 | 19.21% | 62.31 | 19.21% | 104405.65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 891411 - GOODLAND, KS, CITY OF | WATER | WATER TREATMENT | 2020-02-04 | 2020-07-31 | 2020-01-14 | 2020-07-31 | PRIME CONTRACTOR | PUBLIC | COST REIMBURSIBLE | 1004798¦¦2020-03-31
UP | CJ | Yes | 1005185 |  | RCWD ACE BOWEN GEAR HEAD | GRACE, GARY L. |  | 34005 | 0 | 34005 |  |  | 0 | 0 | 0 |  | 26628 | 0 | 26628 | [20 empty] | 7377 | 21.69% | 0 | 7377 | 21.69% | 0 | [5 empty] | 34005 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878683 - RANCHO CALIFORNIA WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-01-10 | 2020-05-15 | 2020-01-10 | 2020-05-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1005185¦¦2020-03-31
TM | C | Yes | 1005186 |  | KERKSIECK BROTHERS PR | SCHERM, LOGAN M | 100% | 10000 | 0 | 10000 | 10163.87 | 10163.87 | 10926.18 | 0 | 0 | 10163.87 | 6800 | 0 | 6800 | 1303.64 | 559.81 | 267.48 |  | 476.35 |  |  | 8288.93 | 3922.66 | 303.48 |  | 4062.79 |  |  | 1874.94 | 0 | 121.9% |  | 0 | 8288.93 | 3200 | 32% | 0 | 3200 | 32% | 0 |  | 1874.94 | 18.45% | 1874.94 | 18.45% | -163.87 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 893102 - KERKSIECK BROTHERS | WATER | WATER REPAIR & INSTALLATION | 2020-02-06 | 2020-04-30 | 2020-02-06 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | CONSTRUCTION MANAGEMENT | 1005186¦¦2020-03-31
UP | C | Yes | 1005187 |  | EXXON MOBILE BRPO 2020 FLOW | LOPEZ-VASQUEZ, JUAN C. | 100% | 5400 | 0 | 5400 | 5400 | 5400 | 5400 | 0 | 0 | 5400 | 3468 | 0 | 3468 | 2353.72 | 1208.28 | 565.78 |  | 579.66 |  |  | 3115.81 | 1594.98 | 751.28 |  | 769.55 |  |  | 2284.19 | 0 | 89.84% |  | 0 | 3115.81 | 1932 | 35.78% | 0 | 1932 | 35.78% | 0 |  | 2284.19 | 42.3% | 2284.19 | 42.3% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 890523 - EXXONMOBIL REFINING & MARKETING | WATER | WATER REPAIR & INSTALLATION | 2020-02-06 | 2020-04-30 | 2020-02-06 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1005187¦¦2020-03-31
UP | CJ | Yes | 1005200 |  | FAIRVIEW WELL PUMP | GRACE, GARY L. | 100% | 36759 | 0 | 36759 | 36759 | 36759 | 0 | 0 | 0 | 36759 | 25585 | 0 | 25585 | 17351.56 | 8312.77 | 3328.48 |  | 5710.31 |  |  | 44153.66 | 22123.53 | 10227.94 |  | 11802.19 |  |  | 0 | 7394.66 | 172.6% |  | 0 | 44153.66 | 11174 | 30.4% | 0 | 11174 | 30.4% | 0 |  | -7394.66 | -20.12% | -7394.66 | -20.12% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887781 - CALLEGUAS MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-04-20 | 2020-02-04 | 2020-04-20 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1005200¦¦2020-03-31
UP | CJ | Yes | 1005201 |  | SOMERS NY REHABS | CROOK, CHARLES M | 100% | 61725 | 16810 | 78535 | 87310 | 87310 | 87310 | 87310 | 0 | 87310 | 53725 | 10550 | 64275 | 46728.87 | 20894.18 | 9510.25 |  | 16324.44 |  |  | 62243.15 | 27849.5 | 11812.94 |  | 22580.71 |  |  | 25066.85 | 0 | 96.84% |  | 0 | 62243.15 | 8000 | 12.96% | 6260 | 14260 | 18.16% | 6260 |  | 25066.85 | 28.71% | 25066.85 | 28.71% | -8775 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 1003047 - SEBASTIAN CAPITAL INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-05 | 2020-02-28 | 2020-02-05 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1005201¦¦2020-03-31
UP | C | Yes | 1006128 |  | LAFARGE SOIL BORINGS | COMBS, TAYLOR E. | 100% | 79788 | 0 | 79788 | 78454.76 | 78454.76 | 78454.76 | 78454.76 | 0 | 78454.76 | 59229 | 0 | 59229 | 2042.4 |  |  |  | 2042.4 |  |  | 37837.57 | 15966.65 | 11393.11 |  | 10477.81 |  |  | 40617.19 | 0 | 63.88% |  | 0 | 37837.57 | 20559 | 25.77% | 0 | 20559 | 25.77% | 0 |  | 40617.19 | 51.77% | 40617.19 | 51.77% | 1333.24 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 893333 - LAFARGE BUILDING MATERIALS | WATER | WATER REPAIR & INSTALLATION | 2020-01-29 | 2020-02-21 | 2020-01-29 | 2020-02-21 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1006128¦¦2020-03-31
UP | CJ | Yes | 1006129 |  | EACMD WELL 5 | SCHANAMAN, MIKE L. | 100% | 20999 | 0 | 20999 | 12520 | 12520 | 12520 | 0 | 0 | 12520 | 13565 | 0 | 13565 | 7408.83 | 3287.7 | 1652.37 |  | 2468.76 |  |  | 7408.83 | 3287.7 | 1652.37 |  | 2468.76 |  |  | 5111.17 | 0 | 54.62% |  | 0 | 7408.83 | 7434 | 35.4% | 0 | 7434 | 35.4% | 0 |  | 5111.17 | 40.82% | 5111.17 | 40.82% | 8479 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878958 - EASTERN ADAMS COUNTY METROPOLITAN DISTR | WATER | WATER REPAIR & INSTALLATION | 2020-02-07 | 2020-04-30 | 2020-02-07 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1006129¦¦2020-03-31
UP | CJ | Yes | 1006202 |  | JG BOSWELL PULL AND INSPECT | GRACE, GARY L. | 100% | 15930 | 31079.5 | 47009.5 | 43412 | 43412 | 43480.64 | 0 | 0 | 43412 | 14203 | 22862.87 | 37065.87 | 16532.72 | 7242.8 | 3012.22 |  | 6277.7 |  |  | 29064 | 12928.58 | 5780.38 |  | 10355.04 |  |  | 14348 | 0 | 78.41% |  | 0 | 29064 | 1727 | 10.84% | 8216.63 | 9943.63 | 21.15% | 8216.63 | 8216.63 | 14348 | 33.05% | 14348 | 33.05% | 3597.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878568 - J G BOSWELL | WATER | WATER REPAIR & INSTALLATION | 2020-02-06 | 2020-04-01 | 2020-02-06 | 2020-04-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1006202¦¦2020-03-31
UP | C | Yes | 1006203 |  | STERLING HILL CC YARD WELL | MAI, JONATHAN | 100% | 21626 | 0 | 21626 | 20017.71 | 20017.71 | 0 | 0 | 0 | 20017.71 | 15316 | 0 | 15316 | 299.57 |  |  |  | 299.57 |  |  | 16172.2 | 5413.12 | 2418.58 |  | 8340.5 |  |  | 3845.51 | 0 | 105.6% |  | 0 | 16172.2 | 6310 | 29.18% | 0 | 6310 | 29.18% | 0 |  | 3845.51 | 19.21% | 3845.51 | 19.21% | 1608.29 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878945 - STERLING HILLS GOLF CLUB | WATER | WATER REPAIR & INSTALLATION | 2020-02-06 | 2020-04-17 | 2020-02-06 | 2020-04-17 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1006203¦¦2020-03-31
UP | CJ | Yes | 1006242 |  | OXFORD MS WELL 3 | ANDERSON, STEPHEN P. | 100% | 9885 | 0 | 9885 | 9885 | 9885 | 9885 | 0 | 0 | 9885 | 7608 | 0 | 7608 | 13570.54 | 6450.84 | 1656.98 |  | 5462.72 |  |  | 13570.54 | 6450.84 | 1656.98 |  | 5462.72 |  |  | 0 | 3685.54 | 178.4% |  | 0 | 13570.54 | 2277 | 23.03% | 0 | 2277 | 23.03% | 0 |  | -3685.54 | -37.28% | -3685.54 | -37.28% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895929 - OXFORD, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-03-03 | 2020-02-10 | 2020-03-03 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1006242¦¦2020-03-31
UP | CJ | Yes | 1006245 |  | OXFORD NY WELL 1 QUICK REHAB | CROOK, CHARLES M | 100% | 14875 | 0 | 14875 | 8079.73 | 8079.73 | 0 | 0 | 0 | 8079.73 | 11875 | 0 | 11875 | 6402.12 | 3896.49 | 1382.18 |  | 1123.45 |  |  | 6527.57 | 4020.18 | 1382.18 |  | 1125.21 |  |  | 1552.16 | 0 | 54.97% |  | 0 | 6527.57 | 3000 | 20.17% | 0 | 3000 | 20.17% | 0 |  | 1552.16 | 19.21% | 1552.16 | 19.21% | 6795.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 895931 - OXFORD, NY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-03-20 | 2020-02-10 | 2020-03-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1006245¦¦2020-03-31
UP | CJ | Yes | 1006246 |  | WC LAKE CHARLES WELL 36 MOTOR | GNAU, CASEY T | 100% | 24700 | 0 | 24700 | 4384.51 | 4384.51 | 0 | 0 | 0 | 4384.51 | 14766 | 0 | 14766 | 816.15 | 530.51 |  |  | 285.64 |  |  | 3542.22 | 1973.81 | 563.89 |  | 1004.52 |  |  | 842.29 | 0 | 23.99% |  | 0 | 3542.22 | 9934 | 40.22% | 0 | 9934 | 40.22% | 0 |  | 842.29 | 19.21% | 842.29 | 19.21% | 20315.49 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878710 - AXIALL CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-03-01 | 2020-02-10 | 2020-03-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1006246¦¦2020-03-31
UP | C | Yes | 1006688 |  | PITKIN TEST | GNAU, CASEY T | 100% | 1000 | 0 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 1000 | 500 | 0 | 500 | 0 |  |  |  | 0 |  |  | 792.42 | 403.7 | 185.5 |  | 203.22 |  |  | 207.58 | 0 | 158.5% |  | 0 | 792.42 | 500 | 50% | 0 | 500 | 50% | 0 |  | 207.58 | 20.76% | 207.58 | 20.76% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 1006189 - PITKIN WATER SYSTEM | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-03-01 | 2020-02-10 | 2020-03-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1006688¦¦2020-03-31
UP | CJ | Yes | 1006689 |  | ARB CACTUS CREEK | GRACE, GARY L. | 100% | 29775 | 0 | 29775 | 6125 | 6125 | 6125 | 6125 | 0 | 6125 | 20371 | 0 | 20371 | 2.37 |  |  |  | 2.37 | 0 |  | 3932.04 | 1164.63 | 515.28 |  | 782.13 | 1470 |  | 2192.96 | 0 | 19.3% |  | 0 | 3932.04 | 9404 | 31.58% | 0 | 9404 | 31.58% | 0 |  | 2192.96 | 35.8% | 2192.96 | 35.8% | 23650 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 120454 - ARB INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-06 | 2020-04-20 | 2020-02-06 | 2020-04-20 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 1006689¦¦2020-03-31
UP | CJ | Yes | 1006690 |  | DELAWARE 2020 MONITORING | BELL, JAMES J. | 100% | 10552 | 0 | 10552 | 215.6 | 215.6 | 0 | 0 | 0 | 215.6 | 6997 | 0 | 6997 | 174.18 | 170.66 |  |  | 3.52 |  |  | 174.18 | 170.66 |  |  | 3.52 |  |  | 41.42 | 0 | 2.489% |  | 0 | 174.18 | 3555 | 33.69% | 0 | 3555 | 33.69% | 0 |  | 41.42 | 19.21% | 41.42 | 19.21% | 10336.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 879115 - DELAWARE, CITY OF | WATER | WATER SUPPLY | 2020-02-03 | 2020-02-10 | 2020-02-03 | 2020-02-10 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1006690¦¦2020-03-31
FP | CJ | Yes | 1006698 |  | DESERT OASIS ATS | CHESLEY, ANDREW J | 100% | 359750 | 1001 | 360751 | 107925 | 107925 | 107925 | 0 | 0 | 107925 | 243995.87 | 660.4 | 244656.27 | 37655.51 | 967.89 |  |  | 36687.62 |  |  | 72256.49 | 1464.67 |  |  | 70791.82 |  |  | 35668.51 | 0 | 29.53% |  | 0 | 72256.49 | 115754.13 | 32.18% | 340.6 | 116094.73 | 32.18% | 340.6 | 340.6 | 35668.51 | 33.05% | 35668.51 | 33.05% | 252826 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 878759 - FELIX CONSTRUCTION COMPANY | WATER | WATER TREATMENT | 2020-02-10 | 2020-05-31 | 2020-02-10 | 2020-05-31 | SUBCONTRACTOR | PUBLIC | COST REIMBURSIBLE | 1006698¦¦2020-03-31
UP | CJ | Yes | 1006699 |  | SOUTH ELGIN IL WELL 4 | SNELTEN, BRIAN M | 100% | 24030 | 40298 | 64328 | 46403.71 | 46403.71 | 15303 | 0 | 0 | 46403.71 | 15957 | 22542 | 38499 | 27529.92 | 17904.54 | 2369.2 |  | 7256.18 |  |  | 37489.3 | 24909.89 | 3522.86 |  | 9056.55 |  |  | 8914.41 | 0 | 97.38% |  | 0 | 37489.3 | 8073 | 33.6% | 17756 | 25829 | 40.15% | 17756 | 17756 | 8914.41 | 19.21% | 8914.41 | 19.21% | 17924.29 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 898030 - SOUTH ELGIN, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-05-22 | 2020-02-10 | 2020-05-22 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1006699¦¦2020-03-31
FP | C | Yes | 1006700 |  | MEMC WELL 1 AND 2 | WHITE, CATHLEEN R | 100% | 2470 | 35234 | 37704 | 37704 | 37704 | 37704 | 0 | 0 | 37704 | 1750 | 26945.13 | 28695.13 | 776.05 | 494.04 |  |  | 282.01 |  |  | 27931.22 | 10362.23 | 1786.05 |  | 15782.94 |  |  | 9772.78 | 0 | 97.34% |  | 0 | 27931.22 | 720 | 29.15% | 8288.87 | 9008.87 | 23.89% | 8288.87 |  | 9772.78 | 25.92% | 9772.78 | 25.92% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 894508 - MEMC ELECTRONIC MATERIALS | WATER | WATER REPAIR & INSTALLATION | 2020-02-03 | 2020-03-31 | 2020-02-03 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1006700¦¦2020-03-31
TM | CJ | Yes | 1006701 |  | SIMPSON III FARMS LLC PR | SCHERM, LOGAN M | 100% | 25000 | 0 | 25000 | 22479.39 | 22479.39 | 0 | 0 | 0 | 22479.39 | 20000 | 0 | 20000 | 17796.15 | 4400.96 | 862.92 |  | 12532.27 |  |  | 18160.98 | 4608.41 | 862.92 |  | 12689.65 |  |  | 4318.41 | 0 | 90.8% |  | 0 | 18160.98 | 5000 | 20% | 0 | 5000 | 20% | 0 |  | 4318.41 | 19.21% | 4318.41 | 19.21% | 2520.61 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 897868 - SIMPSON III FARMS, LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-04-30 | 2020-02-10 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 1006701¦¦2020-03-31
UP | CJ | Yes | 1006702 |  | CLAWA STATION 1 G1 BOOSTER | BRASHEAR, DAVID M | 100% | 6887 | 45975.86 | 52862.86 | 41990.23 | 41990.23 | 6886.59 | 0 | 0 | 41990.23 | 4820 | 36783.41 | 41603.41 | 28690.15 | 5268.08 | 93.28 |  | 6587.06 | 16741.73 |  | 33923.68 | 8350.18 | 556.48 |  | 8275.29 | 16741.73 |  | 8066.55 | 0 | 81.54% |  | 0 | 33923.68 | 2067 | 30.01% | 9192.45 | 11259.45 | 21.3% | 9192.45 | 9192.45 | 8066.55 | 19.21% | 8066.55 | 19.21% | 10872.63 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878584 - CRESTLINE LAKE ARROWHEAD WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-06-01 | 2020-02-10 | 2020-06-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1006702¦¦2020-03-31
UP | CJ | Yes | 1006703 |  | INFRAMARK BOOSTER 120 | GRACE, GARY L. | 100% | 19090 | 32197 | 51287 | 4315 | 4315 | 4315 | 0 | 0 | 4315 | 14150 | 25660.49 | 39810.49 | 2.09 | -0.02 |  |  | 2.11 |  |  | 2681.97 | 1009.21 | 890.89 |  | 781.87 |  |  | 1633.03 | 0 | 6.737% |  | 0 | 2681.97 | 4940 | 25.88% | 6536.51 | 11476.51 | 22.38% | 6536.51 | 6536.51 | 1633.03 | 37.85% | 1633.03 | 37.85% | 46972 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879063 - INFRAMARK | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-04-30 | 2020-02-10 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1006703¦¦2020-03-31
FP | CJ | Yes | 1006898 |  | JCWA LATERAL INSPECTION | SMITH, ANDREW J. | 100% | 19875 | 0 | 19875 | 19120.11 | 19120.11 | 0 | 0 | 0 | 19120.11 | 15000 | 0 | 15000 | 11131.99 | 1431.44 |  |  | 4468.55 | 5232 |  | 15447.03 | 2111.24 | 2575.13 |  | 5528.66 | 5232 |  | 3673.08 | 0 | 103% |  | 0 | 15447.03 | 4875 | 24.53% | 0 | 4875 | 24.53% | 0 |  | 3673.08 | 19.21% | 3673.08 | 19.21% | 754.89 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 892775 - JEFFERSON COUNTY WATER AUTHORITY | WATER | WATER REPAIR & INSTALLATION | 2020-02-11 | 2020-05-01 | 2020-02-11 | 2020-05-01 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1006898¦¦2020-03-31
FP | CJ | Yes | 1006902 |  | KIOWA LAKE HOUSE PUMP 4 | MIGUEL, SEAN J. | 100% | 46900 | 29155 | 76055 | 35635.68 | 35635.68 | 22000 | 0 | 0 | 35635.68 | 37055 | 21228 | 58283 | 28164.15 | 12839.62 | 2675.16 |  | 12649.37 |  |  | 28789.87 | 13240.47 | 2746.26 |  | 12803.14 |  |  | 6845.81 | 0 | 49.4% |  | 0 | 28789.87 | 9845 | 20.99% | 7927 | 17772 | 23.37% | 7927 | 7927 | 6845.81 | 19.21% | 6845.81 | 19.21% | 40419.32 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878860 - KIOWA POWER PARTNERS LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-03-30 | 2020-02-10 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1006902¦¦2020-03-31
FP | CJ | Yes | 1006903 |  | RAIN CARBON TEST WELL 3 | GNAU, CASEY T |  | 1500 | 0 | 1500 |  |  | 0 | 0 | 0 |  | 800 | 0 | 800 | [20 empty] | 700 | 46.67% | 0 | 700 | 46.67% | 0 | [5 empty] | 1500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879116 - RAIN CII CARBON LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-11 | 2020-03-01 | 2020-02-11 | 2020-03-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1006903¦¦2020-03-31
FP | CJ | Yes | 1006905 |  | TYSON DAKOTA CITY WELL 8 REHAB | GANSEBOM, JASON W. | 100% | 54396 | 0 | 54396 | 53956 | 53956 | 53956 | 0 | 0 | 53956 | 33468 | 0 | 33468 | 42451.76 | 9708.78 | 5069.76 |  | 23562.17 | 4111.05 |  | 42451.76 | 9708.78 | 5069.76 |  | 23562.17 | 4111.05 |  | 11504.24 | 0 | 126.8% |  | 0 | 42451.76 | 20928 | 38.47% | 0 | 20928 | 38.47% | 0 |  | 11504.24 | 21.32% | 11504.24 | 21.32% | 440 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878938 - TYSON FRESH MEATS INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-11 | 2020-05-31 | 2020-02-11 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1006905¦¦2020-03-31
FP | CJ | Yes | 1006908 |  | GRACE 3037A STUFFING BOX | GNAU, CASEY T | 100% | 7000 | 0 | 7000 | 6935 | 6935 | 6935 | 6935 | 0 | 6935 | 3500 | 0 | 3500 | 946.03 | 642.23 |  |  | 303.8 |  |  | 4347.41 | 2636.35 | 484.26 |  | 1226.8 |  |  | 2587.59 | 0 | 124.2% |  | 0 | 4347.41 | 3500 | 50% | 0 | 3500 | 50% | 0 |  | 2587.59 | 37.31% | 2587.59 | 37.31% | 65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879019 - W R GRACE & CO CONN | WATER | WATER REPAIR & INSTALLATION | 2020-02-11 | 2020-03-30 | 2020-02-11 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1006908¦¦2020-03-31
FP | CJ | Yes | 1007268 |  | CITGO J2 | GNAU, CASEY T | 100% | 25000 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 25000 | 12500 | 0 | 12500 | 18085 | 9592.07 | 2220.25 |  | 6272.68 |  |  | 32402.15 | 12244.66 | 2660.66 |  | 17496.83 |  |  | 0 | 7402.15 | 259.2% |  | 0 | 32402.15 | 12500 | 50% | 0 | 12500 | 50% | 0 |  | -7402.15 | -29.61% | -7402.15 | -29.61% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878864 - CITGO PETROLEUM CORP | WATER | WATER REPAIR & INSTALLATION | 2020-02-11 | 2020-02-28 | 2020-02-11 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1007268¦¦2020-03-31
FP | CJ | Yes | 1007271 |  | TRACT WELL 3 SERVICE CALL | SEIDEN, ANDREW L. |  | 680 | 0 | 680 |  |  | 0 | 0 | 0 |  | 505 | 0 | 505 | [20 empty] | 175 | 25.74% | 0 | 175 | 25.74% | 0 | [5 empty] | 680 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 899072 - TRACT 349 MUTUAL WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-02-11 | 2020-12-31 | 2020-02-11 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1007271¦¦2020-03-31
UP | CJ | Yes | 1007272 |  | BERMUDA WATER WELL 2 | BRASHEAR, DAVID M | 100% | 60027 | 0 | 60027 | 11512.06 | 11512.06 | 0 | 0 | 0 | 11512.06 | 42573 | 0 | 42573 | 8956.8 | 4068.32 | 1586.88 |  | 3301.6 |  |  | 9300.53 | 4068.32 | 1586.88 |  | 3645.33 |  |  | 2211.53 | 0 | 21.85% |  | 0 | 9300.53 | 17454 | 29.08% | 0 | 17454 | 29.08% | 0 |  | 2211.53 | 19.21% | 2211.53 | 19.21% | 48514.94 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1006909 - BERMUDA WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-04-30 | 2020-02-04 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1007272¦¦2020-03-31
UP | CJ | Yes | 1007273 |  | ABILITY FIRST CAMP PAIVIKA | BRASHEAR, DAVID M | 100% | 3642 | 0 | 3642 | 3641.58 | 3641.58 | 3819.38 | 0 | 0 | 3641.58 | 2605 | 0 | 2605 | 2261.32 | 304.92 |  |  | 1956.4 |  |  | 2302.13 | 304.92 |  |  | 1997.21 |  |  | 1339.45 | 0 | 88.37% |  | 0 | 2302.13 | 1037 | 28.47% | 0 | 1037 | 28.47% | 0 |  | 1339.45 | 36.78% | 1339.45 | 36.78% | 0.42 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1006854 - ABILITY FIRST | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-03-15 | 2020-02-10 | 2020-03-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1007273¦¦2020-03-31
UP | LJ | Yes | 1007512 |  | JG BOSWELL S240 | TRAMMELL, DUANE R. | 16.22% | 795005.5 | 0 | 795005.5 | 128976.4556 | 155433 | 155433 | 0 | 0 | 795005.5 | 625924.26 | 0 | 625924.26 | 99976.11 | 39915.05 | 24651.2 |  | 34879.86 | 530 |  | 102329.16 | 41090.87 | 24651.2 |  | 36057.09 | 530 |  | 53103.84 | 0 | 16.35% |  | 528423.52 | 630752.68 | 169081.24 | 21.27% | 0 | 169081.24 | 21.27% | 0 |  | 26647.3 | 20.66% | 164252.82 | 20.66% | 666029.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892822 - JG BOSWELL COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-02-01 | 2020-05-15 | 2020-01-21 | 2020-05-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1007512¦¦2020-03-31
TM | C | Yes | 1007610 |  | OZ TYLER WELL 2 | MIGUEL, SEAN J. | 100% | 1665 | 18026 | 19691 | 19691 | 19691 | 19691 | 0 | 0 | 19691 | 1295 | 13832 | 15127 | 9295.97 | 3182.17 | 712.2 |  | 5401.6 |  |  | 14178.51 | 5821.21 | 1805.38 |  | 6551.92 |  |  | 5512.49 | 0 | 93.73% |  | 0 | 14178.51 | 370 | 22.22% | 4194 | 4564 | 23.18% | 4194 |  | 5512.49 | 27.99% | 5512.49 | 27.99% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895947 - OZ TYLER DISTILLERY | WATER | WATER REPAIR & INSTALLATION | 2020-02-12 | 2020-03-30 | 2020-02-12 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1007610¦¦2020-03-31
UP | CJ | Yes | 1007619 |  | CVWD WELL 16 | GRACE, GARY L. | 100% | 13648 | 0 | 13648 | 13648 | 13648 | 13195.55 | 0 | 0 | 13648 | 9494 | 0 | 9494 | 10000.43 | 4981.33 | 2084.41 |  | 2934.69 |  |  | 14731.58 | 7484.66 | 2876.19 |  | 4370.73 |  |  | 0 | 1083.58 | 155.2% |  | 0 | 14731.58 | 4154 | 30.44% | 0 | 4154 | 30.44% | 0 |  | -1083.58 | -7.939% | -1083.58 | -7.939% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878809 - CUCAMONGA VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-02-11 | 2020-03-18 | 2020-02-11 | 2020-03-18 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1007619¦¦2020-03-31
FP | C | Yes | 1007620 |  | DES PLAINES MHP WELL 3 | SNELTEN, BRIAN M | 100% | 3384 | 0 | 3384 | 3259 | 3259 | 3265.19 | 0 | 0 | 3259 | 2168 | 0 | 2168 | 2705.36 | 1717.6 | 521.93 |  | 465.83 |  |  | 2851.07 | 1717.6 | 521.93 |  | 611.54 |  |  | 407.93 | 0 | 131.5% |  | 0 | 2851.07 | 1216 | 35.93% | 0 | 1216 | 35.93% | 0 |  | 407.93 | 12.52% | 407.93 | 12.52% | 125 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 889570 - DES PLAINES MOBILE HOME PARK | WATER | WATER REPAIR & INSTALLATION | 2020-02-12 | 2020-02-12 | 2020-02-12 | 2020-02-12 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 1007620¦¦2020-03-31
UP | C | Yes | 1007621 |  | ENTERGY ARKANSAS SUB PUMP | SCHERM, LOGAN M | 100% | 10400 | 0 | 10400 | 16714.98 | 16714.98 | 16714.98 | 6032.7 | 0 | 16714.98 | 7280 | 0 | 7280 | 2.85 |  |  |  | 2.85 |  |  | 4715.85 | 133.09 |  |  | 4582.76 |  |  | 11999.13 | 0 | 64.78% |  | 0 | 4715.85 | 3120 | 30% | 0 | 3120 | 30% | 0 |  | 11999.13 | 71.79% | 11999.13 | 71.79% | -6314.98 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 890289 - ENTERGY INDEPENDENCE PLANT | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-05-20 | 2020-02-07 | 2020-05-20 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1007621¦¦2020-03-31
FP | CJ | Yes | 1007622 |  | VALMONT 509 FIRE WELL PUMP | GANSEBOM, JASON W. | 100% | 10097 | 0 | 10097 | 25293 | 25293 | 26411.25 | 0 | 0 | 25293 | 7067 | 0 | 7067 | 14530.95 | 2698.59 | 1367.83 |  | 10464.53 |  |  | 14530.95 | 2698.59 | 1367.83 |  | 10464.53 |  |  | 10762.05 | 0 | 205.6% |  | 0 | 14530.95 | 3030 | 30.01% | 0 | 3030 | 30.01% | 0 |  | 10762.05 | 42.55% | 10762.05 | 42.55% | -15196 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 899554 - VALMONT INDUSTRIES | WATER | WATER REPAIR & INSTALLATION | 2020-02-12 | 2020-04-30 | 2020-02-12 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1007622¦¦2020-03-31
TM | CJ | Yes | 1007763 |  | VAN WERT PUMP 2 | BARNES, MATTHEW D | 100% | 3800 | 23474 | 27274 | 9301.75 | 9301.75 | 0 | 0 | 0 | 9301.75 | 2660 | 18325 | 20985 | 5559.35 | 2281.48 | 773.36 |  | 995.51 | 1509 |  | 7514.83 | 3195.71 | 1278.4 |  | 1531.72 | 1509 |  | 1786.92 | 0 | 35.81% |  | 0 | 7514.83 | 1140 | 30% | 5149 | 6289 | 23.06% | 5149 | 5149 | 1786.92 | 19.21% | 1786.92 | 19.21% | 17972.25 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 899576 - VAN WERT, OH, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-13 | 2020-03-30 | 2020-02-13 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1007763¦¦2020-03-31
UP | CJ | Yes | 1007764 |  | TYSON SEDALIA MO WELLS 1 AND 2 | WARTICK, LOGAN M | 100% | 108341 | 0 | 108341 | 88076.35 | 88076.35 | 61585 | 61585 | 0 | 88076.35 | 75838 | 0 | 75838 | 14538.34 | 7529.97 | 3309.41 |  | 3698.96 |  |  | 71156.4 | 7636.85 | 3309.41 |  | 60210.14 |  |  | 16919.95 | 0 | 93.83% |  | 0 | 71156.4 | 32503 | 30% | 0 | 32503 | 30% | 0 |  | 16919.95 | 19.21% | 16919.95 | 19.21% | 20264.65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 879071 - TYSON FOODS SEDALIA FEEDMILL | WATER | WATER REPAIR & INSTALLATION | 2020-02-14 | 2020-07-15 | 2020-02-14 | 2020-07-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1007764¦¦2020-03-31
UP | CJ | Yes | 1007956 |  | SOUTHERN IONICS WELL 1 | GNAU, CASEY T | 100% | 20500 | 22470 | 42970 | 42970 | 42970 | 42970 | 0 | 0 | 42970 | 10819 | 12006 | 22825 | 3769.81 | 2726.8 | 1168.15 |  | -125.14 |  |  | 24420.02 | 11192.11 | 4480.5 |  | 8747.41 |  |  | 18549.98 | 0 | 107% |  | 0 | 24420.02 | 9681 | 47.22% | 10464 | 20145 | 46.88% | 10464 | 10464 | 18549.98 | 43.17% | 18549.98 | 43.17% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 898039 - SOUTHERN IONICS INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-13 | 2020-02-28 | 2020-02-13 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1007956¦¦2020-03-31
FP | CJ | Yes | 1007957 |  | CITY OF PORT ST LUCIE | BRUGGER, CRAIG J. | 100% | 9565 | 0 | 9565 | 9565 | 9565 | 9565 | 0 | 0 | 9565 | 5790 | 0 | 5790 | 74.53 | 51.34 |  |  | 23.19 |  |  | 2628.11 | 678.01 | 1718.66 |  | 231.44 |  |  | 6936.89 | 0 | 45.39% |  | 0 | 2628.11 | 3775 | 39.47% | 0 | 3775 | 39.47% | 0 |  | 6936.89 | 72.52% | 6936.89 | 72.52% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 1007734 - PORT ST LUCIE FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-01-30 | 2020-02-29 | 2020-01-30 | 2020-02-29 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1007957¦¦2020-03-31
FP | CJ | Yes | 1007966 |  | WINNER SD PUMP PULLS AND INSP | GANSEBOM, JASON W. | 100% | 7876 | 0 | 7876 | 7876 | 7876 | 7876 | 0 | 0 | 7876 | 6931 | 0 | 6931 | 12696.26 | 3972.82 | 1454.84 |  | 6019.65 | 1248.95 |  | 12696.26 | 3972.82 | 1454.84 |  | 6019.65 | 1248.95 |  | 0 | 4820.26 | 183.2% |  | 0 | 12696.26 | 945 | 12% | 0 | 945 | 12% | 0 |  | -4820.26 | -61.2% | -4820.26 | -61.2% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 900408 - WINNER, SD, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-12 | 2020-04-30 | 2020-02-12 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1007966¦¦2020-03-31
UP | CJ | Yes | 1008126 |  | LIBERTY NY PUMP REPLACEMENT | CROOK, CHARLES M | 100% | 14755 | 0 | 14755 | 14755 | 14755 | 14755 | 0 | 0 | 14755 | 11445 | 0 | 11445 | 10214.68 | 5498.84 | 806.28 |  | 3909.56 |  |  | 10464.78 | 5726.3 | 806.28 |  | 3932.2 |  |  | 4290.22 | 0 | 91.44% |  | 0 | 10464.78 | 3310 | 22.43% | 0 | 3310 | 22.43% | 0 |  | 4290.22 | 29.08% | 4290.22 | 29.08% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 893728 - LIBERTY, NY, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-13 | 2020-03-20 | 2020-02-13 | 2020-03-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1008126¦¦2020-03-31
TM | CJ | Yes | 1008418 |  | IRONTON RWP 3 | BARNES, MATTHEW D | 100% | 4350 | 0 | 4350 | 4350 | 4350 | 0 | 0 | 0 | 4350 | 3000 | 0 | 3000 | 5970.26 | 3906.66 | 742.76 |  | 1320.84 |  |  | 5970.26 | 3906.66 | 742.76 |  | 1320.84 |  |  | 0 | 1620.26 | 199% |  | 0 | 5970.26 | 1350 | 31.03% | 0 | 1350 | 31.03% | 0 |  | -1620.26 | -37.25% | -1620.26 | -37.25% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 1008084 - IRONTON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-13 | 2020-03-30 | 2020-02-13 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1008418¦¦2020-03-31
FP | CJ | Yes | 1008419 |  | MEMPHIS BIOFUELS | ANDERSON, STEPHEN P. | 100% | 1220 | 0 | 1220 | 1220 | 1220 | 1220 | 1220 | 0 | 1220 | 721 | 0 | 721 | 0.6 |  |  |  | 0.6 |  |  | 0.6 |  |  |  | 0.6 |  |  | 1219.4 | 0 | 0.08322% |  | 0 | 0.6 | 499 | 40.9% | 0 | 499 | 40.9% | 0 |  | 1219.4 | 99.95% | 1219.4 | 99.95% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 1008062 - BIO ENERGY DEVELOPMENT GROUP LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-13 | 2020-02-28 | 2020-02-13 | 2020-02-28 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1008419¦¦2020-03-31
UP | CJ | Yes | 1008420 |  | WESTERN HEIGHTS WELL 6 | SEIDEN, ANDREW L. | 100% | 41935 | 0 | 41935 | 50945 | 50945 | 50945 | 50945 | 0 | 50945 | 33521 | 0 | 33521 | 33180.72 | 13801.16 | 9647.15 |  | 9732.41 |  |  | 33180.72 | 13801.16 | 9647.15 |  | 9732.41 |  |  | 17764.28 | 0 | 98.98% |  | 0 | 33180.72 | 8414 | 20.06% | 0 | 8414 | 20.06% | 0 |  | 17764.28 | 34.87% | 17764.28 | 34.87% | -9010 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878663 - WESTERN HEIGHTS WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-02-14 | 2020-12-31 | 2020-02-14 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1008420¦¦2020-03-31
UP | C | Yes | 1008659 |  | CONNELLY WELL | SEIDEN, ANDREW L. | 100% | 600 | 0 | 600 | 600 | 600 | 600 | 0 | 0 | 600 | 418 | 0 | 418 | 0.29 |  |  |  | 0.29 |  |  | 0.29 |  |  |  | 0.29 |  |  | 599.71 | 0 | 0.06938% |  | 0 | 0.29 | 182 | 30.33% | 0 | 182 | 30.33% | 0 |  | 599.71 | 99.95% | 599.71 | 99.95% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1008272 - CIRCLE VISION LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-12 | 2020-02-29 | 2020-02-12 | 2020-02-29 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1008659¦¦2020-03-31
UP | CJ | Yes | 1008796 |  | RAIN CARBON SPARE PUMP | GNAU, CASEY T | 100% | 13224 | 0 | 13224 | 7967.35 | 7967.35 | 0 | 0 | 0 | 7967.35 | 6600 | 0 | 6600 | 6436.78 |  |  |  | 6436.78 |  |  | 6436.78 |  |  |  | 6436.78 |  |  | 1530.57 | 0 | 97.53% |  | 0 | 6436.78 | 6624 | 50.09% | 0 | 6624 | 50.09% | 0 |  | 1530.57 | 19.21% | 1530.57 | 19.21% | 5256.65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879116 - RAIN CII CARBON LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-18 | 2020-03-31 | 2020-02-18 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1008796¦¦2020-03-31
TM | C | Yes | 1008802 |  | MIDWEST OILSEEDS INC | SCHERM, LOGAN M | 100% | 45000 | 0 | 45000 | 43265.07 | 43265.07 | 46618.09 | 0 | 0 | 43265.07 | 30000 | 0 | 30000 | 28337.57 | 10165.65 | 3210.76 |  | 14961.16 |  |  | 28337.57 | 10165.65 | 3210.76 |  | 14961.16 |  |  | 14927.5 | 0 | 94.46% |  | 0 | 28337.57 | 15000 | 33.33% | 0 | 15000 | 33.33% | 0 |  | 14927.5 | 34.5% | 14927.5 | 34.5% | 1734.93 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 926290 - MIDWEST OILSEEDS INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-02-18 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1008802¦¦2020-03-31
UP | CJ | Yes | 1008803 |  | HORN LAKE MS PWM TESTING | ANDERSON, STEPHEN P. | 100% | 3200 | 0 | 3200 | 2428.52 | 2428.52 | 0 | 0 | 0 | 2428.52 | 2837 | 0 | 2837 | 736.6 | 281.39 | 74.2 |  | 381.01 |  |  | 1961.99 | 842.68 | 241.15 |  | 878.16 |  |  | 466.53 | 0 | 69.16% |  | 0 | 1961.99 | 363 | 11.34% | 0 | 363 | 11.34% | 0 |  | 466.53 | 19.21% | 466.53 | 19.21% | 771.48 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 892263 - HORN LAKE, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-18 | 2020-03-03 | 2020-02-18 | 2020-03-03 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1008803¦¦2020-03-31
UP | CJ | Yes | 1009072 |  | SB ENERGY ATHOS | BRASHEAR, DAVID M | 100% | 85150 | 0 | 85150 | 29860.5 | 29860.5 | 29860.5 | 0 | 0 | 29860.5 | 59465 | 0 | 59465 | 5071.95 | 782.43 | 3060.99 |  | 1228.53 |  |  | 14486.56 | 4619.43 | 4182.31 |  | 5684.82 |  |  | 15373.94 | 0 | 24.36% |  | 0 | 14486.56 | 25685 | 30.16% | 0 | 25685 | 30.16% | 0 |  | 15373.94 | 51.49% | 15373.94 | 51.49% | 55289.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1008815 - SB ENERGY | WATER | WATER REPAIR & INSTALLATION | 2020-01-27 | 2020-07-31 | 2020-01-27 | 2020-07-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1009072¦¦2020-03-31
UP | C | Yes | 1009212 |  | BAYOU LIBERTY NEW PANEL | GREGORY, CRYSTAL N | 100% | 2800 | 0 | 2800 | 2800 | 2800 | 2800 | 0 | 0 | 2800 | 2070 | 0 | 2070 | 1912.42 |  |  |  | 1912.42 |  |  | 1912.42 |  |  |  | 1912.42 |  |  | 887.58 | 0 | 92.39% |  | 0 | 1912.42 | 730 | 26.07% | 0 | 730 | 26.07% | 0 |  | 887.58 | 31.7% | 887.58 | 31.7% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878648 - BAYOU LIBERTY WATER CORPORATION | WATER | WATER EQUIPMENT SALES | 2020-02-18 | 2020-03-31 | 2020-02-18 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1009212¦¦2020-03-31
UP | CJ | Yes | 1009213 |  | US AMINES AXIS AL SBS WELL PUL | PARSLEY, TRISTAN S | 100% | 8540 | 51925 | 60465 | 60465 | 60465 | 60465 | 0 | 0 | 60465 | 5804 | 36383.65 | 42187.65 | 29606.07 | 7118.2 | 3046.06 |  | 19441.81 |  |  | 34219.13 | 9241.01 | 3536.44 |  | 21441.68 |  |  | 26245.87 | 0 | 81.11% |  | 0 | 34219.13 | 2736 | 32.04% | 15541.35 | 18277.35 | 30.23% | 15541.35 | 15541.35 | 26245.87 | 43.41% | 26245.87 | 43.41% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 899431 - US AMINES | WATER | WATER SUPPLY | 2020-02-04 | 2020-04-30 | 2020-02-20 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1009213¦¦2020-03-31
TM | CJ | Yes | 1009215 |  | JEN MARLA LLC | SCHERM, LOGAN M | 100% | 15000 | 0 | 15000 | 3392.67 | 3392.67 | 0 | 0 | 0 | 3392.67 | 10000 | 0 | 10000 | 2740.92 | 1249.57 | 149.74 |  | 1341.61 |  |  | 2740.92 | 1249.57 | 149.74 |  | 1341.61 |  |  | 651.75 | 0 | 27.41% |  | 0 | 2740.92 | 5000 | 33.33% | 0 | 5000 | 33.33% | 0 |  | 651.75 | 19.21% | 651.75 | 19.21% | 11607.33 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 1009083 - JENMARLA LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-18 | 2021-02-03 | 2020-02-18 | 2021-02-03 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1009215¦¦2020-03-31
FP | CJ | Yes | 1009299 |  | INDORAMA WELL 9 | GNAU, CASEY T |  | 24500 | 0 | 24500 |  |  | 0 | 0 | 0 |  | 14636 | 0 | 14636 | [20 empty] | 9864 | 40.26% | 0 | 9864 | 40.26% | 0 | [5 empty] | 24500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 1009261 - INDORAMA | WATER | WATER REPAIR & INSTALLATION | 2020-02-19 | 2020-03-31 | 2020-02-19 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1009299¦¦2020-03-31
FP | CJ | Yes | 1009300 |  | SCHENECTADY NY WELL 8 MOTOR | CROOK, CHARLES M | 100% | 6145 | 0 | 6145 | 2520 | 2520 | 2520 | 0 | 0 | 2520 | 4500 | 0 | 4500 | 1489.18 | 1029.36 | 166.62 |  | 293.2 |  |  | 1489.18 | 1029.36 | 166.62 |  | 293.2 |  |  | 1030.82 | 0 | 33.09% |  | 0 | 1489.18 | 1645 | 26.77% | 0 | 1645 | 26.77% | 0 |  | 1030.82 | 40.91% | 1030.82 | 40.91% | 3625 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 897569 - SCHENECTADY, NY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-19 | 2020-04-02 | 2020-02-19 | 2020-04-02 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1009300¦¦2020-03-31
UP | CJ | Yes | 1009301 |  | PHENIX CITY WELL 2 | PARSLEY, TRISTAN S |  | 37450 | 0 | 37450 |  |  | 0 | 0 | 0 |  | 29683 | 0 | 29683 | [20 empty] | 7767 | 20.74% | 0 | 7767 | 20.74% | 0 | [5 empty] | 37450 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 1009214 - SOUTHERN REWINDING | WATER | WATER SUPPLY | 2020-02-19 | 2020-03-31 | 2020-02-19 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1009301¦¦2020-03-31
UP | CJ | Yes | 1009304 |  | OTTAWA IL WELL NO 11 | EISHA, JOSEPH J. | 100% | 24640 | 0 | 24640 | 24548 | 24548 | 24548 | 0 | 0 | 24548 | 15250 | 0 | 15250 | 11521.5 | 7863.65 | 1601.45 |  | 2056.4 |  |  | 18527.75 | 12776.76 | 2435.59 |  | 3315.4 |  |  | 6020.25 | 0 | 121.5% |  | 0 | 18527.75 | 9390 | 38.11% | 0 | 9390 | 38.11% | 0 |  | 6020.25 | 24.52% | 6020.25 | 24.52% | 92 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 895898 - OTTAWA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-12 | 2020-03-30 | 2020-02-12 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1009304¦¦2020-03-31
UP | CJ | Yes | 1009903 |  | DAKESSIAN PUMP PULL AND INSPEC | SEIDEN, ANDREW L. | 100% | 6103 | 15270.13 | 21373.13 | 16708.51 | 16708.51 | 6103 | 0 | 0 | 16708.51 | 5006 | 13994.71 | 19000.71 | 13498.71 | 4237.47 | 1140.03 |  | 8121.21 |  |  | 13498.71 | 4237.47 | 1140.03 |  | 8121.21 |  |  | 3209.8 | 0 | 71.04% |  | 0 | 13498.71 | 1097 | 17.97% | 1275.42 | 2372.42 | 11.1% | 1275.42 | 1275.42 | 3209.8 | 19.21% | 3209.8 | 19.21% | 4664.62 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1009631 - DAKESSIAN, JACOB | WATER | WATER REPAIR & INSTALLATION | 2020-02-19 | 2020-12-30 | 2020-02-19 | 2020-12-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1009903¦¦2020-03-31
FP | CJ | Yes | 1009904 |  | GGNS WELL 3 ASSISTANCE | HARTMAN, MICHAEL | 100% | 88000 | 0 | 88000 | 27920.36 | 27920.36 | 0 | 0 | 0 | 27920.36 | 65185 | 0 | 65185 | 22556.71 | 14136.14 |  |  | 8420.57 |  |  | 22556.71 | 14136.14 |  |  | 8420.57 |  |  | 5363.65 | 0 | 34.6% |  | 0 | 22556.71 | 22815 | 25.93% | 0 | 22815 | 25.93% | 0 |  | 5363.65 | 19.21% | 5363.65 | 19.21% | 60079.64 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 890293 - ENTERGY OPERATIONS GRAND GULF | WATER | WATER REPAIR & INSTALLATION | 2020-02-14 | 2020-04-30 | 2020-02-14 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1009904¦¦2020-03-31
UP | CJ | Yes | 1009905 |  | ERM AMEREN TAYLORVILLE WEST | WHITE, CATHLEEN R | 100% | 14510 | 0 | 14510 | 13010 | 13010 | 13010 | 13010 | 0 | 13010 | 10200 | 0 | 10200 | 7583.31 | 4295.43 | 640.74 |  | 2647.14 |  |  | 7729.34 | 4295.43 | 640.74 |  | 2793.17 |  |  | 5280.66 | 0 | 75.78% |  | 0 | 7729.34 | 4310 | 29.7% | 0 | 4310 | 29.7% | 0 |  | 5280.66 | 40.59% | 5280.66 | 40.59% | 1500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 918468 - ERM | WATER | WATER SUPPLY | 2020-01-27 | 2020-03-31 | 2020-01-27 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1009905¦¦2020-03-31
FP | CJ | Yes | 1009906 |  | GRACE 3037A CAMERA | GNAU, CASEY T | 100% | 20800 | 0 | 20800 | 20800 | 20800 | 20800 | 20800 | 0 | 20800 | 10400 | 0 | 10400 | 9033.25 | 5001.78 | 982.26 |  | 2499.21 | 550 |  | 11605.29 | 6164.84 | 1555.48 |  | 3334.97 | 550 |  | 9194.71 | 0 | 111.6% |  | 0 | 11605.29 | 10400 | 50% | 0 | 10400 | 50% | 0 |  | 9194.71 | 44.21% | 9194.71 | 44.21% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879019 - W R GRACE & CO CONN | WATER | WATER REPAIR & INSTALLATION | 2020-02-20 | 2020-03-20 | 2020-02-20 | 2020-03-20 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1009906¦¦2020-03-31
FP | C | Yes | 1009907 |  | MEADOWVIEW BOOSTER IRRIGATION | WHITE, CATHLEEN R | 100% | 5859 | 0 | 5859 | 5859 | 5859 | 5859 | 0 | 0 | 5859 | 4135 | 0 | 4135 | 1867.36 |  |  |  | 1867.36 |  |  | 4227.82 |  |  |  | 4227.82 |  |  | 1631.18 | 0 | 102.2% |  | 0 | 4227.82 | 1724 | 29.42% | 0 | 1724 | 29.42% | 0 |  | 1631.18 | 27.84% | 1631.18 | 27.84% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 894468 - MEADOWVIEW GOLF COURSE | WATER | WATER SUPPLY | 2020-02-20 | 2020-03-31 | 2020-02-20 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1009907¦¦2020-03-31
UP | CJ | Yes | 1011033 |  | JOHN BORCHARD NEW WELL | MCMAHON, PERRY J | 100% | 315570 | 0 | 315570 | 948.3 | 948.3 | 0 | 0 | 0 | 948.3 | 239483.25 | 0 | 239483.25 | 766.13 |  |  |  | 766.13 |  |  | 766.13 |  |  |  | 766.13 |  |  | 182.17 | 0 | 0.3199% |  | 0 | 766.13 | 76086.75 | 24.11% | 0 | 76086.75 | 24.11% | 0 |  | 182.17 | 19.21% | 182.17 | 19.21% | 314621.7 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1009633 - BORCHARD, JOHON | WATER | WATER REPAIR & INSTALLATION | 2020-02-01 | 2020-04-09 | 2020-02-01 | 2020-04-09 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1011033¦¦2020-03-31
FP | CJ | Yes | 1011034 |  | BUCKEYE PARTNERS PUMP REPAIR | EISHA, JOSEPH J. |  | 171209 | 0 | 171209 |  |  | 0 | 0 | 0 |  | 100000 | 0 | 100000 | [20 empty] | 71209 | 41.59% | 0 | 71209 | 41.59% | 0 | [5 empty] | 171209 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 887558 - BUCKEYE PARTNERS L P | WATER | WATER REPAIR & INSTALLATION | 2020-01-17 | 2020-05-20 | 2020-01-17 | 2020-05-20 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1011034¦¦2020-03-31
FP | CJ | Yes | 1011035 |  | MIDAMERICAN ENERGY WELL 407 | HEILIGER, TERENCE L. | 100% | 25860 | 0 | 25860 | 2749.34 | 2749.34 | 0 | 0 | 0 | 2749.34 | 19588 | 0 | 19588 | 486.98 | 139.96 | 11.7 |  | 335.32 |  |  | 2221.18 | 139.96 | 11.7 |  | 2069.52 |  |  | 528.16 | 0 | 11.34% |  | 0 | 2221.18 | 6272 | 24.25% | 0 | 6272 | 24.25% | 0 |  | 528.16 | 19.21% | 528.16 | 19.21% | 23110.66 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 894624 - MIDAMERICAN ENERGY COUNCIL BLUFFS | WATER | WATER REPAIR & INSTALLATION | 2020-01-24 | 2020-04-30 | 2020-01-29 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1011035¦¦2020-03-31
FP | CJ | Yes | 1011103 |  | SIBLEY IA WELL 4 PUMP REPAIRS | HEILIGER, TERENCE L. | 100% | 11450 | 0 | 11450 | 10492.21 | 10492.21 | 0 | 0 | 0 | 10492.21 | 8935 | 0 | 8935 | 8476.6 | 1225.95 | 845.82 |  | 5508.83 | 896 |  | 8476.6 | 1225.95 | 845.82 |  | 5508.83 | 896 |  | 2015.61 | 0 | 94.87% |  | 0 | 8476.6 | 2515 | 21.97% | 0 | 2515 | 21.97% | 0 |  | 2015.61 | 19.21% | 2015.61 | 19.21% | 957.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 1010494 - CITY OF SIBLEY | WATER | WATER REPAIR & INSTALLATION | 2020-02-04 | 2020-04-30 | 2020-02-14 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1011103¦¦2020-03-31
UP | CJ | Yes | 1011329 |  | CO CAPE CORAL NORTH | MCCULLERS, BLAKE E. | 100% | 414928 | 0 | 414928 | 113832 | 113832 | 113832 | 0 | 0 | 113832 | 310575 | 0 | 310575 | 23698.13 | 7883.18 | 7667.52 |  | 8097.43 | 50 |  | 23698.13 | 7883.18 | 7667.52 |  | 8097.43 | 50 |  | 90133.87 | 0 | 7.63% |  | 0 | 23698.13 | 104353 | 25.15% | 0 | 104353 | 25.15% | 0 |  | 90133.87 | 79.18% | 90133.87 | 79.18% | 301096 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-24 | 2020-09-01 | 2020-02-24 | 2020-09-01 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1011329¦¦2020-03-31
UP | CJ | Yes | 1011330 |  | UPPER JASPER COUNTY WELL 3 | ALBARADO, JORDAN A | 100% | 16300 | 0 | 16300 | 28047 | 28047 | 28047 | 0 | 0 | 28047 | 7661 | 0 | 7661 | 10641.06 | 2530.17 | 963.28 |  | 6582.11 | 565.5 |  | 10641.06 | 2530.17 | 963.28 |  | 6582.11 | 565.5 |  | 17405.94 | 0 | 138.9% |  | 0 | 10641.06 | 8639 | 53% | 0 | 8639 | 53% | 0 |  | 17405.94 | 62.06% | 17405.94 | 62.06% | -11747 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 1021009 - UPPER JASPER, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-24 | 2020-03-31 | 2020-02-24 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1011330¦¦2020-03-31
UP | CJ | Yes | 1011531 |  | CO CAPE CORAL SOUTH | MCCULLERS, BLAKE E. | 100% | 340484 | 0 | 340484 | 100142 | 100142 | 100142 | 0 | 0 | 100142 | 254819 | 0 | 254819 | 15552.72 | 5413.66 | 6330.42 |  | 3458.64 | 350 |  | 15552.72 | 5413.66 | 6330.42 |  | 3458.64 | 350 |  | 84589.28 | 0 | 6.103% |  | 0 | 15552.72 | 85665 | 25.16% | 0 | 85665 | 25.16% | 0 |  | 84589.28 | 84.47% | 84589.28 | 84.47% | 240342 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 887899 - CAPE CORAL, FL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-25 | 2020-09-01 | 2020-02-25 | 2020-09-01 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1011531¦¦2020-03-31
TM | CJ | Yes | 1011662 |  | BAYER WILDLIFE AND FARM MGMT | SCHERM, LOGAN M |  | 3400 | 0 | 3400 |  |  | 0 | 0 | 0 |  | 2750 | 0 | 2750 | [20 empty] | 650 | 19.12% | 0 | 650 | 19.12% | 0 | [5 empty] | 3400 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879114 - MONSANTO WILDLIFE & FARM MANAGEMENT CENT | WATER | WATER REPAIR & INSTALLATION | 2020-02-25 | 2020-05-31 | 2020-02-25 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | EXPENSE JOB | 1011662¦¦2020-03-31
FP | CJ | Yes | 1011663 |  | LOCKPORT WELL 15 PUMP BID | EISHA, JOSEPH J. |  | 404469 | 0 | 404469 |  |  | 0 | 0 | 0 |  | 303000 | 0 | 303000 | [20 empty] | 101469 | 25.09% | 0 | 101469 | 25.09% | 0 | [5 empty] | 404469 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878705 - THIENEMAN CONSTRUCTION INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-25 | 2020-10-26 | 2020-02-25 | 2020-10-26 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 1011663¦¦2020-03-31
UP | CJ | Yes | 1011664 |  | DANSVILLE NY WELL MAINTENANCE | CROOK, CHARLES M | 100% | 3045 | 0 | 3045 | 196.16 | 196.16 | 0 | 0 | 0 | 196.16 | 2245 | 0 | 2245 | 158.48 | 156.72 |  |  | 1.76 |  |  | 158.48 | 156.72 |  |  | 1.76 |  |  | 37.68 | 0 | 7.059% |  | 0 | 158.48 | 800 | 26.27% | 0 | 800 | 26.27% | 0 |  | 37.68 | 19.21% | 37.68 | 19.21% | 2848.84 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 1009415 - DANSVILLE, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-24 | 2020-04-23 | 2020-02-24 | 2020-04-23 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1011664¦¦2020-03-31
FP | CJ | Yes | 1011699 |  | LE AX WATER 2020 ANNUAL MONIT | SMITH, ANDREW J. | 100% | 13400 | 0 | 13400 | 431.17 | 431.17 | 0 | 0 | 0 | 431.17 | 9500 | 0 | 9500 | 348.34 | 341.3 |  |  | 7.04 |  |  | 348.34 | 341.3 |  |  | 7.04 |  |  | 82.83 | 0 | 3.667% |  | 0 | 348.34 | 3900 | 29.1% | 0 | 3900 | 29.1% | 0 |  | 82.83 | 19.21% | 82.83 | 19.21% | 12968.83 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878554 - LE AX WATER DISTRICT | WATER | WATER SUPPLY | 2020-02-25 | 2021-03-01 | 2020-02-25 | 2021-03-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1011699¦¦2020-03-31
TM | CJ | Yes | 1011863 |  | CORYDON BOOSTER PUMP | MIGUEL, SEAN J. | 100% | 1665 | 9888 | 11553 | 2096.31 | 2096.31 | 1665 | 0 | 0 | 2096.31 | 1280 | 8065 | 9345 | 1693.6 | 1052.98 | 301.26 |  | 339.36 |  |  | 1693.6 | 1052.98 | 301.26 |  | 339.36 |  |  | 402.71 | 0 | 18.12% |  | 0 | 1693.6 | 385 | 23.12% | 1823 | 2208 | 19.11% | 1823 | 1823 | 402.71 | 19.21% | 402.71 | 19.21% | 9456.69 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889020 - CORYDON, IN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-21 | 2020-03-30 | 2020-02-21 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1011863¦¦2020-03-31
FP | CJ | Yes | 1011864 |  | ENTERPRISE BREAUX BRIDGE PULL | GNAU, CASEY T | 100% | 12000 | 0 | 12000 | 4320 | 4320 | 4320 | 0 | 0 | 4320 | 6000 | 0 | 6000 | 2165.21 | 997.66 | 204.87 |  | 962.68 |  |  | 2165.21 | 997.66 | 204.87 |  | 962.68 |  |  | 2154.79 | 0 | 36.09% |  | 0 | 2165.21 | 6000 | 50% | 0 | 6000 | 50% | 0 |  | 2154.79 | 49.88% | 2154.79 | 49.88% | 7680 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 890304 - ENTERPRISE PRODUCTS BREAUX BRIDGE | WATER | WATER REPAIR & INSTALLATION | 2020-02-25 | 2020-03-31 | 2020-02-25 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1011864¦¦2020-03-31
TM | CJ | Yes | 1012060 |  | ARMSTRONG PUMP PARTS | BARNES, MATTHEW D | 100% | 6698 | 0 | 6698 | 1966.84 | 1966.84 | 0 | 0 | 0 | 1966.84 | 4019 | 0 | 4019 | 1589 | 120.85 | 29.32 |  | 1438.83 |  |  | 1589 | 120.85 | 29.32 |  | 1438.83 |  |  | 377.84 | 0 | 39.54% |  | 0 | 1589 | 2679 | 40% | 0 | 2679 | 40% | 0 |  | 377.84 | 19.21% | 377.84 | 19.21% | 4731.16 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 1011143 - ARMSTRONG WORLD INDUSTRIES | WATER | WATER REPAIR & INSTALLATION | 2020-02-26 | 2020-04-30 | 2020-02-26 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1012060¦¦2020-03-31
FP | CJ | Yes | 1012061 |  | SEBRING FL VIDEO DESOTO WELL | BRUGGER, CRAIG J. | 100% | 2212 | 0 | 2212 | 2212 | 2212 | 2212 | 0 | 0 | 2212 | 1431 | 0 | 1431 | 166.2 |  | 165.12 |  | 1.08 |  |  | 166.2 |  | 165.12 |  | 1.08 |  |  | 2045.8 | 0 | 11.61% |  | 0 | 166.2 | 781 | 35.31% | 0 | 781 | 35.31% | 0 |  | 2045.8 | 92.49% | 2045.8 | 92.49% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 1011923 - SEBRING, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-19 | 2020-03-31 | 2020-02-19 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1012061¦¦2020-03-31
FP | CJ | Yes | 1012062 |  | CHEVRON PASADENA REFINERY 10 | ALBARADO, JORDAN A | 100% | 15911 | 0 | 15911 | 15991 | 15991 | 15991 | 0 | 0 | 15991 | 8910 | 0 | 8910 | 10679.54 | 4322.7 | 2177.24 |  | 4179.6 |  |  | 10679.54 | 4322.7 | 2177.24 |  | 4179.6 |  |  | 5311.46 | 0 | 119.9% |  | 0 | 10679.54 | 7001 | 44% | 0 | 7001 | 44% | 0 |  | 5311.46 | 33.22% | 5311.46 | 33.22% | -80 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 1011939 - CHEVRON PASADENA REFINERY | WATER | WATER REPAIR & INSTALLATION | 2020-02-25 | 2020-03-31 | 2020-02-25 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1012062¦¦2020-03-31
FP | C | Yes | 1012348 |  | LOOGOOTEE REHABS | WILLIAMS, DONALD G. | 100% | 53250 | 8171 | 61421 | 64421 | 64421 | 64421 | 0 | 0 | 64421 | 41847 | 5964 | 47811 | 42094.6 | 17194.84 | 8659.26 |  | 16240.5 |  |  | 42094.6 | 17194.84 | 8659.26 |  | 16240.5 |  |  | 22326.4 | 0 | 88.04% |  | 0 | 42094.6 | 11403 | 21.41% | 2207 | 13610 | 22.16% | 2207 | 2207 | 22326.4 | 34.66% | 22326.4 | 34.66% | -3000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 893900 - LOOGOOTEE, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-26 | 2020-04-30 | 2020-02-26 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1012348¦¦2020-03-31
TM | C | Yes | 1012349 |  | LAURELVILLE PUMP PARTS | BARNES, MATTHEW D | 100% | 1806 | 0 | 1806 | 1803 | 1803 | 1803 | 0 | 0 | 1803 | 1142.69 | 0 | 1142.69 | 1166.69 |  |  |  | 1166.69 |  |  | 1166.69 |  |  |  | 1166.69 |  |  | 636.31 | 0 | 102.1% |  | 0 | 1166.69 | 663.31 | 36.73% | 0 | 663.31 | 36.73% | 0 |  | 636.31 | 35.29% | 636.31 | 35.29% | 3 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 914250 - LAURELVILLE, VILLAGE OF | WATER | WATER EQUIPMENT SALES | 2020-02-26 | 2020-03-30 | 2020-02-26 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1012349¦¦2020-03-31
FP | CJ | Yes | 1012350 |  | HUNTLEY IL 8 MWP | HEALY, THOMAS P. |  | 20000 | 0 | 20000 |  |  | 0 | 0 | 0 |  | 16000 | 0 | 16000 | [20 empty] | 4000 | 20% | 0 | 4000 | 20% | 0 | [5 empty] | 20000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878999 - MUNICIPAL WELL AND PUMP | WATER | WATER REPAIR & INSTALLATION | 2020-02-26 | 2020-05-30 | 2020-02-26 | 2020-05-30 | SUBCONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1012350¦¦2020-03-31
UP | CJ | Yes | 1012352 |  | SAN JACINTO BATH BOOSTER | GRACE, GARY L. | 100% | 4195 | 19771.33 | 23966.33 | 23966.33 | 23966.33 | 24815.19 | 0 | 0 | 23966.33 | 3084 | 14900.73 | 17984.73 | 17656.85 | 5906.5 | 1022.97 |  | 10727.38 |  |  | 17656.85 | 5906.5 | 1022.97 |  | 10727.38 |  |  | 6309.48 | 0 | 98.18% |  | 0 | 17656.85 | 1111 | 26.48% | 4870.6 | 5981.6 | 24.96% | 4870.6 |  | 6309.48 | 26.33% | 6309.48 | 26.33% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 919351 - SAN JACINTO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-27 | 2020-04-27 | 2020-02-27 | 2020-04-27 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1012352¦¦2020-03-31
UP | CJ | Yes | 1012353 |  | MEXICHEM 2020 FLOW TESTS | GREGORY, CRYSTAL N |  | 2500 | 0 | 2500 |  |  | 0 | 0 | 0 |  | 1765 | 0 | 1765 | [20 empty] | 735 | 29.4% | 0 | 735 | 29.4% | 0 | [5 empty] | 2500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878530 - DO NOT USE MEXICHEM FLUOR INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-27 | 2020-03-31 | 2020-02-27 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1012353¦¦2020-03-31
UP | CJ | Yes | 1012354 |  | SATSUMA WELL 3 REHAB | PARSLEY, TRISTAN S | 100% | 6855 | 69673 | 76528 | 57435 | 57435 | 57435 | 57435 | 0 | 57435 | 4662 | 51387.7 | 56049.7 | 29819.56 | 11664.34 | 4036.25 |  | 14118.97 |  |  | 29819.56 | 11664.34 | 4036.25 |  | 14118.97 |  |  | 27615.44 | 0 | 53.2% |  | 0 | 29819.56 | 2193 | 31.99% | 18285.3 | 20478.3 | 26.76% | 18285.3 | 18285.3 | 27615.44 | 48.08% | 27615.44 | 48.08% | 19093 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 897524 - SATSUMA WATER WORKS AND SEWER BOARD | WATER | WATER SUPPLY | 2020-02-17 | 2020-03-31 | 2020-02-21 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1012354¦¦2020-03-31
FP | C | Yes | 1012357 |  | ALIQUIPPA AV VALVE | BARNES, MATTHEW D | 100% | 3211 | 0 | 3211 | 3211 | 3211 | 3211 | 0 | 0 | 3211 | 1926.6 | 0 | 1926.6 | 1605.19 | 552.02 | 186.76 |  | 866.41 |  |  | 1605.19 | 552.02 | 186.76 |  | 866.41 |  |  | 1605.81 | 0 | 83.32% |  | 0 | 1605.19 | 1284.4 | 40% | 0 | 1284.4 | 40% | 0 |  | 1605.81 | 50.01% | 1605.81 | 50.01% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878528 - MUNICIPAL WATER AUTHORITY OF ALIQUIPPA | WATER | WATER REPAIR & INSTALLATION | 2020-02-27 | 2020-03-30 | 2020-02-27 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1012357¦¦2020-03-31
FP | CJ | Yes | 1012364 |  | L KING DENHAM SPRINGS FEMA | LOPEZ-VASQUEZ, JUAN C. |  | 161915 | 0 | 161915 |  |  | 0 | 0 | 0 |  | 117346 | 0 | 117346 | [17 empty] | 0 |  |  | 44569 | 27.53% | 0 | 44569 | 27.53% | 0 | [5 empty] | 161915 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 1011979 - L KING COMPANY LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-26 | 2020-06-26 | 2020-02-26 | 2020-06-26 | . | PUBLIC | BID/BUILD | 1012364¦¦2020-03-31
UP | CJ | Yes | 1012480 |  | BROUSSARD ST JULIAN SOFT START | GNAU, CASEY T | 100% | 2500 | 0 | 2500 | 1340 | 1340 | 1340 | 0 | 0 | 1340 | 1250 | 0 | 1250 | 564.5 | 179.24 | 37.1 |  | 348.16 |  |  | 564.5 | 179.24 | 37.1 |  | 348.16 |  |  | 775.5 | 0 | 45.16% |  | 0 | 564.5 | 1250 | 50% | 0 | 1250 | 50% | 0 |  | 775.5 | 57.87% | 775.5 | 57.87% | 1160 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 887512 - BROUSSARD, LA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-27 | 2020-03-31 | 2020-02-27 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1012480¦¦2020-03-31
TM | CJ | Yes | 1012481 |  | FRANKFORT IL 11 AND 12 REHAB | EISHA, JOSEPH J. | 100% | 57000 | 0 | 57000 | 30012.35 | 30012.35 | 30012.35 | 0 | 0 | 30012.35 | 40000 | 0 | 40000 | 27926.45 | 18127.73 | 4796.76 |  | 5001.96 |  |  | 27926.45 | 18127.73 | 4796.76 |  | 5001.96 |  |  | 2085.9 | 0 | 69.82% |  | 0 | 27926.45 | 17000 | 29.82% | 0 | 17000 | 29.82% | 0 |  | 2085.9 | 6.95% | 2085.9 | 6.95% | 26987.65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878861 - FRANKFORT, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-28 | 2020-05-11 | 2020-02-28 | 2020-05-11 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1012481¦¦2020-03-31
FP | C | Yes | 1012482 |  | P AND G PM TESTING | WHITE, CATHLEEN R | 100% | 5727 | 0 | 5727 | 5727 | 5727 | 5727 | 0 | 0 | 5727 | 4000 | 0 | 4000 | 3515.3 | 2135.01 | 287.54 |  | 1092.75 |  |  | 3515.3 | 2135.01 | 287.54 |  | 1092.75 |  |  | 2211.7 | 0 | 87.88% |  | 0 | 3515.3 | 1727 | 30.16% | 0 | 1727 | 30.16% | 0 |  | 2211.7 | 38.62% | 2211.7 | 38.62% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896598 - PROCTER AND GAMBLE PAPER PRODUCTS, THE | WATER | WATER SUPPLY | 2020-04-13 | 2020-06-30 | 2020-02-17 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1012482¦¦2020-03-31
FP | CJ | Yes | 1012483 |  | EXXON REFINERY WELL 34 | LOPEZ-VASQUEZ, JUAN C. | 100% | 28600 | 0 | 28600 | 7514.11 | 7514.11 | 0 | 0 | 0 | 7514.11 | 19469 | 0 | 19469 | 6070.61 | 2726.27 | 350.03 |  | 2494.31 | 500 |  | 6070.61 | 2726.27 | 350.03 |  | 2494.31 | 500 |  | 1443.5 | 0 | 31.18% |  | 0 | 6070.61 | 9131 | 31.93% | 0 | 9131 | 31.93% | 0 |  | 1443.5 | 19.21% | 1443.5 | 19.21% | 21085.89 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878581 - EXXON MOBIL REFINERY | WATER | WATER REPAIR & INSTALLATION | 2020-02-24 | 2020-06-30 | 2020-02-24 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1012483¦¦2020-03-31
UP | CJ | Yes | 1012484 |  | GOLDEN STATE WATER PAPAGO WELL | BRASHEAR, DAVID M | 100% | 9085 | 0 | 9085 | 7336.68 | 7336.68 | 6075.09 | 0 | 0 | 7336.68 | 7075 | 0 | 7075 | 5927.26 | 674.76 | 222.16 |  | 5030.34 |  |  | 5927.26 | 674.76 | 222.16 |  | 5030.34 |  |  | 1409.42 | 0 | 83.78% |  | 0 | 5927.26 | 2010 | 22.12% | 0 | 2010 | 22.12% | 0 |  | 1409.42 | 19.21% | 1409.42 | 19.21% | 1748.32 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 891367 - GOLDEN STATE WATER CO APPLE VALLEY, CA | WATER | WATER REPAIR & INSTALLATION | 2020-02-27 | 2020-04-30 | 2020-02-27 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1012484¦¦2020-03-31
TM | C | Yes | 1012724 |  | CHRIS SIMPSON PR | SCHERM, LOGAN M | 100% | 6000 | 0 | 6000 | 8838.9 | 8838.9 | 9501.84 | 0 | 0 | 8838.9 | 4000 | 0 | 4000 | 6237.17 | 2455.04 | 543.78 |  | 3238.35 |  |  | 6237.17 | 2455.04 | 543.78 |  | 3238.35 |  |  | 2601.73 | 0 | 155.9% |  | 0 | 6237.17 | 2000 | 33.33% | 0 | 2000 | 33.33% | 0 |  | 2601.73 | 29.43% | 2601.73 | 29.43% | -2838.9 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 888374 - CHRIS SIMPSON | WATER | WATER REPAIR & INSTALLATION | 2020-02-28 | 2020-05-31 | 2020-02-28 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 1012724¦¦2020-03-31
FP | CJ | Yes | 1012725 |  | CHERRY VALLEY IL TEST HOLE | SNELTEN, BRIAN M | 100% | 49190 | 0 | 49190 | 4365.8 | 4365.8 | 0 | 0 | 0 | 4365.8 | 35605 | 0 | 35605 | 3527.11 | 1812.51 | 1060.72 |  | 653.88 |  |  | 3527.11 | 1812.51 | 1060.72 |  | 653.88 |  |  | 838.69 | 0 | 9.906% |  | 0 | 3527.11 | 13585 | 27.62% | 0 | 13585 | 27.62% | 0 |  | 838.69 | 19.21% | 838.69 | 19.21% | 44824.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 888325 - CHERRY VALLEY, IL, VILLAGE OF | WATER | WATER SUPPLY | 2020-02-17 | 2020-02-28 | 2020-02-17 | 2020-02-28 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1012725¦¦2020-03-31
TM | CJ | Yes | 1012726 |  | TAGHLEEF RIGHT ANGLE | MIGUEL, SEAN J. | 100% | 5000 | 0 | 5000 | 2550 | 2550 | 2550 | 0 | 0 | 2550 | 3250 | 0 | 3250 | 1715 | 810.8 | 486.6 |  | 417.6 |  |  | 1715 | 810.8 | 486.6 |  | 417.6 |  |  | 835 | 0 | 52.77% |  | 0 | 1715 | 1750 | 35% | 0 | 1750 | 35% | 0 |  | 835 | 32.75% | 835 | 32.75% | 2450 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 898621 - TAGHLEEF INDUSTRIES, INC | WATER | WATER REPAIR & INSTALLATION | 2020-02-28 | 1930-03-30 | 2020-02-28 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1012726¦¦2020-03-31
FP | C | Yes | 1012727 |  | WYOMING PWM | BARNES, MATTHEW D | 100% | 6885 | 0 | 6885 | 6885 | 6885 | 6885 | 0 | 0 | 6885 | 4131 | 0 | 4131 | 6773.95 | 2473.08 | 3029.11 |  | 1271.76 |  |  | 6773.95 | 2473.08 | 3029.11 |  | 1271.76 |  |  | 111.05 | 0 | 164% |  | 0 | 6773.95 | 2754 | 40% | 0 | 2754 | 40% | 0 |  | 111.05 | 1.613% | 111.05 | 1.613% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 879086 - WYOMING, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-02-28 | 2020-03-30 | 2020-02-28 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1012727¦¦2020-03-31
UP | LJ | Yes | 1012847 |  | TARGA RESOURCES NEW WELL 18 | LOPEZ-VASQUEZ, JUAN C. | 0.06608% | 1208301 | 0 | 1208301 | 798.3989 |  | 0 | 0 | 0 | 1208301 | 952703.64 | 0 | 952703.64 | 629.51 |  |  |  | 629.51 |  |  | 629.51 |  |  |  | 629.51 |  |  | 0 | 629.51 | 0.06608% |  | 952074.13 | 952703.64 | 255597.36 | 21.15% | 0 | 255597.36 | 21.15% | 0 |  | 168.89 | 21.15% | 255597.36 | 21.15% | 1207502.6 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878615 - TARGA DOWNSTREAM LLC HAA | WATER | WATER SUPPLY | 2020-02-28 | 2020-09-30 | 2020-02-28 | 2020-09-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1012847¦¦2020-03-31
UP | CJ | Yes | 1013376 |  | RIPLEY GAS AND WATER PWM | ANDERSON, STEPHEN P. | 100% | 2500 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 2500 | 2380 | 0 | 2380 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 2499.99 | 0 | 0.0004202% |  | 0 | 0.01 | 120 | 4.8% | 0 | 120 | 4.8% | 0 |  | 2499.99 | 100% | 2499.99 | 100% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 897057 - RIPLEY WATER & GAS | WATER | WATER REPAIR & INSTALLATION | 2020-02-27 | 2020-03-04 | 2020-02-27 | 2020-03-04 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1013376¦¦2020-03-31
FP | CJ | Yes | 1013377 |  | RAYONIER FERNANDINA BEACH FL 9 | PARSLEY, TRISTAN S | 100% | 31303 | 0 | 31303 | 12177.49 | 12177.49 | 0 | 0 | 0 | 12177.49 | 17932 | 0 | 17932 | 9838.13 | 5103.05 | 447.91 |  | 4287.17 |  |  | 9838.13 | 5103.05 | 447.91 |  | 4287.17 |  |  | 2339.36 | 0 | 54.86% |  | 0 | 9838.13 | 13371 | 42.71% | 0 | 13371 | 42.71% | 0 |  | 2339.36 | 19.21% | 2339.36 | 19.21% | 19125.51 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 878720 - RAYONIER FERNANDINA BEACH FL | WATER | WATER REPAIR & INSTALLATION | 2020-02-28 | 2020-04-30 | 2020-02-28 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1013377¦¦2020-03-31
FP | CJ | Yes | 1013378 |  | WEST CHICAGO IL WELL 8 | HEALY, THOMAS P. | 100% | 128000 | 0 | 128000 | 20160.5 | 20160.5 | 20160.5 | 20160.5 | 0 | 20160.5 | 94000 | 0 | 94000 | 15715.08 | 10626.89 | 2064.99 |  | 3023.2 |  |  | 15715.08 | 10626.89 | 2064.99 |  | 3023.2 |  |  | 4445.42 | 0 | 16.72% |  | 0 | 15715.08 | 34000 | 26.56% | 0 | 34000 | 26.56% | 0 |  | 4445.42 | 22.05% | 4445.42 | 22.05% | 107839.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878686 - WEST CHICAGO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-05-31 | 2020-03-02 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1013378¦¦2020-03-31
FP | CJ | Yes | 1013379 |  | WIDEFIELD W1 PUMP | SCHANAMAN, MIKE L. | 100% | 25475 | 0 | 25475 | 15626.35 | 15626.35 | 0 | 0 | 0 | 15626.35 | 18784 | 0 | 18784 | 12624.44 |  |  |  | 12624.44 |  |  | 12624.44 |  |  |  | 12624.44 |  |  | 3001.91 | 0 | 67.21% |  | 0 | 12624.44 | 6691 | 26.26% | 0 | 6691 | 26.26% | 0 |  | 3001.91 | 19.21% | 3001.91 | 19.21% | 9848.65 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 900301 - WIDEFIELD WATER | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-03-27 | 2020-03-02 | 2020-03-27 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1013379¦¦2020-03-31
UP | CJ | Yes | 1013380 |  | ACOCET BOREBLAST MONITOR WELLS | BRASHEAR, DAVID M |  | 5575 | 0 | 5575 |  |  | 0 | 0 | 0 |  | 4182 | 0 | 4182 | [20 empty] | 1393 | 24.99% | 0 | 1393 | 24.99% | 0 | [5 empty] | 5575 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1013156 - ACOCET ENVIRONMENTAL | WATER | WATER REPAIR & INSTALLATION | 2020-02-27 | 2020-03-31 | 2020-02-27 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1013380¦¦2020-03-31
UP | LJ | Yes | 1013435 |  | RIETKERK FARMS NEW WELL | TRAMMELL, DUANE R. | 25.69% | 659218 | 0 | 659218 | 167515.772 | 140986 | 140986 | 0 | 0 | 652068 | 517837.3 | 0 | 517837.3 | 130724.22 | 44947.63 | 24820.02 |  | 54801.57 | 6155 |  | 130724.22 | 44947.63 | 24820.02 |  | 54801.57 | 6155 |  | 10261.78 | 0 | 25.24% |  | 378129.84 | 508854.06 | 141380.7 | 21.45% | 0 | 141380.7 | 21.45% | 0 |  | 36791.55 | 21.96% | 143213.94 | 21.96% | 491702.23 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1013176 - RIETKERK FARMS | WATER | WATER SUPPLY | 2020-03-02 | 2020-05-30 | 2020-03-02 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1013435¦¦2020-03-31
FP | LJ | Yes | 1013455 |  | BASIN WELLS GRIC 2 PRODUCTION | COMBS, TAYLOR E. |  | 1100865 | 0 | 1100865 |  |  | 0 | 0 | 0 | 1100865 | 935952 | 0 | 935952 | [18 empty] | 935952 | 935952 | 164913 | 14.98% | 0 | 164913 | 14.98% | 0 |  |  |  | 164913 | 14.98% | 1100865 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 891252 - GILA RIVER INDIAN COMMUNITY | WATER | WATER SUPPLY | 2020-03-02 | 2020-05-29 | 2020-03-02 | 2020-05-29 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1013455¦¦2020-03-31
FP | CJ | Yes | 1013598 |  | SARATOGA FISH HATCHERY | SCHANAMAN, MIKE L. | 100% | 21350 | 0 | 21350 | 3136.62 | 3136.62 | 0 | 0 | 0 | 3136.62 | 15852 | 0 | 15852 | 2534.06 |  |  |  | 2534.06 |  |  | 2534.06 |  |  |  | 2534.06 |  |  | 602.56 | 0 | 15.99% |  | 0 | 2534.06 | 5498 | 25.75% | 0 | 5498 | 25.75% | 0 |  | 602.56 | 19.21% | 602.56 | 19.21% | 18213.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 1013335 - FWS SARATOGA NATIONAL FISH HATCHERY | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-03-27 | 2020-03-02 | 2020-03-27 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1013598¦¦2020-03-31
UP | CJ | Yes | 1013599 |  | JACOBS ENG LAKE HAVASU SUPPORT | SMITH, ANDREW J. |  | 8354 | 0 | 8354 |  |  | 0 | 0 | 0 |  | 5982 | 0 | 5982 | [20 empty] | 2372 | 28.39% | 0 | 2372 | 28.39% | 0 | [5 empty] | 8354 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 938025 - JACOBS ENGINEERING GROUP INC | WATER | WATER SUPPLY | 2020-02-26 | 2020-05-01 | 2020-02-26 | 2020-05-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1013599¦¦2020-03-31
UP | CJ | Yes | 1013600 |  | METROPOLITAN WATER PERRIS PUMP | GRACE, GARY L. | 100% | 2375 | 0 | 2375 | 2375 | 2375 | 2375 | 2375 | 0 | 2375 | 2065 | 0 | 2065 | 3502.9 | 2085.02 | 102.03 |  | 1315.85 |  |  | 3502.9 | 2085.02 | 102.03 |  | 1315.85 |  |  | 0 | 1127.9 | 169.6% |  | 0 | 3502.9 | 310 | 13.05% | 0 | 310 | 13.05% | 0 |  | -1127.9 | -47.49% | -1127.9 | -47.49% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 222927 - METROPOLITAN WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-02-10 | 2020-05-01 | 2020-02-10 | 2020-05-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1013600¦¦2020-03-31
FP | CJ | Yes | 1013601 |  | DOT105 WELL ID6 AND ID7 REHAB | MAI, JONATHAN | 100% | 103151 | 0 | 103151 | 49707.29 | 49707.29 | 50911.97 | 50911.97 | 0 | 49707.29 | 77445 | 0 | 77445 | 49150.93 | 22673.79 | 6867.35 |  | 19609.79 |  |  | 49150.93 | 22673.79 | 6867.35 |  | 19609.79 |  |  | 556.36 | 0 | 63.47% |  | 0 | 49150.93 | 25706 | 24.92% | 0 | 25706 | 24.92% | 0 |  | 556.36 | 1.119% | 556.36 | 1.119% | 53443.71 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878827 - DEPARTMENT OF TRANSPORTATION DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-03-27 | 2020-03-02 | 2020-03-27 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1013601¦¦2020-03-31
UP | LJ | Yes | 1013623 |  | TUCSON WATER H002B | COMBS, TAYLOR E. | 11.47% | 619062 | 0 | 619062 | 71031.9503 |  | 0 | 0 | 0 | 619062 | 487301.89 | 0 | 487301.89 | 55913.63 | 13256.13 | 5230.02 |  | 36252.48 | 1175 |  | 55913.63 | 13256.13 | 5230.02 |  | 36252.48 | 1175 |  | 0 | 55913.63 | 11.47% |  | 431388.26 | 487301.89 | 131760.11 | 21.28% | 0 | 131760.11 | 21.28% | 0 |  | 15118.32 | 21.28% | 131760.11 | 21.28% | 548030.05 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 899186 - TUCSON, CITY OF | WATER | WATER SUPPLY | 2020-02-17 | 2020-05-15 | 2020-02-17 | 2020-05-15 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1013623¦¦2020-03-31
TM | C | Yes | 1013624 |  | ADAMS CO SEAL INSP | MIGUEL, SEAN J. | 100% | 1500 | 0 | 1500 | 675 | 675 | 675 | 0 | 0 | 675 | 1250 | 0 | 1250 | 588.33 | 398.3 | 83.87 |  | 106.16 |  |  | 588.33 | 398.3 | 83.87 |  | 106.16 |  |  | 86.67 | 0 | 47.07% |  | 0 | 588.33 | 250 | 16.67% | 0 | 250 | 16.67% | 0 |  | 86.67 | 12.84% | 86.67 | 12.84% | 825 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | MIDDLETOWN - WA | 1013220 - ADAMS COUNTY REGIONAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-04-30 | 2020-03-02 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1013624¦¦2020-03-31
UP | C | Yes | 1013625 |  | CERTAINTEED GYPSUM PWM | MIGUEL, SEAN J. | 100% | 1200 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 0 | 1200 | 1000 | 0 | 1000 | 1286.4 | 695.39 | 236.05 |  | 354.96 |  |  | 1286.4 | 695.39 | 236.05 |  | 354.96 |  |  | 0 | 86.4 | 128.6% |  | 0 | 1286.4 | 200 | 16.67% | 0 | 200 | 16.67% | 0 |  | -86.4 | -7.2% | -86.4 | -7.2% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888181 - CERTAINTEED GYPSUM & CEILINGS MFG , INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-03-30 | 2020-03-02 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1013625¦¦2020-03-31
UP | C | Yes | 1013907 |  | CORBIN PUMP MAINTENANCE | MIGUEL, SEAN J. | 100% | 3000 | 0 | 3000 | 2460 | 2460 | 2460 | 0 | 0 | 2460 | 2400 | 0 | 2400 | 2237.21 | 980.01 | 306.85 |  | 950.35 |  |  | 2237.21 | 980.01 | 306.85 |  | 950.35 |  |  | 222.79 | 0 | 93.22% |  | 0 | 2237.21 | 600 | 20% | 0 | 600 | 20% | 0 |  | 222.79 | 9.057% | 222.79 | 9.057% | 540 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878574 - CORBIN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-03-30 | 2020-03-02 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1013907¦¦2020-03-31
UP | CJ | Yes | 1013909 |  | GRAYSON CO VIBRATION | MIGUEL, SEAN J. | 100% | 2040 | 0 | 2040 | 510 | 510 | 510 | 0 | 0 | 510 | 1440 | 0 | 1440 | 0.01 |  |  |  | 0.01 |  |  | 0.01 |  |  |  | 0.01 |  |  | 509.99 | 0 | 0.0006944% |  | 0 | 0.01 | 600 | 29.41% | 0 | 600 | 29.41% | 0 |  | 509.99 | 100% | 509.99 | 100% | 1530 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879099 - GRAYSON, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-03 | 2020-12-31 | 2020-03-03 | 2020-12-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1013909¦¦2020-03-31
FP | CJ | Yes | 1013910 |  | BPU 2020 MONITORING | SMITH, ANDREW J. |  | 9900 | 0 | 9900 |  |  | 0 | 0 | 0 |  | 6825 | 0 | 6825 | [20 empty] | 3075 | 31.06% | 0 | 3075 | 31.06% | 0 | [5 empty] | 9900 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 887355 - BPU | WATER | WATER SUPPLY | 2020-03-03 | 2021-03-01 | 2020-03-03 | 2021-03-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1013910¦¦2020-03-31
UP | CJ | Yes | 1013911 |  | KIMBALL RANCH WELL 2 | SEIDEN, ANDREW L. | 100% | 1300 | 0 | 1300 | 1300.42 | 1300.42 | 1300.42 | 0 | 0 | 1300.42 | 768 | 0 | 768 | 492.21 | 237.37 |  |  | 254.84 |  |  | 492.21 | 237.37 |  |  | 254.84 |  |  | 808.21 | 0 | 64.09% |  | 0 | 492.21 | 532 | 40.92% | 0 | 532 | 40.92% | 0 |  | 808.21 | 62.15% | 808.21 | 62.15% | -0.42 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878806 - KIMBALL RANCHES EL HOGAR | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-12-31 | 2020-03-02 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1013911¦¦2020-03-31
TM | CJ | Yes | 1013912 |  | AK BOILERFEED 2020 | SIMPSON, CARL L. | 100% | 200000 | 200000 | 400000 | 323357.21 | 323357.21 | 200000 | 200000 | 0 | 323357.21 | 150000 | 150000 | 300000 | 261238.52 | 7693.83 | 11074.8 |  | 240539.74 | 1930.15 |  | 261238.52 | 7693.83 | 11074.8 |  | 240539.74 | 1930.15 |  | 62118.69 | 0 | 87.08% |  | 0 | 261238.52 | 50000 | 25% | 50000 | 100000 | 25% | 50000 | 50000 | 62118.69 | 19.21% | 62118.69 | 19.21% | 76642.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878647 - AK STEEL CORP | WATER | WATER REPAIR & INSTALLATION | 2020-03-03 | 2020-06-30 | 2020-03-03 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1013912¦¦2020-03-31
UP | CJ | Yes | 1014075 |  | MOSAIC PLANT CITY DEEP WELL 4 | BRUGGER, CRAIG J. | 100% | 15237 | 0 | 15237 | 15237 | 15237 | 15237 | 0 | 0 | 15237 | 10461 | 0 | 10461 | 5527.62 | 2437.28 | 1232.93 |  | 1857.41 |  |  | 5527.62 | 2437.28 | 1232.93 |  | 1857.41 |  |  | 9709.38 | 0 | 52.84% |  | 0 | 5527.62 | 4776 | 31.34% | 0 | 4776 | 31.34% | 0 |  | 9709.38 | 63.72% | 9709.38 | 63.72% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895011 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2020-02-28 | 2020-03-31 | 2020-02-28 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 1014075¦¦2020-03-31
FP | CJ | Yes | 1014076 |  | ALCOA CHLORINATION | MIGUEL, SEAN J. | 100% | 13898.5 | 0 | 13898.5 | 13898.5 | 13898.5 | 13898.5 | 13898.5 | 0 | 13898.5 | 11888 | 0 | 11888 | 13124.08 | 6794.22 | 2097.96 |  | 4231.9 |  |  | 13124.08 | 6794.22 | 2097.96 |  | 4231.9 |  |  | 774.42 | 0 | 110.4% |  | 0 | 13124.08 | 2010.5 | 14.47% | 0 | 2010.5 | 14.47% | 0 |  | 774.42 | 5.572% | 774.42 | 5.572% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 879002 - ALCOA AGC WARRICK STATION | WATER | WATER REPAIR & INSTALLATION | 2020-03-04 | 2020-04-30 | 2020-03-04 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1014076¦¦2020-03-31
FP | CJ | Yes | 1014077 |  | ADM CLINTON IA 4 | HEALY, THOMAS P. | 100% | 148537 | 0 | 148537 | 139957.5 | 139957.5 | 139957.5 | 139957.5 | 0 | 139957.5 | 105000 | 0 | 105000 | 90531.28 | 40149.8 | 10112.51 |  | 40268.97 |  |  | 90531.28 | 40149.8 | 10112.51 |  | 40268.97 |  |  | 49426.22 | 0 | 86.22% |  | 0 | 90531.28 | 43537 | 29.31% | 0 | 43537 | 29.31% | 0 |  | 49426.22 | 35.32% | 49426.22 | 35.32% | 8579.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 878664 - ADM PROCESSING | WATER | WATER REPAIR & INSTALLATION | 2020-03-03 | 2020-05-31 | 2020-03-03 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1014077¦¦2020-03-31
TM | C | Yes | 1014080 |  | BIRDMAN FARMS LLC | SCHERM, LOGAN M | 100% | 15900 | 0 | 15900 | 16184.91 | 16184.91 | 16184.91 | 0 | 0 | 16184.91 | 13000 | 0 | 13000 | 17329.9 | 4505.14 | 3162.43 |  | 9662.33 |  |  | 17329.9 | 4505.14 | 3162.43 |  | 9662.33 |  |  | 0 | 1144.99 | 133.3% |  | 0 | 17329.9 | 2900 | 18.24% | 0 | 2900 | 18.24% | 0 |  | -1144.99 | -7.074% | -1144.99 | -7.074% | -284.91 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 1013776 - BIRDMAN FARMS LLC | WATER | WATER EQUIPMENT SALES | 2020-03-03 | 2020-06-03 | 2020-03-03 | 2020-06-03 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1014080¦¦2020-03-31
UP | CJ | Yes | 1014272 |  | RIPLEY TN WELL 3 | ANDERSON, STEPHEN P. | 100% | 76800 | 0 | 76800 | 69140 | 69140 | 69140 | 0 | 0 | 69140 | 57600 | 0 | 57600 | 44845.3 | 20789.43 | 6373.52 |  | 17682.35 |  |  | 44845.3 | 20789.43 | 6373.52 |  | 17682.35 |  |  | 24294.7 | 0 | 77.86% |  | 0 | 44845.3 | 19200 | 25% | 0 | 19200 | 25% | 0 |  | 24294.7 | 35.14% | 24294.7 | 35.14% | 7660 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 897057 - RIPLEY WATER & GAS | WATER | WATER REPAIR & INSTALLATION | 2020-03-04 | 2020-03-30 | 2020-03-04 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1014272¦¦2020-03-31
UP | CJ | Yes | 1014273 |  | VENTURA WATER NYE 7 EMERGENCY | SEIDEN, ANDREW L. | 100% | 6017 | 0 | 6017 | 20056.5 | 20056.5 | 6016.68 | 0 | 0 | 20056.5 | 4679 | 0 | 4679 | 22415.06 | 7830.97 | 3006.52 |  | 11577.57 |  |  | 22415.06 | 7830.97 | 3006.52 |  | 11577.57 |  |  | 0 | 2358.56 | 479.1% |  | 0 | 22415.06 | 1338 | 22.24% | 0 | 1338 | 22.24% | 0 |  | -2358.56 | -11.76% | -2358.56 | -11.76% | -14039.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 899600 - VENTURA, CA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-04 | 2020-03-30 | 2020-03-04 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1014273¦¦2020-03-31
TM | CJ | Yes | 1014711 |  | JTM TEST REPAIR LEAK | ABBOTT, GRANT D. | 100% | 6000 | 0 | 6000 | 9036 | 9036 | 9036 | 0 | 0 | 9036 | 4200 | 0 | 4200 | 6331.65 | 3647.2 | 1385.22 |  | 1299.23 |  |  | 6331.65 | 3647.2 | 1385.22 |  | 1299.23 |  |  | 2704.35 | 0 | 150.8% |  | 0 | 6331.65 | 1800 | 30% | 0 | 1800 | 30% | 0 |  | 2704.35 | 29.93% | 2704.35 | 29.93% | -3036 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 892957 - J T M | WATER | WATER REPAIR & INSTALLATION | 2020-03-05 | 2020-04-30 | 2020-03-05 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1014711¦¦2020-03-31
UP | CJ | Yes | 1014716 |  | SUEZ 99 REHAB | CROOK, CHARLES M | 100% | 74825 | 0 | 74825 | 615.46 | 615.46 | 0 | 0 | 0 | 615.46 | 59825 | 0 | 59825 | 497.23 | 284.59 |  |  | 212.64 |  |  | 497.23 | 284.59 |  |  | 212.64 |  |  | 118.23 | 0 | 0.8311% |  | 0 | 497.23 | 15000 | 20.05% | 0 | 15000 | 20.05% | 0 |  | 118.23 | 19.21% | 118.23 | 19.21% | 74209.54 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 898467 - SUEZ | WATER | WATER REPAIR & INSTALLATION | 2020-03-06 | 2020-07-20 | 2020-03-06 | 2020-07-20 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1014716¦¦2020-03-31
UP | CJ | Yes | 1014717 |  | GUASTI PARK POOL PUMP REPLACE | BRASHEAR, DAVID M |  | 22368 | 0 | 22368 |  |  | 0 | 0 | 0 |  | 15527 | 0 | 15527 | [20 empty] | 6841 | 30.58% | 0 | 6841 | 30.58% | 0 | [5 empty] | 22368 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 965066 - SAN BERNARDINO, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-06 | 2020-04-30 | 2020-03-06 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1014717¦¦2020-03-31
UP | CJ | Yes | 1014718 |  | GLEN HELEN WELL 3 MOTOR SBCSD | BRASHEAR, DAVID M | 100% | 9293 | 0 | 9293 | 9293.2 | 9293.2 | 9672.95 | 0 | 0 | 9293.2 | 6779 | 0 | 6779 | 6065.03 | 1394.54 | 236.05 |  | 4434.44 |  |  | 6065.03 | 1394.54 | 236.05 |  | 4434.44 |  |  | 3228.17 | 0 | 89.47% |  | 0 | 6065.03 | 2514 | 27.05% | 0 | 2514 | 27.05% | 0 |  | 3228.17 | 34.74% | 3228.17 | 34.74% | -0.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878787 - SAN BERNARDINO SPECIAL DISTRICT COUNTY | WATER | WATER REPAIR & INSTALLATION | 2020-03-05 | 2020-04-30 | 2020-03-05 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1014718¦¦2020-03-31
TM | CJ | Yes | 1014719 |  | HENSGENS SASH FARMS | SCHERM, LOGAN M | 100% | 18000 | 0 | 18000 | 2247.79 | 2247.79 | 0 | 0 | 0 | 2247.79 | 13000 | 0 | 13000 | 1815.98 | 833.58 | 275.48 |  | 706.92 |  |  | 1815.98 | 833.58 | 275.48 |  | 706.92 |  |  | 431.81 | 0 | 13.97% |  | 0 | 1815.98 | 5000 | 27.78% | 0 | 5000 | 27.78% | 0 |  | 431.81 | 19.21% | 431.81 | 19.21% | 15752.21 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892029 - HENSGENS, SARAH | WATER | WATER REPAIR & INSTALLATION | 2020-03-05 | 2020-03-06 | 2020-03-05 | 2020-03-06 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1014719¦¦2020-03-31
FP | C | Yes | 1014727 |  | MACON WELL 6 REHAB | WHITE, CATHLEEN R | 100% | 26668 | 0 | 26668 | 26668 | 26668 | 26668 | 26668 | 0 | 26668 | 4000 | 15529.4 | 19529.4 | 25139.52 | 13963.68 | 3375.77 |  | 7800.07 |  |  | 25139.52 | 13963.68 | 3375.77 |  | 7800.07 |  |  | 1528.48 | 0 | 128.7% |  | 0 | 25139.52 | 22668 | 85% | -15529.4 | 7138.6 | 26.77% | -15529.4 | -15529.4 | 1528.48 | 5.732% | 1528.48 | 5.732% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 894052 - MACON, IL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-06-30 | 2020-03-02 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1014727¦¦2020-03-31
FP | CJ | Yes | 1014728 |  | IP RIVERDALE SELMA AL PUMP | PARSLEY, TRISTAN S | 100% | 3875 | 0 | 3875 | 2090.69 | 2090.69 | 0 | 0 | 0 | 2090.69 | 1683 | 0 | 1683 | 1689.06 |  |  |  | 1689.06 |  |  | 1689.06 |  |  |  | 1689.06 |  |  | 401.63 | 0 | 100.4% |  | 0 | 1689.06 | 2192 | 56.57% | 0 | 2192 | 56.57% | 0 |  | 401.63 | 19.21% | 401.63 | 19.21% | 1784.31 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 878768 - INTERNATIONAL PAPER RIVERDALE | WATER | WATER SUPPLY | 2020-03-03 | 2020-03-31 | 2020-03-05 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1014728¦¦2020-03-31
FP | CJ | Yes | 1014729 |  | COOPER MARINE MOBILE IP | PARSLEY, TRISTAN S | 100% | 3650 | 0 | 3650 | 3650 | 3650 | 3650 | 0 | 0 | 3650 | 1920 | 0 | 1920 | 2307.03 | 825.79 | 468.1 |  | 1013.14 |  |  | 2307.03 | 825.79 | 468.1 |  | 1013.14 |  |  | 1342.97 | 0 | 120.2% |  | 0 | 2307.03 | 1730 | 47.4% | 0 | 1730 | 47.4% | 0 |  | 1342.97 | 36.79% | 1342.97 | 36.79% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 888961 - COOPER MARINE & TIMBERLANDS | WATER | WATER SUPPLY | 2020-03-03 | 2020-03-31 | 2020-03-03 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1014729¦¦2020-03-31
FP | CJ | Yes | 1015649 |  | NEW CUMBERLAND MOTOR | BARNES, MATTHEW D | 100% | 9472 | 0 | 9472 | 10128 | 10128 | 10128 | 0 | 0 | 10128 | 5683 | 0 | 5683 | 7480.14 | 2563.2 | 752.18 |  | 4164.76 |  |  | 7480.14 | 2563.2 | 752.18 |  | 4164.76 |  |  | 2647.86 | 0 | 131.6% |  | 0 | 7480.14 | 3789 | 40% | 0 | 3789 | 40% | 0 |  | 2647.86 | 26.14% | 2647.86 | 26.14% | -656 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 1014927 - NEW CUMBERLAND, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-06 | 2020-04-30 | 2020-03-06 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1015649¦¦2020-03-31
FP | CJ | Yes | 1015663 |  | KENT WELL 11 REHAB | BARNES, MATTHEW D | 100% | 26291 | 13394 | 39685 | 23491 | 23491 | 23491 | 0 | 0 | 23491 | 20218 | 10145 | 30363 | 17101.7 | 7657.41 | 4318.39 |  | 5125.9 |  |  | 17101.7 | 7657.41 | 4318.39 |  | 5125.9 |  |  | 6389.3 | 0 | 56.32% |  | 0 | 17101.7 | 6073 | 23.1% | 3249 | 9322 | 23.49% | 3249 | 3249 | 6389.3 | 27.2% | 6389.3 | 27.2% | 16194 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 893094 - KENT, OH, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-06 | 2020-04-30 | 2020-03-06 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1015663¦¦2020-03-31
TM | CJ | Yes | 1015679 |  | ZELLER REALTY TV WELL | ABBOTT, GRANT D. | 100% | 4800 | 0 | 4800 | 4300 | 4300 | 4300 | 4300 | 0 | 4300 | 3360 | 0 | 3360 | 1308.03 | 865.37 | 369.72 |  | 72.94 |  |  | 1308.03 | 865.37 | 369.72 |  | 72.94 |  |  | 2991.97 | 0 | 38.93% |  | 0 | 1308.03 | 1440 | 30% | 0 | 1440 | 30% | 0 |  | 2991.97 | 69.58% | 2991.97 | 69.58% | 500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 1015148 - ZELLER REALTY GROUP | WATER | WATER REPAIR & INSTALLATION | 2020-03-06 | 2020-04-30 | 2020-03-06 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1015679¦¦2020-03-31
FP | LJ | Yes | 1015770 |  | NJAW PFAS REMOVAL SYSTEM | MCCARTNEY, JEFFREY C | 33.18% | 1167000 | 0 | 1167000 | 387222.5591 | 233400 | 233400 | 233400 | 0 | 1167000 | 707447.91 | 0 | 707447.91 | 240162.22 | 11866.57 |  |  | 166529.14 | 61766.51 |  | 240162.22 | 11866.57 |  |  | 166529.14 | 61766.51 |  | 0 | 6762.22 | 33.95% |  | 483631.64 | 723793.86 | 459552.09 | 39.38% | 0 | 459552.09 | 39.38% | 0 |  | 147060.34 | 37.98% | 443206.14 | 37.98% | 779777.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 895316 - NEW JERSEY AMERICAN WATER | WATER | WATER TREATMENT | 2020-03-06 | 2020-07-31 | 2020-03-06 | 2020-07-31 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 1015770¦¦2020-03-31
UP | CJ | Yes | 1016131 |  | SARALAND FLOW TEST 3 WELLS | PARSLEY, TRISTAN S | 100% | 4250 | 0 | 4250 | 4250 | 4250 | 4250 | 0 | 0 | 4250 | 2776 | 0 | 2776 | 1702.88 | 663.47 | 294.18 |  | 745.23 |  |  | 1702.88 | 663.47 | 294.18 |  | 745.23 |  |  | 2547.12 | 0 | 61.34% |  | 0 | 1702.88 | 1474 | 34.68% | 0 | 1474 | 34.68% | 0 |  | 2547.12 | 59.93% | 2547.12 | 59.93% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 897504 - SARALAND WATER & SEWER BOARD | WATER | WATER SUPPLY | 2020-03-06 | 2020-04-30 | 2020-03-09 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1016131¦¦2020-03-31
UP | CJ | Yes | 1016132 |  | ONEONTA NY PRODUCTION WELLS | CROOK, CHARLES M | 100% | 312200 | 0 | 312200 | 766.45 | 766.45 | 0 | 0 | 0 | 766.45 | 248202 | 0 | 248202 | 619.21 | 552.61 |  |  | 66.6 |  |  | 619.21 | 552.61 |  |  | 66.6 |  |  | 147.24 | 0 | 0.2495% |  | 0 | 619.21 | 63998 | 20.5% | 0 | 63998 | 20.5% | 0 |  | 147.24 | 19.21% | 147.24 | 19.21% | 311433.55 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 1014144 - ONEONTA, TOWN OF | WATER | WATER SUPPLY | 2020-03-09 | 2020-12-20 | 2020-03-09 | 2020-12-20 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1016132¦¦2020-03-31
FP | CJ | Yes | 1016133 |  | WESTROCK 2020 PAINT STREET | GAMBLE, BRAD F. | 100% | 16360 | 0 | 16360 | 8180 | 8180 | 8180 | 8180 | 0 | 8180 | 11361 | 0 | 11361 | 998.83 | 984.75 |  |  | 14.08 |  |  | 998.83 | 984.75 |  |  | 14.08 |  |  | 7181.17 | 0 | 8.792% |  | 0 | 998.83 | 4999 | 30.56% | 0 | 4999 | 30.56% | 0 |  | 7181.17 | 87.79% | 7181.17 | 87.79% | 8180 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 593 - WRD COLLECTOR WELLS | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 900185 - WESTROCK SHARED SERVICES | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2021-03-01 | 2020-03-02 | 2021-03-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1016133¦¦2020-03-31
TM | CJ | Yes | 1016134 |  | BEARSKIN FARMS 2020 | SCHERM, LOGAN M | 100% | 18300 | 0 | 18300 | 7412.33 | 7412.33 | 7968.26 | 7968.26 | 0 | 7412.33 | 13725 | 0 | 13725 | 4956.03 | 783.59 | 267.48 |  | 3904.96 |  |  | 4956.03 | 783.59 | 267.48 |  | 3904.96 |  |  | 2456.3 | 0 | 36.11% |  | 0 | 4956.03 | 4575 | 25% | 0 | 4575 | 25% | 0 |  | 2456.3 | 33.14% | 2456.3 | 33.14% | 10887.67 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878874 - BEARSKIN FARMS | WATER | WATER EQUIPMENT SALES | 2020-03-06 | 2021-03-09 | 2020-03-06 | 2021-03-09 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1016134¦¦2020-03-31
UP | CJ | Yes | 1016135 |  | ADM WELL 9 PUMP REMOVAL | WHITE, CATHLEEN R | 100% | 10180 | 23332 | 33512 | 20752.21 | 20752.21 | 10180 | 10180 | 0 | 20752.21 | 7200 | 18177.42 | 25377.42 | 16765.6 | 6423.43 | 1023.83 |  | 9318.34 |  |  | 16765.6 | 6423.43 | 1023.83 |  | 9318.34 |  |  | 3986.61 | 0 | 66.07% |  | 0 | 16765.6 | 2980 | 29.27% | 5154.58 | 8134.58 | 24.27% | 5154.58 | 5154.58 | 3986.61 | 19.21% | 3986.61 | 19.21% | 12759.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 885915 - ADM QUINCY | WATER | WATER REPAIR & INSTALLATION | 2020-03-06 | 2020-06-30 | 2020-03-06 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1016135¦¦2020-03-31
TM | CJ | Yes | 1016136 |  | BLACK INC WS NEW WELL | SCHERM, LOGAN M | 100% | 38800 | 0 | 38800 | 13902.53 | 13902.53 | 0 | 0 | 0 | 13902.53 | 35000 | 0 | 35000 | 11231.78 | 2720.3 | 2 |  | 8199 | 310.48 |  | 11231.78 | 2720.3 | 2 |  | 8199 | 310.48 |  | 2670.75 | 0 | 32.09% |  | 0 | 11231.78 | 3800 | 9.794% | 0 | 3800 | 9.794% | 0 |  | 2670.75 | 19.21% | 2670.75 | 19.21% | 24897.47 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887160 - BLACK INC | WATER | WATER SUPPLY | 2020-03-06 | 2020-06-30 | 2020-03-06 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1016136¦¦2020-03-31
FP | CJ | Yes | 1016137 |  | MARATHON WELL 16 RENTAL PUMP | SEIDEN, ANDREW L. | 100% | 52600 | 0 | 52600 | 13220.69 | 13220.69 | 0 | 0 | 0 | 13220.69 | 39451 | 0 | 39451 | 10680.92 | 3103.62 | 148.4 |  | 2646.28 | 4782.62 |  | 10680.92 | 3103.62 | 148.4 |  | 2646.28 | 4782.62 |  | 2539.77 | 0 | 27.07% |  | 0 | 10680.92 | 13149 | 25% | 0 | 13149 | 25% | 0 |  | 2539.77 | 19.21% | 2539.77 | 19.21% | 39379.31 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 379884 - TESORO REFINING & MARKETING COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-03-10 | 2020-12-31 | 2020-03-10 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1016137¦¦2020-03-31
TM | CJ | Yes | 1016138 |  | MOMENTIVE CW 4 NORTH PUMP | BARNES, MATTHEW D | 100% | 42027 | 0 | 42027 | 18202 | 18202 | 18202 | 18202 | 0 | 18202 | 28216 | 0 | 28216 | 11779.02 | 7186.26 | 2555.59 |  | 2037.17 |  |  | 11779.02 | 7186.26 | 2555.59 |  | 2037.17 |  |  | 6422.98 | 0 | 41.75% |  | 0 | 11779.02 | 13811 | 32.86% | 0 | 13811 | 32.86% | 0 |  | 6422.98 | 35.29% | 6422.98 | 35.29% | 23825 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 894878 - MOMENTIVE PERFORMANCE MATERIALS | WATER | WATER REPAIR & INSTALLATION | 2020-03-09 | 2020-04-30 | 2020-03-09 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1016138¦¦2020-03-31
TM | C | Yes | 1016140 |  | HARDINSBURG PUMP 1 | MIGUEL, SEAN J. | 100% | 10000 | 0 | 10000 | 10480 | 10480 | 10480 | 3405 | 0 | 10480 | 8000 | 0 | 8000 | 6994 | 1180.32 | 749.8 |  | 5063.88 |  |  | 6994 | 1180.32 | 749.8 |  | 5063.88 |  |  | 3486 | 0 | 87.42% |  | 0 | 6994 | 2000 | 20% | 0 | 2000 | 20% | 0 |  | 3486 | 33.26% | 3486 | 33.26% | -480 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878784 - HARDINSBURG, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-09 | 2020-04-30 | 2020-03-09 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1016140¦¦2020-03-31
TM | CJ | Yes | 1016301 |  | A AND R FARMS TRUST WS | SCHERM, LOGAN M | 100% | 25262 | 0 | 25262 | 5057.62 | 5057.62 | 0 | 0 | 0 | 5057.62 | 21988 | 0 | 21988 | 4086.02 | 140.48 |  |  | 3945.54 |  |  | 4086.02 | 140.48 |  |  | 3945.54 |  |  | 971.6 | 0 | 18.58% |  | 0 | 4086.02 | 3274 | 12.96% | 0 | 3274 | 12.96% | 0 |  | 971.6 | 19.21% | 971.6 | 19.21% | 20204.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 886452 - A&R FARMS TRUST | WATER | WATER SUPPLY | 2020-03-10 | 2020-06-30 | 2020-03-10 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1016301¦¦2020-03-31
UP | CJ | Yes | 1016302 |  | THREE OAKS WWRP MIT FOR WSP | MARTINEZ, MIGUEL E |  | 23696 | 0 | 23696 |  |  | 0 | 0 | 0 |  | 16467 | 0 | 16467 | [20 empty] | 7229 | 30.51% | 0 | 7229 | 30.51% | 0 | [5 empty] | 23696 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 955325 - WSP USA INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-09 | 2020-05-01 | 2020-03-23 | 2020-05-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 1016302¦¦2020-03-31
FP | CJ | Yes | 1016507 |  | CITY OF HIALEAH MIT FOR JLA | MARTINEZ, MIGUEL E | 100% | 51000 | 0 | 51000 | 51000 | 51000 | 51000 | 51000 | 0 | 51000 | 34930 | 0 | 34930 | 9751.99 | 2979.79 | 5426.2 |  | 1346 |  |  | 9751.99 | 2979.79 | 5426.2 |  | 1346 |  |  | 41248.01 | 0 | 27.92% |  | 0 | 9751.99 | 16070 | 31.51% | 0 | 16070 | 31.51% | 0 |  | 41248.01 | 80.88% | 41248.01 | 80.88% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 892851 - JLA GEOSCIENCES INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-11 | 2020-06-01 | 2020-03-11 | 2020-06-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 1016507¦¦2020-03-31
FP | CJ | Yes | 1016806 |  | MARTIN MARIETTA RANDOLPH MINE | WARTICK, LOGAN M |  | 4135 | 0 | 4135 |  |  | 0 | 0 | 0 |  | 3100 | 0 | 3100 | [20 empty] | 1035 | 25.03% | 0 | 1035 | 25.03% | 0 | [5 empty] | 4135 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 1016406 - MARTIN MARIETTA MATERIALS | WATER | WATER SUPPLY | 2020-03-10 | 2020-07-01 | 2020-03-10 | 2020-07-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1016806¦¦2020-03-31
FP | C | Yes | 1016807 |  | P66 WELL NP 81 | WHITE, CATHLEEN R | 100% | 8930 | 18475.04 | 27405.04 | 27405.04 | 27405.04 | 27405.04 | 0 | 0 | 27405.04 | 6250 | 15488.41 | 21738.41 | 23557.19 | 11419.8 | 3858.51 |  | 8278.88 |  |  | 23557.19 | 11419.8 | 3858.51 |  | 8278.88 |  |  | 3847.85 | 0 | 108.4% |  | 0 | 23557.19 | 2680 | 30.01% | 2986.63 | 5666.63 | 20.68% | 2986.63 | 2986.63 | 3847.85 | 14.04% | 3847.85 | 14.04% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896286 - PHILLIPS 66 WOOD RIVER REFINERY | WATER | WATER REPAIR & INSTALLATION | 2020-03-11 | 2020-06-30 | 2020-03-11 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1016807¦¦2020-03-31
TM | CJ | Yes | 1016864 |  | SINCLAIR BLDG 12 MOTOR | ABBOTT, GRANT D. | 100% | 4000 | 5920 | 9920 | 9920 | 9920 | 0 | 0 | 0 | 9920 | 2800 | 3955.78 | 6755.78 | 11199.54 | 3059.22 | 1114.41 |  | 775.91 | 6250 |  | 11199.54 | 3059.22 | 1114.41 |  | 775.91 | 6250 |  | 0 | 1279.54 | 165.8% |  | 0 | 11199.54 | 1200 | 30% | 1964.22 | 3164.22 | 31.9% | 1964.22 | 1964.22 | -1279.54 | -12.9% | -1279.54 | -12.9% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 897874 - SINCLAIR COLLEGE | WATER | WATER REPAIR & INSTALLATION | 2020-03-11 | 2020-04-30 | 2020-03-11 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1016864¦¦2020-03-31
UP | CJ | Yes | 1016865 |  | NORTHBROOK IL PUMP 9 | KENNEDY, CHRISTOPHER C. | 100% | 115000 | 0 | 115000 | 2144.87 | 2144.87 | 0 | 0 | 0 | 2144.87 | 92000 | 0 | 92000 | 1732.83 | 1285.39 | 94.92 |  | 352.52 |  |  | 1732.83 | 1285.39 | 94.92 |  | 352.52 |  |  | 412.04 | 0 | 1.884% |  | 0 | 1732.83 | 23000 | 20% | 0 | 23000 | 20% | 0 |  | 412.04 | 19.21% | 412.04 | 19.21% | 112855.13 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 1016699 - VILLAGE OF NORTHBROOK ILLINOIS | WATER | WATER REPAIR & INSTALLATION | 2020-03-11 | 2020-08-05 | 2020-03-11 | 2020-08-05 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1016865¦¦2020-03-31
FP | C | Yes | 1017062 |  | TETRA TECH METER | ABBOTT, GRANT D. | 100% | 1200 | 0 | 1200 | 1200 | 1200 | 1200 | 0 | 0 | 1200 | 840 | 0 | 840 | 501.17 | 242.39 | 133.5 |  | 125.28 |  |  | 501.17 | 242.39 | 133.5 |  | 125.28 |  |  | 698.83 | 0 | 59.66% |  | 0 | 501.17 | 360 | 30% | 0 | 360 | 30% | 0 |  | 698.83 | 58.24% | 698.83 | 58.24% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 1017220 - TETRA TECH INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-11 | 2020-04-30 | 2020-03-11 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017062¦¦2020-03-31
UP | CJ | Yes | 1017066 |  | CADIZ WELL 34 | BRASHEAR, DAVID M | 100% | 329632 | 0 | 329632 | 197870.53 | 197870.53 | 120491.96 | 120491.96 | 0 | 197870.53 | 258468 | 0 | 258468 | 159858.52 | 1302.44 | 672.87 |  | 157883.21 |  |  | 159858.52 | 1302.44 | 672.87 |  | 157883.21 |  |  | 38012.01 | 0 | 61.85% |  | 0 | 159858.52 | 71164 | 21.59% | 0 | 71164 | 21.59% | 0 |  | 38012.01 | 19.21% | 38012.01 | 19.21% | 131761.47 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 887709 - CADIZ INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-01 | 2020-06-30 | 2020-03-01 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1017066¦¦2020-03-31
UP | CJ | Yes | 1017067 |  | OTEGO NY NEW PUMP | CROOK, CHARLES M | 100% | 15900 | 0 | 15900 | 275.13 | 275.13 | 0 | 0 | 0 | 275.13 | 11900 | 0 | 11900 | 222.28 | 219.11 |  |  | 3.17 |  |  | 222.28 | 219.11 |  |  | 3.17 |  |  | 52.85 | 0 | 1.868% |  | 0 | 222.28 | 4000 | 25.16% | 0 | 4000 | 25.16% | 0 |  | 52.85 | 19.21% | 52.85 | 19.21% | 15624.87 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 895892 - OTEGO, NY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-12 | 2020-04-20 | 2020-03-12 | 2020-04-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1017067¦¦2020-03-31
UP | CJ | Yes | 1017074 |  | JEFFERSON DAVIS 4 TEST 3 WELLS | GNAU, CASEY T | 100% | 2400 | 0 | 2400 | 2400 | 2400 | 2400 | 2400 | 0 | 2400 | 1600 | 0 | 1600 | 791.78 | 428.78 | 185.5 |  | 177.5 |  |  | 791.78 | 428.78 | 185.5 |  | 177.5 |  |  | 1608.22 | 0 | 49.49% |  | 0 | 791.78 | 800 | 33.33% | 0 | 800 | 33.33% | 0 |  | 1608.22 | 67.01% | 1608.22 | 67.01% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 892776 - JEFFERSON DAVIS WWD 4 | WATER | WATER REPAIR & INSTALLATION | 2020-03-12 | 2020-03-31 | 2020-03-12 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1017074¦¦2020-03-31
FP | CJ | Yes | 1017075 |  | ALLSTATE BOOSTER 4 | KENNEDY, CHRISTOPHER C. | 100% | 6370 | 17028 | 23398 | 4953 | 4953 | 4953 | 4953 | 0 | 4953 | 4760 | 11631.92 | 16391.92 | 3632.42 | 2659.05 | 217.97 |  | 755.4 |  |  | 3632.42 | 2659.05 | 217.97 |  | 755.4 |  |  | 1320.58 | 0 | 22.16% |  | 0 | 3632.42 | 1610 | 25.27% | 5396.08 | 7006.08 | 29.94% | 5396.08 | 5396.08 | 1320.58 | 26.66% | 1320.58 | 26.66% | 18445 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 886118 - ALLSTATE INSURANCE COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-03-12 | 2020-05-20 | 2020-03-12 | 2020-05-20 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017075¦¦2020-03-31
FP | CJ | Yes | 1017080 |  | EARTH CITY LEVEE MOTOR INSTALL | WHITE, CATHLEEN R | 100% | 39960 | 0 | 39960 | 100.83 | 100.83 | 0 | 0 | 0 | 100.83 | 28000 | 0 | 28000 | 81.46 | 46.22 |  |  | 35.24 |  |  | 81.46 | 46.22 |  |  | 35.24 |  |  | 19.37 | 0 | 0.2909% |  | 0 | 81.46 | 11960 | 29.93% | 0 | 11960 | 29.93% | 0 |  | 19.37 | 19.21% | 19.37 | 19.21% | 39859.17 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878960 - EARTH CITY LEVEE DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-03-05 | 2020-06-30 | 2020-03-05 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1017080¦¦2020-03-31
UP | CJ | Yes | 1017321 |  | AQUA IL NUNDA WELL 1 | HEALY, THOMAS P. | 100% | 37042 | 0 | 37042 | 491.62 | 491.62 | 0 | 0 | 0 | 491.62 | 26000 | 0 | 26000 | 397.18 | 274.18 | 47.46 |  | 75.54 |  |  | 397.18 | 274.18 | 47.46 |  | 75.54 |  |  | 94.44 | 0 | 1.528% |  | 0 | 397.18 | 11042 | 29.81% | 0 | 11042 | 29.81% | 0 |  | 94.44 | 19.21% | 94.44 | 19.21% | 36550.38 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 886378 - AQUA ILLINOIS KANKAKEE | WATER | WATER REPAIR & INSTALLATION | 2020-03-12 | 2020-04-30 | 2020-03-12 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017321¦¦2020-03-31
FP | CJ | Yes | 1017323 |  | ENTERGY 9MILE POINT WELL2MOTOR | GREGORY, CRYSTAL N |  | 21000 | 0 | 21000 |  |  | 0 | 0 | 0 |  | 14177 | 0 | 14177 | [20 empty] | 6823 | 32.49% | 0 | 6823 | 32.49% | 0 | [5 empty] | 21000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 890291 - ENTERGY LOUISIANA, LLC WESTWEGO, LA | WATER | WATER EQUIPMENT SALES | 2020-03-11 | 2020-05-30 | 2020-03-11 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017323¦¦2020-03-31
FP | CJ | Yes | 1017324 |  | BRW LULA AND LAFAYETTE | GREGORY, CRYSTAL N | 100% | 3950 | 0 | 3950 | 1585.03 | 1585.03 | 0 | 0 | 0 | 1585.03 | 2980 | 0 | 2980 | 1280.54 | 684.14 | 254.58 |  | 341.82 |  |  | 1280.54 | 684.14 | 254.58 |  | 341.82 |  |  | 304.49 | 0 | 42.97% |  | 0 | 1280.54 | 970 | 24.56% | 0 | 970 | 24.56% | 0 |  | 304.49 | 19.21% | 304.49 | 19.21% | 2364.97 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878599 - BATON ROUGE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-03-13 | 2020-04-30 | 2020-03-13 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017324¦¦2020-03-31
UP | CJ | Yes | 1017325 |  | HARRISON STEEL PWM | MIGUEL, SEAN J. |  | 1950 | 0 | 1950 |  |  | 0 | 0 | 0 |  | 1655 | 0 | 1655 | [20 empty] | 295 | 15.13% | 0 | 295 | 15.13% | 0 | [5 empty] | 1950 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878983 - HARRISON STEEL CASTINGS COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-03-11 | 2020-04-30 | 2020-03-11 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017325¦¦2020-03-31
TM | CJ | Yes | 1017326 |  | DANISCO WELL 2 | MIGUEL, SEAN J. | 100% | 10500 | 0 | 10500 | 4950.96 | 4950.96 | 0 | 0 | 0 | 4950.96 | 7350 | 0 | 7350 | 3999.85 | 2459.26 | 682.98 |  | 857.61 |  |  | 3999.85 | 2459.26 | 682.98 |  | 857.61 |  |  | 951.11 | 0 | 54.42% |  | 0 | 3999.85 | 3150 | 30% | 0 | 3150 | 30% | 0 |  | 951.11 | 19.21% | 951.11 | 19.21% | 5549.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 889311 - DANISCO USA | WATER | WATER REPAIR & INSTALLATION | 2020-03-11 | 2020-04-30 | 2020-03-11 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017326¦¦2020-03-31
UP | CJ | Yes | 1017327 |  | BRANDENBURG TESTS | MIGUEL, SEAN J. |  | 850 | 0 | 850 |  |  | 0 | 0 | 0 |  | 650 | 0 | 650 | [20 empty] | 200 | 23.53% | 0 | 200 | 23.53% | 0 | [5 empty] | 850 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 887377 - BRANDENBURG, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-06 | 2020-04-30 | 2020-03-06 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1017327¦¦2020-03-31
FP | CJ | Yes | 1017328 |  | PRINCETON 9 REHAB | MIGUEL, SEAN J. | 100% | 19450 | 9212 | 28662 | 12320.22 | 12320.22 | 0 | 0 | 0 | 12320.22 | 14288 | 6909 | 21197 | 9953.44 | 3990.33 | 1707.78 |  | 4255.33 |  |  | 9953.44 | 3990.33 | 1707.78 |  | 4255.33 |  |  | 2366.78 | 0 | 46.96% |  | 0 | 9953.44 | 5162 | 26.54% | 2303 | 7465 | 26.04% | 2303 | 2303 | 2366.78 | 19.21% | 2366.78 | 19.21% | 16341.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 896586 - PRINCETON, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-13 | 2020-04-30 | 2020-03-13 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1017328¦¦2020-03-31
UP | C | Yes | 1017416 |  | CAROL STREAM IL 6 | HEALY, THOMAS P. | 100% | 1000 | 0 | 1000 | 934.45 | 934.45 | 0 | 0 | 0 | 934.45 | 750 | 0 | 750 | 754.94 | 586.26 | 55.37 |  | 113.31 |  |  | 754.94 | 586.26 | 55.37 |  | 113.31 |  |  | 179.51 | 0 | 100.7% |  | 0 | 754.94 | 250 | 25% | 0 | 250 | 25% | 0 |  | 179.51 | 19.21% | 179.51 | 19.21% | 65.55 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 1017318 - VILLAGE OF CAROL STREAM | WATER | WATER REPAIR & INSTALLATION | 2020-03-12 | 2020-03-31 | 2020-03-12 | 2020-03-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1017416¦¦2020-03-31
FP | CJ | Yes | 1017984 |  | LEBANON MEDIA REPLACEMENT | WILLIAMS, DONALD G. |  | 57200 | 0 | 57200 |  |  | 0 | 0 | 0 |  | 42778 | 0 | 42778 | [20 empty] | 14422 | 25.21% | 0 | 14422 | 25.21% | 0 | [5 empty] | 57200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 1017313 - LEBANON UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2020-03-10 | 2020-05-31 | 2020-03-10 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1017984¦¦2020-03-31
UP | C | Yes | 1017986 |  | STEEL TECHNOLOGIES TESTS | MIGUEL, SEAN J. | 100% | 1200 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 0 | 1200 | 1000 | 0 | 1000 | 713.49 | 324.29 | 222.16 |  | 167.04 |  |  | 713.49 | 324.29 | 222.16 |  | 167.04 |  |  | 486.51 | 0 | 71.35% |  | 0 | 713.49 | 200 | 16.67% | 0 | 200 | 16.67% | 0 |  | 486.51 | 40.54% | 486.51 | 40.54% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 910925 - STEEL TECHNOLOGIES | WATER | WATER REPAIR & INSTALLATION | 2020-03-13 | 2020-04-30 | 2020-03-13 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017986¦¦2020-03-31
UP | CJ | Yes | 1017987 |  | MONTICELLO IL WELL 2 REHAB | HEALY, THOMAS P. |  | 16450 | 0 | 16450 |  |  | 0 | 0 | 0 |  | 12000 | 0 | 12000 | [20 empty] | 4450 | 27.05% | 0 | 4450 | 27.05% | 0 | [5 empty] | 16450 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 878751 - MONTICELLO, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-13 | 2020-05-23 | 2020-03-13 | 2020-05-23 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1017987¦¦2020-03-31
TM | C | Yes | 1017988 |  | PARKERS CHAPEL WATER WELL 1 TV | SCHERM, LOGAN M | 100% | 24000 | 0 | 24000 | 22501.14 | 22501.14 | 24413.73 | 0 | 0 | 22501.14 | 16800 | 0 | 16800 | 17339.54 | 8394.88 | 3355.75 |  | 5588.91 |  |  | 17339.54 | 8394.88 | 3355.75 |  | 5588.91 |  |  | 5161.6 | 0 | 103.2% |  | 0 | 17339.54 | 7200 | 30% | 0 | 7200 | 30% | 0 |  | 5161.6 | 22.94% | 5161.6 | 22.94% | 1498.86 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 896039 - PARKERS CHAPEL WATER ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2020-03-16 | 2020-07-28 | 2020-03-16 | 2020-07-28 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1017988¦¦2020-03-31
FP | CJ | Yes | 1017989 |  | JOLIET IL GRAVEL WELL 105 | EISHA, JOSEPH J. | 100% | 2990 | 21996 | 24986 | 9397.9 | 9397.9 | 2900 | 0 | 0 | 9397.9 | 2000 | 15015.4 | 17015.4 | 7592.51 | 3761.61 | 987.65 |  | 2843.25 |  |  | 7592.51 | 3761.61 | 987.65 |  | 2843.25 |  |  | 1805.39 | 0 | 44.62% |  | 0 | 7592.51 | 990 | 33.11% | 6980.6 | 7970.6 | 31.9% | 6980.6 | 6980.6 | 1805.39 | 19.21% | 1805.39 | 19.21% | 15588.1 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 878985 - JOLIET, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-18 | 2020-05-18 | 2020-03-18 | 2020-05-18 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1017989¦¦2020-03-31
UP | CJ | Yes | 1017990 |  | INDIAN WELLS WELL 34 PUMP | BRASHEAR, DAVID M |  | 9998 | 0 | 9998 |  |  | 0 | 0 | 0 |  | 7533 | 0 | 7533 | [20 empty] | 2465 | 24.65% | 0 | 2465 | 24.65% | 0 | [5 empty] | 9998 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892526 - INDIAN WELLS VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-03-16 | 2020-04-30 | 2020-03-16 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1017990¦¦2020-03-31
UP | CJ | Yes | 1017991 |  | WALMART DIST PALESTINE | ALBARADO, JORDAN A | 100% | 20000 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 20000 | 10000 | 0 | 10000 | 20782.14 | 6229.31 | 2184.79 |  | 12368.04 |  |  | 20782.14 | 6229.31 | 2184.79 |  | 12368.04 |  |  | 0 | 782.14 | 207.8% |  | 0 | 20782.14 | 10000 | 50% | 0 | 10000 | 50% | 0 |  | -782.14 | -3.911% | -782.14 | -3.911% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 899808 - WALMART DISTRIBUTION CENTER | WATER | WATER REPAIR & INSTALLATION | 2020-03-17 | 2020-03-30 | 2020-03-17 | 2020-03-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1017991¦¦2020-03-31
UP | CJ | Yes | 1018005 |  | TERRACON HWY 18 CUSHENBURY GRV | COMBS, TAYLOR E. | 100% | 14580 | 0 | 14580 | 8700 | 8700 | 8700 | 8700 | 0 | 8700 | 11599 | 0 | 11599 | 7649.87 | 2993.51 | 3051.75 |  | 1604.61 |  |  | 7649.87 | 2993.51 | 3051.75 |  | 1604.61 |  |  | 1050.13 | 0 | 65.95% |  | 0 | 7649.87 | 2981 | 20.45% | 0 | 2981 | 20.45% | 0 |  | 1050.13 | 12.07% | 1050.13 | 12.07% | 5880 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 898731 - TERRACON | WATER | WATER SPECIALTY DRILLING | 2020-03-16 | 2020-03-31 | 2020-03-16 | 2020-03-31 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 1018005¦¦2020-03-31
FP | CJ | Yes | 1018006 |  | SUEZ HYANNIS MA AST INSPECTION | RANFT, DONALD R | 100% | 3325 | 0 | 3325 | 1020.5 | 1020.5 | 0 | 0 | 0 | 1020.5 | 2150 | 0 | 2150 | 824.46 | 471.2 |  |  | 353.26 |  |  | 824.46 | 471.2 |  |  | 353.26 |  |  | 196.04 | 0 | 38.35% |  | 0 | 824.46 | 1175 | 35.34% | 0 | 1175 | 35.34% | 0 |  | 196.04 | 19.21% | 196.04 | 19.21% | 2304.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 878992 - SUEZ | WATER | WATER TREATMENT | 2020-03-13 | 2020-04-30 | 2020-03-13 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 1018006¦¦2020-03-31
UP | CJ | Yes | 1018240 |  | GERDAU PWM TESTING | ANDERSON, STEPHEN P. |  | 1000 | 0 | 1000 |  |  | 0 | 0 | 0 |  | 840 | 0 | 840 | [20 empty] | 160 | 16% | 0 | 160 | 16% | 0 | [5 empty] | 1000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 891221 - GERDAU AMERISTEEL | WATER | WATER REPAIR & INSTALLATION | 2020-03-16 | 2020-04-20 | 2020-03-16 | 2020-04-20 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1018240¦¦2020-03-31
FP | CJ | Yes | 1018242 |  | EVERGY JEFFREY ENERGY STMARY24 | WARTICK, LOGAN M | 100% | 29628 | 0 | 29628 | 27128 | 27128 | 27128 | 0 | 0 | 27128 | 20740 | 0 | 20740 | 21057.42 | 10183.88 | 4712.8 |  | 6160.74 |  |  | 21057.42 | 10183.88 | 4712.8 |  | 6160.74 |  |  | 6070.58 | 0 | 101.5% |  | 0 | 21057.42 | 8888 | 30% | 0 | 8888 | 30% | 0 |  | 6070.58 | 22.38% | 6070.58 | 22.38% | 2500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 879035 - WESTAR ENERGY JEFFREY ENERGY CENTER | WATER | WATER REPAIR & INSTALLATION | 2020-03-17 | 2020-04-30 | 2020-03-17 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1018242¦¦2020-03-31
TM | CJ | Yes | 1018243 |  | BRIAN ENGELKES PIPE | SCHERM, LOGAN M | 100% | 20305 | 0 | 20305 | 176.71 | 176.71 | 0 | 0 | 0 | 176.71 | 15000 | 0 | 15000 | 142.76 |  |  |  |  | 142.76 |  | 142.76 |  |  |  |  | 142.76 |  | 33.95 | 0 | 0.9517% |  | 0 | 142.76 | 5305 | 26.13% | 0 | 5305 | 26.13% | 0 |  | 33.95 | 19.21% | 33.95 | 19.21% | 20128.29 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 890259 - ENGELKES, BRIAN | WATER | WATER EQUIPMENT SALES | 2020-03-17 | 2020-06-30 | 2020-03-17 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 1018243¦¦2020-03-31
UP | CJ | Yes | 1018244 |  | CHENANGO NY NORTHGATE WELL | CROOK, CHARLES M | 100% | 7905 | 0 | 7905 | 7905 | 7905 | 7905 | 0 | 0 | 7905 | 5405 | 0 | 5405 | 4636.12 | 3319.42 | 551.24 |  | 765.46 |  |  | 4636.12 | 3319.42 | 551.24 |  | 765.46 |  |  | 3268.88 | 0 | 85.77% |  | 0 | 4636.12 | 2500 | 31.63% | 0 | 2500 | 31.63% | 0 |  | 3268.88 | 41.35% | 3268.88 | 41.35% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 888290 - CHENANGO, NY, TOWN OF | WATER | WATER SUPPLY | 2020-03-18 | 2020-03-20 | 2020-03-18 | 2020-03-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1018244¦¦2020-03-31
UP | CJ | Yes | 1018466 |  | TERRACON GRAVEL UPLAND CA | COMBS, TAYLOR E. | 100% | 44348 | 0 | 44348 | 48579 | 48579 | 48579 | 48579 | 0 | 48579 | 31440 | 0 | 31440 | 27876.43 | 11638.34 | 9543.79 |  | 6694.3 |  |  | 27876.43 | 11638.34 | 9543.79 |  | 6694.3 |  |  | 20702.57 | 0 | 88.67% |  | 0 | 27876.43 | 12908 | 29.11% | 0 | 12908 | 29.11% | 0 |  | 20702.57 | 42.62% | 20702.57 | 42.62% | -4231 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 898731 - TERRACON | WATER | WATER REPAIR & INSTALLATION | 2020-03-17 | 2020-04-01 | 2020-03-17 | 2020-05-01 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 1018466¦¦2020-03-31
FP | CJ | Yes | 1018473 |  | IP CANTONMENT PULL SPRAY PUMP | PARSLEY, TRISTAN S | 100% | 4400 | 0 | 4400 | 4400 | 4400 | 4400 | 4400 | 0 | 4400 | 2683 | 0 | 2683 | 4539.58 | 2014.36 | 723.5 |  | 1801.72 |  |  | 4539.58 | 2014.36 | 723.5 |  | 1801.72 |  |  | 0 | 139.58 | 169.2% |  | 0 | 4539.58 | 1717 | 39.02% | 0 | 1717 | 39.02% | 0 |  | -139.58 | -3.172% | -139.58 | -3.172% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 879056 - INTERNATIONAL PAPER CANTONMENT | WATER | WATER SUPPLY | 2020-03-03 | 2020-04-30 | 2020-03-03 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1018473¦¦2020-03-31
FP | CJ | Yes | 1018474 |  | OMEGA TEST | GNAU, CASEY T | 100% | 2000 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 2000 | 1000 | 0 | 1000 | 1180.61 | 730.47 | 148.4 |  | 301.74 |  |  | 1180.61 | 730.47 | 148.4 |  | 301.74 |  |  | 819.39 | 0 | 118.1% |  | 0 | 1180.61 | 1000 | 50% | 0 | 1000 | 50% | 0 |  | 819.39 | 40.97% | 819.39 | 40.97% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 895786 - OMEGA PROTEIN ABBEVILLE | WATER | WATER REPAIR & INSTALLATION | 2020-03-18 | 2020-04-30 | 2020-03-18 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1018474¦¦2020-03-31
UP | CJ | Yes | 1018475 |  | WATER SERVICES CLINTON KY HSP | ANDERSON, STEPHEN P. | 100% | 1120 | 0 | 1120 | 1120 | 1120 | 1120 | 0 | 0 | 1120 | 840 | 0 | 840 | 821.11 | 378.08 | 166.95 |  | 276.08 |  |  | 821.11 | 378.08 | 166.95 |  | 276.08 |  |  | 298.89 | 0 | 97.75% |  | 0 | 821.11 | 280 | 25% | 0 | 280 | 25% | 0 |  | 298.89 | 26.69% | 298.89 | 26.69% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 899921 - WATER SERVICE CORP OF KENTUCKY | WATER | WATER REPAIR & INSTALLATION | 2020-03-18 | 2020-03-30 | 2020-03-18 | 2020-03-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1018475¦¦2020-03-31
UP | CJ | Yes | 1018476 |  | GSW CALIPATRIA D WELL | GRACE, GARY L. | 100% | 5615 | 0 | 5615 | 4742.36 | 4742.36 | 0 | 0 | 0 | 4742.36 | 4435 | 0 | 4435 | 3831.33 | 1505.1 | 1205.32 |  | 1120.91 |  |  | 3831.33 | 1505.1 | 1205.32 |  | 1120.91 |  |  | 911.03 | 0 | 86.39% |  | 0 | 3831.33 | 1180 | 21.02% | 0 | 1180 | 21.02% | 0 |  | 911.03 | 19.21% | 911.03 | 19.21% | 872.64 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878770 - GOLDEN STATE WATER COMPANY CALIPATRIA | WATER | WATER REPAIR & INSTALLATION | 2020-03-18 | 2020-04-25 | 2020-03-18 | 2020-04-25 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1018476¦¦2020-03-31
UP | CJ | Yes | 1018477 |  | EVONIK THEODORE AL PULL PUMP | PARSLEY, TRISTAN S | 100% | 13550 | 84440 | 97990 | 13550 | 13550 | 13550 | 13550 | 0 | 13550 | 9050 | 60960.15 | 70010.15 | 7221.62 | 2612.09 | 757.63 |  | 3851.9 |  |  | 7221.62 | 2612.09 | 757.63 |  | 3851.9 |  |  | 6328.38 | 0 | 10.32% |  | 0 | 7221.62 | 4500 | 33.21% | 23479.85 | 27979.85 | 28.55% | 23479.85 | 23479.85 | 6328.38 | 46.7% | 6328.38 | 46.7% | 84440 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 890484 - EVONIK DEGUSSA CORPORATION | WATER | WATER SUPPLY | 2020-03-16 | 2020-04-30 | 2020-03-17 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1018477¦¦2020-03-31
UP | CJ | Yes | 1018528 |  | BROKAW NURSERY CL2 TREATMENT | SEIDEN, ANDREW L. | 100% | 4794 | 0 | 4794 | 4794.67 | 4794.67 | 4794.67 | 4794.67 | 0 | 4794.67 | 3698 | 0 | 3698 | 3216.19 | 1650.67 | 338.26 |  | 1227.26 |  |  | 3216.19 | 1650.67 | 338.26 |  | 1227.26 |  |  | 1578.48 | 0 | 86.97% |  | 0 | 3216.19 | 1096 | 22.86% | 0 | 1096 | 22.86% | 0 |  | 1578.48 | 32.92% | 1578.48 | 32.92% | -0.67 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1018483 - BROKAW NURSERY | WATER | WATER REPAIR & INSTALLATION | 2020-03-17 | 2020-12-30 | 2020-03-17 | 2020-12-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1018528¦¦2020-03-31
UP | CJ | Yes | 1018529 |  | LODERS CROKLAAN BACKUP PUMP | EISHA, JOSEPH J. |  | 123200 | 0 | 123200 |  |  | 0 | 0 | 0 |  | 74000 | 0 | 74000 | [20 empty] | 49200 | 39.94% | 0 | 49200 | 39.94% | 0 | [5 empty] | 123200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 878807 - LODERS CROKLAAN | WATER | WATER REPAIR & INSTALLATION | 2020-03-19 | 2020-10-23 | 2020-03-19 | 2020-10-23 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1018529¦¦2020-03-31
UP | CJ | Yes | 1018532 |  | WICHITA KS H AND E 2020 EXTRAC | WARTICK, LOGAN M | 100% | 362980 | 0 | 362980 | 5281.73 | 5281.73 | 0 | 0 | 0 | 5281.73 | 283030 | 0 | 283030 | 4267.08 |  |  |  | 4267.08 |  |  | 4267.08 |  |  |  | 4267.08 |  |  | 1014.65 | 0 | 1.508% |  | 0 | 4267.08 | 79950 | 22.03% | 0 | 79950 | 22.03% | 0 |  | 1014.65 | 19.21% | 1014.65 | 19.21% | 357698.27 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA | 900295 - WICHITA DEPT HEALTH & ENVIRO | WATER | WATER SUPPLY | 2020-03-19 | 2020-06-30 | 2020-03-19 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1018532¦¦2020-03-31
FP | CJ | Yes | 1018727 |  | NORFOLK NE WELL 4 LINER | GANSEBOM, JASON W. |  | 71750 | 0 | 71750 |  |  | 0 | 0 | 0 |  | 55965 | 0 | 55965 | [20 empty] | 15785 | 22% | 0 | 15785 | 22% | 0 | [5 empty] | 71750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 879054 - NORFOLK, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-02 | 2020-07-31 | 2020-03-02 | 2020-07-31 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 1018727¦¦2020-03-31
TM | C | Yes | 1018748 |  | PEAVINE FARMING CO | SCHERM, LOGAN M | 100% | 20000 | 0 | 20000 | 20000 | 20000 | 20000 | 0 | 0 | 20000 | 16000 | 0 | 16000 | 19821.87 | 5036.23 | 3608.27 |  | 11177.37 |  |  | 19821.87 | 5036.23 | 3608.27 |  | 11177.37 |  |  | 178.13 | 0 | 123.9% |  | 0 | 19821.87 | 4000 | 20% | 0 | 4000 | 20% | 0 |  | 178.13 | 0.8906% | 178.13 | 0.8906% | 0 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 879069 - PEAVINE FARMING COMPANY | WATER | WATER SUPPLY | 2020-03-19 | 2021-03-19 | 2020-03-19 | 2021-03-19 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1018748¦¦2020-03-31
UP | CJ | Yes | 1018749 |  | ACS TINKER AFB REHAB 4 WELLS | EVANS, TRAVIS L | 100% | 100982 | 0 | 100982 | 22064.23 | 22064.23 | 0 | 0 | 0 | 22064.23 | 58356 | 0 | 58356 | 17825.57 | 8734.84 | 4615.28 |  | 4475.45 |  |  | 17825.57 | 8734.84 | 4615.28 |  | 4475.45 |  |  | 4238.66 | 0 | 30.55% |  | 0 | 17825.57 | 42626 | 42.21% | 0 | 42626 | 42.21% | 0 |  | 4238.66 | 19.21% | 4238.66 | 19.21% | 78917.77 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 885921 - ADVANCED CONSTRUCTION SERVICES INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-20 | 2020-12-13 | 2020-03-20 | 2020-12-13 | SUBCONTRACTOR | PUBLIC | DESIGN/BUILD | 1018749¦¦2020-03-31
FP | CJ | Yes | 1018750 |  | COCA COLA BR RI AND TESTING | LOPEZ-VASQUEZ, JUAN C. |  | 31872 | 0 | 31872 |  |  | 0 | 0 | 0 |  | 21246 | 0 | 21246 | [20 empty] | 10626 | 33.34% | 0 | 10626 | 33.34% | 0 | [5 empty] | 31872 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 1018664 - COCA COLA BOTTLING COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-03-18 | 2020-06-30 | 2020-03-18 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1018750¦¦2020-03-31
FP | CJ | Yes | 1020184 |  | MONROVIA WELL 6 TROUBLESHOOT | GRACE, GARY L. | 100% | 1900 | 0 | 1900 | 885.6 | 885.6 | 0 | 0 | 0 | 885.6 | 1398 | 0 | 1398 | 715.47 | 455.55 |  |  | 259.92 |  |  | 715.47 | 455.55 |  |  | 259.92 |  |  | 170.13 | 0 | 51.18% |  | 0 | 715.47 | 502 | 26.42% | 0 | 502 | 26.42% | 0 |  | 170.13 | 19.21% | 170.13 | 19.21% | 1014.4 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879074 - MONROVIA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-20 | 2020-03-27 | 2020-03-20 | 2020-03-27 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1020184¦¦2020-03-31
UP | CJ | Yes | 1020185 |  | CITY OF CHANDLER COLT RECIRC | VAN ALLEN, WESLEY C. | 100% | 3150 | 0 | 3150 | 2793.51 | 2793.51 | 0 | 0 | 0 | 2793.51 | 2511 | 0 | 2511 | 2256.86 | 1229.91 | 264.35 |  | 762.6 |  |  | 2256.86 | 1229.91 | 264.35 |  | 762.6 |  |  | 536.65 | 0 | 89.88% |  | 0 | 2256.86 | 639 | 20.29% | 0 | 639 | 20.29% | 0 |  | 536.65 | 19.21% | 536.65 | 19.21% | 356.49 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878895 - CHANDLER, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-20 | 2020-04-24 | 2020-03-20 | 2020-04-24 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1020185¦¦2020-03-31
UP | CJ | Yes | 1020194 |  | RIPLEY SITE EVALUATION | GAMBLE, BRAD F. | 100% | 9800 | 0 | 9800 | 1699.96 | 1699.96 | 0 | 0 | 0 | 1699.96 | 6703 | 0 | 6703 | 1373.39 | 1354.03 |  |  | 19.36 |  |  | 1373.39 | 1354.03 |  |  | 19.36 |  |  | 326.57 | 0 | 20.49% |  | 0 | 1373.39 | 3097 | 31.6% | 0 | 3097 | 31.6% | 0 |  | 326.57 | 19.21% | 326.57 | 19.21% | 8100.04 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 897057 - RIPLEY WATER & GAS | WATER | WATER SUPPLY | 2020-03-23 | 2020-05-01 | 2020-03-23 | 2020-05-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1020194¦¦2020-03-31
TM | CJ | Yes | 1020464 |  | MT STERLING RWP | MIGUEL, SEAN J. | 100% | 4800 | 0 | 4800 | 2620.56 | 2620.56 | 0 | 0 | 0 | 2620.56 | 3800 | 0 | 3800 | 2117.14 | 813.39 | 396.17 |  | 511.58 | 396 |  | 2117.14 | 813.39 | 396.17 |  | 511.58 | 396 |  | 503.42 | 0 | 55.71% |  | 0 | 2117.14 | 1000 | 20.83% | 0 | 1000 | 20.83% | 0 |  | 503.42 | 19.21% | 503.42 | 19.21% | 2179.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895088 - MT STERLING WATER & SEWER | WATER | WATER REPAIR & INSTALLATION | 2020-03-23 | 2020-04-30 | 2020-03-23 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1020464¦¦2020-03-31
UP | CJ | Yes | 1020595 |  | KLEINFELDER LADWP NH 34 AND 37 | BRASHEAR, DAVID M | 100% | 42864 | 0 | 42864 | 470.56 | 470.56 | 0 | 0 | 0 | 470.56 | 32148 | 0 | 32148 | 380.16 | 189.88 | 27.83 |  | 162.45 |  |  | 380.16 | 189.88 | 27.83 |  | 162.45 |  |  | 90.4 | 0 | 1.183% |  | 0 | 380.16 | 10716 | 25% | 0 | 10716 | 25% | 0 |  | 90.4 | 19.21% | 90.4 | 19.21% | 42393.44 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 800495 - KLEINFELDER INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-23 | 2020-05-30 | 2020-03-23 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1020595¦¦2020-03-31
UP | CJ | Yes | 1020609 |  | OLIVE BRANCH KENT SESSUM HSP | ANDERSON, STEPHEN P. | 100% | 992 | 0 | 992 | 364.85 | 364.85 | 0 | 0 | 0 | 364.85 | 630 | 0 | 630 | 294.76 | 103.34 | 46.38 |  | 145.04 |  |  | 294.76 | 103.34 | 46.38 |  | 145.04 |  |  | 70.09 | 0 | 46.79% |  | 0 | 294.76 | 362 | 36.49% | 0 | 362 | 36.49% | 0 |  | 70.09 | 19.21% | 70.09 | 19.21% | 627.15 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895759 - OLIVE BRANCH, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-24 | 2020-04-03 | 2020-03-24 | 2020-04-03 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1020609¦¦2020-03-31
UP | CJ | Yes | 1020610 |  | OLIVE BRANCH PWM TESTING | ANDERSON, STEPHEN P. |  | 3950 | 0 | 3950 |  |  | 0 | 0 | 0 |  | 3781 | 0 | 3781 | [20 empty] | 169 | 4.278% | 0 | 169 | 4.278% | 0 | [5 empty] | 3950 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 895759 - OLIVE BRANCH, MS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-24 | 2020-04-30 | 2020-03-24 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1020610¦¦2020-03-31
FP | CJ | Yes | 1020611 |  | EXXON REFINERY WELL 78 | LOPEZ-VASQUEZ, JUAN C. | 100% | 19920 | 0 | 19920 | 12736.22 | 12736.22 | 0 | 0 | 0 | 12736.22 | 11953 | 0 | 11953 | 10289.52 | 6648.57 | 782.95 |  | 2858 |  |  | 10289.52 | 6648.57 | 782.95 |  | 2858 |  |  | 2446.7 | 0 | 86.08% |  | 0 | 10289.52 | 7967 | 39.99% | 0 | 7967 | 39.99% | 0 |  | 2446.7 | 19.21% | 2446.7 | 19.21% | 7183.78 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 878581 - EXXON MOBIL REFINERY | WATER | WATER REPAIR & INSTALLATION | 2020-03-24 | 2020-04-30 | 2020-03-24 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1020611¦¦2020-03-31
FP | CJ | Yes | 1020874 |  | PPG RW4 RW5 MAINTENANCE | ABBOTT, GRANT D. | 100% | 137200 | 0 | 137200 | 1052.72 | 1052.72 | 0 | 0 | 0 | 1052.72 | 102900 | 0 | 102900 | 850.49 | 637.53 | 63.28 |  | 149.68 |  |  | 850.49 | 637.53 | 63.28 |  | 149.68 |  |  | 202.23 | 0 | 0.8265% |  | 0 | 850.49 | 34300 | 25% | 0 | 34300 | 25% | 0 |  | 202.23 | 19.21% | 202.23 | 19.21% | 136147.28 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878532 - PPG INDUSTRIES INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-20 | 2020-12-31 | 2020-03-20 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1020874¦¦2020-03-31
UP | CJ | Yes | 1020937 |  | WALTON NY AUSTIN LINCOLN WELL2 | CROOK, CHARLES M | 100% | 23560 | 0 | 23560 | 8845.21 | 8845.21 | 0 | 0 | 0 | 8845.21 | 17560 | 0 | 17560 | 7146 | 4966.63 | 607.68 |  | 1571.69 |  |  | 7146 | 4966.63 | 607.68 |  | 1571.69 |  |  | 1699.21 | 0 | 40.69% |  | 0 | 7146 | 6000 | 25.47% | 0 | 6000 | 25.47% | 0 |  | 1699.21 | 19.21% | 1699.21 | 19.21% | 14714.79 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 899828 - WALTON, NY, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-24 | 2020-04-10 | 2020-03-24 | 2020-04-10 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1020937¦¦2020-03-31
UP | CJ | Yes | 1020938 |  | TOWN OF JAY FL WELL 1 R AND I | PARSLEY, TRISTAN S | 100% | 22500 | 0 | 22500 | 14552.07 | 14552.07 | 0 | 0 | 0 | 14552.07 | 15725 | 0 | 15725 | 11756.54 | 3879.79 | 1479.38 |  | 6397.37 |  |  | 11756.54 | 3879.79 | 1479.38 |  | 6397.37 |  |  | 2795.53 | 0 | 74.76% |  | 0 | 11756.54 | 6775 | 30.11% | 0 | 6775 | 30.11% | 0 |  | 2795.53 | 19.21% | 2795.53 | 19.21% | 7947.93 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 892747 - JAY, TOWN OF | WATER | WATER SUPPLY | 2020-03-24 | 2020-04-30 | 2020-03-25 | 2020-04-03 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1020938¦¦2020-03-31
UP | CJ | Yes | 1020939 |  | WYNSTONE POA WELL 5 | KENNEDY, CHRISTOPHER C. |  | 130000 | 0 | 130000 |  |  | 0 | 0 | 0 |  | 101400 | 0 | 101400 | [20 empty] | 28600 | 22% | 0 | 28600 | 22% | 0 | [5 empty] | 130000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 878897 - WYNSTONE PROPERTY OWNERS ASSOCIATION | WATER | WATER REPAIR & INSTALLATION | 2020-03-25 | 2020-08-31 | 2020-03-25 | 2020-08-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1020939¦¦2020-03-31
UP | CJ | Yes | 1020940 |  | LAKE ZURICH IL WELL 8 | BALLUFF, WILLIAM O. |  | 93615 | 0 | 93615 |  |  | 0 | 0 | 0 |  | 73000 | 0 | 73000 | [20 empty] | 20615 | 22.02% | 0 | 20615 | 22.02% | 0 | [5 empty] | 93615 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 879001 - LAKE ZURICH, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-25 | 2020-07-30 | 2020-03-25 | 2020-07-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1020940¦¦2020-03-31
FP | CJ | Yes | 1020956 |  | MARSHALL IL TEST HOLE | WHITE, CATHLEEN R |  | 11285 | 0 | 11285 |  |  | 0 | 0 | 0 |  | 7900 | 0 | 7900 | [20 empty] | 3385 | 30% | 0 | 3385 | 30% | 0 | [5 empty] | 11285 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 894270 - MARSHALL, CITY OF | WATER | WATER SUPPLY | 2020-03-24 | 2020-06-30 | 2020-03-24 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1020956¦¦2020-03-31
UP | CJ | Yes | 1020957 |  | SOUTHERN IONICS SPARE SUB | GREGORY, CRYSTAL N |  | 10320 | 0 | 10320 |  |  | 0 | 0 | 0 |  | 6755 | 0 | 6755 | [20 empty] | 3565 | 34.54% | 0 | 3565 | 34.54% | 0 | [5 empty] | 10320 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 898039 - SOUTHERN IONICS INC | WATER | WATER EQUIPMENT SALES | 2020-03-25 | 2020-04-30 | 2020-03-25 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1020957¦¦2020-03-31
UP | CJ | Yes | 1021008 |  | INEOS JOLIET WELL 3 | BALLUFF, WILLIAM O. | 100% | 75000 | 0 | 75000 | 13275.64 | 13275.64 | 0 | 0 | 0 | 13275.64 | 52500 | 0 | 52500 | 10725.32 | 6270.04 | 2843.76 |  | 1611.52 |  |  | 10725.32 | 6270.04 | 2843.76 |  | 1611.52 |  |  | 2550.32 | 0 | 20.43% |  | 0 | 10725.32 | 22500 | 30% | 0 | 22500 | 30% | 0 |  | 2550.32 | 19.21% | 2550.32 | 19.21% | 61724.36 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 879000 - INEOS JOLIET LLC | WATER | WATER REPAIR & INSTALLATION | 2020-03-25 | 2020-04-30 | 2020-03-25 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1021008¦¦2020-03-31
UP | CJ | Yes | 1021362 |  | RAYONIER JESUP GA WELL 9 | PARSLEY, TRISTAN S |  | 47120 | 0 | 47120 |  |  | 0 | 0 | 0 |  | 30043 | 0 | 30043 | [20 empty] | 17077 | 36.24% | 0 | 17077 | 36.24% | 0 | [5 empty] | 47120 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 896807 - RAYONIER | WATER | WATER REPAIR & INSTALLATION | 2020-03-26 | 2020-05-31 | 2020-03-26 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1021362¦¦2020-03-31
FP | CJ | Yes | 1021363 |  | JEFF DAVIS AIR RELEASE VALVE | GNAU, CASEY T |  | 1600 | 0 | 1600 |  |  | 0 | 0 | 0 |  | 950 | 0 | 950 | [20 empty] | 650 | 40.62% | 0 | 650 | 40.62% | 0 | [5 empty] | 1600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 892764 - JEFF DAVIS WATER & SEWER COMMISSION 1 | WATER | WATER REPAIR & INSTALLATION | 2020-03-26 | 2020-04-30 | 2020-03-26 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1021363¦¦2020-03-31
UP | CJ | Yes | 1021736 |  | MIDWAY WELL 2 PULL AND VIDEO | PARSLEY, TRISTAN S |  | 19630 | 0 | 19630 |  |  | 0 | 0 | 0 |  | 13675 | 0 | 13675 | [20 empty] | 5955 | 30.34% | 0 | 5955 | 30.34% | 0 | [5 empty] | 19630 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 894652 - MIDWAY WATER SYSTEM, INC | WATER | WATER SUPPLY | 2020-03-16 | 2020-05-31 | 2020-03-30 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1021736¦¦2020-03-31
TM | CJ | Yes | 1021737 |  | TONY AND VALERIE DAVIS | SCHERM, LOGAN M | 100% | 8000 | 0 | 8000 | 614.76 | 614.76 | 0 | 0 | 0 | 614.76 | 6000 | 0 | 6000 | 496.66 | 205.55 | 133.74 |  | 157.37 |  |  | 496.66 | 205.55 | 133.74 |  | 157.37 |  |  | 118.1 | 0 | 8.278% |  | 0 | 496.66 | 2000 | 25% | 0 | 2000 | 25% | 0 |  | 118.1 | 19.21% | 118.1 | 19.21% | 7385.24 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 899009 - TONY & VALERIE DAVIS | WATER | WATER REPAIR & INSTALLATION | 2020-03-27 | 2020-06-30 | 2020-03-27 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 1021737¦¦2020-03-31
UP | LJ | Yes | 1021768 |  | PCL TARP WELL R127A | COMBS, TAYLOR E. | 3.183% | 660570 | 0 | 660570 | 21022.801 |  | 0 | 0 | 0 | 660570 | 561424.14 | 0 | 561424.14 | 17880.19 | 3483.11 | 1964.33 |  | 7532.75 | 4900 |  | 17880.19 | 3483.11 | 1964.33 |  | 7532.75 | 4900 |  | 0 | 17880.19 | 3.185% |  | 543943.95 | 561824.14 | 99145.86 | 15.01% | 0 | 99145.86 | 15.01% | 0 |  | 3142.61 | 14.95% | 98745.86 | 14.95% | 639547.2 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 326778 - PCL CONSTRUCTION INC | WATER | WATER REPAIR & INSTALLATION | 2020-03-27 | 2020-06-26 | 2020-03-27 | 2020-06-26 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 1021768¦¦2020-03-31
UP | CJ | Yes | 1022099 |  | BAYER PWM | WARTICK, LOGAN M |  | 3900 | 0 | 3900 |  |  | 0 | 0 | 0 |  | 2925 | 0 | 2925 | [20 empty] | 975 | 25% | 0 | 975 | 25% | 0 | [5 empty] | 3900 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 886866 - BAYER CROPSCIENCE LP | WATER | WATER REPAIR & INSTALLATION | 2020-03-20 | 2020-07-15 | 2020-03-20 | 2020-07-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022099¦¦2020-03-31
UP | CJ | Yes | 1022100 |  | JG BOSWELL HR190 | GRACE, GARY L. |  | 15950 | 0 | 15950 |  |  | 0 | 0 | 0 |  | 11922 | 0 | 11922 | [20 empty] | 4028 | 25.25% | 0 | 4028 | 25.25% | 0 | [5 empty] | 15950 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878568 - J G BOSWELL | WATER | WATER REPAIR & INSTALLATION | 2020-03-20 | 2020-05-01 | 2020-03-20 | 2020-05-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022100¦¦2020-03-31
UP | CJ | Yes | 1022101 |  | CVWD BOOSTER 3C2 MOTOR SWAP | GRACE, GARY L. |  | 4300 | 0 | 4300 |  |  | 0 | 0 | 0 |  | 2853 | 0 | 2853 | [20 empty] | 1447 | 33.65% | 0 | 1447 | 33.65% | 0 | [5 empty] | 4300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878809 - CUCAMONGA VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-03-27 | 2020-04-30 | 2020-03-27 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022101¦¦2020-03-31
UP | CJ | Yes | 1022102 |  | TITAN TIRE PWM TESTING | ANDERSON, STEPHEN P. |  | 2400 | 0 | 2400 |  |  | 0 | 0 | 0 |  | 2126 | 0 | 2126 | [20 empty] | 274 | 11.42% | 0 | 274 | 11.42% | 0 | [5 empty] | 2400 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 898969 - TITAN TIRE UNION CITY | WATER | WATER REPAIR & INSTALLATION | 2020-03-30 | 2020-04-17 | 2020-03-30 | 2020-04-17 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022102¦¦2020-03-31
UP | CJ | Yes | 1022103 |  | WALKER LA 2020 FLOW TEST | GREGORY, CRYSTAL N |  | 2800 | 0 | 2800 |  |  | 0 | 0 | 0 |  | 2034 | 0 | 2034 | [20 empty] | 766 | 27.36% | 0 | 766 | 27.36% | 0 | [5 empty] | 2800 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 899791 - WALKER, LA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-30 | 2020-04-30 | 2020-03-30 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022103¦¦2020-03-31
UP | CJ | Yes | 1022137 |  | IP CANTONMENT WELL 2 BEARING | PARSLEY, TRISTAN S |  | 3235 | 0 | 3235 |  |  | 0 | 0 | 0 |  | 2120 | 0 | 2120 | [20 empty] | 1115 | 34.47% | 0 | 1115 | 34.47% | 0 | [5 empty] | 3235 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 879056 - INTERNATIONAL PAPER CANTONMENT | WATER | WATER SUPPLY | 2020-03-27 | 2020-04-30 | 2020-03-27 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022137¦¦2020-03-31
TM | CJ | Yes | 1022138 |  | CHANDLER HSP 1 | MIGUEL, SEAN J. |  | 2598 | 1085 | 3683 |  |  | 0 | 0 | 0 |  | 1930 | 959 | 2889 | [20 empty] | 668 | 25.71% | 126 | 794 | 21.56% | 126 | 126 |  |  |  |  | 3683 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888216 - CHANDLER WATERWORKS | WATER | WATER REPAIR & INSTALLATION | 2020-03-30 | 2020-04-30 | 2020-03-30 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022138¦¦2020-03-31
FP | CJ | Yes | 1022169 |  | CHEMASSIST VIDEO SURVEY | BRASHEAR, DAVID M |  | 1250 | 0 | 1250 |  |  | 0 | 0 | 0 |  | 804 | 0 | 804 | [20 empty] | 446 | 35.68% | 0 | 446 | 35.68% | 0 | [5 empty] | 1250 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1022144 - CHEMASSIST | WATER | WATER REPAIR & INSTALLATION | 2020-03-27 | 2020-04-30 | 2020-03-27 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022169¦¦2020-03-31
FP | CJ | Yes | 1022170 |  | NPPD COOPER NUCLEAR WELLS A B | HEILIGER, TERENCE L. |  | 53886 | 0 | 53886 |  |  | 0 | 0 | 0 |  | 39365 | 0 | 39365 | [20 empty] | 14521 | 26.95% | 0 | 14521 | 26.95% | 0 | [5 empty] | 53886 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 895582 - NPPD COPPER STATION | WATER | WATER REPAIR & INSTALLATION | 2020-03-30 | 2020-05-15 | 2020-03-30 | 2020-05-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022170¦¦2020-03-31
FP | CJ | Yes | 1022171 |  | RLH RENTAL TIGGLAAR FARM PUMP | EISHA, JOSEPH J. | 100% | 13200 | 0 | 13200 | 4229.51 | 4229.51 | 0 | 0 | 0 | 4229.51 | 9250 | 0 | 9250 | 3417 |  |  |  | 3417 |  |  | 3417 |  |  |  | 3417 |  |  | 812.51 | 0 | 36.94% |  | 0 | 3417 | 3950 | 29.92% | 0 | 3950 | 29.92% | 0 |  | 812.51 | 19.21% | 812.51 | 19.21% | 8970.49 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 994978 - RLH RENTAL | WATER | WATER REPAIR & INSTALLATION | 2020-03-30 | 2020-04-16 | 2020-03-30 | 2020-04-16 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022171¦¦2020-03-31
TM | CJ | Yes | 1022242 |  | PORT OF WEST ST MARY | ALBARADO, JORDAN A | 100% | 15000 | 0 | 15000 | 3299.97 | 3299.97 | 0 | 0 | 0 | 3299.97 | 7500 | 0 | 7500 | 2666.03 |  |  |  | 2666.03 |  |  | 2666.03 |  |  |  | 2666.03 |  |  | 633.94 | 0 | 35.55% |  | 0 | 2666.03 | 7500 | 50% | 0 | 7500 | 50% | 0 |  | 633.94 | 19.21% | 633.94 | 19.21% | 11700.03 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 1022193 - PORT OF WEST STAINT MARY | WATER | WATER REPAIR & INSTALLATION | 2020-03-28 | 2020-03-31 | 2020-03-28 | 2020-03-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022242¦¦2020-03-31
TM | CJ | Yes | 1022243 |  | KENNETH GRAVES WS | SCHERM, LOGAN M |  | 23900 | 0 | 23900 |  |  | 0 | 0 | 0 |  | 19110 | 0 | 19110 | [20 empty] | 4790 | 20.04% | 0 | 4790 | 20.04% | 0 | [5 empty] | 23900 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 893084 - KENNETH GRAVES | WATER | WATER SUPPLY | 2020-03-31 | 2020-06-30 | 2020-03-31 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 1022243¦¦2020-03-31
TM | CJ | Yes | 1022244 |  | HERRERA FARMING PR | SCHERM, LOGAN M |  | 9570 | 0 | 9570 |  |  | 0 | 0 | 0 |  | 7656 | 0 | 7656 | [20 empty] | 1914 | 20% | 0 | 1914 | 20% | 0 | [5 empty] | 9570 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892049 - HERRERA FARMING CO | WATER | WATER REPAIR & INSTALLATION | 2020-03-31 | 2020-06-30 | 2020-03-31 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 1022244¦¦2020-03-31
TM | CJ | Yes | 1022245 |  | BISCOE AR CITY OF HS PR | SCHERM, LOGAN M |  | 10000 | 0 | 10000 |  |  | 0 | 0 | 0 |  | 7500 | 0 | 7500 | [20 empty] | 2500 | 25% | 0 | 2500 | 25% | 0 | [5 empty] | 10000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 887137 - BISCOE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-31 | 2020-07-28 | 2020-03-31 | 2020-07-28 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022245¦¦2020-03-31
FP | CJ | Yes | 1022288 |  | CITY OF MIRAMAR MITS | MARTINEZ, MIGUEL E |  | 242091 | 0 | 242091 |  |  | 0 | 0 | 0 |  | 167734 | 0 | 167734 | [20 empty] | 74357 | 30.71% | 0 | 74357 | 30.71% | 0 | [5 empty] | 242091 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 894788 - MIRAMAR, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-01 | 2020-05-15 | 2020-04-01 | 2020-05-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022288¦¦2020-03-31
UP | CJ | Yes | 1022289 |  | SBD COUNTY ZONE J BOOSTER 2 | BRASHEAR, DAVID M |  | 4670 | 0 | 4670 |  |  | 0 | 0 | 0 |  | 3752 | 0 | 3752 | [20 empty] | 918 | 19.66% | 0 | 918 | 19.66% | 0 | [5 empty] | 4670 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 965066 - SAN BERNARDINO, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-01 | 2020-04-03 | 2020-04-01 | 2020-04-03 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022289¦¦2020-03-31
UP | CJ | Yes | 1022290 |  | FAIRBURY IL WELL 7 REHAB | EISHA, JOSEPH J. |  | 33000 | 0 | 33000 |  |  | 0 | 0 | 0 |  | 21450 | 0 | 21450 | [20 empty] | 11550 | 35% | 0 | 11550 | 35% | 0 | [5 empty] | 33000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 890535 - FAIRBURY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-03-31 | 2020-05-20 | 2020-03-31 | 2020-05-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022290¦¦2020-03-31
UP | LJ | Yes | 1022291 |  | SVMD A2 DEN2 WELLS | DECKER, JASEN |  | 1123940 | 0 | 1123940 |  |  | 0 | 0 | 0 | 1123940 | 949584.89 | 0 | 949584.89 | [18 empty] | 949584.89 | 949584.89 | 174355.11 | 15.51% | 0 | 174355.11 | 15.51% | 0 |  |  |  | 174355.11 | 15.51% | 1123940 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878715 - SPRING VALLEY METROPOLITAN DISTRICT 1 | WATER | WATER SUPPLY | 2020-03-13 | 2020-07-02 | 2020-03-13 | 2020-07-02 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022291¦¦2020-03-31
TM | CJ | Yes | 1022296 |  | KILDEER SD96 PWM TEST | KENNEDY, CHRISTOPHER C. |  | 1784 | 0 | 1784 |  |  | 0 | 0 | 0 |  | 1400 | 0 | 1400 | [20 empty] | 384 | 21.52% | 0 | 384 | 21.52% | 0 | [5 empty] | 1784 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 1022195 - KILDEER COUNTRYSIDE CCSD 96 | WATER | WATER REPAIR & INSTALLATION | 2020-03-31 | 2020-07-01 | 2020-03-31 | 2020-07-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022296¦¦2020-03-31
FP | CJ | Yes | 1022297 |  | CLYSAR 2020 PWM | KENNEDY, CHRISTOPHER C. |  | 3688 | 0 | 3688 |  |  | 0 | 0 | 0 |  | 2766 | 0 | 2766 | [20 empty] | 922 | 25% | 0 | 922 | 25% | 0 | [5 empty] | 3688 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 879112 - CLYSAR LLC | WATER | WATER REPAIR & INSTALLATION | 2020-03-31 | 2020-06-05 | 2020-03-31 | 2020-06-05 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022297¦¦2020-03-31
UP | CJ | Yes | 1022336 |  | RAIN CII CARBON EMERGENCY | LOPEZ-VASQUEZ, JUAN C. |  | 4338 | 0 | 4338 |  |  | 0 | 0 | 0 |  | 2866 | 0 | 2866 | [20 empty] | 1472 | 33.93% | 0 | 1472 | 33.93% | 0 | [5 empty] | 4338 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 879116 - RAIN CII CARBON LLC | WATER | WATER REPAIR & INSTALLATION | 2020-04-01 | 2020-04-30 | 2020-04-01 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022336¦¦2020-03-31
FP | CJ | Yes | 1022337 |  | CORONA RECLAIM POND PUMP 2 | GRACE, GARY L. |  | 6998 | 0 | 6998 |  |  | 0 | 0 | 0 |  | 5785 | 0 | 5785 | [20 empty] | 1213 | 17.33% | 0 | 1213 | 17.33% | 0 | [5 empty] | 6998 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878883 - CORONA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-01 | 2020-06-06 | 2020-04-01 | 2020-06-06 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022337¦¦2020-03-31
FP | CJ | Yes | 1022417 |  | P66 NP85 SERVICE WORK | WHITE, CATHLEEN R |  | 10151 | 0 | 10151 |  |  | 0 | 0 | 0 |  | 7100 | 0 | 7100 | [20 empty] | 3051 | 30.06% | 0 | 3051 | 30.06% | 0 | [5 empty] | 10151 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896286 - PHILLIPS 66 WOOD RIVER REFINERY | WATER | WATER SUPPLY | 2020-03-31 | 2020-06-30 | 2020-03-31 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022417¦¦2020-03-31
TM | CJ | Yes | 1022418 |  | SAM TARKINGTON PUMP | SCHERM, LOGAN M |  | 19172 | 0 | 19172 |  |  | 0 | 0 | 0 |  | 12291 | 0 | 12291 | [20 empty] | 6881 | 35.89% | 0 | 6881 | 35.89% | 0 | [5 empty] | 19172 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 897407 - SAM TARKINGTON | WATER | WATER EQUIPMENT SALES | 2020-04-02 | 2020-07-31 | 2020-04-02 | 2020-07-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022418¦¦2020-03-31
UP | CJ | Yes | 1022419 |  | GRACE 3137A REHAB AND UPGRADE | GNAU, CASEY T |  | 287055 | 0 | 287055 |  |  | 0 | 0 | 0 |  | 172177 | 0 | 172177 | [17 empty] | 0 |  |  | 114878 | 40.02% | 0 | 114878 | 40.02% | 0 | [5 empty] | 287055 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879019 - W R GRACE & CO CONN | WATER | WATER REPAIR & INSTALLATION | 2020-04-02 | 2020-08-30 | 2020-04-02 | 2020-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022419¦¦2020-03-31
UP | CJ | Yes | 1022420 |  | GRACE 3037A UPGRADE | GNAU, CASEY T |  | 137555 | 0 | 137555 |  |  | 0 | 0 | 0 |  | 82527 | 0 | 82527 | [20 empty] | 55028 | 40% | 0 | 55028 | 40% | 0 | [5 empty] | 137555 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879019 - W R GRACE & CO CONN | WATER | WATER REPAIR & INSTALLATION | 2020-04-02 | 2020-08-30 | 2020-04-02 | 2020-08-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022420¦¦2020-03-31
UP | CJ | Yes | 1022421 |  | TIMBERLANE NEW EQUPIMENT | GREGORY, CRYSTAL N |  | 36081 | 0 | 36081 |  |  | 0 | 0 | 0 |  | 27154 | 0 | 27154 | [17 empty] | 0 |  |  | 8927 | 24.74% | 0 | 8927 | 24.74% | 0 | [5 empty] | 36081 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 1022294 - TIMBERLANE GOLF AND RECREATION | WATER | WATER REPAIR & INSTALLATION | 2020-04-02 | 2020-06-30 | 2020-04-02 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022421¦¦2020-03-31
FP | CJ | Yes | 1022422 |  | SANDERSON FARMS MOULTRIE GA 2 | PARSLEY, TRISTAN S |  | 11226 | 0 | 11226 |  |  | 0 | 0 | 0 |  | 5645 | 0 | 5645 | [20 empty] | 5581 | 49.71% | 0 | 5581 | 49.71% | 0 | [5 empty] | 11226 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA | 878808 - SANDERSON FARMS MOULTRIE PLANT | WATER | WATER REPAIR & INSTALLATION | 2020-04-01 | 2020-05-31 | 2020-04-01 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022422¦¦2020-03-31
UP | LJ | Yes | 1022424 |  | CID NEW WELL 107 | TRAMMELL, DUANE R. |  | 694485.5 | 0 | 694485.5 |  |  | 0 | 0 | 0 | 694485 | 546273.05 | 0 | 546273.05 | [18 empty] | 545657 | 545657 | 148212.45 | 21.34% | 0 | 148212.45 | 21.34% | 0 |  |  |  | 148828 | 21.43% | 694485.5 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878571 - CORCORAN IRRIGATION DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-04-02 | 2020-07-15 | 2020-04-02 | 2020-07-15 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022424¦¦2020-03-31
TM | CJ | Yes | 1022481 |  | GREENVILLE MO PUMP REPAIR | WHITE, CATHLEEN R |  | 22000 | 0 | 22000 |  |  | 0 | 0 | 0 |  | 15500 | 0 | 15500 | [20 empty] | 6500 | 29.55% | 0 | 6500 | 29.55% | 0 | [5 empty] | 22000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 1022442 - GREENVILLE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-02 | 2020-06-30 | 2020-04-02 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022481¦¦2020-03-31
UP | CJ | Yes | 1022482 |  | XCEL RMEC WELL REHAB | SCHANAMAN, MIKE L. |  | 59730 | 0 | 59730 |  |  | 0 | 0 | 0 |  | 41811 | 0 | 41811 | [20 empty] | 17919 | 30% | 0 | 17919 | 30% | 0 | [5 empty] | 59730 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 900557 - XCEL ENERGY | WATER | WATER REPAIR & INSTALLATION | 2020-04-03 | 2020-04-30 | 2020-04-03 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022482¦¦2020-03-31
FP | FJ | Yes | 1022483 |  | AECI ST JUDE INDUSTRIAL PARK | SCHERM, LOGAN M |  | 237600 | 0 | 237600 |  |  | 0 | 0 | 0 | 237600 | 159082.55 | 0 | 159082.55 | [18 empty] | 159082.55 | 159082.55 | 78517.45 | 33.05% | 0 | 78517.45 | 33.05% | 0 |  |  |  | 78517.45 | 33.05% | 237600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 1022469 - ARTISAN CONTRACTING LLC | WATER | WATER SUPPLY | 2020-04-03 | 2020-09-03 | 2020-04-03 | 2020-09-03 | SUBCONTRACTOR | PRIVATE | BID/BUILD | 1022483¦¦2020-03-31
UP | CJ | Yes | 1022542 |  | JOSH WATERS WELL 7 EMERGENCY | SEIDEN, ANDREW L. |  | 18185 | 0 | 18185 |  |  | 0 | 0 | 0 |  | 13482 | 0 | 13482 | [20 empty] | 4703 | 25.86% | 0 | 4703 | 25.86% | 0 | [5 empty] | 18185 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 968987 - JOSH WATER | WATER | WATER REPAIR & INSTALLATION | 2020-04-06 | 2020-12-31 | 2020-04-06 | 2020-12-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022542¦¦2020-03-31
UP | CJ | Yes | 1022543 |  | TOPA TOPA N WELL EQUIPPING | SEIDEN, ANDREW L. |  | 99277 | 0 | 99277 |  |  | 0 | 0 | 0 |  | 76490 | 0 | 76490 | [20 empty] | 22787 | 22.95% | 0 | 22787 | 22.95% | 0 | [5 empty] | 99277 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878563 - TOPA TOPA RANCH & NURSERY LLC | WATER | WATER REPAIR & INSTALLATION | 2020-04-06 | 2020-04-30 | 2020-04-06 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022543¦¦2020-03-31
UP | CJ | Yes | 1022566 |  | BUDGET DRILLING MTN FALLS 2 | BRASHEAR, DAVID M |  | 81019 | 0 | 81019 |  |  | 0 | 0 | 0 |  | 60765 | 0 | 60765 | [20 empty] | 20254 | 25% | 0 | 20254 | 25% | 0 | [5 empty] | 81019 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879107 - BUDGET DRILLING COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-04-02 | 2020-05-31 | 2020-04-02 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022566¦¦2020-03-31
FP | CJ | Yes | 1022567 |  | KEMRON PASCAGOULA SUB PUMP | LOPEZ-VASQUEZ, JUAN C. |  | 4440 | 0 | 4440 |  |  | 0 | 0 | 0 |  | 3050 | 0 | 3050 | [20 empty] | 1390 | 31.31% | 0 | 1390 | 31.31% | 0 | [5 empty] | 4440 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 796659 - KEMRON ENVIRONMENTAL SERVICES | WATER | WATER EQUIPMENT SALES | 2020-04-06 | 2020-04-30 | 2020-04-06 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022567¦¦2020-03-31
FP | CJ | Yes | 1022568 |  | BUNGE CB IA PUMP TESTING | GANSEBOM, JASON W. |  | 5310 | 0 | 5310 |  |  | 0 | 0 | 0 |  | 3974 | 0 | 3974 | [20 empty] | 1336 | 25.16% | 0 | 1336 | 25.16% | 0 | [5 empty] | 5310 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 887605 - BUNGE NORTH AMERICA INC | WATER | WATER REPAIR & INSTALLATION | 2020-04-06 | 2020-05-31 | 2020-04-06 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022568¦¦2020-03-31
UP | CJ | Yes | 1022594 |  | RUMMEL EASTMARK WELL ABANDON | VAN ALLEN, WESLEY C. |  | 31036 | 0 | 31036 |  |  | 0 | 0 | 0 |  | 23226 | 0 | 23226 | [20 empty] | 7810 | 25.16% | 0 | 7810 | 25.16% | 0 | [5 empty] | 31036 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 878971 - RUMMEL CONSTRUCTION | WATER | WATER REPAIR & INSTALLATION | 2020-04-07 | 2020-05-31 | 2020-04-07 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022594¦¦2020-03-31
FP | CJ | Yes | 1022606 |  | COLONIAL PIPELINE WELL1 R I | LOPEZ-VASQUEZ, JUAN C. |  | 28200 | 0 | 28200 |  |  | 0 | 0 | 0 |  | 21780 | 0 | 21780 | [17 empty] | 0 |  |  | 6420 | 22.77% | 0 | 6420 | 22.77% | 0 | [5 empty] | 28200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 886991 - BENGAL PIPELINE | WATER | WATER REPAIR & INSTALLATION | 2020-04-07 | 2020-06-30 | 2020-04-07 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022606¦¦2020-03-31
UP | CJ | Yes | 1022609 |  | BRIGHTON CO WELL A | SCHANAMAN, MIKE L. |  | 68787 | 0 | 68787 |  |  | 0 | 0 | 0 |  | 55030 | 0 | 55030 | [20 empty] | 13757 | 20% | 0 | 13757 | 20% | 0 | [5 empty] | 68787 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 878569 - BRIGHTON, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-07 | 2020-06-30 | 2020-04-07 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022609¦¦2020-03-31
UP | CJ | Yes | 1022634 |  | TANIMURA 2 BOOSTER PUMPS | SEIDEN, ANDREW L. |  | 3040 | 0 | 3040 |  |  | 0 | 0 | 0 |  | 2459 | 0 | 2459 | [20 empty] | 581 | 19.11% | 0 | 581 | 19.11% | 0 | [5 empty] | 3040 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 906315 - TANIMURA & ANTLE | WATER | WATER REPAIR & INSTALLATION | 2020-04-06 | 2020-12-30 | 2020-04-06 | 2020-12-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022634¦¦2020-03-31
TM | CJ | Yes | 1022635 |  | BOONVILLE WELL 8 | MIGUEL, SEAN J. |  | 18500 | 0 | 18500 |  |  | 0 | 0 | 0 |  | 14399 | 0 | 14399 | [20 empty] | 4101 | 22.17% | 0 | 4101 | 22.17% | 0 | [5 empty] | 18500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 887294 - BOONVILLE, IN, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-07 | 2020-05-31 | 2020-04-07 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022635¦¦2020-03-31
UP | CJ | Yes | 1022674 |  | VERNON PARISH WARD 4 TEST | GNAU, CASEY T |  | 1300 | 0 | 1300 |  |  | 0 | 0 | 0 |  | 780 | 0 | 780 | [20 empty] | 520 | 40% | 0 | 520 | 40% | 0 | [5 empty] | 1300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879015 - VERNON PARISH WWD WARD 4 | WATER | WATER REPAIR & INSTALLATION | 2020-04-08 | 2020-04-30 | 2020-04-08 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022674¦¦2020-03-31
UP | CJ | Yes | 1022685 |  | TROY KS BOOSTER PUMP R AND I | WARTICK, LOGAN M |  | 4615 | 0 | 4615 |  |  | 0 | 0 | 0 |  | 3461 | 0 | 3461 | [20 empty] | 1154 | 25.01% | 0 | 1154 | 25.01% | 0 | [5 empty] | 4615 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 899161 - TROY, KS, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-10 | 2020-08-10 | 2020-04-10 | 2020-08-10 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022685¦¦2020-03-31
UP | CJ | Yes | 1022697 |  | NATIONAL COLD STORAGE SOUTHWEL | WARTICK, LOGAN M |  | 7645 | 0 | 7645 |  |  | 0 | 0 | 0 |  | 6498 | 0 | 6498 | [20 empty] | 1147 | 15% | 0 | 1147 | 15% | 0 | [5 empty] | 7645 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 1022686 - NATIONAL COLD STORAGE | WATER | WATER REPAIR & INSTALLATION | 2020-04-08 | 2020-08-08 | 2020-04-08 | 2020-08-08 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022697¦¦2020-03-31
UP | CJ | Yes | 1022727 |  | EMWD CONTAINER MOVE | GRACE, GARY L. |  | 2600 | 0 | 2600 |  |  | 0 | 0 | 0 |  | 2003 | 0 | 2003 | [20 empty] | 597 | 22.96% | 0 | 597 | 22.96% | 0 | [5 empty] | 2600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878619 - EASTERN MUNICIPAL WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-04-03 | 2020-04-21 | 2020-04-03 | 2020-04-21 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022727¦¦2020-03-31
UP | CJ | Yes | 1022762 |  | INGREDION MO WELL 32 REHAB | WARTICK, LOGAN M |  | 20318 | 0 | 20318 |  |  | 0 | 0 | 0 |  | 16254 | 0 | 16254 | [20 empty] | 4064 | 20% | 0 | 4064 | 20% | 0 | [5 empty] | 20318 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 879079 - INGREDION INCORPORATED | WATER | WATER REPAIR & INSTALLATION | 2020-04-10 | 2020-08-15 | 2020-04-10 | 2020-08-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022762¦¦2020-03-31
UP | CJ | Yes | 1022763 |  | EASTMAN CHEMICAL PARTS | ANDERSON, STEPHEN P. |  | 4620 | 0 | 4620 |  |  | 0 | 0 | 0 |  | 2954 | 0 | 2954 | [20 empty] | 1666 | 36.06% | 0 | 1666 | 36.06% | 0 | [5 empty] | 4620 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 889970 - EASTMAN CHEMICAL COMPANY | WATER | WATER EQUIPMENT SALES | 2020-04-09 | 2020-05-02 | 2020-04-09 | 2020-05-02 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022763¦¦2020-03-31
TM | CJ | Yes | 1022764 |  | RTR FARMS REPLACE VFD PANEL | SCHERM, LOGAN M |  | 22500 | 0 | 22500 |  |  | 0 | 0 | 0 |  | 18350 | 0 | 18350 | [20 empty] | 4150 | 18.44% | 0 | 4150 | 18.44% | 0 | [5 empty] | 22500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 897290 - RTR FARMS, LLC | WATER | WATER EQUIPMENT SALES | 2020-04-09 | 2021-04-10 | 2020-04-09 | 2021-04-10 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022764¦¦2020-03-31
UP | CJ | Yes | 1022765 |  | LEWISBURG WATER NEW PUMP | ANDERSON, STEPHEN P. |  | 66000 | 0 | 66000 |  |  | 0 | 0 | 0 |  | 44521 | 0 | 44521 | [20 empty] | 21479 | 32.54% | 0 | 21479 | 32.54% | 0 | [5 empty] | 66000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 893698 - LEWISBURG WATER SYSTEM | WATER | WATER REPAIR & INSTALLATION | 2020-04-09 | 2020-05-20 | 2020-04-09 | 2020-05-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022765¦¦2020-03-31
UP | CJ | Yes | 1022779 |  | PARADIGM REPAIR NON POT 3819N | BRASHEAR, DAVID M |  | 110182 | 0 | 110182 |  |  | 0 | 0 | 0 |  | 66458 | 0 | 66458 | [20 empty] | 43724 | 39.68% | 0 | 43724 | 39.68% | 0 | [5 empty] | 110182 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1022737 - PARADIGM MECHANICAL CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-04-02 | 2020-07-30 | 2020-04-02 | 2020-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022779¦¦2020-03-31
FP | CJ | Yes | 1022827 |  | MADISONVILLE RWP1 | MIGUEL, SEAN J. |  | 35000 | 0 | 35000 |  |  | 0 | 0 | 0 |  | 25550 | 0 | 25550 | [20 empty] | 9450 | 27% | 0 | 9450 | 27% | 0 | [5 empty] | 35000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888520 - MADISONVILLE, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-07 | 2020-06-30 | 2020-04-07 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022827¦¦2020-03-31
FP | CJ | Yes | 1022828 |  | P66 CAVERN PUMP 250 | WHITE, CATHLEEN R |  | 28620 | 0 | 28620 |  |  | 0 | 0 | 0 |  | 20050 | 0 | 20050 | [20 empty] | 8570 | 29.94% | 0 | 8570 | 29.94% | 0 | [5 empty] | 28620 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878724 - PHILLIPS 66 | WATER | WATER SUPPLY | 2020-04-03 | 2020-06-30 | 2020-04-03 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1022828¦¦2020-03-31
UP | CJ | Yes | 1022894 |  | MOSAIC PLANT CITY PULL PUMP | BRUGGER, CRAIG J. |  | 30632 | 0 | 30632 |  |  | 0 | 0 | 0 |  | 19673 | 0 | 19673 | [20 empty] | 10959 | 35.78% | 0 | 10959 | 35.78% | 0 | [5 empty] | 30632 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 895011 - MOSAIC FERTILIZER LLC | WATER | WATER REPAIR & INSTALLATION | 2020-04-13 | 2020-04-29 | 2020-04-13 | 2020-04-29 | PRIME CONTRACTOR | PRIVATE | JOB ORDER CONTRACT | 1022894¦¦2020-03-31
UP | CJ | Yes | 1022895 |  | PACE WATER WELL 5 UPGRADE | PARSLEY, TRISTAN S |  | 9100 | 0 | 9100 |  |  | 0 | 0 | 0 |  | 6555 | 0 | 6555 | [20 empty] | 2545 | 27.97% | 0 | 2545 | 27.97% | 0 | [5 empty] | 9100 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 1022876 - PACE WATER SYSTEM | WATER | WATER SUPPLY | 2020-04-08 | 2020-05-31 | 2020-04-10 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1022895¦¦2020-03-31
FP | CJ | Yes | 1022896 |  | WESTROCK HODGE WELL 30 | GNAU, CASEY T |  | 24500 | 0 | 24500 |  |  | 0 | 0 | 0 |  | 14526 | 0 | 14526 | [20 empty] | 9974 | 40.71% | 0 | 9974 | 40.71% | 0 | [5 empty] | 24500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2020-04-13 | 2020-04-30 | 2020-04-13 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022896¦¦2020-03-31
UP | LJ | Yes | 1022897 |  | POJOAQUE BASIN REGIONAL WATER | HARTMAN, MICHAEL |  | 3291924 | 0 | 3291924 |  |  | 0 | 0 | 0 | 3291924 | 2383304.81 | 0 | 2383304.81 | [18 empty] | 2383305 | 2383305 | 908619.19 | 27.6% | 0 | 908619.19 | 27.6% | 0 |  |  |  | 908619 | 27.6% | 3291924 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878719 - CDM SMITH | WATER | WATER SUPPLY | 2020-04-13 | 2021-05-01 | 2020-04-13 | 2021-05-01 | SUBCONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022897¦¦2020-03-31
FP | CJ | Yes | 1022965 |  | BICKNELL WELL 1 REHAB | WILLIAMS, DONALD G. |  | 24500 | 0 | 24500 |  |  | 0 | 0 | 0 |  | 19110 | 0 | 19110 | [20 empty] | 5390 | 22% | 0 | 5390 | 22% | 0 | [5 empty] | 24500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 887084 - BICKNELL, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-14 | 2020-05-30 | 2020-04-14 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1022965¦¦2020-03-31
FP | CJ | Yes | 1022966 |  | JOHN ROTH AND SON PROD WELL | GANSEBOM, JASON W. |  | 7893 | 0 | 7893 |  |  | 0 | 0 | 0 |  | 6156 | 0 | 6156 | [20 empty] | 1737 | 22.01% | 0 | 1737 | 22.01% | 0 | [5 empty] | 7893 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 1022909 - JOHN ROTH AND SON | WATER | WATER REPAIR & INSTALLATION | 2020-04-14 | 2020-05-31 | 2020-04-14 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022966¦¦2020-03-31
FP | CJ | Yes | 1022967 |  | WARD 2 VERSAILLES BUDDY ELLIS1 | GREGORY, CRYSTAL N |  | 4920 | 0 | 4920 |  |  | 0 | 0 | 0 |  | 3775 | 0 | 3775 | [20 empty] | 1145 | 23.27% | 0 | 1145 | 23.27% | 0 | [5 empty] | 4920 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 899839 - WARD 2 WATER WORKS | WATER | WATER REPAIR & INSTALLATION | 2020-04-14 | 2020-05-30 | 2020-04-14 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022967¦¦2020-03-31
FP | CJ | Yes | 1022969 |  | HDR LINCOLN NE WELL TEST | GANSEBOM, JASON W. |  | 22742 | 0 | 22742 |  |  | 0 | 0 | 0 |  | 17738 | 0 | 17738 | [20 empty] | 5004 | 22% | 0 | 5004 | 22% | 0 | [5 empty] | 22742 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 891956 - HDR ENGINEERING INC | WATER | WATER REPAIR & INSTALLATION | 2020-04-14 | 2020-05-31 | 2020-04-14 | 2020-05-31 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1022969¦¦2020-03-31
FP | CJ | Yes | 1023032 |  | JEFFERSON CTY PWSD2 SUGARCREEK | WHITE, CATHLEEN R |  | 93866 | 0 | 93866 |  |  | 0 | 0 | 0 |  | 65500 | 0 | 65500 | [20 empty] | 28366 | 30.22% | 0 | 28366 | 30.22% | 0 | [5 empty] | 93866 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 878887 - JEFFERSON COUNTY MO PWSD NO 2 | WATER | WATER REPAIR & INSTALLATION | 2020-04-15 | 2020-06-30 | 2020-04-15 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1023032¦¦2020-03-31
UP | CJ | Yes | 1023033 |  | THOMPSON BROTHERS ELLISVILLE | PARSLEY, TRISTAN S |  | 1850 | 0 | 1850 |  |  | 0 | 0 | 0 |  | 1105 | 0 | 1105 | [20 empty] | 745 | 40.27% | 0 | 745 | 40.27% | 0 | [5 empty] | 1850 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 898913 - THOMPSON BROTHERS DRILLING INC | WATER | WATER REPAIR & INSTALLATION | 2020-04-07 | 2020-05-31 | 2020-04-15 | 2020-05-31 | SUBCONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023033¦¦2020-03-31
TM | CJ | Yes | 1023034 |  | WINNSBORO WELL 4 | GNAU, CASEY T |  | 35000 | 0 | 35000 |  |  | 0 | 0 | 0 |  | 21000 | 0 | 21000 | [20 empty] | 14000 | 40% | 0 | 14000 | 40% | 0 | [5 empty] | 35000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 900409 - WINNSBORO, LA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-15 | 2020-04-30 | 2020-04-15 | 2020-04-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023034¦¦2020-03-31
TM | CJ | Yes | 1023076 |  | HMI PROPERTIES WS | SCHERM, LOGAN M |  | 43275 | 0 | 43275 |  |  | 0 | 0 | 0 |  | 35000 | 0 | 35000 | [20 empty] | 8275 | 19.12% | 0 | 8275 | 19.12% | 0 | [5 empty] | 43275 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 878656 - HMI PROPERTIES | WATER | WATER SUPPLY | 2020-04-15 | 2020-08-31 | 2020-04-15 | 2020-08-31 | PRIME CONTRACTOR | PRIVATE | DESIGN/BUILD | 1023076¦¦2020-03-31
FP | CJ | Yes | 1023152 |  | TRENTON LS PUMP | ABBOTT, GRANT D. |  | 7500 | 0 | 7500 |  |  | 0 | 0 | 0 |  | 5600 | 0 | 5600 | [20 empty] | 1900 | 25.33% | 0 | 1900 | 25.33% | 0 | [5 empty] | 7500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 899103 - TRENTON, OH, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-14 | 2020-05-31 | 2020-04-14 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023152¦¦2020-03-31
UP | CJ | Yes | 1023153 |  | BRACKEN CO VIBRATION | MIGUEL, SEAN J. |  | 1000 | 0 | 1000 |  |  | 0 | 0 | 0 |  | 900 | 0 | 900 | [20 empty] | 100 | 10% | 0 | 100 | 10% | 0 | [5 empty] | 1000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 887356 - BRACKEN, COUNTY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-16 | 2020-05-30 | 2020-04-16 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023153¦¦2020-03-31
UP | CJ | Yes | 1023154 |  | CAVE RUN VIBRATION | MIGUEL, SEAN J. |  | 1350 | 0 | 1350 |  |  | 0 | 0 | 0 |  | 1150 | 0 | 1150 | [20 empty] | 200 | 14.81% | 0 | 200 | 14.81% | 0 | [5 empty] | 1350 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 888054 - CAVE RUN WATER COMMISSION | WATER | WATER REPAIR & INSTALLATION | 2020-04-15 | 2020-05-30 | 2020-04-15 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023154¦¦2020-03-31
UP | CJ | Yes | 1023155 |  | GALLATIN CO TESTS | MIGUEL, SEAN J. |  | 750 | 0 | 750 |  |  | 0 | 0 | 0 |  | 650 | 0 | 650 | [20 empty] | 100 | 13.33% | 0 | 100 | 13.33% | 0 | [5 empty] | 750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 891013 - GALLATIN COUNTY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-04-16 | 2020-05-31 | 2020-04-15 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023155¦¦2020-03-31
FP | CJ | Yes | 1023156 |  | GLASGOW BLOWER MAINTENANCE | MIGUEL, SEAN J. |  | 300 | 0 | 300 |  |  | 0 | 0 | 0 |  | 225 | 0 | 225 | [20 empty] | 75 | 25% | 0 | 75 | 25% | 0 | [5 empty] | 300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 891285 - GLASGOW WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-04-15 | 2020-05-31 | 2020-04-15 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023156¦¦2020-03-31
UP | CJ | Yes | 1023157 |  | LAWRENCEBURG PMP MAINTENANCE | MIGUEL, SEAN J. |  | 1225 | 0 | 1225 |  |  | 0 | 0 | 0 |  | 1125 | 0 | 1125 | [20 empty] | 100 | 8.163% | 0 | 100 | 8.163% | 0 | [5 empty] | 1225 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 893542 - LAWRENCEBURG WATER PLANT | WATER | WATER REPAIR & INSTALLATION | 2020-04-16 | 2020-05-31 | 2018-02-14 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023157¦¦2020-03-31
UP | CJ | Yes | 1023158 |  | MILTON TESTS | MIGUEL, SEAN J. |  | 900 | 0 | 900 |  |  | 0 | 0 | 0 |  | 800 | 0 | 800 | [20 empty] | 100 | 11.11% | 0 | 100 | 11.11% | 0 | [5 empty] | 900 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 894704 - MILTON, KY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-16 | 2020-05-31 | 2020-04-16 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023158¦¦2020-03-31
UP | CJ | Yes | 1023160 |  | WARSAW TESTS | MIGUEL, SEAN J. |  | 1750 | 0 | 1750 |  |  | 0 | 0 | 0 |  | 1200 | 0 | 1200 | [20 empty] | 550 | 31.43% | 0 | 550 | 31.43% | 0 | [5 empty] | 1750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 899860 - WARSAW, KY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-16 | 2020-05-31 | 2018-02-15 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023160¦¦2020-03-31
UP | CJ | Yes | 1023161 |  | WESTERN FLEMING MAINTENANCE | MIGUEL, SEAN J. |  | 675 | 0 | 675 |  |  | 0 | 0 | 0 |  | 600 | 0 | 600 | [20 empty] | 75 | 11.11% | 0 | 75 | 11.11% | 0 | [5 empty] | 675 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 900098 - WESTERN FLEMING COUNTY WATER | WATER | WATER REPAIR & INSTALLATION | 2020-04-15 | 2020-05-31 | 2020-04-15 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023161¦¦2020-03-31
TM | CJ | Yes | 1023162 |  | HENRY CO 8 CHECK VLV | MIGUEL, SEAN J. |  | 1400 | 0 | 1400 |  |  | 0 | 0 | 0 |  | 1140 | 0 | 1140 | [20 empty] | 260 | 18.57% | 0 | 260 | 18.57% | 0 | [5 empty] | 1400 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 892021 - HENRY COUNTY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-04-16 | 2020-05-31 | 2020-04-16 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023162¦¦2020-03-31
UP | CJ | Yes | 1023165 |  | FLOMATON AL WELL 2 R AND I | PARSLEY, TRISTAN S |  | 13785 | 0 | 13785 |  |  | 0 | 0 | 0 |  | 9645 | 0 | 9645 | [20 empty] | 4140 | 30.03% | 0 | 4140 | 30.03% | 0 | [5 empty] | 13785 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 1023122 - FLOMATON, CITY OF | WATER | WATER SUPPLY | 2020-04-15 | 2020-05-31 | 2020-04-16 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023165¦¦2020-03-31
UP | CJ | Yes | 1023198 |  | BROWNSVILLE TN PWM TESTING | ANDERSON, STEPHEN P. |  | 4500 | 0 | 4500 |  |  | 0 | 0 | 0 |  | 3361 | 0 | 3361 | [20 empty] | 1139 | 25.31% | 0 | 1139 | 25.31% | 0 | [5 empty] | 4500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 887527 - BROWNSVILLE UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2020-04-17 | 2020-05-06 | 2020-04-17 | 2020-05-06 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023198¦¦2020-03-31
UP | CJ | Yes | 1023199 |  | STANTON TN PWM TESTING | ANDERSON, STEPHEN P. |  | 1500 | 0 | 1500 |  |  | 0 | 0 | 0 |  | 1155 | 0 | 1155 | [20 empty] | 345 | 23% | 0 | 345 | 23% | 0 | [5 empty] | 1500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 898246 - STANTON WATER SYSTEM | WATER | WATER REPAIR & INSTALLATION | 2020-04-17 | 2020-05-06 | 2020-04-17 | 2020-05-06 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023199¦¦2020-03-31
UP | CJ | Yes | 1023200 |  | VANDERBILT CHEMICAL PWM TEST | ANDERSON, STEPHEN P. |  | 3500 | 0 | 3500 |  |  | 0 | 0 | 0 |  | 3446 | 0 | 3446 | [20 empty] | 54 | 1.543% | 0 | 54 | 1.543% | 0 | [5 empty] | 3500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 899566 - VANDERBILT CHEMICAL | WATER | WATER REPAIR & INSTALLATION | 2020-04-17 | 2020-05-12 | 2020-04-17 | 2020-05-12 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023200¦¦2020-03-31
UP | CJ | Yes | 1023201 |  | PHILLIPS 66 WELL 11 DRESSER | GNAU, CASEY T |  | 2600 | 0 | 2600 |  |  | 0 | 0 | 0 |  | 1681 | 0 | 1681 | [20 empty] | 919 | 35.35% | 0 | 919 | 35.35% | 0 | [5 empty] | 2600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 878724 - PHILLIPS 66 | WATER | WATER REPAIR & INSTALLATION | 2020-04-17 | 2020-04-30 | 2020-04-17 | 2020-04-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023201¦¦2020-03-31
FP | CJ | Yes | 1023202 |  | PANHANDLE EASTER PUMP REPLACE | WHITE, CATHLEEN R |  | 47714 | 0 | 47714 |  |  | 0 | 0 | 0 |  | 33309 | 0 | 33309 | [20 empty] | 14405 | 30.19% | 0 | 14405 | 30.19% | 0 | [5 empty] | 47714 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896011 - PANHANDLE EASTERN PIPELINE | WATER | WATER REPAIR & INSTALLATION | 2020-04-15 | 2020-07-30 | 2020-04-15 | 2020-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023202¦¦2020-03-31
UP | CJ | Yes | 1023205 |  | JG BOSWELL S110 | GRACE, GARY L. |  | 14750 | 0 | 14750 |  |  | 0 | 0 | 0 |  | 9210 | 0 | 9210 | [20 empty] | 5540 | 37.56% | 0 | 5540 | 37.56% | 0 | [5 empty] | 14750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892822 - JG BOSWELL COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-04-14 | 2020-06-16 | 2020-04-14 | 2020-06-16 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023205¦¦2020-03-31
UP | CJ | Yes | 1023206 |  | JG BOSWELL S189 | GRACE, GARY L. |  | 13900 | 0 | 13900 |  |  | 0 | 0 | 0 |  | 9210 | 0 | 9210 | [20 empty] | 4690 | 33.74% | 0 | 4690 | 33.74% | 0 | [5 empty] | 13900 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 892822 - JG BOSWELL COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-04-14 | 2020-06-16 | 2020-04-14 | 2020-06-16 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023206¦¦2020-03-31
UP | CJ | Yes | 1023207 |  | OU HSC WELL 5 PULL | EVANS, TRAVIS L |  | 3750 | 0 | 3750 |  |  | 0 | 0 | 0 |  | 3220 | 0 | 3220 | [20 empty] | 530 | 14.13% | 0 | 530 | 14.13% | 0 | [5 empty] | 3750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA | 895909 - OU HEALTH & SCIENCE CENTER | WATER | WATER SUPPLY | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2020-04-17 | PRIME CONTRACTOR | PUBLIC | DESIGN/BUILD | 1023207¦¦2020-03-31
UP | CJ | Yes | 1023219 |  | SEDALIA MO WELL 13 INSTALL | WARTICK, LOGAN M |  | 70431 | 0 | 70431 |  |  | 0 | 0 | 0 |  | 56345 | 0 | 56345 | [20 empty] | 14086 | 20% | 0 | 14086 | 20% | 0 | [5 empty] | 70431 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 1023196 - SEDALIA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-15 | 2020-08-15 | 2020-04-15 | 2020-08-15 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1023219¦¦2020-03-31
UP | CJ | Yes | 1023220 |  | INGEVITY PUMP MOTOR ORDER | ANDERSON, STEPHEN P. |  | 24085 | 0 | 24085 |  |  | 0 | 0 | 0 |  | 15655 | 0 | 15655 | [20 empty] | 8430 | 35% | 0 | 8430 | 35% | 0 | [5 empty] | 24085 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 892547 - INGEVITY SOUTH CAROLINA, LLC | WATER | WATER EQUIPMENT SALES | 2020-04-17 | 2020-07-10 | 2020-04-17 | 2020-07-10 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023220¦¦2020-03-31
FP | CJ | Yes | 1023255 |  | TOPEKA WTP RELIEF WELL PUMP | WARTICK, LOGAN M |  | 13860 | 0 | 13860 |  |  | 0 | 0 | 0 |  | 10395 | 0 | 10395 | [20 empty] | 3465 | 25% | 0 | 3465 | 25% | 0 | [5 empty] | 13860 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 878455 - TOPEKA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-17 | 2020-08-20 | 2020-04-17 | 2020-08-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023255¦¦2020-03-31
UP | CJ | Yes | 1023256 |  | PLATTE MO RWD 4 WELL 4 REHAB | WARTICK, LOGAN M |  | 15787 | 0 | 15787 |  |  | 0 | 0 | 0 |  | 12630 | 0 | 12630 | [20 empty] | 3157 | 20% | 0 | 3157 | 20% | 0 | [5 empty] | 15787 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA | 879031 - PLATTE CO PWSD NO 4 | WATER | WATER REPAIR & INSTALLATION | 2020-04-17 | 2020-08-20 | 2020-04-17 | 2020-08-20 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023256¦¦2020-03-31
UP | CJ | Yes | 1023279 |  | VESTAL NY MECHANICAL SEAL | CROOK, CHARLES M |  | 2990 | 0 | 2990 |  |  | 0 | 0 | 0 |  | 2190 | 0 | 2190 | [20 empty] | 800 | 26.76% | 0 | 800 | 26.76% | 0 | [5 empty] | 2990 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA | 899641 - VESTAL, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-20 | 2020-04-25 | 2020-04-20 | 2020-04-25 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023279¦¦2020-03-31
FP | CJ | Yes | 1023280 |  | SARATOGA FISH HATCHERY REPAIR | SCHANAMAN, MIKE L. |  | 36175 | 0 | 36175 |  |  | 0 | 0 | 0 |  | 25324 | 0 | 25324 | [20 empty] | 10851 | 30% | 0 | 10851 | 30% | 0 | [5 empty] | 36175 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA | 1013335 - FWS SARATOGA NATIONAL FISH HATCHERY | WATER | WATER REPAIR & INSTALLATION | 2020-04-17 | 2020-05-31 | 2020-04-17 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1023280¦¦2020-03-31
FP | CJ | Yes | 1023312 |  | LEE COUNTY PINEWOODS RO5 PUMP | MCCULLERS, BLAKE E. |  | 11500 | 0 | 11500 |  |  | 0 | 0 | 0 |  | 7964 | 0 | 7964 | [20 empty] | 3536 | 30.75% | 0 | 3536 | 30.75% | 0 | [5 empty] | 11500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA | 893633 - LEE COUNTY UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2020-04-20 | 2020-04-27 | 2020-04-20 | 2020-04-27 | PRIME CONTRACTOR | PUBLIC | JOB ORDER CONTRACT | 1023312¦¦2020-03-31
TM | CJ | Yes | 1023313 |  | DE-BRA KUEMPEL PUMP | MIGUEL, SEAN J. |  | 600 | 0 | 600 |  |  | 0 | 0 | 0 |  | 500 | 0 | 500 | [20 empty] | 100 | 16.67% | 0 | 100 | 16.67% | 0 | [5 empty] | 600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 1023263 - DEBRA KUEMPEL | WATER | WATER REPAIR & INSTALLATION | 2020-04-20 | 2020-05-31 | 2020-04-20 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023313¦¦2020-03-31
FP | CJ | Yes | 1023314 |  | EATON KEARNEY NE HS PUMP PULL | GANSEBOM, JASON W. |  | 5750 | 0 | 5750 |  |  | 0 | 0 | 0 |  | 4485 | 0 | 4485 | [20 empty] | 1265 | 22% | 0 | 1265 | 22% | 0 | [5 empty] | 5750 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 889995 - EATON CORPORATION | WATER | WATER REPAIR & INSTALLATION | 2020-04-20 | 2020-05-31 | 2020-04-20 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023314¦¦2020-03-31
FP | CJ | Yes | 1023341 |  | WELL 12C PUMP LIBERTY UTILITIE | GRACE, GARY L. |  | 91949 | 0 | 91949 |  |  | 0 | 0 | 0 |  | 73937 | 0 | 73937 | [20 empty] | 18012 | 19.59% | 0 | 18012 | 19.59% | 0 | [5 empty] | 91949 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 893732 - LIBERTY UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2020-04-07 | 2020-09-30 | 2020-04-07 | 2020-09-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1023341¦¦2020-03-31
TM | CJ | Yes | 1023342 |  | JOHNNY LARKAN | SCHERM, LOGAN M |  | 9000 | 0 | 9000 |  |  | 0 | 0 | 0 |  | 6000 | 0 | 6000 | [20 empty] | 3000 | 33.33% | 0 | 3000 | 33.33% | 0 | [5 empty] | 9000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA | 892879 - JOHNNY LARKAN | WATER | WATER REPAIR & INSTALLATION | 2020-04-20 | 2020-08-31 | 2020-04-20 | 2020-08-31 | PRIME CONTRACTOR | PRIVATE | EXPENSE JOB | 1023342¦¦2020-03-31
UP | CJ | Yes | 1023343 |  | TANIMURA AND ANTLE BOOSTER 3 | SEIDEN, ANDREW L. |  | 4331 | 0 | 4331 |  |  | 0 | 0 | 0 |  | 2880 | 0 | 2880 | [20 empty] | 1451 | 33.5% | 0 | 1451 | 33.5% | 0 | [5 empty] | 4331 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 906315 - TANIMURA & ANTLE | WATER | WATER REPAIR & INSTALLATION | 2020-04-17 | 2020-12-30 | 2020-04-17 | 2020-12-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023343¦¦2020-03-31
UP | CJ | Yes | 1023387 |  | FIRST SOLAR WELL INVESTIGATION | GRACE, GARY L. |  | 5200 | 0 | 5200 |  |  | 0 | 0 | 0 |  | 4162 | 0 | 4162 | [20 empty] | 1038 | 19.96% | 0 | 1038 | 19.96% | 0 | [5 empty] | 5200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1023354 - FIRST SOLAR DEVELOPMENT | WATER | WATER REPAIR & INSTALLATION | 2020-04-20 | 2020-06-30 | 2020-04-20 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023387¦¦2020-03-31
FP | CJ | Yes | 1023415 |  | JEFF DAVIS 4 WELL 3 REHAB | GNAU, CASEY T |  | 35000 | 0 | 35000 |  |  | 0 | 0 | 0 |  | 21669 | 0 | 21669 | [20 empty] | 13331 | 38.09% | 0 | 13331 | 38.09% | 0 | [5 empty] | 35000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 892776 - JEFFERSON DAVIS WWD 4 | WATER | WATER REPAIR & INSTALLATION | 2020-04-21 | 2020-05-30 | 2020-04-21 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023415¦¦2020-03-31
FP | CJ | Yes | 1023416 |  | SUEZ NANUET AND TALLMAN AST | RANFT, DONALD R |  | 5640.01 | 0 | 5640.01 |  |  | 0 | 0 | 0 |  | 3782 | 0 | 3782 | [20 empty] | 1858.01 | 32.94% | 0 | 1858.01 | 32.94% | 0 | [5 empty] | 5640.01 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 898467 - SUEZ | WATER | WATER TREATMENT | 2020-04-15 | 2020-05-31 | 2020-04-15 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | COST REIMBURSIBLE | 1023416¦¦2020-03-31
FP | CJ | Yes | 1023448 |  | HOMER GLEN IL HERITAGE PARK | EISHA, JOSEPH J. |  | 18000 | 0 | 18000 |  |  | 0 | 0 | 0 |  | 12120 | 0 | 12120 | [20 empty] | 5880 | 32.67% | 0 | 5880 | 32.67% | 0 | [5 empty] | 18000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 831 - WRD AURORA | AURORA - WA | 1023381 - HOMER GLEN, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-21 | 2020-05-14 | 2020-04-21 | 2020-05-14 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023448¦¦2020-03-31
FP | CJ | Yes | 1023478 |  | HONEYWELL UOP APRIL 2020 TEST | GREGORY, CRYSTAL N |  | 3200 | 0 | 3200 |  |  | 0 | 0 | 0 |  | 1820 | 0 | 1820 | [20 empty] | 1380 | 43.12% | 0 | 1380 | 43.12% | 0 | [5 empty] | 3200 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 899383 - U O P LLC | WATER | WATER REPAIR & INSTALLATION | 2020-04-21 | 2020-05-30 | 2020-04-21 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023478¦¦2020-03-31
UP | CJ | Yes | 1023527 |  | PINNACLE PEAK CC SOFT START | VAN ALLEN, WESLEY C. |  | 9649 | 0 | 9649 |  |  | 0 | 0 | 0 |  | 6592 | 0 | 6592 | [20 empty] | 3057 | 31.68% | 0 | 3057 | 31.68% | 0 | [5 empty] | 9649 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 896350 - PINNACLE PEAK COUNTRY CLUB | WATER | WATER REPAIR & INSTALLATION | 2020-04-21 | 2020-05-30 | 2020-04-21 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023527¦¦2020-03-31
UP | CJ | Yes | 1023528 |  | P AND G REPAIR N REBUILD PUMP | WHITE, CATHLEEN R |  | 84550 | 0 | 84550 |  |  | 0 | 0 | 0 |  | 62460 | 0 | 62460 | [20 empty] | 22090 | 26.13% | 0 | 22090 | 26.13% | 0 | [5 empty] | 84550 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896598 - PROCTER AND GAMBLE PAPER PRODUCTS, THE | WATER | WATER REPAIR & INSTALLATION | 2020-04-09 | 2020-07-30 | 2020-04-09 | 2020-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023528¦¦2020-03-31
UP | CJ | Yes | 1023579 |  | GOLDEN STATE MOHAWK BOOSTER8 | BRASHEAR, DAVID M |  | 4225 | 0 | 4225 |  |  | 0 | 0 | 0 |  | 3380 | 0 | 3380 | [20 empty] | 845 | 20% | 0 | 845 | 20% | 0 | [5 empty] | 4225 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 231962 - GOLDEN STATE WATER COMPANY | WATER | WATER REPAIR & INSTALLATION | 2020-04-01 | 2020-06-30 | 2020-04-01 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1023579¦¦2020-03-31
TM | CJ | Yes | 1023610 |  | WYOMING SLUDGE PUMPS | BARNES, MATTHEW D |  | 5000 | 0 | 5000 |  |  | 0 | 0 | 0 |  | 3250 | 0 | 3250 | [20 empty] | 1750 | 35% | 0 | 1750 | 35% | 0 | [5 empty] | 5000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 879086 - WYOMING, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-24 | 2020-06-30 | 2020-04-24 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023610¦¦2020-03-31
UP | CJ | Yes | 1023611 |  | VERSAILLES PUMP MAINTENANCE | MIGUEL, SEAN J. |  | 1250 | 0 | 1250 |  |  | 0 | 0 | 0 |  | 1050 | 0 | 1050 | [20 empty] | 200 | 16% | 0 | 200 | 16% | 0 | [5 empty] | 1250 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 899632 - VERSAILLES, KY, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-21 | 2020-05-30 | 2020-04-21 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023611¦¦2020-03-31
FP | CJ | Yes | 1023612 |  | RAIN CARBON WELL 3 | GNAU, CASEY T |  | 16500 | 0 | 16500 |  |  | 0 | 0 | 0 |  | 9900 | 0 | 9900 | [20 empty] | 6600 | 40% | 0 | 6600 | 40% | 0 | [5 empty] | 16500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879116 - RAIN CII CARBON LLC | WATER | WATER REPAIR & INSTALLATION | 2020-04-23 | 2020-05-30 | 2020-04-23 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023612¦¦2020-03-31
UP | CJ | Yes | 1023613 |  | CEDAR RAPIDS NE SOUTHWELL | GANSEBOM, JASON W. |  | 9205 | 0 | 9205 |  |  | 0 | 0 | 0 |  | 7017 | 0 | 7017 | [20 empty] | 2188 | 23.77% | 0 | 2188 | 23.77% | 0 | [5 empty] | 9205 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 888107 - CEDAR RAPIDS, NE, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-23 | 2020-06-30 | 2020-04-23 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023613¦¦2020-03-31
UP | CJ | Yes | 1023614 |  | CLECO CAJUN 2 WELL 8 FLOWTEST | LOPEZ-VASQUEZ, JUAN C. |  | 1500 | 0 | 1500 |  |  | 0 | 0 | 0 |  | 918 | 0 | 918 | [20 empty] | 582 | 38.8% | 0 | 582 | 38.8% | 0 | [5 empty] | 1500 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 914432 - NRG BIG CAJUN 1 | WATER | WATER REPAIR & INSTALLATION | 2020-04-23 | 2020-05-30 | 2020-04-23 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023614¦¦2020-03-31
FP | CJ | Yes | 1023676 |  | FMI SIERRITA CANOA DW1 HEAD | VAN ALLEN, WESLEY C. |  | 21656 | 0 | 21656 |  |  | 0 | 0 | 0 |  | 15818 | 0 | 15818 | [20 empty] | 5838 | 26.96% | 0 | 5838 | 26.96% | 0 | [5 empty] | 21656 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA | 890921 - FREEPORT MCMORAN SIERRITA | WATER | WATER REPAIR & INSTALLATION | 2020-04-23 | 2020-06-30 | 2020-04-23 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023676¦¦2020-03-31
UP | CJ | Yes | 1023748 |  | GULF POWER CRIST PLANT SUBPUMP | PARSLEY, TRISTAN S |  | 4000 | 0 | 4000 |  |  | 0 | 0 | 0 |  | 2165 | 0 | 2165 | [20 empty] | 1835 | 45.88% | 0 | 1835 | 45.88% | 0 | [5 empty] | 4000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 891691 - GULF POWER COMPANY | WATER | WATER SUPPLY | 2020-04-22 | 2020-05-31 | 2020-04-24 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023748¦¦2020-03-31
FP | CJ | Yes | 1023749 |  | CITY OF REDLANDS TEXAS ST WELL | GRACE, GARY L. |  | 52995 | 0 | 52995 |  |  | 0 | 0 | 0 |  | 37099 | 0 | 37099 | [20 empty] | 15896 | 30% | 0 | 15896 | 30% | 0 | [5 empty] | 52995 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 896853 - REDLANDS, CA, CITY OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-22 | 2020-05-30 | 2020-04-22 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1023749¦¦2020-03-31
FP | CJ | Yes | 1023750 |  | WOOD ENV LMC GREAT NECK NY AST | RANFT, DONALD R |  | 65825 | 0 | 65825 |  |  | 0 | 0 | 0 |  | 41488.9 | 0 | 41488.9 | [20 empty] | 24336.1 | 36.97% | 0 | 24336.1 | 36.97% | 0 | [5 empty] | 65825 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA | 987381 - WOOD ENVIRONMENT AND INFRASTRUCTURE INC | WATER | WATER TREATMENT | 2020-04-24 | 2020-08-31 | 2020-04-24 | 2020-08-31 | SUBCONTRACTOR | PRIVATE | COST REIMBURSIBLE | 1023750¦¦2020-03-31
FP | CJ | Yes | 1023751 |  | P66 NP 80 SERVICE WORK TREAT | WHITE, CATHLEEN R |  | 41118 | 0 | 41118 |  |  | 0 | 0 | 0 |  | 28750 | 0 | 28750 | [20 empty] | 12368 | 30.08% | 0 | 12368 | 30.08% | 0 | [5 empty] | 41118 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA | 896286 - PHILLIPS 66 WOOD RIVER REFINERY | WATER | WATER REPAIR & INSTALLATION | 2020-04-20 | 2020-07-30 | 2020-04-20 | 2020-07-30 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023751¦¦2020-03-31
UP | CJ | Yes | 1023753 |  | NEWARK IL WELL 3 | KENNEDY, CHRISTOPHER C. |  | 15000 | 0 | 15000 |  |  | 0 | 0 | 0 |  | 11250 | 0 | 11250 | [20 empty] | 3750 | 25% | 0 | 3750 | 25% | 0 | [5 empty] | 15000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 1023738 - NEWARK, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-24 | 2020-05-01 | 2020-04-24 | 2020-05-01 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023753¦¦2020-03-31
FP | CJ | Yes | 1023755 |  | OXBOW 2020 FLOW TESTS | GREGORY, CRYSTAL N |  | 1700 | 0 | 1700 |  |  | 0 | 0 | 0 |  | 967 | 0 | 967 | [20 empty] | 733 | 43.12% | 0 | 733 | 43.12% | 0 | [5 empty] | 1700 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 879058 - OXBOW CALCINING LLC | WATER | WATER REPAIR & INSTALLATION | 2020-04-24 | 2020-05-30 | 2020-04-24 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023755¦¦2020-03-31
UP | CJ | Yes | 1023756 |  | WESTROCK SPARE 14 | GNAU, CASEY T |  | 15000 | 0 | 15000 |  |  | 0 | 0 | 0 |  | 8500 | 0 | 8500 | [20 empty] | 6500 | 43.33% | 0 | 6500 | 43.33% | 0 | [5 empty] | 15000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 879065 - WESTROCK HODGE MILL | WATER | WATER REPAIR & INSTALLATION | 2020-04-24 | 2020-05-30 | 2020-04-24 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023756¦¦2020-03-31
UP | CJ | Yes | 1023860 |  | CRESTLINE LAKE PULL E4 BOOSTER | BRASHEAR, DAVID M |  | 6887 | 0 | 6887 |  |  | 0 | 0 | 0 |  | 4820 | 0 | 4820 | [20 empty] | 2067 | 30.01% | 0 | 2067 | 30.01% | 0 | [5 empty] | 6887 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 878584 - CRESTLINE LAKE ARROWHEAD WATER AGENCY | WATER | WATER REPAIR & INSTALLATION | 2020-04-27 | 2020-06-01 | 2020-04-27 | 2020-06-01 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023860¦¦2020-03-31
UP | CJ | Yes | 1023861 |  | POLLOCK LA TEST 7 WELLS | GNAU, CASEY T |  | 5600 | 0 | 5600 |  |  | 0 | 0 | 0 |  | 3360 | 0 | 3360 | [20 empty] | 2240 | 40% | 0 | 2240 | 40% | 0 | [5 empty] | 5600 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 896447 - POLLOCK, LA, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-27 | 2020-05-15 | 2020-04-27 | 2020-05-15 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023861¦¦2020-03-31
UP | CJ | Yes | 1023862 |  | BUZZI UNICEM R AND I EMERGENCY | GREGORY, CRYSTAL N |  | 6300 | 0 | 6300 |  |  | 0 | 0 | 0 |  | 3724 | 0 | 3724 | [17 empty] | 0 |  |  | 2576 | 40.89% | 0 | 2576 | 40.89% | 0 | [5 empty] | 6300 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 887684 - BUZZI UNICEM USA INC | WATER | WATER REPAIR & INSTALLATION | 2020-04-27 | 2020-05-30 | 2020-04-27 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023862¦¦2020-03-31
UP | CJ | Yes | 1023879 |  | MISSION SPRINGS VALLEY BOOSTER | BRASHEAR, DAVID M |  | 1992 | 0 | 1992 |  |  | 0 | 0 | 0 |  | 1493 | 0 | 1493 | [20 empty] | 499 | 25.05% | 0 | 499 | 25.05% | 0 | [5 empty] | 1992 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 879011 - MISSION SPRINGS WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-04-27 | 2020-05-31 | 2020-04-27 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | BID/BUILD | 1023879¦¦2020-03-31
UP | CJ | Yes | 1023881 |  | EVWD PLANT 125 40HP BOOSTER | GRACE, GARY L. |  | 4375 | 0 | 4375 |  |  | 0 | 0 | 0 |  | 3447 | 0 | 3447 | [20 empty] | 928 | 21.21% | 0 | 928 | 21.21% | 0 | [5 empty] | 4375 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA | 1023859 - EAST VALLEY WATER DISTRICT | WATER | WATER REPAIR & INSTALLATION | 2020-04-24 | 2020-06-30 | 2020-04-24 | 2020-06-30 | PRIME CONTRACTOR | PUBLIC | BID/BUILD | 1023881¦¦2020-03-31
UP | LJ | Yes | 1023903 |  | WELFL LEWIS AND CLARK SITE B | HARTMAN, MICHAEL |  | 3956145 | 0 | 3956145 |  |  | 0 | 0 | 0 |  | 2777329.02 | 0 | 2777329.02 | [20 empty] | 1178815.98 | 29.8% | 0 | 1178815.98 | 29.8% | 0 | [5 empty] | 3956145 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA | 878673 - WELFL CONSTRUCTION | WATER | WATER SUPPLY | 2020-04-27 | 2021-05-01 | 2020-04-29 | 2021-05-01 | SUBCONTRACTOR | PUBLIC | BID/BUILD | 1023903¦¦2020-03-31
UP | CJ | Yes | 1023993 |  | FREMONT UTILITIES WELL 6 | GANSEBOM, JASON W. |  | 8752 | 0 | 8752 |  |  | 0 | 0 | 0 |  | 6126 | 0 | 6126 | [20 empty] | 2626 | 30% | 0 | 2626 | 30% | 0 | [5 empty] | 8752 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 878915 - FREMONT DEPARTMENT OF UTILITIES | WATER | WATER REPAIR & INSTALLATION | 2020-04-28 | 2020-05-31 | 2020-04-28 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023993¦¦2020-03-31
UP | CJ | Yes | 1023994 |  | CHANNAHON IL WELL NO 2 | EISHA, JOSEPH J. |  | 30000 | 0 | 30000 |  |  | 0 | 0 | 0 |  | 21500 | 0 | 21500 | [20 empty] | 8500 | 28.33% | 0 | 8500 | 28.33% | 0 | [5 empty] | 30000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA | 888218 - CHANNAHON, IL, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-28 | 2020-06-11 | 2020-04-28 | 2020-06-11 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1023994¦¦2020-03-31
UP | CJ | Yes | 1023995 |  | TESI COUNTRY LANE | GNAU, CASEY T |  | 10000 | 0 | 10000 |  |  | 0 | 0 | 0 |  | 6000 | 0 | 6000 | [20 empty] | 4000 | 40% | 0 | 4000 | 40% | 0 | [5 empty] | 10000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA | 898763 - TESI | WATER | WATER REPAIR & INSTALLATION | 2020-04-28 | 2020-05-01 | 2020-04-28 | 2020-05-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1023995¦¦2020-03-31
UP | CJ | Yes | 1024017 |  | JUNIATA NE WELL 1 PULL | GANSEBOM, JASON W. |  | 7880 | 0 | 7880 |  |  | 0 | 0 | 0 |  | 6149 | 0 | 6149 | [20 empty] | 1731 | 21.97% | 0 | 1731 | 21.97% | 0 | [5 empty] | 7880 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA | 892969 - JUNIATA, NE, VILLAGE OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-28 | 2020-05-31 | 2020-04-28 | 2020-05-31 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1024017¦¦2020-03-31
FP | CJ | Yes | 1024018 |  | ATLANTIC ICON CORRY FIELD WELL | PARSLEY, TRISTAN S |  | 6235 | 0 | 6235 |  |  | 0 | 0 | 0 |  | 4050 | 0 | 4050 | [20 empty] | 2185 | 35.04% | 0 | 2185 | 35.04% | 0 | [5 empty] | 6235 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA | 886613 - ATLANTIC ICON CORPORATION | WATER | WATER SUPPLY | 2020-04-28 | 2020-05-31 | 2020-04-28 | 2020-05-31 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1024018¦¦2020-03-31
FP | CJ | Yes | 1024075 |  | COLONIAL PIPELINE FLOW TEST | GREGORY, CRYSTAL N |  | 2100 | 0 | 2100 |  |  | 0 | 0 | 0 |  | 1585 | 0 | 1585 | [20 empty] | 515 | 24.52% | 0 | 515 | 24.52% | 0 | [5 empty] | 2100 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA | 890197 - ELS | WATER | WATER REPAIR & INSTALLATION | 2020-04-29 | 2020-06-30 | 2020-04-29 | 2020-06-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1024075¦¦2020-03-31
FP | CJ | Yes | 1024076 |  | EAST FORK NEW FILTER | WILLIAMS, DONALD G. |  | 375000 | 0 | 375000 |  |  | 0 | 0 | 0 |  | 308835 | 0 | 308835 | [20 empty] | 66165 | 17.64% | 0 | 66165 | 17.64% | 0 | [5 empty] | 375000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 878557 - EAST FORK WATER INC | WATER | WATER REPAIR & INSTALLATION | 2020-04-29 | 2020-10-30 | 2020-04-29 | 2020-10-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1024076¦¦2020-03-31
TM | CJ | Yes | 1024077 |  | OAKTOWN TESTS | WILLIAMS, DONALD G. |  | 1000 | 0 | 1000 |  |  | 0 | 0 | 0 |  | 900 | 0 | 900 | [20 empty] | 100 | 10% | 0 | 100 | 10% | 0 | [5 empty] | 1000 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA | 895643 - OAKTOWN, IN, TOWN OF | WATER | WATER REPAIR & INSTALLATION | 2020-04-29 | 2020-05-30 | 2020-04-29 | 2020-05-30 | PRIME CONTRACTOR | PUBLIC | NO BID (NEGOTIATED) | 1024077¦¦2020-03-31
TM | CJ | Yes | 1024078 |  | PIXELLE WELL 18 MOTOR | BARNES, MATTHEW D |  | 4092 | 0 | 4092 |  |  | 0 | 0 | 0 |  | 2660 | 0 | 2660 | [20 empty] | 1432 | 35% | 0 | 1432 | 35% | 0 | [5 empty] | 4092 | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA | 878886 - PIXELLE SPECIALTY SOLUTIONS | MANUFACTURING | MANUFACTURING ALL | 2020-04-29 | 2020-05-30 | 2020-04-29 | 2020-05-30 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1024078¦¦2020-03-31
FP | CJ | Yes | 1024111 |  | CLEVELAND CONST NEW MOTOR | ANDERSON, STEPHEN P. | [6 empty] | 0 | 0 | 0 | [36 empty] | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA | 888677 - CLEVELAND CONSTRUCTION | WATER | WATER EQUIPMENT SALES | 2020-04-29 | 2020-05-01 | 2020-04-29 | 2020-05-01 | PRIME CONTRACTOR | PRIVATE | NO BID (NEGOTIATED) | 1024111¦¦2020-03-31
UP | C | Yes | 6008980 |  | CLOSED JOB ACTIVITY - WA |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -0.01 |  |  |  | -0.01 |  |  | -3210992.94 | 1821.17 | 379.56 |  | -3213193.67 |  |  | 3210992.94 | 0 |  |  | 0 | -3210992.94 | [7 empty] | 3210992.94 |  | 3210992.94 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6008980¦¦2020-03-31
UP | C | Yes | 6008995 |  | AREA/REGION ALLOW - REDLANDS |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 25553.11 | 279577 |  |  | 61712.59 |  | -315736.48 | 131149.92 | 2748811.37 | 2269.05 |  | 594202.17 |  | -3214132.67 | 0 | 131149.92 |  |  | 0 | 131149.92 | [7 empty] | -131149.92 |  | -131149.92 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 860 - WRD REDLANDS | REDLANDS - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6008995¦¦2020-03-31
UP | C | Yes | 6009995 |  | AREA/REGION ALLOW - HANFORD |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -1592.67 | 2234.38 |  |  | 76.78 |  | -3903.83 | -17064.76 | 66636.87 | 4494 |  | 8907.75 |  | -97103.38 | 17064.76 | 0 |  |  | 0 | -17064.76 | [7 empty] | 17064.76 |  | 17064.76 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 591 - WRD WEST | 861 - WRD HANFORD | HANFORD - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6009995¦¦2020-03-31
UP | C | Yes | 6010995 |  | AREA/REGION ALLOW - HOUSTON | OMAN, TIMOTHY S. | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 63895.27 | 65082.62 |  |  | 9542.65 |  | -10730 | 104296.6 | 490296.16 | 29694.81 |  | 182354.65 |  | -598049.02 | 0 | 104296.6 |  |  | 0 | 104296.6 | [7 empty] | -104296.6 |  | -104296.6 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 865 - WRD HOUSTON | HOUSTON - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6010995¦¦2020-03-31
UP | C | Yes | 6012978 |  | CORP ALLOC - WRD CO 60 |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 14513.73 | [5 empty] | 14513.73 | -31762.09 | [5 empty] | -31762.09 | 31762.09 | 0 |  |  | 0 | -31762.09 | [7 empty] | 31762.09 |  | 31762.09 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 597 - WATER ADMIN | 767 - WATER ADMIN | WATER CORP ADMIN - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6012978¦¦2020-03-31
UP | C | Yes | 6012980 |  | CLOSED JOB ACTIVITY - WA | [7 empty] | 0 | 0 | 0 | [36 empty] | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6012980¦¦2020-03-31
UP | C | Yes | 6012995 |  | AREA/REGION ALLOW - CHANDLER |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 106483.59 | 145112.11 |  |  | 18292.01 |  | -56920.53 | 107004.38 | 1197602.89 |  |  | 248938.28 |  | -1339536.79 | 0 | 107004.38 |  |  | 0 | 107004.38 | [7 empty] | -107004.38 |  | -107004.38 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 867 - WRD CHANDLER | CHANDLER - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6012995¦¦2020-03-31
UP | C | Yes | 6013995 |  | AREA/REGION ALLOW - DENVER |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 29294.89 | 57731.78 |  |  | 16150.22 |  | -44587.11 | 99020.91 | 701724.13 |  |  | 324028.33 |  | -926731.55 | 0 | 99020.91 |  |  | 0 | 99020.91 | [7 empty] | -99020.91 |  | -99020.91 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 868 - WRD DENVER | DENVER - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6013995¦¦2020-03-31
UP | C | Yes | 6014980 |  | CLOSED JOB ACTIVITY - WA |  | 100% | [5 empty] | 4379 | 0 | 0 |  |  |  |  | 0.01 |  |  |  | 0.01 |  |  | -463.62 | 1937.64 | 920.76 |  | 1056.98 |  | -4379 | 463.62 | 0 |  |  | 0 | -463.62 | [7 empty] | 463.62 |  | 463.62 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6014980¦¦2020-03-31
UP | C | Yes | 6014995 |  | AREA/REGION ALLOW-KANSAS CITY |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 15278.87 | 39322.54 | 1079.51 |  | 7352.36 |  | -32475.54 | -11952.17 | 319059.44 | 23677.82 |  | 86233.4 |  | -440922.83 | 11952.17 | 0 |  |  | 0 | -11952.17 | [7 empty] | 11952.17 |  | 11952.17 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 830 - WRD KANSAS CITY | KANSAS CITY - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6014995¦¦2020-03-31
UP | C | Yes | 6015995 |  | AREA/REGION ALLOW - AURORA |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 103300.06 | 118614.11 | 4447.38 |  | 45046.67 |  | -64808.1 | 198840.34 | 847389.07 | 63525.24 |  | 228664.08 |  | -940738.05 | 0 | 198840.34 |  | 0 | 0 | 198840.34 | [7 empty] | -198840.34 |  | -198840.34 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 831 - WRD AURORA | AURORA - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6015995¦¦2020-03-31
UP | C | Yes | 6017995 |  | AREA/REGION ALLOW - OMAHA |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 2392.07 | 39109.5 | 1122.6 |  | 15338.24 |  | -53178.27 | 10436.42 | 479728.48 | 18331.65 |  | 135573.03 |  | -623196.74 | 0 | 10436.42 |  |  | 0 | 10436.42 | [7 empty] | -10436.42 |  | -10436.42 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 833 - WRD OMAHA | OMAHA - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6017995¦¦2020-03-31
UP | C | Yes | 6018995 |  | AREA/REGION ALLOW - ST LOUIS |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -16721.24 | 49344.62 | 2082.87 |  | 5420.26 |  | -73568.99 | 10827.94 | 473627.16 | 13837.96 |  | 67354.02 |  | -543991.2 | 0 | 10827.94 |  |  | 0 | 10827.94 | [7 empty] | -10827.94 |  | -10827.94 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 834 - WRD ST. LOUIS | ST. LOUIS - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6018995¦¦2020-03-31
UP | C | Yes | 6019995 |  | AREA/REGION ALLOW - WICHITA |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 14273.29 | 34325.27 | 253.12 |  | 2798.35 |  | -23103.45 | 25429.2 | 269411.47 | 10716 |  | 64346.51 |  | -319044.78 | 0 | 25429.2 |  |  | 0 | 25429.2 | [7 empty] | -25429.2 |  | -25429.2 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 835 - WRD WICHITA | WICHITA - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6019995¦¦2020-03-31
UP | C | Yes | 6020995 |  | AREA/REGION ALLOW - GUTHRIE |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -23494.94 | 27275.18 | 253.12 |  | 4589.45 |  | -55612.69 | 14098.18 | 253933.43 | 6897.96 |  | 48138 |  | -294871.21 | 0 | 14098.18 |  |  | 0 | 14098.18 | [7 empty] | -14098.18 |  | -14098.18 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 836 - WRD GUTHRIE | GUTHRIE - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6020995¦¦2020-03-31
UP | C | Yes | 6021995 |  | AREA/REGION ALLOW - STUTTGART |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 34277.52 | 98256.31 | 0 |  | 21089.47 |  | -85068.26 | 127602.57 | 951956.64 | 11234.39 |  | 338279.06 |  | -1173867.52 | 0 | 127602.57 |  | 20 | 0 | 127602.57 | [7 empty] | -127602.57 |  | -127602.57 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 839 - WRD STUTTGART | STUTTGART - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6021995¦¦2020-03-31
UP | C | Yes | 6022995 |  | AREA/REGION ALLOW - MEMPHIS |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -12261.79 | 54097.53 | 1506.44 |  | 8343.24 |  | -76209 | -29521.19 | 487989.5 | 22667.54 |  | 83619.82 |  | -623798.05 | 29521.19 | 0 |  |  | 0 | -29521.19 | [7 empty] | 29521.19 |  | 29521.19 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 840 - WRD MEMPHIS | MEMPHIS - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6022995¦¦2020-03-31
UP | C | Yes | 6023995 |  | AREA/REGION ALLOW - RAYNE |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 94399.19 | 102703.61 | 2516.71 |  | 8098.57 |  | -18919.7 | 190617.76 | 453294.25 | 24181.58 |  | 111572.46 |  | -398430.53 | 0 | 190617.76 |  |  | 0 | 190617.76 | [7 empty] | -190617.76 |  | -190617.76 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 841 - WRD RAYNE | RAYNE - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6023995¦¦2020-03-31
UP | C | Yes | 6024995 |  | AREA/REGION ALLOW - JACKSON | [7 empty] | 0 | 0 | 0 | [36 empty] | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 846 - WRD JACKSON | JACKSON - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6024995¦¦2020-03-31
UP | C | Yes | 6025995 |  | AREA/REGION ALLOW - PLEASANTON | [7 empty] | 0 | 0 | 0 | [36 empty] | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 592 - WRD SOUTHWEST | 869 - WRD PLEASANTON | PLEASANTON - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6025995¦¦2020-03-31
UP | C | Yes | 6026995 |  | AREA/REGION ALLOW - WAUSAU |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 634.72 | 634.72 | [5 empty] | 694.25 | 634.72 |  |  | 59.53 |  |  | 0 | 694.25 |  |  | 0 | 694.25 | [7 empty] | -694.25 |  | -694.25 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 586 - WRD CENTRAL | 870 - WRD WAUSAU | WAUSAU - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6026995¦¦2020-03-31
UP | C | Yes | 6027980 |  | CLOSED JOB ACTIVITY - WA |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 9286.11 | 3541.09 | 1193.4 |  | 4551.62 |  |  | 9286.11 | 3541.09 | 1193.4 |  | 4551.62 |  |  | 0 | 9286.11 |  |  | 0 | 9286.11 | [7 empty] | -9286.11 |  | -9286.11 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2020-01-01 | 1900-01-01 | 2020-01-01 | 1900-01-01 | PRIME CONTRACTOR | TOTAL COMPANY | NOT APPLICABLE | 6027980¦¦2020-03-31
UP | C | Yes | 6027995 |  | AREA/REGION ALLOW - PENSACOLA |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 391.77 | 46595.31 | 565.99 |  | 5263.22 |  | -52032.75 | 10626.33 | 323601.16 | 11727.08 |  | 80840.78 |  | -405542.69 | 0 | 10626.33 |  |  | 0 | 10626.33 | [7 empty] | -10626.33 |  | -10626.33 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 842 - WRD PENSACOLA | PENSACOLA - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6027995¦¦2020-03-31
UP | C | Yes | 6028995 |  | AREA/REGION ALLOW-PRAIRIEVILLE |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 39487.25 | 69465.12 | 2646.01 |  | 10957.83 |  | -43581.71 | 39161.08 | 461889.13 | 27428.48 |  | 191781.02 |  | -641937.55 | 0 | 39161.08 |  |  | 0 | 39161.08 | [7 empty] | -39161.08 |  | -39161.08 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 843 - WRD PRAIRIEVILLE | PRAIRIEVILLE - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6028995¦¦2020-03-31
UP | C | Yes | 6029995 |  | AREA/REGION ALLOW -LONG ISLAND |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 11838.45 | 35651.41 | 1442.43 |  | 9922.61 |  | -35178 | 36870.9 | 348438.21 | 19169.26 |  | 57354.79 |  | -388091.36 | 0 | 36870.9 |  |  | 0 | 36870.9 | [7 empty] | -36870.9 |  | -36870.9 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 847 - WRD LONG ISLAND | LONG ISLAND - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6029995¦¦2020-03-31
UP | C | Yes | 6031995 |  | AREA/REGION ALLOW - SCHOHARIE |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 10280.97 | 26302.11 | 2458.74 |  | 8430.12 |  | -26910 | 43708.74 | 315610.19 | 14658.93 |  | 72109.2 |  | -358669.58 | 0 | 43708.74 |  |  | 0 | 43708.74 | [7 empty] | -43708.74 |  | -43708.74 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 850 - WRD SCHOHARIE | SCHOHARIE - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6031995¦¦2020-03-31
UP | C | Yes | 6032980 |  | CLOSED JOB ACTIVITY - WA | [7 empty] | 0 | 0 | 0 | [36 empty] | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6032980¦¦2020-03-31
UP | C | Yes | 6032995 |  | AREA/REGION ALLOW - FORT MYERS |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -1233.26 | 53536.39 | 736.33 |  | 13757.88 |  | -69263.86 | -17030.6 | 592697.78 | 16053.39 |  | 209817.17 |  | -835598.94 | 17030.6 | 0 |  |  | 0 | -17030.6 | [7 empty] | 17030.6 |  | 17030.6 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 838 - WRD FT. MYERS | FT. MYERS - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6032995¦¦2020-03-31
UP | C | Yes | 6033980 |  | CLOSED JOB ACTIVITY - WA |  | 100% | [5 empty] | 0 | 0 | 0 | [11 empty] | 10370.23 | 4006.2 |  |  | 6364.03 |  |  | 0 | 10370.23 |  |  | 0 | 10370.23 | [7 empty] | -10370.23 |  | -10370.23 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6033980¦¦2020-03-31
UP | C | Yes | 6033995 |  | AREA/REGION ALLOW -WATER TREAT |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -6073.51 | 30871.62 |  |  | 1270.13 |  | -38215.26 | 62375.45 | 314715.09 | 2305.16 |  | 12292.25 |  | -266937.05 | 0 | 62375.45 |  |  | 0 | 62375.45 | [7 empty] | -62375.45 |  | -62375.45 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 590 - WRD WATER TREATMENT | 858 - WRD WATER TREATMENT | WATER TREATMENT - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6033995¦¦2020-03-31
UP | C | Yes | 6040995 |  | AREA/REGION ALLOW - ALBANY |  | 100% | [5 empty] | 0 | 0 | 0 | [11 empty] | 24.91 | 20053.05 |  |  | 1739.87 |  | -21768.01 | 0 | 24.91 |  |  | 0 | 24.91 | [7 empty] | -24.91 |  | -24.91 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 844 - WRD ALBANY | ALBANY - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6040995¦¦2020-03-31
UP | C | Yes | 6041995 |  | AREA/REGION ALLOW - SAVANNAH |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 46857.93 | 40186.62 | 986.59 |  | 19917.12 |  | -14232.4 | 42385.88 | 193857.74 | 1696.92 |  | 58794.62 |  | -211963.4 | 0 | 42385.88 |  |  | 0 | 42385.88 | [7 empty] | -42385.88 |  | -42385.88 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 587 - WRD SOUTHEAST | 845 - WRD SAVANNAH | SAVANNAH - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6041995¦¦2020-03-31
UP | C | Yes | 6401995 |  | AREA/REGION ALLOW-COLLECT WLL |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -24730.93 | 29102.32 | 2952.69 |  | 20439.06 |  | -77225 | -64087.48 | 542742.92 | 32814.44 |  | 97025.66 |  | -736670.5 | 64087.48 | 0 |  |  | 0 | -64087.48 | [7 empty] | 64087.48 |  | 64087.48 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 848 - WRD COLLECTOR WELLS | COLLECTOR WELLS - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6401995¦¦2020-03-31
UP | C | Yes | 6402995 |  | AREA/REGION ALLOW - MIDDLETOWN |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 24804.6 | 47766.37 | 7990.48 |  | 3127.75 |  | -34080 | 83749.23 | 427082.61 | 47126.45 |  | 84399.13 |  | -474858.96 | 0 | 83749.23 |  |  | 0 | 83749.23 | [7 empty] | -83749.23 |  | -83749.23 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 851 - WRD MIDDLETOWN | MIDDLETOWN - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6402995¦¦2020-03-31
UP | C | Yes | 6403978 |  | CORP ALLOC - WRD CO 64 |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | -7099.32 | [5 empty] | -7099.32 | -39139 | [5 empty] | -39139 | 39139 | 0 |  |  | 0 | -39139 | [7 empty] | 39139 |  | 39139 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 871 - WRD EQUIPMENT MIDEAST | LAYNE HEAVY CIVIL - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6403978¦¦2020-03-31
UP | C | Yes | 6403980 |  | CLOSED JOB ACTIVITY - WA | [7 empty] | 0 | 0 | 0 | [36 empty] | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6403980¦¦2020-03-31
UP | C | Yes | 6403995 |  | AREA/REGION ALLOW - LOUISVILLE |  | 100% | [5 empty] | 0 | 0 | 0 |  |  |  |  | 4932.6 | 49071.66 | 7534.63 |  | 15296.31 |  | -66970 | 84145.83 | 644283.41 | 63256.66 |  | 156614.11 |  | -780008.35 | 0 | 84145.83 |  | 0 | 0 | 84145.83 | [7 empty] | -84145.83 |  | -84145.83 |  |  | 222 - WATER & MINERAL SERVICES GROUP | 413 - WATER RESOURCES | 588 - WRD NORTHEAST | 852 - WRD LOUISVILLE | LOUISVILLE - WA |  | NOT APPLICABLE | NOT APPLICABLE | 2019-05-01 | 1900-01-01 | 2019-12-31 | 1900-01-01 | . | TOTAL COMPANY | NOT APPLICABLE | 6403995¦¦2020-03-31